## Job Scheduling
Contract Job Description | Total Contract | Contract Cost TD | Est Cost to Complete | Est Total Cost | Est Gross Profit | Est Gross Profit % | Percent Complete | Gain (Fade) From Prior Mth | Billings To Date | (Over) / Under Billings | Contract Revenues Earned | Gross Profit (Loss) TD | Gross Profit % TD
2231. UDOT Bangerter Hwy Aqueduct Protection | 1872000 | 876456.94 | 449899.56 | 1326356.5 | 545643.5 | 29.15% | 66.08% | 0 | 1274515.59 | -37497.1928 | 1237018.3972 | 360561.4572 | 19.26%
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 21919978.29 | 17058641.35 | 9004.29 | 17067645.64 | 4852332.65 | 22.14% | 99.95% | 0 | 21878831.02 | 29583.0598 | 21908414.0798 | 4849772.7298 | 22.12%
2316. CUWCD CWP Wellhouse 16 | 20019214.71 | 16610839.03 | 322766.88 | 16933605.91 | 3085608.8 | 15.41% | 98.09% | -1202.85 | 19938265.26 | -300631.3844 | 19637633.8756 | 3026794.8456 | 15.12%
2321. CUWCD Santaquin Reach | 77392042 | 63703897.83 | 2779920.72 | 66483818.55 | 10908223.45 | 14.09% | 95.82% | 0 | 76015455.61 | -1859445.2612 | 74156010.3488 | 10452112.5188 | 13.51%
2325. Santaquin Flowfill/CLSM Project | 0 | 1184.6 | -1183.03 | 1.57 | -1.57 | 0% | 75452% | 0 | 0 | 0 | 0 | -1184.6 | 0%
2350. Fab Shop Jobs 2023 Projects | 0 | 0.01 | 20194.65 | 20194.66 | -20194.66 | 0% | 4.952e-05% | -20191.53 | 0 | 0 | 0 | -0.01 | 0%
2407. So SLC Lift Station | 12014289.85 | 6002143.45 | 1887781.58 | 7889925.03 | 4124364.82 | 34.33% | 76.07% | 30586.29 | 11507261.42 | -2367568.6022 | 9139692.8178 | 3137549.3678 | 26.12%
2408. Santaquin City WRF Phase 3 Upgrades | 10850256 | 3923347.76 | 5957428.94 | 9880776.7 | 969479.3 | 8.935% | 39.71% | 75956 | 6023451.34 | -1715153.6357 | 4308297.7043 | 384949.9443 | 3.548%
2409. JVWCD 2024 Vault Improvement Project | 2376189.24 | 1072372.29 | 280155.04 | 1352527.33 | 1023661.91 | 43.08% | 79.29% | -359297.66 | 2257125.33 | -373126.8035 | 1883998.5265 | 811626.2365 | 34.16%
2410. Wellington Waterline Coal Creek PRV | 330624.08 | 214720.87 | 66828.79 | 281549.66 | 49074.42 | 14.84% | 76.26% | -19684.65 | 299635 | -47488.0427 | 252146.9573 | 37426.0873 | 11.32%
2411. CWSID Dewatering Bldg HVACV Project | 6027761.72 | 2861235.35 | 1598356.24 | 4459591.59 | 1568170.13 | 26.02% | 64.16% | 16611.9 | 4535479.81 | -668120.0829 | 3867359.7271 | 1006124.3771 | 16.69%
2450. Fab Shop Jobs 2024 Projects | 0 | 2.17 | 1 | 3.17 | -3.17 | 0% | 68.45% | -0.01 | 0 | 0 | 0 | -2.17 | 0%
2503. HVSSD Headworks Upgrade | 1603291.15 | 1251248.43 | 102038.7 | 1353287.13 | 250004.02 | 15.59% | 92.46% | 20879.46 | 1557483.45 | -75081.4602 | 1482401.9898 | 231153.5598 | 14.42%
2505. JVWCD JVWTP Chemical Bldg Upgrade | 532110.3 | 202355.62 | 75900.64 | 278256.26 | 253854.04 | 47.71% | 72.72% | 0 | 514613.35 | -127648.0768 | 386965.2732 | 184609.6532 | 34.69%
2506. UDOT Big Cottonwood Creek Culvert Preservation | 494405 | 75703.08 | 300345.76 | 376048.84 | 118356.16 | 23.94% | 20.13% | 0 | 0 | 99529.5751 | 99529.5751 | 23826.4951 | 4.819%
2507. SLC Industrial Lift Station | 1105465.68 | 656268.77 | 156399.89 | 812668.66 | 292797.02 | 26.49% | 80.75% | 53060.31 | 1016792.05 | -124075.6973 | 892716.3527 | 236447.5827 | 21.39%
2508. Turner Dam & Joint Diversion Rehab | 2594713.56 | 1136940.61 | 646924.09 | 1783864.7 | 810848.86 | 31.25% | 63.73% | 534250 | 1241028.44 | 412704.1652 | 1653732.6052 | 516791.9952 | 19.92%
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 5440663.71 | 3447199.06 | 942472.13 | 4389671.19 | 1050992.52 | 19.32% | 78.53% | -267953.23 | 4433769.28 | -161228.1226 | 4272541.1574 | 825342.0974 | 15.17%
2510. Draper Pump Station #3 Improvements | 1763831.79 | 675147.1 | 843925.99 | 1519073.09 | 244758.7 | 13.88% | 44.44% | 49498.87 | 945586.79 | -161657.4809 | 783929.3091 | 108782.2091 | 6.167%
2511. GHID 25H East Rec. & Decker N. Improvements | 312700 | 203393.75 | 218251.62 | 421645.37 | -108945.37 | -34.84% | 48.24% | -10978.72 | 179680 | -28839.4355 | 150840.5645 | -52553.1855 | -16.81%
2512. South SLC Davis Tank Lid Replacement | 1605265.56 | 888920.12 | 289869.51 | 1178789.63 | 426475.93 | 26.57% | 75.41% | 5791.97 | 1412664.06 | -202140.3008 | 1210523.7592 | 321603.6392 | 20.03%
2513. CUWCD Summit Creek Irrigation HDPE | 1191451 | 930849.09 | 91324.8 | 1022173.89 | 169277.11 | 14.21% | 91.07% | 0 | 1171451 | -86448.6438 | 1085002.3562 | 154153.2662 | 12.94%
2515. UWCD Steinaker Service Canal Gate Rahab | 121000 | 82360.06 | 0 | 82360.06 | 38639.94 | 31.93% | 100% | -446.15 | 121000 | 0 | 121000 | 38639.94 | 31.93%
2516. Ephraim Lower Penstock Replacement | 3043752.82 | 1814443.76 | 971612.77 | 2786056.53 | 257696.29 | 8.466% | 65.13% | 0 | 1977956.57 | 4314.1599 | 1982270.7299 | 167826.9699 | 5.514%
2517. CUWCD Ashley Valley BWRB Rehab | 967000 | 16764.98 | 852357.22 | 869122.2 | 97877.8 | 10.12% | 1.929% | -14503.94 | 8500 | 10152.9992 | 18652.9992 | 1888.0192 | 0.1952%
2518. Mt Pleasant Lagoon Improvement | 1774867 | 26802.36 | 1628192.95 | 1654995.31 | 119871.69 | 6.754% | 1.619% | 0 | 46500 | -17756.3389 | 28743.6611 | 1941.3011 | 0.1094%
2519. Corix IEC Site Utilities | 896500 | 248455.7 | 510139.32 | 758595.02 | 137904.98 | 15.38% | 32.75% | 0 | 656500 | -362877.5411 | 293622.4589 | 45166.7589 | 5.038%
2550. Fab Shop Jobs 2025 Projects | 0 | 2.07 | 1 | 3.07 | -3.07 | 0% | 67.43% | -2.01 | 0 | 0 | 0 | -2.07 | 0%
2570. Jon Stubbs Hauling | 125487 | 132515.9 | -2422.43 | 130093.47 | -4606.47 | -3.671% | 101.9% | 0 | 124238 | 1249 | 125487 | -4692.2456 | -3.739%
2601. 2026 Misc. Jobs | 88165.27 | 41510.52 | -16088.7 | 25421.82 | 62743.45 | 71.17% | 163.3% | 30148.24 | 80844.81 | 7320.46 | 88165.27 | 102451.8794 | 116.2%
2602. JVWCD Rosecrest WSP Pipeline | 15082000 | 90133.56 | 14092223.18 | 14182356.74 | 899643.26 | 5.965% | 0.6355% | 0 | 211237.5 | -115386.41 | 95851.09 | 5717.53 | 0.03791%
2603. Highland City Mitchell Hollow Trail | 1841000 | 22872.7 | 1649949.24 | 1672821.94 | 168178.06 | 9.135% | 1.367% | 0 | 17000 | 8172.2193 | 25172.2193 | 2299.5193 | 0.1249%
2604. Murray 900 East Storm Drain Phase 2 | 2877000 | 26498.02 | 2587535 | 2614033.02 | 262966.98 | 9.14% | 1.014% | -4.61 | 0 | 29163.6727 | 29163.6727 | 2665.6527 | 0.09265%
2605. Highland City Well #1&#5 Chlorine | 467000 | 6737.8 | 414026.84 | 420764.64 | 46235.36 | 9.901% | 1.601% | 3108.58 | 9000 | -1521.8227 | 7478.1773 | 740.3773 | 0.1585%
2606. SLCo FAC126702 SMH HVAC Replacement | 487000 | 5474.04 | 463761.57 | 469235.61 | 17764.39 | 3.648% | 1.167% | 0 | 18000 | -12318.723 | 5681.277 | 207.237 | 0.04255%
2607. CUWCD Cathodic & Pump Improvements | 1482000 | 13650.08 | 1256169.55 | 1269819.63 | 212180.37 | 14.32% | 1.075% | 0 | 0 | 15930.9386 | 15930.9386 | 2280.8586 | 0.1539%
2608. Springville City WRF Headworks | 1667000 | 13173.13 | 1448964.66 | 1462137.79 | 204862.21 | 12.29% | 0.9009% | 204862.21 | 0 | 15018.836 | 15018.836 | 1845.706 | 0.1107%
2609. JVWCD JA-1 Internal Buttstraps | 83750 | 47121.61 | 18799.74 | 65921.35 | 17828.65 | 21.29% | 71.48% | 17828.65 | 0 | 59865.8073 | 59865.8073 | 12744.1973 | 15.22%
2611. CDSD Trickling Filter Replacement | 54600 | 0 | 44698.33 | 44698.33 | 9901.67 | 18.13% | 0% | 9901.67 | 0 | 0 | 0 | 0 | 0%
2650. Fab Shop Jobs 2026 Projects | 0 | 1.01 | 1 | 2.01 | -2.01 | 0% | 50.25% | -0.01 | 0 | 0 | 0 | -1.01 | 0%
14924. Elberta Pit Job | 393337.68 | 358407.1 | -13043.12 | 345363.98 | 47973.7 | 12.2% | 103.8% | 10295 | 393338.19 | -0.51 | 393337.68 | 49785.4892 | 12.66%
| 200897713.41 | 124739791.68 | 42945485.91 | 167685277.59 | 33212435.82 | 15.81% | 1894% | 368513.78 | 159867203.87 | -8153006.6758 | 151714197.1942 | 27047394.2071 | 11.67%