## Productivity Summary
Job | Phase | Actual Hours | Est Hours | Variance | Percent Used | Units Complete | Actual Units | % Complete | Calculated Budget Hrs | Calculated Budget Hrs-Actual | Calculated Projected Hours | Projected Hours | Efficiency Rate |  | End Date
2321. - CUWCD Santaquin Reach | 600.2930. - AP Asphalt Prep (DO NOT USE) | 24.99 | 48 | 23.01 | 52.06% | 0 | 48 | 0% | 48 | 23.01 | 48 | 82.34 | 28.46% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 2220.5 | 1887.4 | -333.1 | 117.6% | 514 | 713.5 | 70.38% | 1328.3256 | -892.1744 | 3155.0785 | 2187.9 | 84.08% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7800. - PRK Park Equipment | 0 | 107.8 | 107.8 | 0% | 63.616 | 79.52 | 80% | 86.24 | 86.24 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2080. - EXS Excavate Structure | 823.83 | 2051.75 | 1227.92 | 40.15% | 180 | 319 | 100% | 2051.75 | 1227.92 | 823.83 | 823.83 | 159.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2800. - BFST Backfill (DO NOT USE) | 183.93 | 100.25 | -83.68 | 183.5% | 49 | 64 | 100% | 100.25 | -83.68 | 183.93 | 183.93 | 16.53% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2710. - FWF Flowable Fill | 6 | 55 | 49 | 10.91% | 95 | 125 | 100% | 55 | 49 | 6 | 6 | 189.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.3000. - CNC Concrete Work | 1775.11 | 891.25 | -883.86 | 199.2% | 1890 | 2364.5 | 80% | 713 | -1062.11 | 2218.8875 | 1895.11 | -12.64% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 18577.98 | 5213.95 | -13364.03 | 356.3% | 3595.89 | 5422.89 | 100% | 5213.95 | -13364.03 | 18577.98 | 18623.92 | -157.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1600. - TC Traffic Control | 177.91 | 185 | 7.09 | 96.17% | 60 | 65 | 100% | 185 | 7.09 | 177.91 | 174.91 | 105.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 305.5000. - MET Metals | 71.15 | 35 | -36.15 | 203.3% | 28 | 28 | 44.44% | 15.5556 | -55.5944 | 160.0875 | 91.15 | -60.43% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2760. - HO Haul Off | 74.28 | 113.51 | 39.23 | 65.44% | 117.8 | 113.51 | 100% | 113.51 | 39.23 | 74.28 | 118.93 | 95.23% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2080. - EXS Excavate Structure | 4705.52 | 404.49 | -4301.03 | 1163% | 782.022 | 404.49 | 60% | 242.694 | -4462.826 | 7842.5333 | 4734.52 | -970.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2760. - HO Haul Off | 297.31 | 95.36 | -201.95 | 311.8% | 95.36 | 95.36 | 100% | 95.36 | -201.95 | 297.31 | 294.86 | -109.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.5000. - MET Metals | 24.72 | 85 | 60.28 | 29.08% | 79 | 79 | 97.41% | 82.7973 | 58.0773 | 25.3777 | 29.72 | 165% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.5000. - MET Metals | 5 | 101 | 96 | 4.95% | 103 | 103 | 97.52% | 98.4998 | 93.4998 | 5.1269 | 55 | 145.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2080. - EXS Excavate Structure | 444.19 | 3710 | 3265.81 | 11.97% | 435 | 485 | 100% | 3710 | 3265.81 | 444.19 | 442.19 | 188.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2300. - WPL Water Pipe Laying (DO NOT USE) | 49.38 | 355.16 | 305.78 | 13.9% | 209.56 | 209.56 | 100% | 355.16 | 305.78 | 49.38 | 49.38 | 186.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1940. - PL Punch List Work | 22.96 | 60 | 37.04 | 38.27% | 0 | 180 | 0% | 60 | 37.04 | 60 | 62.96 | 95.07% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 235.2300. - WPL Water Pipe Laying (DO NOT USE) | 300.2 | 145.38 | -154.82 | 206.5% | 205.38 | 205.38 | 100% | 145.38 | -154.82 | 300.2 | 293.2 | -1.678% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2300. - WPL Water Pipe Laying (DO NOT USE) | 118.13 | 1845.9 | 1727.77 | 6.4% | 219.51 | 363.9 | 90% | 1661.31 | 1543.18 | 131.2556 | 118.13 | 193.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2080. - EXS Excavate Structure | 3715.18 | 652 | -3063.18 | 569.8% | 465.75 | 457.5 | 100% | 652 | -3063.18 | 3715.18 | 3698.08 | -367.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.5110. - FAB Shop Pipe Fabrication (DO NOT USE) | 323.04 | 75 | -248.04 | 430.7% | 1 | 77 | 100% | 75 | -248.04 | 323.04 | 323.04 | -230.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.3000. - CNC Concrete Work | 177.77 | 360 | 182.23 | 49.38% | 318.8 | 840 | 100% | 360 | 182.23 | 177.77 | 297.77 | 117.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2710. - FWF Flowable Fill | 2 | 30 | 28 | 6.667% | 16.5 | 64 | 100% | 30 | 28 | 2 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2610. - PT Pressure Test/Chlorinating | 71.34 | 0 | -71.34 |  | 0 | 0 | 0% | 0 | -71.34 | 71.34 | 71.34 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2050. - RW Retaining Walls | 7.08 | 124.44 | 117.36 | 5.689% | 0 | 126.66 | 0% | 124.44 | 117.36 | 124.44 | 132.08 | 93.86% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.7100. - IMP Interior Mech/Piping | 124.61 | 20 | -104.61 | 623.1% | 25 | 30 | 100% | 20 | -104.61 | 124.61 | 124.61 | -423.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 5110.46 | 3884.88 | -1225.58 | 131.5% | 90 | 3884.88 | 87.5% | 3399.27 | -1711.19 | 5840.5257 | 5482.63 | 58.87% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2090. - MTL Materials | 14.64 | 68.04 | 53.4 | 21.52% | 144.12 | 144.12 | 75.95% | 51.6746 | 37.0346 | 19.2765 | 63.64 | 106.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2760. - HO Haul Off | 235.95 | 2855.51 | 2619.56 | 8.263% | 2855.51 | 2855.51 | 100% | 2855.51 | 2619.56 | 235.95 | 233.7 | 191.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 247.96 | 314.35 | 66.39 | 78.88% | 174.8 | 174.8 | 28.66% | 90.1015 | -157.8585 | 865.0939 | 207.96 | 133.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.7900. - ELC Electrical | 6 | 165.86 | 159.86 | 3.618% | 198.48 | 215.48 | 100% | 165.86 | 159.86 | 6 | 6 | 196.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 210.2300. - WPL Water Pipe Laying (DO NOT USE) | 9705.6 | 1734.55 | -7971.05 | 559.5% | 2787.44 | 1514.64 | 100% | 1734.5504 | -7971.0496 | 9705.5978 | 9714.93 | -360.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2300. - WPL Water Pipe Laying (DO NOT USE) | 1081.95 | 1965.5 | 883.55 | 55.05% | 756 | 756 | 100% | 1965.5 | 883.55 | 1081.95 | 1117.12 | 143.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2750. - H Hauling | 217.97 | 1185.24 | 967.27 | 18.39% | 1185.24 | 1185.24 | 100% | 1185.24 | 967.27 | 217.97 | 238.69 | 179.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1710. - FS Starup/Commissioning | 0 | 30 | 30 | 0% | 0 | 60 | 0% | 30 | 30 | 30 | 30 | 100% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2800. - Unknown Phase | 469.22 | 51.33 | -417.89 | 914.1% | 162.711 | 38.49 | 90% | 46.197 | -423.023 | 521.3556 | 524.22 | -821.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 240.2750. - H Hauling | 36.19 | 50 | 13.81 | 72.38% | 50 | 50 | 100% | 50 | 13.81 | 36.19 | 47.14 | 105.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 800.1940. - PL Punch List Work | 8.49 | 150 | 141.51 | 5.66% | 0 | 300 | 0% | 150 | 141.51 | 150 | 158.49 | 94.34% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7900. - ELC Electrical | 101.34 | 54.75 | -46.59 | 185.1% | 46 | 76 | 100% | 54.75 | -46.59 | 101.34 | 101.34 | 14.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2300. - WPL Water Pipe Laying (DO NOT USE) | 1062.83 | 1178.67 | 115.84 | 90.17% | 543.83 | 543.83 | 31.57% | 372.1313 | -690.6987 | 3366.3547 | 1062.83 | 109.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1200. - HOOK Hook Truck Dumpster Transporting | 6.47 | 30 | 23.53 | 21.57% | 28.5 | 30 | 95% | 28.5 | 22.03 | 6.8105 | 6.47 | 178.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 161.3000. - CNC Concrete Work | -29.49 | 25 | 54.49 | -118% | 50 | 50 | 86.21% | 21.5517 | 51.0417 | -34.2084 | -29.49 | 318% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.2750. - H Hauling | 20.45 | 3.41 | -17.04 | 599.7% | 3.41 | 3.41 | 100% | 3.41 | -17.04 | 20.45 | 9.53 | -79.47% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.6500. - Unknown Phase | 1 | 0 | -1 |  | -32.03 | 420 | -5.898% | 0 | -1 | -16.9543 | 1 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2610. - PT Pressure Test/Chlorinating | 0 | 17.5 | 17.5 | 0% | 20 | 20 | 100% | 17.5 | 17.5 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 21.72 | 0 | -21.72 |  | 0 | 0 | 0% | 0 | -21.72 | 21.72 | 21.72 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1930. - MC Misc Cleanup | 18.16 | 120 | 101.84 | 15.13% | 90 | 120 | 62.5% | 75 | 56.84 | 29.056 | 118.16 | 101.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1501. - SM Safety Meetings | 357.21 | 0 | -357.21 |  | 0 | 0 | 0% | 0 | -357.21 | 357.21 | 344.14 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.5400. - HAT Hatch/Skylights | 4 | 43 | 39 | 9.302% | 0 | 56 | 0% | 43 | 39 | 43 | 40 | 107% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2080. - EXS Excavate Structure | 389.45 | 418 | 28.55 | 93.17% | 198 | 340 | 100% | 418 | 28.55 | 389.45 | 389.45 | 106.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7900. - ELC Electrical | 291.97 | 289 | -2.97 | 101% | 257 | 427 | 100% | 289 | -2.97 | 291.97 | 260.32 | 109.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1510. - S Surveying | 375.43 | 210 | -165.43 | 178.8% | 39 | 90 | 65% | 136.5 | -238.93 | 577.5846 | 375.43 | 21.22% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.6200. - IN Insulation | 97.1 | 40 | -57.1 | 242.8% | 120 | 120 | 98.75% | 39.5 | -57.6 | 98.3291 | 74.32 | 14.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.7500. - PUMP Pumps/Motors | 106.68 | 15 | -91.68 | 711.2% | -10 | 45 | -33.33% | 15 | -91.68 | -320.04 | 186.68 | -1045% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2300. - WPL Water Pipe Laying (DO NOT USE) | 10914.56 | 2963.58 | -7950.98 | 368.3% | 2395.34 | 2445.34 | 100% | 2963.58 | -7950.98 | 10914.56 | 10862.06 | -166.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.1510. - S Surveying | 302.37 | 100 | -202.37 | 302.4% | 40 | 50 | 36.67% | 36.6667 | -265.7033 | 824.6455 | 352.37 | -152.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2800. - BFST Backfill (DO NOT USE) | 276.79 | 280 | 3.21 | 98.85% | 210 | 210 | 100% | 280 | 3.21 | 276.79 | 276.79 | 101.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 180.2060. - FE Fencing | 8 | 5.68 | -2.32 | 140.8% | 5.851 | 8.53 | 84.83% | 4.8184 | -3.1816 | 9.4304 | 8 | 59.15% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.3000. - CNC Concrete Work | 381.13 | 575 | 193.87 | 66.28% | 1340 | 1410 | 100% | 575 | 193.87 | 381.13 | 501.13 | 112.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.5000. - MET Metals | 87.41 | 123 | 35.59 | 71.07% | 139.65 | 147 | 95% | 116.85 | 29.44 | 92.0105 | 87.41 | 128.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.6500. - P Painting | 3 | 0 | -3 |  | 30 | 60 | 38.75% | 0 | -3 | 7.7419 | 3 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.1930. - MC Misc Cleanup | 12.87 | 80 | 67.13 | 16.09% | 16 | 80 | 10% | 8 | -4.87 | 128.7 | 62.87 | 121.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 103.15 | 139.5 | 36.35 | 73.94% | 72 | 92 | 75% | 104.625 | 1.475 | 137.5333 | 101.15 | 127.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2310. - WS Water Services (DO NOT USE) | 211.22 | 411.18 | 199.96 | 51.37% | 267 | 267 | 100% | 411.18 | 199.96 | 211.22 | 211.22 | 148.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2300. - WPL Water Pipe Laying (DO NOT USE) | 55.87 | 708.93 | 653.06 | 7.881% | 199.27 | 220.77 | 99.78% | 707.355 | 651.485 | 55.9944 | 57.87 | 191.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 67.93 | 651.2 | 583.27 | 10.43% | 100 | 100 | 100% | 651.2 | 583.27 | 67.93 | 69.93 | 189.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 850.7100. - IMP Interior Mech/Piping | 71.76 | 0 | -71.76 |  | 0 | 0 | 0% | 0 | -71.76 | 71.76 | 71.76 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2020. - CG Clearing/Grubbing | 576.24 | 20 | -556.24 | 2881% | 20 | 20 | 100% | 20 | -556.24 | 576.24 | 576.24 | -2681% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2080. - EXS Excavate Structure | 321.79 | 350 | 28.21 | 91.94% | 75 | 75 | 100% | 350 | 28.21 | 321.79 | 321.62 | 108.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.7800. - PRK Park Equipment | 21.13 | 98 | 76.87 | 21.56% | 70 | 70 | 100% | 98 | 76.87 | 21.13 | 21.13 | 178.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2800. - BFST Backfill (DO NOT USE) | 278.21 | 180 | -98.21 | 154.6% | 135 | 135 | 100% | 180 | -98.21 | 278.21 | 274.76 | 47.36% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.2080. - EXS Excavate Structure | 8.12 | 50.5 | 42.38 | 16.08% | 0 | 45 | 0% | 50.5 | 42.38 | 50.5 | 8.12 | 183.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2060. - FE Fencing | 16.02 | 12 | -4.02 | 133.5% | 18 | 18 | 100% | 12 | -4.02 | 16.02 | 16.02 | 66.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.7100. - IMP Interior Mech/Piping | 161.25 | 125.67 | -35.58 | 128.3% | 269 | 269 | 76.12% | 95.6585 | -65.5915 | 211.84 | 227.25 | 19.17% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2750. - Unknown Phase | 8.44 | 3.2 | -5.24 | 263.8% | 0 | 2 | 0% | 3.2 | -5.24 | 8.44 | 8.44 | -63.75% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 800.1930. - MC Misc Cleanup | 306.21 | 375 | 68.79 | 81.66% | 270 | 300 | 90% | 337.5 | 31.29 | 340.2333 | 432.01 | 84.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7800. - PRK Park Equipment | 21 | 96.3 | 75.3 | 21.81% | 72 | 72 | 100% | 96.3 | 75.3 | 21 | 21 | 178.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 88.35 | 1079.77 | 991.42 | 8.182% | 501.34 | 501.34 | 100% | 1079.77 | 991.42 | 88.35 | 98.35 | 190.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1930. - MC Misc Cleanup | 22.05 | 60 | 37.95 | 36.75% | 54 | 60 | 70% | 42 | 19.95 | 31.5 | 62.05 | 96.58% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1610. - TC Concrete & Water Barrier | 20 | 181.34 | 161.34 | 11.03% | 110.67 | 110.67 | 100% | 181.34 | 161.34 | 20 | 20 | 189% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2750. - H Hauling | 269.55 | 135.38 | -134.17 | 199.1% | 103.8 | 134.8 | 85% | 115.073 | -154.477 | 317.1176 | 290.29 | -14.43% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2060. - FE Fencing | 2 | 20 | 18 | 10% | 30 | 30 | 80% | 16 | 14 | 2.5 | 2 | 190% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 1704.43 | 1618.52 | -85.91 | 105.3% | 872.52 | 832.52 | 100% | 1618.52 | -85.91 | 1704.43 | 1837.43 | 86.47% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1704. - FS Quality Control/Assurance | 3551.76 | 681.21 | -2870.55 | 521.4% | 90 | 681.21 | 87.5% | 596.0588 | -2955.7013 | 4059.1543 | 3598.76 | -328.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.5100. - W Welding | 838.1 | 122 | -716.1 | 687% | 61 | 61 | 100% | 122 | -716.1 | 838.1 | 854.1 | -500.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 290.7800. - PRK Park Equipment | 2241.04 | 1603.6 | -637.44 | 139.8% | 1312.16 | 1202.4 | 97.63% | 1565.5192 | -675.5208 | 2295.5527 | 2268.04 | 58.57% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2750. - H Hauling | 271.02 | 103.29 | -167.73 | 262.4% | 105.29 | 103.29 | 100% | 103.29 | -167.73 | 271.02 | 275.95 | -67.16% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2750. - H Hauling | 394.18 | 120.45 | -273.73 | 327.3% | 81.81 | 98.41 | 100% | 120.45 | -273.73 | 394.18 | 372.11 | -108.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2710. - FWF Flowable Fill | 182.65 | 209.52 | 26.87 | 87.18% | 419.04 | 419.04 | 100% | 209.52 | 26.87 | 182.65 | 203.38 | 102.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2750. - H Hauling | 665.39 | 1197.64 | 532.25 | 55.56% | 1197.64 | 1197.64 | 100% | 1197.64 | 532.25 | 665.39 | 663.64 | 144.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1930. - MC Misc Cleanup | 239.9 | 60 | -179.9 | 399.8% | 0 | 60 | 0% | 60 | -179.9 | 239.9 | 239.9 | -199.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2060. - FE Fencing | 30.67 | 10 | -20.67 | 306.7% | 15 | 15 | 92% | 9.2 | -21.47 | 33.337 | 30.67 | -106.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2080. - EXS Excavate Structure | 218.33 | 220 | 1.67 | 99.24% | 90 | 90 | 100% | 220 | 1.67 | 218.33 | 218.33 | 100.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2710. - FWF Flowable Fill | 16.18 | 13.33 | -2.85 | 121.4% | 40 | 40 | 100% | 13.33 | -2.85 | 16.18 | 16.18 | 78.62% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2050. - RW Retaining Walls | 539.69 | 60 | -479.69 | 899.5% | 118.33 | 80 | 100% | 60 | -479.69 | 539.69 | 539.69 | -699.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.5000. - MET Metals | 30.2 | 43 | 12.8 | 70.23% | 43 | 43 | 97.5% | 41.925 | 11.725 | 30.9744 | 30.2 | 129.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 270.2760. - HO Haul Off | -1.83 | 65 | 66.83 | -2.815% | 37.05 | 65 | 60% | 39 | 40.83 | -3.05 | 0.17 | 199.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2940. - CP Concrete Prep (DO NOT USE) | 439.86 | 855.86 | 416 | 51.39% | 840.02 | 790.02 | 100% | 855.86 | 416 | 439.86 | 442.86 | 148.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1940. - PL Punch List Work | 26.45 | 30 | 3.55 | 88.17% | 0 | 90 | 0% | 30 | 3.55 | 30 | 56.45 | 11.83% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 8 | 390 | 382 | 2.051% | 45.225 | 380 | 90% | 351 | 343 | 8.8889 | 8 | 197.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1930. - MC Misc Cleanup | 44.39 | 80 | 35.61 | 55.49% | 60 | 80 | 62.5% | 50 | 5.61 | 71.024 | 69.39 | 113.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.7100. - IMP Interior Mech/Piping | 283.13 | 68.33 | -214.8 | 414.4% | 119.592 | 131.5 | 59.93% | 40.9472 | -242.1828 | 472.4689 | 324.13 | -274.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1930. - MC Misc Cleanup | 273.85 | 110 | -163.85 | 249% | 60 | 100 | 30% | 33 | -240.85 | 912.8333 | 338.37 | -107.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2750. - H Hauling | 94.53 | 67.79 | -26.74 | 139.4% | 50.46 | 61.79 | 100% | 67.79 | -26.74 | 94.53 | 108.78 | 39.53% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2080. - EXS Excavate Structure | 222.22 | 432.5 | 210.28 | 51.38% | 320 | 320 | 99.87% | 431.926 | 209.706 | 222.5153 | 222.22 | 148.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2800. - BFST Backfill (DO NOT USE) | 487.97 | 207.32 | -280.65 | 235.4% | 153.99 | 153.99 | 82.79% | 171.6319 | -316.3381 | 589.4356 | 489.97 | -36.34% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 380.2610. - PT Pressure Test/Chlorinating | 475.77 | 246.25 | -229.52 | 193.2% | 315.5 | 310 | 99.56% | 245.1614 | -230.6086 | 477.8827 | 475.77 | 6.794% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1930. - MC Misc Cleanup | 10.47 | 80 | 69.53 | 13.09% | 40 | 80 | 50% | 40 | 29.53 | 20.94 | 90.47 | 86.91% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 280.2300. - WPL Water Pipe Laying (DO NOT USE) | 14.64 | 100 | 85.36 | 14.64% | 45 | 40 | 100% | 100 | 85.36 | 14.64 | 14.64 | 185.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2750. - H Hauling | 173.43 | 458.86 | 285.43 | 37.8% | 422.69 | 458.86 | 36.04% | 165.3937 | -8.0363 | 481.1555 | 153.99 | 166.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.6200. - IN Insulation | 97.86 | 50 | -47.86 | 195.7% | 41.4 | 150 | 22.02% | 11.0106 | -86.8494 | 444.3884 | 430.95 | -661.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2940. - CP Concrete Prep (DO NOT USE) | 28.1 | 22.54 | -5.56 | 124.7% | 20.8 | 20.8 | 100% | 22.54 | -5.56 | 28.1 | 28.1 | 75.33% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2750. - H Hauling | 182.21 | 228.87 | 46.66 | 79.61% | 284.784 | 228.87 | 93.59% | 214.2071 | 31.9971 | 194.6826 | 251.44 | 90.14% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2940. - CP Concrete Prep (DO NOT USE) | 3.4 | 20 | 16.6 | 17% | 0 | 15 | 0% | 20 | 16.6 | 20 | 3.4 | 183% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.3000. - CNC Concrete Work | 498.56 | 80 | -418.56 | 623.2% | 135 | 180 | 100% | 80 | -418.56 | 498.56 | 498.56 | -423.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2800. - BFST Backfill (DO NOT USE) | 505.92 | 404 | -101.92 | 125.2% | 151.5 | 303 | 21.43% | 86.5714 | -419.3486 | 2360.96 | 769.89 | 9.433% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 395.5100. - W Welding | 7918.27 | 7592 | -326.27 | 104.3% | 3717.8 | 3787 | 98.78% | 7499.49 | -418.78 | 8015.9459 | 7946.52 | 95.33% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2800. - BFST Backfill (DO NOT USE) | 594.02 | 897.32 | 303.3 | 66.2% | 631.67 | 633.46 | 71.32% | 639.9341 | 45.9141 | 832.939 | 589.02 | 134.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1510. - S Surveying | 1034.36 | 237.5 | -796.86 | 435.5% | 95 | 115 | 98.33% | 233.5417 | -800.8183 | 1051.8915 | 1034.36 | -235.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 185.31 | 1432.96 | 1247.65 | 12.93% | 273.1 | 546.19 | 100% | 1432.96 | 1247.65 | 185.31 | 185.31 | 187.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.5000. - MET Metals | 188.4 | 701 | 512.6 | 26.88% | 55.288 | 557.5 | 7.51% | 52.6461 | -135.7539 | 2508.6076 | 596.4 | 114.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 390.2300. - WPL Water Pipe Laying (DO NOT USE) | 2754.87 | 1297.58 | -1457.29 | 212.3% | 3134.53 | 3512.71 | 99.77% | 1294.6171 | -1460.2529 | 2761.175 | 2753.37 | -12.19% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9010. - Re-Work Pipe | 128.17 | 0.2 | -127.97 | 64085% | 0.4 | 0.4 | 100% | 0.2 | -127.97 | 128.17 | 128.17 | -63885% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1705. - FS Estimator/Change Orders/Scheduling | 0 | 10 | 10 | 0% | 10 | 10 | 100% | 10 | 10 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1230. - T Transporting | 218.26 | 120 | -98.26 | 181.9% | 114 | 120 | 95% | 114 | -104.26 | 229.7474 | 218.26 | 18.12% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 240.2760. - HO Haul Off | 558.02 | 625.5 | 67.48 | 89.21% | 625.5 | 625.5 | 100% | 625.5 | 67.48 | 558.02 | 490.87 | 121.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1200. - HOOK Hook Truck Dumpster Transporting | 9.63 | 10 | 0.37 | 96.3% | 7.5 | 10 | 100% | 10 | 0.37 | 9.63 | 11.8 | 82% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1230. - T Transporting | 12 | 40 | 28 | 30% | 40 | 40 | 125% | 50 | 38 | 9.6 | 12 | 170% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2020. - Unknown Phase | 2180.27 | 3171.6 | 991.33 | 68.74% | 1704.6 | 1704.6 | 100% | 3171.6 | 991.33 | 2180.27 | 2228.17 | 129.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.5100. - W Welding | 82.67 | 35 | -47.67 | 236.2% | 17.5 | 17.5 | 100% | 35 | -47.67 | 82.67 | 82.67 | -36.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2300. - WPL Water Pipe Laying (DO NOT USE) | 23898.43 | 7273.25 | -16625.18 | 328.6% | 5978.25 | 6207.75 | 100% | 7273.25 | -16625.18 | 23898.43 | 23736.26 | -126.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.6200. - IN Insulation | 49.85 | 30 | -19.85 | 166.2% | 171.9 | 60 | 90% | 27 | -22.85 | 55.3889 | 49.85 | 33.83% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2020. - CG Clearing/Grubbing | 59.86 | 8 | -51.86 | 748.2% | 4 | 4 | 100% | 8 | -51.86 | 59.86 | 59.86 | -548.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2020. - CG Clearing/Grubbing | 8.58 | 8 | -0.58 | 107.2% | 6 | 6 | 100% | 8 | -0.58 | 8.58 | 8.58 | 92.75% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7100. - IMP Interior Mech/Piping | 186.61 | 105.01 | -81.6 | 177.7% | 201.906 | 224.34 | 69.07% | 72.526 | -114.084 | 270.1915 | 189.91 | 19.15% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2800. - BFST Backfill (DO NOT USE) | 234.69 | 2241.82 | 2007.13 | 10.47% | 1623.357 | 1653.73 | 90% | 2017.638 | 1782.948 | 260.7667 | 234.69 | 189.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.7900. - ELC Electrical | 546.41 | 190 | -356.41 | 287.6% | 173.33 | 253.33 | 57.57% | 109.3848 | -437.0252 | 949.1069 | 545.41 | -87.06% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2300. - WPL Water Pipe Laying (DO NOT USE) | 67.3 | 160.09 | 92.79 | 42.04% | 113.06 | 113.06 | 100% | 160.09 | 92.79 | 67.3 | 67.3 | 158% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2080. - EXS Excavate Structure | 420.81 | 3158 | 2737.19 | 13.33% | 558 | 558 | 100% | 3158 | 2737.19 | 420.81 | 419.31 | 186.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.6500. - P Painting | 0 | 0 | 0 |  | 0 | 150 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 270.2750. - H Hauling | 3.73 | 32.96 | 29.23 | 11.32% | 18.786 | 32.96 | 60% | 19.776 | 16.046 | 6.2167 | 15.73 | 152.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 240.2300. - WPL Water Pipe Laying (DO NOT USE) | 9745.91 | 2090 | -7655.91 | 466.3% | 1590.75 | 1784 | 100% | 2090 | -7655.91 | 9745.91 | 9749.95 | -266.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 340.2300. - WPL Water Pipe Laying (DO NOT USE) | 174.64 | 540.98 | 366.34 | 32.28% | 529.083 | 540.98 | 98.17% | 531.0648 | 356.4248 | 177.9006 | 193.64 | 164.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1700. - FS Project Manager | 32.25 | 20 | -12.25 | 161.2% | 0 | 20 | 0% | 20 | -12.25 | 32.25 | 72.25 | -161.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.7100. - IMP Interior Mech/Piping | 341.76 | 145.4 | -196.36 | 235% | 171 | 171 | 65.53% | 95.2866 | -246.4734 | 521.4992 | 310.04 | -13.23% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.6200. - IN Insulation | 4 | 10 | 6 | 40% | 0 | 30 | 0% | 10 | 6 | 10 | 34.92 | -149.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.3000. - CNC Concrete Work | 803.05 | 338.62 | -464.43 | 237.2% | 918.995 | 937.75 | 98% | 331.8476 | -471.2024 | 819.4388 | 923.05 | -72.59% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1230. - T Transporting | 140.98 | 90 | -50.98 | 156.6% | 90 | 90 | 100% | 90 | -50.98 | 140.98 | 141.98 | 42.24% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.1510. - S Surveying | 144.32 | 176 | 31.68 | 82% | 88 | 88 | 100% | 176 | 31.68 | 144.32 | 144.32 | 118% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1703. - FS Job Site Superintendent | 7852.91 | 6138.16 | -1714.75 | 127.9% | 90 | 6138.16 | 87.5% | 5370.89 | -2482.02 | 8974.7543 | 8087.91 | 68.24% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 330.1600. - TC Traffic Control | 2017.87 | 9300 | 7282.13 | 21.7% | 860 | 800 | 99.07% | 9213.2464 | 7195.3764 | 2036.8706 | 2040.6 | 178.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2070. - RGC Rough Grade Cut | 18.32 | 8 | -10.32 | 229% | 6 | 12 | 50% | 4 | -14.32 | 36.64 | 18.32 | -29% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1940. - PL Punch List Work | 0 | 30 | 30 | 0% | 0 | 90 | 0% | 30 | 30 | 30 | 30 | 100% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.5100. - W Welding | 210.67 | 130 | -80.67 | 162.1% | 65 | 65 | 40% | 52 | -158.67 | 526.675 | 260.67 | -0.5154% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1230. - T Transporting | 193.83 | 50 | -143.83 | 387.7% | 50 | 50 | 100% | 50 | -143.83 | 193.83 | 193.83 | -187.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.1230. - T Transporting | 6267.56 | 867 | -5400.56 | 722.9% | 972 | 862 | 87.8% | 761.208 | -5506.352 | 7138.6195 | 6335.92 | -530.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.5000. - MET Metals | 941.35 | 351.5 | -589.85 | 267.8% | 371.4 | 389.4 | 54.88% | 192.8927 | -748.4573 | 1715.3812 | 973.35 | -76.91% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9005. - Re-Work Surveying | 44 | 2 | -42 | 2200% | 1 | 1 | 100% | 2 | -42 | 44 | 44 | -2000% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 235.2080. - EXS Excavate Structure | 278.15 | 2940 | 2661.85 | 9.461% | 360 | 360 | 100% | 2940 | 2661.85 | 278.15 | 266.15 | 190.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.7800. - PRK Park Equipment | 380.04 | 43.32 | -336.72 | 877.3% | 36.66 | 36.66 | 100% | 43.32 | -336.72 | 380.04 | 380.04 | -677.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 181.3100. - CNC Rebar | 224.26 | 0 | -224.26 |  | 0 | 0 | 0% | 0 | -224.26 | 224.26 | 224.26 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.3000. - CNC Concrete Work | 2503.85 | 731.92 | -1771.93 | 342.1% | 1503.416 | 1879.27 | 57.58% | 421.4095 | -2082.4405 | 4348.7818 | 2707.6 | -169.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2760. - HO Haul Off | 0 | 152.5 | 152.5 | 0% | 22.875 | 152.5 | 99.98% | 152.4667 | 152.4667 | 0 | 4 | 197.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 183.32 | 265.5 | 82.18 | 69.05% | 110 | 201 | 100% | 265.5 | 82.18 | 183.32 | 183.32 | 131% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1510. - S Surveying | 45.12 | 230 | 184.88 | 19.62% | 75 | 110 | 100% | 230 | 184.88 | 45.12 | 57.54 | 175% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.6500. - P Painting | 0 | 0 | 0 |  | 32.03 | 60 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1930. - MC Misc Cleanup | 10.55 | 40 | 29.45 | 26.38% | 36 | 40 | 90% | 36 | 25.45 | 11.7222 | 20.55 | 148.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1710. - FS Starup/Commissioning | 1.29 | 30 | 28.71 | 4.3% | 0 | 40 | 0% | 30 | 28.71 | 30 | 41.29 | 62.37% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1200. - HOOK Hook Truck Dumpster Transporting | 3.7 | 20 | 16.3 | 18.5% | 13 | 20 | 65% | 13 | 9.3 | 5.6923 | 3.7 | 181.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1600. - TC Traffic Control | 70.5 | 1050 | 979.5 | 6.714% | 400 | 400 | 100% | 1050 | 979.5 | 70.5 | 70.5 | 193.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.5100. - W Welding | 99.33 | 316.6 | 217.27 | 31.37% | 80 | 80 | 100% | 316.6 | 217.27 | 99.33 | 99.33 | 168.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.5100. - W Welding | 334.52 | 66.34 | -268.18 | 504.3% | 16.67 | 30.17 | 100% | 66.34 | -268.18 | 334.52 | 332.52 | -301.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1700. - FS Project Manager | 2527.75 | 4180.8 | 1653.05 | 60.46% | 144 | 4180.8 | 87.23% | 3646.8037 | 1119.0537 | 2897.8848 | 2798.75 | 133.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.2750. - H Hauling | 74.2 | 1.14 | -73.06 | 6509% | 0 | 1.14 | 0% | 1.14 | -73.06 | 74.2 | 72.2 | -6133% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2040. - LR Landscaping/Restoration | 98.28 | 4268.71 | 4170.43 | 2.302% | 2349.19 | 2865.59 | 100% | 4268.71 | 4170.43 | 98.28 | 95.28 | 197.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2750. - H Hauling | 279.05 | 200.25 | -78.8 | 139.4% | 95.725 | 191.45 | 37.5% | 75.0935 | -203.9565 | 744.1359 | 337.68 | 31.37% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7100. - IMP Interior Mech/Piping | 313.9 | 184.66 | -129.24 | 170% | 410.33 | 410.33 | 73.62% | 135.9459 | -177.9541 | 426.3813 | 361.74 | 4.105% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.6300. - DAW Doors & Windows | 55.67 | 30 | -25.67 | 185.6% | 63 | 90 | 52.5% | 15.75 | -39.92 | 106.0381 | 105.67 | -152.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2410. - IS Irrigation Services (DO NOT USE) | 99.53 | 1017.33 | 917.8 | 9.783% | 658.84 | 658.84 | 100% | 1017.33 | 917.8 | 99.53 | 88.53 | 191.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.7900. - ELC Electrical | 102.82 | 123.72 | 20.9 | 83.11% | 42.002 | 200.28 | 20% | 24.744 | -78.076 | 514.1 | 103.82 | 116.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2750. - H Hauling | 285.42 | 804.73 | 519.31 | 35.47% | 797.73 | 804.73 | 100% | 804.73 | 519.31 | 285.42 | 283.54 | 164.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2800. - BFST Backfill (DO NOT USE) | 528.81 | 517.88 | -10.93 | 102.1% | 214.956 | 388.41 | 90% | 466.092 | -62.718 | 587.5667 | 528.81 | 97.89% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 295.7900. - ELC Electrical | 476.37 | 1459.83 | 983.46 | 32.63% | 1913.21 | 1931.34 | 100% | 1459.83 | 983.46 | 476.37 | 481.37 | 167% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2760. - HO Haul Off | 582.07 | 1645 | 1062.93 | 35.38% | 1645 | 1645 | 100% | 1645 | 1062.93 | 582.07 | 560.5 | 165.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 285.2760. - HO Haul Off | 6 | 98.5 | 92.5 | 6.091% | 98.5 | 98.5 | 100% | 98.5 | 92.5 | 6 | 5 | 194.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2050. - RW Retaining Walls | 176.98 | 42.61 | -134.37 | 415.3% | 31.96 | 63.92 | 68% | 28.9734 | -148.0066 | 260.2776 | 31.98 | 124.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 210.2750. - H Hauling | 209.19 | 271.82 | 62.63 | 76.96% | 135.91 | 271.82 | 100% | 271.82 | 62.63 | 209.19 | 229.91 | 115.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.5000. - MET Metals | 46.11 | 83 | 36.89 | 55.55% | 121.25 | 75 | 83.45% | 69.2621 | 23.1521 | 55.2558 | 55.71 | 132.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.5100. - W Welding | 26.44 | 40 | 13.56 | 66.1% | 20 | 20 | 100% | 40 | 13.56 | 26.44 | 26.44 | 133.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.2800. - BFST Backfill (DO NOT USE) | 215 | 21.33 | -193.67 | 1008% | 0 | 15.99 | 0% | 21.33 | -193.67 | 215 | 215 | -808% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2700. - SG Sand & Gravel | 6.37 | -10 | -16.37 |  | 1 | -10 | 100% | -10 | -16.37 | 6.37 | 2 | 220% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.3000. - CNC Concrete Work | 698.65 | 27.98 | -670.67 | 2497% | 18 | 50 | 56.52% | 15.8148 | -682.8352 | 1236.0731 | 686.65 | -2254% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2750. - H Hauling | 2134.32 | 1431.99 | -702.33 | 149% | 1412.49 | 1431.99 | 100% | 1431.99 | -702.33 | 2134.32 | 2111.04 | 52.58% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9015. - Re-Work Concrete | 27.26 | 0.2 | -27.06 | 13630% | 0.4 | 0.4 | 100% | 0.2 | -27.06 | 27.26 | 27.26 | -13430% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.2080. - EXS Excavate Structure | 309.74 | 2940 | 2630.26 | 10.54% | 360 | 360 | 100% | 2940 | 2630.26 | 309.74 | 309.74 | 189.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1500. - VIS Meetings (Vision, Safety, Training) | 95.51 | 0 | -95.51 |  | 0 | 0 | 0% | 0 | -95.51 | 95.51 | 95.51 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 15.67 | 279 | 263.33 | 5.616% | 90 | 90 | 100% | 279 | 263.33 | 15.67 | 15.67 | 194.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.7900. - ELC Electrical | 33.72 | 0 | -33.72 |  | 0 | 0 | 0% | 0 | -33.72 | 33.72 | 33.72 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2910. - MP Milling/Pulverize | 46.53 | 239.47 | 192.94 | 19.43% | 235.79 | 235.79 | 100% | 239.47 | 192.94 | 46.53 | 46.53 | 180.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 345.2300. - WPL Water Pipe Laying (DO NOT USE) | 2171.11 | 1050 | -1121.11 | 206.8% | 1050 | 1050 | 100% | 1050 | -1121.11 | 2171.11 | 2151.81 | -4.934% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7500. - PUMP Pumps/Motors | 107.31 | 15 | -92.31 | 715.4% | 45 | 45 | 91.67% | 13.75 | -93.56 | 117.0655 | 107.31 | -515.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 385.2300. - WPL Water Pipe Laying (DO NOT USE) | 107.79 | 1141.66 | 1033.87 | 9.442% | 2846.51 | 2968.34 | 99.97% | 1141.3211 | 1033.5311 | 107.822 | 102.79 | 191% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | -5.15 | 344 | 349.15 | -1.497% | 172 | 172 | 100% | 344 | 349.15 | -5.15 | -5.15 | 201.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2140. - SVR Services | 225.98 | 136 | -89.98 | 166.2% | 1 | 171 | 100% | 136 | -89.98 | 225.98 | 225.98 | 33.84% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2020. - CG Clearing/Grubbing | 420.96 | 120 | -300.96 | 350.8% | 30 | 60 | 100% | 120 | -300.96 | 420.96 | 425.96 | -155% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.6200. - IN Insulation | 145.99 | 28.16 | -117.83 | 518.4% | 84.48 | 84.48 | 100% | 28.16 | -117.83 | 145.99 | 110.99 | -194.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1510. - S Surveying | 589.14 | 100 | -489.14 | 589.1% | 50 | 50 | 100% | 100 | -489.14 | 589.14 | 589.14 | -389.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.7900. - ELC Electrical | 0 | 87.5 | 87.5 | 0% | 108 | 114 | 100% | 87.5 | 87.5 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2110. - SS Sewer Services (DO NOT USE) | 219.48 | 1153.75 | 934.27 | 19.02% | 580.67 | 580.67 | 100% | 1153.75 | 934.27 | 219.48 | 215.48 | 181.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7500. - PUMP Pumps/Motors | 20.64 | 15 | -5.64 | 137.6% | 45 | 45 | 97.5% | 14.625 | -6.015 | 21.1692 | 20.64 | 62.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2930. - AP Asphalt Prep (DO NOT USE) | 710.07 | 68.89 | -641.18 | 1031% | 88.88 | 88.88 | 100% | 68.89 | -641.18 | 710.07 | 704.19 | -822.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 114.02 | 78.06 | -35.96 | 146.1% | 0 | 83 | 0% | 78.06 | -35.96 | 114.02 | 111.52 | 57.14% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 750.2300. - WPL Water Pipe Laying (DO NOT USE) | 442.64 | 321.5 | -121.14 | 137.7% | 0 | 0 | 0% | 321.5 | -121.14 | 442.64 | 442.64 | 62.32% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1940. - PL Punch List Work | 5.94 | 30 | 24.06 | 19.8% | 0 | 90 | 0% | 30 | 24.06 | 30 | 35.94 | 80.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2080. - EXS Excavate Structure | 989.81 | 183.23 | -806.58 | 540.2% | 114.3 | 114.3 | 100% | 183.23 | -806.58 | 989.81 | 992.58 | -341.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.3000. - CNC Concrete Work | 1378.75 | 735 | -643.75 | 187.6% | 1824 | 1830 | 100% | 735 | -643.75 | 1378.75 | 1378.75 | 12.41% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2080. - EXS Excavate Structure | 1635.38 | 312.34 | -1323.04 | 523.6% | 231.67 | 231.67 | 100% | 312.34 | -1323.04 | 1635.38 | 1786.38 | -371.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.5000. - MET Metals | 94.87 | 40.01 | -54.86 | 237.1% | 22 | 42.02 | 86.22% | 34.4984 | -60.3716 | 110.0267 | 104.87 | -62.11% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.3000. - CNC Concrete Work | 1325.56 | 833 | -492.56 | 159.1% | 1894.25 | 1909.25 | 100% | 833 | -492.56 | 1325.56 | 1325.56 | 40.87% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9012. - Re-Work Mechanical | 3 | 0.2 | -2.8 | 1500% | 0.4 | 0.4 | 100% | 0.2 | -2.8 | 3 | 3 | -1300% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1230. - T Transporting | 285.83 | 62 | -223.83 | 461% | 60 | 62 | 100% | 62 | -223.83 | 285.83 | 285.83 | -261% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7500. - PUMP Pumps/Motors | 23.8 | 15 | -8.8 | 158.7% | 45 | 45 | 100% | 15 | -8.8 | 23.8 | 23.8 | 41.33% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2800. - BFST Backfill (DO NOT USE) | 1380.03 | 400.94 | -979.09 | 344.2% | 263.67 | 263.67 | 84.92% | 340.4711 | -1039.5589 | 1625.1282 | 1375.03 | -143% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 285.2300. - WPL Water Pipe Laying (DO NOT USE) | 815.02 | 444.15 | -370.87 | 183.5% | 238.866 | 387.38 | 60% | 266.49 | -548.53 | 1358.3667 | 818.52 | 15.71% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2760. - HO Haul Off | 94.37 | 0 | -94.37 |  | 0 | 0 | 0% | 0 | -94.37 | 94.37 | 109.87 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 180.2040. - LR Landscaping/Restoration | 5 | 20 | 15 | 25% | 1 | 20 | 66.67% | 13.3333 | 8.3333 | 7.5 | 5 | 175% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2710. - FWF Flowable Fill | 22.7 | 147.94 | 125.24 | 15.34% | 295.88 | 295.88 | 100% | 147.94 | 125.24 | 22.7 | 22.7 | 184.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.5100. - W Welding | 294.13 | 110 | -184.13 | 267.4% | 40 | 55 | 86.67% | 95.3333 | -198.7967 | 339.3808 | 294.13 | -67.39% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 210.2760. - HO Haul Off | 461.5 | 781 | 319.5 | 59.09% | 671.6 | 777 | 100% | 781 | 319.5 | 461.5 | 444.9 | 143% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 235.2800. - BFST Backfill (DO NOT USE) | 64.67 | 642 | 577.33 | 10.07% | 360 | 402 | 100% | 642 | 577.33 | 64.67 | 64.67 | 189.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.6200. - IN Insulation | 50.43 | 37 | -13.43 | 136.3% | 99.9 | 111 | 90% | 33.3 | -17.13 | 56.0333 | 50.43 | 63.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2030. - D Demolition | 4.37 | 51.5 | 47.13 | 8.485% | 39 | 39 | 100% | 51.5 | 47.13 | 4.37 | 4.37 | 191.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2080. - EXS Excavate Structure | 60.9 | 36.5 | -24.4 | 166.8% | 26 | 26 | 100% | 36.5 | -24.4 | 60.9 | 60.9 | 33.15% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 808.25 | 1814.28 | 1006.03 | 44.55% | 1035.71 | 1124.71 | 99.93% | 1812.9405 | 1004.6905 | 808.8472 | 792.25 | 156.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 305.2800. - BFST Backfill (DO NOT USE) | 58.92 | 21.33 | -37.59 | 276.2% | 0 | 15.99 | 0% | 21.33 | -37.59 | 58.92 | 58.92 | -76.23% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.2800. - BFST Backfill (DO NOT USE) | 337.47 | 210 | -127.47 | 160.7% | 180 | 180 | 100% | 210 | -127.47 | 337.47 | 332.47 | 41.68% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2070. - RGC Rough Grade Cut | 3607.09 | 761.8 | -2845.29 | 473.5% | 1460.3 | 1067 | 96.46% | 734.8384 | -2872.2516 | 3739.4362 | 3618.78 | -275% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1510. - S Surveying | 322.34 | 100 | -222.34 | 322.3% | 50 | 50 | 100% | 100 | -222.34 | 322.34 | 322.34 | -122.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 175.2300. - WPL Water Pipe Laying (DO NOT USE) | 147.23 | 0 | -147.23 |  | 1 | 0 | 66.67% | 0 | -147.23 | 220.845 | 156.33 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1940. - PL Punch List Work | 16 | 50 | 34 | 32% | 0 | 150 | 0% | 50 | 34 | 50 | 57.25 | 85.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2760. - HO Haul Off | 22.24 | 67.33 | 45.09 | 33.03% | 67.33 | 67.33 | 100% | 67.33 | 45.09 | 22.24 | 22.24 | 167% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.7500. - PUMP Pumps/Motors | 0 | 15 | 15 | 0% | 36 | 45 | 61.25% | 9.1875 | 9.1875 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7100. - IMP Interior Mech/Piping | 1054.92 | 164.96 | -889.96 | 639.5% | 343.767 | 361.86 | 73.08% | 120.5549 | -934.3651 | 1443.4879 | 1081.67 | -455.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.5000. - MET Metals | 33.57 | 140.5 | 106.93 | 23.89% | 0 | 132 | 0% | 140.5 | 106.93 | 140.5 | 173.57 | 76.46% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2800. - BFST Backfill (DO NOT USE) | 529.03 | 783.47 | 254.44 | 67.52% | 486.22 | 486.22 | 100% | 783.47 | 254.44 | 529.03 | 529.03 | 132.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.7100. - IMP Interior Mech/Piping | 76.4 | 60 | -16.4 | 127.3% | 64.8 | 120 | 60% | 36 | -40.4 | 127.3333 | 76.4 | 72.67% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.6500. - P Painting | 0 | 0 | 0 |  | 0 | 1077 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.7900. - ELC Electrical | 75.82 | 137.5 | 61.68 | 55.14% | 80 | 188 | 99.27% | 136.4927 | 60.6727 | 76.3796 | 75.82 | 144.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2300. - WPL Water Pipe Laying (DO NOT USE) | 6 | 77.69 | 71.69 | 7.723% | 117.69 | 117.69 | 100% | 77.69 | 71.69 | 6 | 8 | 189.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2300. - WPL Water Pipe Laying (DO NOT USE) | 1029.35 | 757.58 | -271.77 | 135.9% | 416.3 | 416.3 | 100% | 757.58 | -271.77 | 1029.35 | 1037.85 | 63% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2300. - WPL Water Pipe Laying (DO NOT USE) | 84.37 | 69 | -15.37 | 122.3% | 62 | 62 | 100% | 69 | -15.37 | 84.37 | 84.37 | 77.72% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.2800. - BFST Backfill (DO NOT USE) | 86.34 | 600 | 513.66 | 14.39% | 360 | 360 | 100% | 600 | 513.66 | 86.34 | 94.34 | 184.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2610. - PT Pressure Test/Chlorinating | 2.66 | 8.75 | 6.09 | 30.4% | 0 | 10 | 0% | 8.75 | 6.09 | 8.75 | 2.66 | 169.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.5100. - W Welding | 549.23 | 240 | -309.23 | 228.8% | 120 | 120 | 100% | 240 | -309.23 | 549.23 | 549.23 | -28.85% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2060. - Unknown Phase | 83.66 | 481.58 | 397.92 | 17.37% | 652.6 | 652.6 | 100% | 481.58 | 397.92 | 83.66 | 82.66 | 182.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2610. - PT Pressure Test/Chlorinating | 53.57 | 35 | -18.57 | 153.1% | 40 | 40 | 100% | 35 | -18.57 | 53.57 | 53.57 | 46.94% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.6000. - IF Interior Finishes | 10.23 | 2 | -8.23 | 511.5% | 6 | 6 | 75% | 1.5 | -8.73 | 13.64 | 10.23 | -311.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2800. - BFST Backfill (DO NOT USE) | 351.77 | 388.65 | 36.88 | 90.51% | 247.18 | 271.82 | 100% | 388.65 | 36.88 | 351.77 | 351.77 | 109.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.7100. - IMP Interior Mech/Piping | 234.45 | 100 | -134.45 | 234.4% | 84.375 | 150 | 67.31% | 67.3077 | -167.1423 | 348.3257 | 284.45 | -84.45% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.6200. - IN Insulation | 2.73 | 0.04 | -2.69 | 6825% | 1 | 0.12 | 50% | 0.02 | -2.71 | 5.46 | 2.73 | -6625% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 234.37 | 694 | 459.63 | 33.77% | 900 | 1076 | 100% | 693.9764 | 459.6064 | 234.378 | 234.37 | 166.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2760. - HO Haul Off | 49.11 | 764.92 | 715.81 | 6.42% | 583.677 | 798.04 | 90% | 688.428 | 639.318 | 54.5667 | 49.11 | 193.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 131.07 | 260.59 | 129.52 | 50.3% | 105.12 | 105.12 | 100% | 260.59 | 129.52 | 131.07 | 131.07 | 149.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2710. - FWF Flowable Fill | 0 | 204.44 | 204.44 | 0% | 408.88 | 408.88 | 100% | 204.44 | 204.44 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2750. - H Hauling | 275.41 | 95.4 | -180.01 | 288.7% | 14.31 | 95.4 | 100% | 95.4 | -180.01 | 275.41 | 261.41 | -74.01% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1510. - S Surveying | 152.28 | 60 | -92.28 | 253.8% | 30 | 30 | 100% | 60 | -92.28 | 152.28 | 152.28 | -53.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1930. - MC Misc Cleanup | 64.47 | 60 | -4.47 | 107.5% | 30 | 60 | 37.5% | 22.5 | -41.97 | 171.92 | 64.47 | 92.55% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1700. - FS Project Manager | 4 | 40 | 36 | 10% | 0 | 40 | 0% | 40 | 36 | 40 | 34 | 115% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.7100. - IMP Interior Mech/Piping | 774.44 | 494.67 | -279.77 | 156.6% | 326.2 | 1028 | 21.63% | 106.9925 | -667.4475 | 3580.5536 | 1236.45 | -49.95% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2750. - H Hauling | 331.31 | 144.47 | -186.84 | 229.3% | 132.27 | 135.27 | 80% | 115.576 | -215.734 | 414.1375 | 326.81 | -26.21% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2750. - H Hauling | 610.88 | 520.61 | -90.27 | 117.3% | 477.86 | 500.61 | 100% | 520.61 | -90.27 | 610.88 | 556.24 | 93.16% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1510. - S Surveying | 304.58 | 150 | -154.58 | 203.1% | 75 | 75 | 86.67% | 130 | -174.58 | 351.4385 | 304.58 | -3.053% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.6200. - IN Insulation | 75.96 | 34.09 | -41.87 | 222.8% | 161.7 | 102.27 | 99.42% | 33.8915 | -42.0685 | 76.405 | 82.96 | -43.36% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2750. - H Hauling | 58.52 | 0.09 | -58.43 | 65022% | 0.09 | 0.09 | 100% | 0.09 | -58.43 | 58.52 | 60.52 | -67044% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.6200. - IN Insulation | 126.27 | 28.16 | -98.11 | 448.4% | 84.48 | 84.48 | 100% | 28.16 | -98.11 | 126.27 | 136.27 | -283.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.5100. - W Welding | 41.3 | 15 | -26.3 | 275.3% | 7.5 | 7.5 | 100% | 15 | -26.3 | 41.3 | 32.8 | -18.67% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2080. - EXS Excavate Structure | 300.98 | 740 | 439.02 | 40.67% | 180 | 180 | 19.57% | 144.7826 | -156.1974 | 1538.3422 | 298.68 | 159.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2800. - BFST Backfill (DO NOT USE) | 172.79 | 600 | 427.21 | 28.8% | 360 | 360 | 100% | 600 | 427.21 | 172.79 | 172.79 | 171.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1200. - HOOK Hook Truck Dumpster Transporting | 277.34 | 60 | -217.34 | 462.2% | 57 | 60 | 92.5% | 55.5 | -221.84 | 299.827 | 303.51 | -305.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.7900. - ELC Electrical | 50.95 | 55 | 4.05 | 92.64% | 90 | 90 | 100% | 55 | 4.05 | 50.95 | 50.95 | 107.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 285.2750. - H Hauling | 40.42 | 92.18 | 51.76 | 43.85% | 13.83 | 92.18 | 100% | 92.18 | 51.76 | 40.42 | 40.42 | 156.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.6500. - P Painting | 0 | 0 | 0 |  | 0 | 225 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.7800. - PRK Park Equipment | 85.98 | 32.5 | -53.48 | 264.6% | 42.5 | 42.5 | 56.67% | 18.4167 | -67.5633 | 151.7294 | 110.98 | -141.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1702. - FS People Superintendent | 11182.04 | 2901.22 | -8280.82 | 385.4% | 225 | 2901.22 | 87.5% | 2538.5675 | -8643.4725 | 12779.4743 | 11281.65 | -188.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1100. - TF Temporary Office Trailer, Conex, Dumpsters, Skids | 77.8 | 0 | -77.8 |  | 0 | 0 | 0% | 0 | -77.8 | 77.8 | 107.8 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.7100. - IMP Interior Mech/Piping | 561.32 | 180.2 | -381.12 | 311.5% | 306.9 | 357 | 59.8% | 107.7618 | -453.5582 | 938.6426 | 746.04 | -214% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2710. - FWF Flowable Fill | 3 | 34.46 | 31.46 | 8.706% | 6.204 | 68.92 | 60% | 20.676 | 17.676 | 5 | 3 | 191.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.5000. - MET Metals | 141.27 | 151.5 | 10.23 | 93.25% | 228.51 | 171 | 90% | 136.35 | -4.92 | 156.9667 | 141.27 | 106.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.6500. - P Painting | 0 | 0 | 0 |  | 17.25 | 345 | 100% | 0 | 0 | 0 | 0 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.6500. - P Painting | 3 | 0 | -3 |  | 0 | 90 | 0% | 0 | -3 | 3 | 3 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2760. - HO Haul Off | 2110.11 | 1657 | -453.11 | 127.3% | 1657 | 1657 | 100% | 1657 | -453.11 | 2110.11 | 2073.54 | 74.86% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1940. - PL Punch List Work | 0 | 100 | 100 | 0% | 0 | 200 | 0% | 100 | 100 | 100 | 100 | 100% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.2750. - H Hauling | 29.86 | 0.68 | -29.18 | 4391% | 0.68 | 0.68 | 100% | 0.68 | -29.18 | 29.86 | 29.86 | -4191% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2060. - FE Fencing | 11.6 | 16 | 4.4 | 72.5% | 24 | 24 | 100% | 16 | 4.4 | 11.6 | 11.6 | 127.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 360.5100. - W Welding | 88.93 | 0 | -88.93 |  | 0 | 0 | 0% | 0 | -88.93 | 88.93 | 88.93 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.3000. - CNC Concrete Work | 5 | 36 | 31 | 13.89% | 33.6 | 84 | 40% | 14.4 | 9.4 | 12.5 | 5 | 186.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.6000. - IF Interior Finishes | 15.25 | 2 | -13.25 | 762.5% | 5.7 | 6 | 93.75% | 1.875 | -13.375 | 16.2667 | 35.25 | -1562% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7900. - ELC Electrical | 5 | 90.1 | 85.1 | 5.549% | 89.802 | 122.67 | 60% | 54.06 | 49.06 | 8.3333 | 5 | 194.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2030. - Unknown Phase | 361.65 | 2934.77 | 2573.12 | 12.32% | 1583.47 | 1583.47 | 100% | 2934.77 | 2573.12 | 361.65 | 361.65 | 187.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.2800. - BFST Backfill (DO NOT USE) | 125.65 | 80 | -45.65 | 157.1% | 31.5 | 60 | 50% | 40 | -85.65 | 251.3 | 125.65 | 42.94% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.7500. - PUMP Pumps/Motors | 13.2 | 15 | 1.8 | 88% | 45 | 45 | 90% | 13.5 | 0.3 | 14.6667 | 13.2 | 112% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2760. - Unknown Phase | 10.75 | 10 | -0.75 | 107.5% | 1 | 10 | 100% | 10 | -0.75 | 10.75 | 16.5 | 35% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.7100. - IMP Interior Mech/Piping | 19.64 | 20 | 0.36 | 98.2% | 0 | 30 | 0% | 20 | 0.36 | 20 | 19.64 | 101.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.6200. - IN Insulation | 61.14 | 70 | 8.86 | 87.34% | 189 | 210 | 67.5% | 47.25 | -13.89 | 90.5778 | 76.14 | 91.23% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 250.2300. - WPL Water Pipe Laying (DO NOT USE) | 3736.9 | 1011.78 | -2725.12 | 369.3% | 1855.14 | 855.14 | 100% | 1011.78 | -2725.12 | 3736.9 | 3779.3 | -173.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1650. - SB Signage | 10.52 | 25 | 14.48 | 42.08% | 20 | 20 | 100% | 25 | 14.48 | 10.52 | 10.52 | 157.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.3000. - CNC Concrete Work | 864.27 | 517 | -347.27 | 167.2% | 1282.87 | 1325.87 | 100% | 517 | -347.27 | 864.27 | 984.27 | 9.619% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2760. - HO Haul Off | 274.56 | 158.94 | -115.62 | 172.7% | 158.94 | 158.94 | 100% | 158.94 | -115.62 | 274.56 | 277.06 | 25.68% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2080. - EXS Excavate Structure | 94.13 | 164.3 | 70.17 | 57.29% | 117.26 | 117.26 | 100% | 164.3 | 70.17 | 94.13 | 94.13 | 142.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2800. - BFST Backfill (DO NOT USE) | 284.4 | 160 | -124.4 | 177.8% | 120 | 120 | 100% | 160 | -124.4 | 284.4 | 289.4 | 19.12% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9055. - Re-Work Finishes | 6 | 1 | -5 | 600% | 3 | 3 | 100% | 1 | -5 | 6 | 6 | -400% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.7800. - PRK Park Equipment | 22.31 | 52.5 | 30.19 | 42.5% | 47.5 | 47.5 | 100% | 52.5 | 30.19 | 22.31 | 22.31 | 157.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1230. - T Transporting | 110.23 | 100 | -10.23 | 110.2% | 64 | 100 | 80% | 80 | -30.23 | 137.7875 | 119.88 | 80.12% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.3000. - CNC Concrete Work | 544.45 | 475.76 | -68.69 | 114.4% | 1317.13 | 1317.13 | 100% | 475.76 | -68.69 | 544.45 | 664.45 | 60.34% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 320.21 | 4731.8 | 4411.59 | 6.767% | 0 | 0 | 0% | 4731.8 | 4411.59 | 4731.8 | 327.04 | 193.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2030. - D Demolition | 6.15 | 69.08 | 62.93 | 8.903% | 66.81 | 66.81 | 100% | 69.08 | 62.93 | 6.15 | 6.15 | 191.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2760. - HO Haul Off | 3 | 32.15 | 29.15 | 9.331% | 1.61 | 32.15 | 100% | 32.15 | 29.15 | 3 | 8.16 | 174.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2930. - AP Asphalt Prep (DO NOT USE) | 720.26 | 593.46 | -126.8 | 121.4% | 181.916 | 321.46 | 87.5% | 519.2806 | -200.9794 | 823.1494 | 749.26 | 73.75% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.7100. - IMP Interior Mech/Piping | 425.83 | 4.5 | -421.33 | 9463% | 13.5 | 13.5 | 81.25% | 3.6562 | -422.1737 | 524.0985 | 422.51 | -9189% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.1230. - T Transporting | 325.8 | 90 | -235.8 | 362% | 63 | 90 | 40% | 36 | -289.8 | 814.5 | 310.63 | -145.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2070. - RGC Rough Grade Cut | 79.74 | 1099 | 1019.26 | 7.256% | 869.56 | 1099 | 88.02% | 967.3193 | 887.5793 | 90.595 | 106.22 | 190.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2800. - BFST Backfill (DO NOT USE) | 216.53 | 60 | -156.53 | 360.9% | 33.75 | 45 | 100% | 60 | -156.53 | 216.53 | 215.53 | -159.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.5100. - W Welding | 5.95 | 60 | 54.05 | 9.917% | 0.8 | 30 | 88.89% | 53.3333 | 47.3833 | 6.6937 | 5.95 | 190.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 160.5000. - Unknown Phase | 32.79 | 276 | 243.21 | 11.88% | -27.43 | 197 | 123.9% | 342.0392 | 309.2492 | 26.4591 | 32.79 | 188.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2760. - HO Haul Off | 10.64 | 28.57 | 17.93 | 37.24% | 28.57 | 28.57 | 100% | 28.57 | 17.93 | 10.64 | 10.64 | 162.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.3000. - CNC Concrete Work | 370.2 | 432.99 | 62.79 | 85.5% | 1038 | 1041.99 | 94.12% | 407.5408 | 37.3408 | 393.3174 | 490.2 | 86.79% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2760. - HO Haul Off | 117.04 | 28.79 | -88.25 | 406.5% | 26.79 | 28.79 | 100% | 28.79 | -88.25 | 117.04 | 96.04 | -133.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2070. - RGC Rough Grade Cut | 127.88 | 52 | -75.88 | 245.9% | 48 | 48 | 100% | 52 | -75.88 | 127.88 | 127.88 | -45.92% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 270.2300. - WPL Water Pipe Laying (DO NOT USE) | 625.09 | 354.4 | -270.69 | 176.4% | 211.074 | 345.26 | 60% | 212.64 | -412.45 | 1041.8167 | 611.09 | 27.57% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1230. - T Transporting | 439.02 | 122 | -317.02 | 359.9% | 98 | 122 | 89% | 108.58 | -330.44 | 493.2809 | 437.52 | -158.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1940. - PL Punch List Work | 5.95 | 60 | 54.05 | 9.917% | 0 | 180 | 0% | 60 | 54.05 | 60 | 65.95 | 90.08% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.7900. - ELC Electrical | 47.58 | 128.72 | 81.14 | 36.96% | 119.97 | 140.28 | 100% | 128.72 | 81.14 | 47.58 | 47.58 | 163% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.3000. - CNC Concrete Work | 49.44 | 150 | 100.56 | 32.96% | 353.5 | 350 | 100% | 150 | 100.56 | 49.44 | 56.44 | 162.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.6300. - DAW Doors & Windows | 21.85 | 20 | -1.85 | 109.2% | 60 | 60 | 93.75% | 18.75 | -3.1 | 23.3067 | 21.85 | 90.75% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9100. - Job Related Equipment Repairs | 15.5 | 1 | -14.5 | 1550% | 1 | 1 | 66.67% | 0.66667 | -14.8333 | 23.25 | 15.5 | -1350% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1230. - T Transporting | 348.98 | 50 | -298.98 | 698% | 50 | 50 | 90% | 45 | -303.98 | 387.7556 | 371.78 | -543.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1515. - S Drone/Lidar Requirements | 401.24 | 11 | -390.24 | 3648% | 10.45 | 11 | 86.6% | 9.526 | -391.714 | 463.3256 | 431.24 | -3720% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.3000. - CNC Concrete Work | 11687.26 | 3186.97 | -8500.29 | 366.7% | 7799.86 | 8105.6 | 87.81% | 2798.3492 | -8888.9108 | 13310.3283 | 11487.86 | -160.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2020. - CG Clearing/Grubbing | 203.92 | 35.44 | -168.48 | 575.4% | 8.86 | 17.72 | 100% | 35.44 | -168.48 | 203.92 | 198.92 | -361.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1940. - PL Punch List Work | 21.26 | 50 | 28.74 | 42.52% | 0 | 150 | 0% | 50 | 28.74 | 50 | 71.26 | 57.48% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.6500. - P Painting | 12.67 | 0 | -12.67 |  | 75 | 75 | 100% | 0 | -12.67 | 12.67 | 12.67 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2760. - HO Haul Off | 656.11 | 257.08 | -399.03 | 255.2% | 257.08 | 257.08 | 62.5% | 160.675 | -495.435 | 1049.776 | 663.64 | -58.15% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.5000. - MET Metals | 117.39 | 115 | -2.39 | 102.1% | 57.42 | 114 | 60% | 69 | -48.39 | 195.65 | 127.71 | 88.95% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2760. - HO Haul Off | 386.54 | 74.29 | -312.25 | 520.3% | 74.29 | 74.29 | 90% | 66.861 | -319.679 | 429.4889 | 354.54 | -277.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.2300. - WPL Water Pipe Laying (DO NOT USE) | 323.7 | 190 | -133.7 | 170.4% | 270 | 270 | 100% | 190 | -133.7 | 323.7 | 323.7 | 29.63% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.5100. - W Welding | 73.87 | 100 | 26.13 | 73.87% | 32.5 | 50 | 100% | 100 | 26.13 | 73.87 | 123.87 | 76.13% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.2300. - WPL Water Pipe Laying (DO NOT USE) | 43.42 | 175 | 131.58 | 24.81% | 210 | 210 | 100% | 175 | 131.58 | 43.42 | 43.42 | 175.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.7800. - PRK Park Equipment | 1 | 107.8 | 106.8 | 0.9276% | 77.14 | 81.2 | 100% | 107.8 | 106.8 | 1 | 1 | 199.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1200. - HOOK Hook Truck Dumpster Transporting | 3.92 | 20 | 16.08 | 19.6% | 19 | 20 | 100% | 20 | 16.08 | 3.92 | 3.92 | 180.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7800. - PRK Park Equipment | 6.27 | 192.2 | 185.93 | 3.262% | 142 | 142 | 100% | 192.2 | 185.93 | 6.27 | 6.27 | 196.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2760. - HO Haul Off | 4452.78 | 2149 | -2303.78 | 207.2% | 2149 | 2149 | 100% | 2149 | -2303.78 | 4452.78 | 4515.2 | -10.11% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1510. - S Surveying | 21718.08 | 3753 | -17965.08 | 578.7% | 2137.5 | 2301 | 95% | 3565.35 | -18152.73 | 22861.1368 | 21932.78 | -384.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.3000. - CNC Concrete Work | 5 | 184 | 179 | 2.717% | 381.78 | 378 | 67.48% | 124.1605 | 119.1605 | 7.4098 | 5 | 197.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 1110.41 | 1855.1 | 744.69 | 59.86% | 906.06 | 906.06 | 100.8% | 1870.418 | 760.008 | 1101.3162 | 1123.27 | 139.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2300. - WPL Water Pipe Laying (DO NOT USE) | 2153.25 | 876.05 | -1277.2 | 245.8% | 671.39 | 675.9 | 81.29% | 712.1453 | -1441.1047 | 2648.8341 | 2160.25 | -46.59% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2930. - AP Asphalt Prep (DO NOT USE) | 4345.05 | 277.21 | -4067.84 | 1567% | 1108.764 | 334.73 | 66.68% | 184.8402 | -4160.2098 | 6516.3928 | 4519.85 | -1430% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2605. - BYP Bypass Pumping | 0 | 80 | 80 | 0% | 120 | 120 | 100% | 80 | 80 | 0 | 0 | 200% |  | 2026-05-01
2507. - SLC Industrial Lift Station | 150.2750. - Unknown Phase | 97.04 | 64.11 | -32.93 | 151.4% | 63.804 | 37.35 | 100% | 64.1128 | -32.9272 | 97.0358 | 97.04 | 48.64%
2507. - SLC Industrial Lift Station | 800.1930. - MC Misc Cleanup | 134.07 | 40 | -94.07 | 335.2% | 60 | 120 | 50% | 20 | -114.07 | 268.14 | 174.07 | -235.2%
2507. - SLC Industrial Lift Station | 100.1703. - FS Job Site Superintendent | 301.07 | 138.75 | -162.32 | 217% | 116.55 | 138.75 | 84% | 116.55 | -184.52 | 358.4167 | 304.57 | -19.51%
2507. - SLC Industrial Lift Station | 200.2085. - BFST Backfill Structure | 45.57 | 23 | -22.57 | 198.1% | 0 | 36 | 0% | 23 | -22.57 | 45.57 | 45.57 | 1.87%
2507. - SLC Industrial Lift Station | 150.2760. - Unknown Phase | 27.94 | 6.66 | -21.28 | 419.5% | 3.33 | 6.66 | 100% | 6.66 | -21.28 | 27.94 | 27.94 | -219.5%
2507. - SLC Industrial Lift Station | 200.2600. - DW Dewatering | 296.62 | 413.22 | 116.6 | 71.78% | 0 | 124.96 | 0% | 413.22 | 116.6 | 413.22 | 296.62 | 128.2%
2507. - SLC Industrial Lift Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 369.76 | 11.36 | -358.4 | 3255% | 80.655 | 101.36 | 82% | 9.3152 | -360.4448 | 450.9279 | 384.76 | -3187%
2507. - SLC Industrial Lift Station | 100.1700. - FS Project Manager | 230 | 155.5 | -74.5 | 147.9% | 90.61 | 155.5 | 82% | 127.51 | -102.49 | 280.4878 | 233 | 50.16%
2507. - SLC Industrial Lift Station | 200.3000. - Unknown Phase | 168.67 | 103.4 | -65.27 | 163.1% | 0 | 451.2 | 0% | 103.4 | -65.27 | 168.67 | 168.67 | 36.88%
2507. - SLC Industrial Lift Station | 200.2140. - SVR Services | 6.32 | 70 | 63.68 | 9.029% | 30 | 40 | 100% | 70 | 63.68 | 6.32 | 6.32 | 191%
2507. - SLC Industrial Lift Station | 150.1230. - T Transporting | 63.78 | 101 | 37.22 | 63.15% | 98.98 | 101 | 98% | 98.98 | 35.2 | 65.0816 | 63.78 | 136.9%
2507. - SLC Industrial Lift Station | 200.2605. - BYP Bypass Pumping | 69.14 | 31.25 | -37.89 | 221.2% | 25 | 50 | 100% | 31.25 | -37.89 | 69.14 | 69.14 | -21.25%
2507. - SLC Industrial Lift Station | 200.2030. - Unknown Phase | 40.82 | 175.16 | 134.34 | 23.3% | 0 | 134.16 | 0% | 175.16 | 134.34 | 175.16 | 40.82 | 176.7%
2507. - SLC Industrial Lift Station | 200.5400. - HAT Hatch/Skylights | 11 | 6.25 | -4.75 | 176% | 15 | 15 | 100% | 6.25 | -4.75 | 11 | 11 | 24%
2507. - SLC Industrial Lift Station | 200.1600. - TC Traffic Control | 96 | 405.51 | 309.51 | 23.67% | 142 | 142 | 100% | 405.51 | 309.51 | 96 | 96 | 176.3%
2507. - SLC Industrial Lift Station | 900.9012. - Re-Work Mechanical | 11.7 | 0.2 | -11.5 | 5850% | 0 | 0.6 | 0% | 0.2 | -11.5 | 11.7 | 11.7 | -5650%
2507. - SLC Industrial Lift Station | 200.2610. - PT Pressure Test/Chlorinating | 9.13 | 40 | 30.87 | 22.82% | 0 | 60 | 0% | 40 | 30.87 | 40 | 9.13 | 177.2%
2507. - SLC Industrial Lift Station | 200.2170. - HDPE Fusion Pipe <15' Depth | 478.38 | 813.15 | 334.77 | 58.83% | 372 | 471.74 | 100% | 813.15 | 334.77 | 478.38 | 478.38 | 141.2%
2507. - SLC Industrial Lift Station | 900.9015. - Re-Work Concrete | 0 | 0.2 | 0.2 | 0% | 0 | 0.6 | 0% | 0.2 | 0.2 | 0.2 | 0 | 200%
2507. - SLC Industrial Lift Station | 200.7900. - ELC Electrical | 50.85 | 27.5 | -23.35 | 184.9% | 0 | 20 | 0% | 27.5 | -23.35 | 50.85 | 50.85 | 15.09%
2507. - SLC Industrial Lift Station | 200.2240. - PCS Precast Structures | 290.68 | 45.5 | -245.18 | 638.9% | 0 | 28 | 0% | 45.5 | -245.18 | 290.68 | 290.68 | -438.9%
2507. - SLC Industrial Lift Station | 180.1600. - TC Traffic Control | 14.73 | 0 | -14.73 |  | 0 | 0 | 0% | 0 | -14.73 | 14.73 | 14.73 | 0%
2507. - SLC Industrial Lift Station | 150.1200. - HOOK Hook Truck Dumpster Transporting | 10 | 7.5 | -2.5 | 133.3% | 7.35 | 7.5 | 98% | 7.35 | -2.65 | 10.2041 | 7 | 106.7%
2507. - SLC Industrial Lift Station | 200.7100. - IMP Interior Mech/Piping | 171.81 | 87.26 | -84.55 | 196.9% | 258 | 259.89 | 100% | 87.26 | -84.55 | 171.81 | 171.81 | 3.106%
2507. - SLC Industrial Lift Station | 200.7500. - PUMP Pumps/Motors | 0 | 46 | 46 | 0% | 78 | 78 | 100% | 46 | 46 | 0 | 0 | 200%
2507. - SLC Industrial Lift Station | 100.1706. - FS Executive | 1 | 1 | 0 | 100% | 1 | 1 | 100% | 1 | 0 | 1 | 1 | 100%
2507. - SLC Industrial Lift Station | 100.1510. - S Surveying | 78.75 | 120 | 41.25 | 65.62% | 30 | 40 | 100% | 120 | 41.25 | 78.75 | 78.75 | 134.4%
2507. - SLC Industrial Lift Station | 200.2075. - FG Finish Grade | 20.68 | 39.4 | 18.72 | 52.49% | 56.439 | 45.25 | 95% | 37.4298 | 16.7498 | 21.7685 | 20.68 | 147.5%
2507. - SLC Industrial Lift Station | 200.1800. - PH Potholing | 40.02 | 100 | 59.98 | 40.02% | 150 | 150 | 100% | 100 | 59.98 | 40.02 | 40.02 | 160%
2507. - SLC Industrial Lift Station | 100.1704. - FS Quality Control/Assurance | 12.5 | 36.15 | 23.65 | 34.58% | 0 | 36.15 | 0% | 36.15 | 23.65 | 36.15 | 12.5 | 165.4%
2507. - SLC Industrial Lift Station | 900.9100. - Job Related Equipment Repairs | 0 | 1 | 1 | 0% | 0 | 1 | 0% | 1 | 1 | 1 | 0 | 200%
2507. - SLC Industrial Lift Station | 200.5000. - MET Metals | 7.86 | 38.5 | 30.64 | 20.42% | 85.5 | 85.5 | 100% | 38.5 | 30.64 | 7.86 | 7.86 | 179.6%
2507. - SLC Industrial Lift Station | 100.1702. - FS People Superintendent | 35.5 | 92.17 | 56.67 | 38.52% | 46.085 | 92.17 | 99.99% | 92.16 | 56.66 | 35.5039 | 35.5 | 161.5%
2507. - SLC Industrial Lift Station | 150.1201. - HOOK Hook Truck Conex, Skid Transporting | 6 | 7.5 | 1.5 | 80% | 7.35 | 7.5 | 98% | 7.35 | 1.35 | 6.1224 | 9 | 80%
2507. - SLC Industrial Lift Station | 800.1940. - PL Punch List Work | 466.85 | 90 | -376.85 | 518.7% | 128.25 | 135 | 95% | 85.5 | -381.35 | 491.4211 | 553.45 | -414.9%
2219. - GHID 20D Kent Booster Station | 220.2080. - EXS Excavate Structure | 88.03 | 822.5 | 734.47 | 10.7% | 0 | 320 | 0% | 822.5 | 734.47 | 822.5 | 88.03 | 189.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.2080. - EXS Excavate Structure | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9100. - Job Related Equipment Repairs | 2 | 2 | 0 | 100% | 1 | 1 | 50% | 1 | -1 | 4 | 2 | 100% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7600. - MEQ Mechanical Equipment | 197.67 | 1 | -196.67 | 19767% | 3 | 3 | 75% | 0.75 | -196.92 | 263.56 | 197.67 | -19567% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.5000. - MET Metals | 4 | 2 | -2 | 200% | 1 | 1 | 33.33% | 0.66667 | -3.3333 | 12 | 4 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.2300. - WPL Water Pipe Laying (DO NOT USE) | 228.42 | 145 | -83.42 | 157.5% | 139 | 139 | 48.94% | 70.9683 | -157.4517 | 466.6999 | 228.42 | 42.47% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.7100. - IMP Interior Mech/Piping | 305.79 | 0 | -305.79 |  | 0 | 0 | 0% | 0 | -305.79 | 305.79 | 305.79 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.6500. - P Painting | 2 | 30 | 28 | 6.667% | 90 | 90 | 75% | 22.5 | 20.5 | 2.6667 | 2 | 193.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 700.2300. - WPL Water Pipe Laying (DO NOT USE) | 247.07 | 400 | 152.93 | 61.77% | 600 | 600 | 60% | 240 | -7.07 | 411.7833 | 247.07 | 138.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.5100. - W Welding | 23.01 | 84 | 60.99 | 27.39% | 0 | 4 | 0% | 84 | 60.99 | 84 | 23.01 | 172.6% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.2600. - DW Dewatering | 2 | 27.5 | 25.5 | 7.273% | 0 | 30 | 0% | 27.5 | 25.5 | 27.5 | 2 | 192.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.3000. - CNC Concrete Work | 235.5 | 1 | -234.5 | 23550% | 6 | 3 | 75% | 0.75 | -234.75 | 314 | 235.5 | -23350% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2800. - BFST Backfill (DO NOT USE) | 225.81 | 280 | 54.19 | 80.65% | 240 | 240 | 46.15% | 129.2308 | -96.5792 | 489.255 | 225.81 | 119.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9010. - Re-Work Pipe | 638.85 | 0.4 | -638.45 | 159712% | 0.4 | 0.4 | 66.67% | 0.26667 | -638.5833 | 958.275 | 638.85 | -159512% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1700. - FS Project Manager | 77.25 | 1 | -76.25 | 7725% | 0 | 0 | 0% | 1 | -76.25 | 77.25 | 77.25 | -7525% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7500. - PUMP Pumps/Motors | 16.55 | 120 | 103.45 | 13.79% | 0 | 180 | 0% | 120 | 103.45 | 120 | 16.55 | 186.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 655.98 | 510 | -145.98 | 128.6% | 350 | 350 | 40.7% | 207.5581 | -448.4219 | 1611.8366 | 656.48 | 71.28% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2600. - DW Dewatering | 183.84 | 62.5 | -121.34 | 294.1% | 0 | 15 | 0% | 62.5 | -121.34 | 183.84 | 183.84 | -94.14% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 210.7600. - MEQ Mechanical Equipment | 478.2 | 225 | -253.2 | 212.5% | 380 | 400 | 58.02% | 130.5344 | -347.6656 | 824.2658 | 478.2 | -12.53% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.2300. - WPL Water Pipe Laying (DO NOT USE) | 172.48 | 138 | -34.48 | 125% | 230 | 230 | 71.88% | 99.1875 | -73.2925 | 239.9722 | 172.48 | 75.01% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.5000. - MET Metals | 94.02 | 68 | -26.02 | 138.3% | 115 | 115 | 62.84% | 42.7322 | -51.2878 | 149.6144 | 94.02 | 61.74% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.3000. - CNC Concrete Work | 129.03 | 68.31 | -60.72 | 188.9% | 151.08 | 151.08 | 70.47% | 48.1379 | -80.8921 | 183.1 | 129.03 | 11.11% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6000. - IF Interior Finishes | 143.88 | 15 | -128.88 | 959.2% | 42.75 | 45 | 71.25% | 10.6875 | -133.1925 | 201.9368 | 143.88 | -759.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2070. - RGC Rough Grade Cut | 44.41 | 90 | 45.59 | 49.34% | 90 | 90 | 51.67% | 46.5 | 2.09 | 85.9548 | 44.41 | 150.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.2800. - BFST Backfill (DO NOT USE) | 345.21 | 175 | -170.21 | 197.3% | 150 | 150 | 46.15% | 80.7692 | -264.4408 | 747.955 | 345.21 | 2.737% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2010. - RG Grading (DO NOT USE) | 0 | 43.5 | 43.5 | 0% | 0 | 51 | 0% | 43.5 | 43.5 | 43.5 | 10.72 | 175.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 180.2040. - LR Landscaping/Restoration | 738.87 | 218.7 | -520.17 | 337.8% | 0 | 1 | 0% | 218.7 | -520.17 | 738.87 | 738.87 | -137.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1510. - S Surveying | 6293.91 | 1000 | -5293.91 | 629.4% | 1000 | 1000 | 50% | 500 | -5793.91 | 12587.82 | 6293.91 | -429.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.6500. - P Painting | 105.99 | 62 | -43.99 | 171% | 150 | 150 | 75% | 46.5 | -59.49 | 141.32 | 105.99 | 29.05% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6500. - Unknown Phase | 567.67 | 277 | -290.67 | 204.9% | 1094 | 1095.54 | 79.8% | 221.0343 | -346.6357 | 711.4036 | 567.67 | -4.935% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.6500. - P Painting | 10 | 50 | 40 | 20% | 150 | 150 | 75% | 37.5 | 27.5 | 13.3333 | 10 | 180% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 370.5100. - W Welding | 113.86 | 100 | -13.86 | 113.9% | 0 | 50 | 0% | 100 | -13.86 | 113.86 | 113.86 | 86.14% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.7100. - IMP Interior Mech/Piping | 137.18 | 50 | -87.18 | 274.4% | 105 | 105 | 67.74% | 33.871 | -103.309 | 202.5038 | 119.18 | -38.36% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 2.5 | 2.5 | 0% | 0 | -15 | 7.273% | 0.18182 | 0.18182 | 0 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.5000. - MET Metals | 4 | 2 | -2 | 200% | 6 | 6 | 75% | 1.5 | -2.5 | 5.3333 | 4 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.5000. - MET Metals | 17.7 | 180.34 | 162.64 | 9.815% | 231 | 231 | 56.16% | 101.2752 | 83.5752 | 31.5183 | 17.7 | 190.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1386.3 | 1 | -1385.3 | 138630% | 0 | 0 | 0% | 1 | -1385.3 | 1386.3 | 1386.3 | -138430% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.7100. - IMP Interior Mech/Piping | 27.47 | 109.65 | 82.18 | 25.05% | 234 | 234 | 74.52% | 81.7137 | 54.2437 | 36.8615 | 27.47 | 174.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.1930. - MC Misc Cleanup | 796.38 | 500 | -296.38 | 159.3% | 380 | 400 | 42.22% | 211.1111 | -585.2689 | 1886.1632 | 796.38 | 40.72% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.5000. - MET Metals | 1 | 0 | -1 |  | 0 | 0 | 0% | 0 | -1 | 1 | 1 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 550.3000. - CNC Concrete Work | 441.89 | 28 | -413.89 | 1578% | 20 | 20 | 66.67% | 18.6667 | -423.2233 | 662.835 | 432.89 | -1346% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.2080. - EXS Excavate Structure | 105.12 | 142.5 | 37.38 | 73.77% | 140 | 140 | 49.56% | 70.6195 | -34.5005 | 212.1171 | 105.12 | 126.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.6500. - P Painting | 238.88 | 100 | -138.88 | 238.9% | 300 | 300 | 75% | 75 | -163.88 | 318.5067 | 238.88 | -38.88% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 1173.66 | 9784.5 | 8610.84 | 12% | 3678 | 3678 | 27.34% | 2674.6482 | 1500.9882 | 4293.5278 | 1182.34 | 187.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7900. - ELC Electrical | 494.55 | 420 | -74.55 | 117.8% | 490 | 490 | 56.32% | 236.5517 | -257.9983 | 878.0786 | 494.55 | 82.25% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 350.5100. - W Welding | 211.92 | 254 | 42.08 | 83.43% | 40 | 40 | 33.33% | 84.6667 | -127.2533 | 635.76 | 211.92 | 116.6% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.5100. - W Welding | 1400.89 | 658 | -742.89 | 212.9% | 329 | 329 | 33.33% | 219.3333 | -1181.5567 | 4202.67 | 1400.89 | -12.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.3000. - CNC Concrete Work | 9 | 15 | 6 | 60% | 33 | 33 | 68.75% | 10.3125 | 1.3125 | 13.0909 | 9 | 140% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.5000. - MET Metals | 12 | 4 | -8 | 300% | 32 | 32 | 88.89% | 3.5556 | -8.4444 | 13.5 | 12 | -100% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1702. - FS People Superintendent | 1600.4 | 1 | -1599.4 | 160040% | 0 | 0 | 0% | 1 | -1599.4 | 1600.4 | 1600.4 | -159840% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2080. - EXS Excavate Structure | 142.24 | 215 | 72.76 | 66.16% | 0 | 165 | 0% | 215 | 72.76 | 215 | 142.24 | 133.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9020. - Re-Work Fab | 205.43 | 0.4 | -205.03 | 51358% | 0.2 | 0.2 | 33.33% | 0.13333 | -205.2967 | 616.29 | 205.43 | -51158% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.1700. - FS Project Manager | 18.53 | 70 | 51.47 | 26.47% | 66.5 | 70 | 47.5% | 33.25 | 14.72 | 39.0105 | 18.53 | 173.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.3000. - Unknown Phase | 2309.66 | 837 | -1472.66 | 275.9% | 2291 | 2016.54 | 71.15% | 595.5177 | -1714.1423 | 3246.2266 | 2309.66 | -75.95% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1704. - FS Quality Control/Assurance | 12 | 1 | -11 | 1200% | 0 | 0 | 0% | 1 | -11 | 12 | 12 | -1000% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 340.3000. - CNC Concrete Work | 17.5 | 32 | 14.5 | 54.69% | 66 | 66 | 67.35% | 21.551 | 4.051 | 25.9848 | 17.5 | 145.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.3000. - CNC Concrete Work | 137.63 | 28.39 | -109.24 | 484.8% | 70.52 | 70.52 | 71.3% | 20.2413 | -117.3887 | 193.0372 | 137.63 | -284.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2800. - Unknown Phase | 2488.64 | 175 | -2313.64 | 1422% | 150 | 150 | 46.15% | 80.7692 | -2407.8708 | 5392.0533 | 2480.64 | -1218% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.2610. - PT Pressure Test/Chlorinating | 411.28 | 525 | 113.72 | 78.34% | 600 | 600 | 53.33% | 280 | -131.28 | 771.15 | 411.28 | 121.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.2800. - BFST Backfill (DO NOT USE) | 174.39 | 175 | 0.61 | 99.65% | 0 | 150 | 0% | 175 | 0.61 | 175 | 174.39 | 100.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.5000. - MET Metals | 234.14 | 809 | 574.86 | 28.94% | 894.9 | 894.9 | 54.07% | 437.3937 | 203.2537 | 433.0635 | 264.14 | 167.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.6200. - IN Insulation | 9 | 70 | 61 | 12.86% | 210 | 210 | 75% | 52.5 | 43.5 | 12 | 9 | 187.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.2080. - EXS Excavate Structure | 30.88 | 31.25 | 0.37 | 98.82% | 25 | 25 | 44.44% | 13.8889 | -16.9911 | 69.48 | 30.88 | 101.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.2300. - WPL Water Pipe Laying (DO NOT USE) | 6421.22 | 528.02 | -5893.2 | 1216% | 354 | 354 | 41.4% | 218.6188 | -6202.6012 | 15508.8788 | 6427.7 | -1017% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 157.44 | 25 | -132.44 | 629.8% | 30 | 30 | 54.55% | 13.6364 | -143.8036 | 288.64 | 152.94 | -411.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 327.62 | 327.62 | 0% | 0 | 135.36 | 0% | 327.62 | 327.62 | 327.62 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.1940. - PL Punch List Work | 1298.46 | 200 | -1098.46 | 649.2% | 540 | 600 | 67.5% | 135 | -1163.46 | 1923.6444 | 1295.46 | -447.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.5100. - W Welding | 34.2 | 45 | 10.8 | 76% | 15 | 15 | 25% | 11.25 | -22.95 | 136.8 | 34.2 | 124% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 107.58 | 54.72 | -52.86 | 196.6% | 0 | 72.96 | 0% | 54.72 | -52.86 | 107.58 | 106.58 | 5.227% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 330.2300. - WPL Water Pipe Laying (DO NOT USE) | 2937.71 | 541.25 | -2396.46 | 542.8% | 0 | 355 | 0% | 541.25 | -2396.46 | 2937.71 | 2917.11 | -339% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 370.7100. - IMP Interior Mech/Piping | -20.77 | 40 | 60.77 | -51.92% | 0 | 60 | 0% | 40 | 60.77 | 40 | 55.23 | 61.92% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.7100. - IMP Interior Mech/Piping | 0 | 24 | 24 | 0% | 0 | 6 | 0% | 24 | 24 | 24 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.5000. - MET Metals | 19.02 | 84 | 64.98 | 22.64% | 202 | 202 | 70.63% | 59.3287 | 40.3087 | 26.9293 | 19.02 | 177.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.7100. - IMP Interior Mech/Piping | 90.38 | 5 | -85.38 | 1808% | 15 | 15 | 75% | 3.75 | -86.63 | 120.5067 | 90.38 | -1608% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9015. - Re-Work Concrete | 4 | 0.4 | -3.6 | 1000% | 0.4 | 0.4 | 66.67% | 0.26667 | -3.7333 | 6 | 4 | -800% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2080. - EXS Excavate Structure | 835.03 | 280.5 | -554.53 | 297.7% | 0 | 303 | 0% | 280.5 | -554.53 | 835.03 | 843.03 | -100.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2300. - Unknown Phase | 1129.25 | 734.71 | -394.54 | 153.7% | 601.64 | 611.64 | 47.15% | 346.4056 | -782.8444 | 2395.0859 | 1126.57 | 46.66% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.3000. - CNC Concrete Work | 3 | 10 | 7 | 30% | 30 | 30 | 75% | 7.5 | 4.5 | 4 | 3 | 170% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2020. - CG Clearing/Grubbing | 26.57 | 30 | 3.43 | 88.57% | 0 | 20 | 0% | 30 | 3.43 | 30 | 35.1 | 83% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.5000. - MET Metals | 237.61 | 196 | -41.61 | 121.2% | 141 | 141 | 52.81% | 103.5056 | -134.1044 | 449.9423 | 237.61 | 78.77% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9012. - Re-Work Mechanical | 47.65 | 0.4 | -47.25 | 11912% | 0.4 | 0.4 | 66.67% | 0.26667 | -47.3833 | 71.475 | 47.65 | -11712% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 769.42 | 1061.5 | 292.08 | 72.48% | 887.5 | 891.35 | 45.02% | 477.9201 | -291.4999 | 1708.9454 | 769.42 | 127.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 19 | 120 | 101 | 15.83% | 0 | 210 | 0% | 120 | 101 | 120 | 19 | 184.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.3000. - CNC Concrete Work | 680.33 | 272.4 | -407.93 | 249.8% | 621.2 | 621.2 | 69.52% | 189.3631 | -490.9669 | 978.6589 | 680.33 | -49.75% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5110. - Fab Shop Pipe Fabrication | 5379.84 | 2283 | -3096.84 | 235.6% | 2283 | 2283 | 50.31% | 1148.5 | -4231.34 | 10694.1008 | 5379.84 | -35.65% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.2800. - BFST Backfill (DO NOT USE) | 31.85 | 140 | 108.15 | 22.75% | 120 | 120 | 46.15% | 64.6154 | 32.7654 | 69.0083 | 31.85 | 177.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.3000. - CNC Concrete Work | 407.59 | 356 | -51.59 | 114.5% | 858 | 858 | 70.68% | 251.6046 | -155.9854 | 576.7066 | 407.59 | 85.51% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 317.34 | 300 | -17.34 | 105.8% | 300 | 300 | 50% | 150 | -167.34 | 634.68 | 317.34 | 94.22% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.2750. - Unknown Phase | 1721.45 | 1167.57 | -553.88 | 147.4% | 1111.98 | 1114.31 | 49.55% | 578.535 | -1142.915 | 3474.1429 | 1521.83 | 69.66% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.2600. - DW Dewatering | 0 | 25 | 25 | 0% | 0 | 30 | 0% | 25 | 25 | 25 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.2010. - RG Grading (DO NOT USE) | 18.85 | 18 | -0.85 | 104.7% | 16 | 16 | 47.06% | 8.4706 | -10.3794 | 40.0562 | 18.35 | 98.06% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.7100. - IMP Interior Mech/Piping | 29.85 | 180 | 150.15 | 16.58% | 75 | 75 | 71.43% | 128.5714 | 98.7214 | 41.79 | 29.85 | 183.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2080. - EXS Excavate Structure | 5 | 31.25 | 26.25 | 16% | 0 | 25 | 0% | 31.25 | 26.25 | 31.25 | 5 | 184% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.7100. - IMP Interior Mech/Piping | 142.28 | 139.65 | -2.63 | 101.9% | 234 | 234 | 66.1% | 92.311 | -49.969 | 215.2441 | 125.78 | 109.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 370.2300. - WPL Water Pipe Laying (DO NOT USE) | 926.68 | 1100 | 173.32 | 84.24% | 0 | 690 | 0% | 1100 | 173.32 | 1100 | 926.68 | 115.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.3000. - CNC Concrete Work | 0 | 40 | 40 | 0% | 110 | 110 | 73.33% | 29.3333 | 29.3333 | 0 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.2800. - BFST Backfill (DO NOT USE) | 0 | 17.5 | 17.5 | 0% | 15 | 15 | 46.15% | 8.0769 | 8.0769 | 0 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9055. - Re-Work Finishes | 6 | 1.1 | -4.9 | 545.5% | 0.2 | 0.2 | 66.67% | 0.73333 | -5.2667 | 9 | 6 | -345.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.6500. - P Painting | 4.27 | 40 | 35.73 | 10.67% | 120 | 120 | 75% | 30 | 25.73 | 5.6933 | 4.27 | 189.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.7100. - IMP Interior Mech/Piping | 27.13 | 106 | 78.87 | 25.59% | 219 | 219 | 67.38% | 71.4277 | 44.2977 | 40.2614 | 33.13 | 168.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2010. - RG Grading (DO NOT USE) | 319.73 | 21.75 | -297.98 | 1470% | 25.5 | 25.5 | 53.97% | 11.7381 | -307.9919 | 592.4409 | 318.25 | -1263% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1600. - TC Traffic Control | 405.6 | 5412 | 5006.4 | 7.494% | 240 | 240 | 4.348% | 235.3043 | -170.2957 | 9328.8 | 405.6 | 192.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.2760. - Unknown Phase | 1841.15 | 2330.86 | 489.71 | 78.99% | 2334 | 2316 | 50% | 1165.43 | -675.72 | 3682.3 | 1948.28 | 116.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2030. - D Demolition | 0 | 15 | 15 | 0% | 15 | 15 | 50% | 7.5 | 7.5 | 0 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.2030. - D Demolition | 0 | 6 | 6 | 0% | 6 | 6 | 50% | 3 | 3 | 0 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7100. - IMP Interior Mech/Piping | 1448.35 | 647.5 | -800.85 | 223.7% | 1339.5 | 1411.54 | 65.66% | 425.1599 | -1023.1901 | 2205.7738 | 1371.35 | -11.79% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2800. - BFST Backfill (DO NOT USE) | 30.29 | 35 | 4.71 | 86.54% | 30 | 30 | 46.15% | 16.1538 | -14.1362 | 65.6283 | 43.29 | 76.31% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.1230. - T Transporting | 1464.11 | 600 | -864.11 | 244% | 600 | 600 | 50% | 300 | -1164.11 | 2928.22 | 1479.37 | -46.56% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.2300. - WPL Water Pipe Laying (DO NOT USE) | 978.34 | 1007.76 | 29.42 | 97.08% | 751.75 | 751.75 | 42.72% | 430.5651 | -547.7749 | 2289.8557 | 971.99 | 103.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.3000. - CNC Concrete Work | 1294.04 | 258.71 | -1035.33 | 500.2% | 627.28 | 627.28 | 70.8% | 183.1664 | -1110.8736 | 1827.7428 | 1294.04 | -300.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5120. - Fab Shop Pipe Linings & Coatings | 3194.33 | 1733 | -1461.33 | 184.3% | 1733 | 1733 | 50% | 866.5 | -2327.83 | 6388.66 | 3194.33 | 15.68% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2800. - BFST Backfill (DO NOT USE) | 5.73 | 105 | 99.27 | 5.457% | 90 | 90 | 46.15% | 48.4615 | 42.7315 | 12.415 | 5.73 | 194.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.2500. - MH Manholes (DO NOT USE) | 1.58 | 0 | -1.58 |  | 0 | 0 | 0% | 0 | -1.58 | 1.58 | 1.58 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.5100. - W Welding | 432.21 | 50 | -382.21 | 864.4% | 25 | 25 | 33.33% | 16.6667 | -415.5433 | 1296.63 | 432.21 | -664.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 40 | 40 | 0% | 0 | 20 | 0% | 40 | 40 | 40 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.7600. - MEQ Mechanical Equipment | 193.23 | 68 | -125.23 | 284.2% | 204 | 204 | 75% | 51 | -142.23 | 257.64 | 193.23 | -84.16% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.7100. - IMP Interior Mech/Piping | 45.05 | 118 | 72.95 | 38.18% | 221 | 221 | 65.38% | 77.1538 | 32.1038 | 68.9 | 45.05 | 161.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 340.2300. - WPL Water Pipe Laying (DO NOT USE) | 918.07 | 951.35 | 33.28 | 96.5% | 849.25 | 849.25 | 45.29% | 430.8981 | -487.1719 | 2026.9429 | 918.07 | 103.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.5100. - W Welding | 24.33 | 20 | -4.33 | 121.6% | 10 | 10 | 33.33% | 6.6667 | -17.6633 | 72.99 | 24.33 | 78.35% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.5000. - MET Metals | 53.24 | 100 | 46.76 | 53.24% | 86 | 86 | 55.13% | 55.1282 | 1.8882 | 96.5749 | 53.24 | 146.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2030. - D Demolition | 625.66 | 1034.51 | 408.85 | 60.48% | 792 | 792 | 43.36% | 448.5778 | -177.0822 | 1442.8968 | 624.66 | 139.6% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.1650. - SB Signage | 28.44 | 50 | 21.56 | 56.88% | 100 | 100 | 66.67% | 33.3333 | 4.8933 | 42.66 | 28.44 | 143.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 550.2930. - AP Asphalt Prep (DO NOT USE) | 1246.33 | 436.66 | -809.67 | 285.4% | 489 | 489 | -6.225% | 436.66 | -809.67 | -20022.4476 | 1251.33 | -86.57% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1703. - FS Job Site Superintendent | 3597.29 | 1 | -3596.29 | 359729% | 0 | 0 | 0% | 1 | -3596.29 | 3597.29 | 3597.29 | -359529% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6300. - DAW Doors & Windows | 318.29 | 30 | -288.29 | 1061% | 60 | 60 | 66.67% | 20 | -298.29 | 477.435 | 318.29 | -861% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.3000. - CNC Concrete Work | 10 | 4 | -6 | 250% | 8 | 8 | 66.67% | 2.6667 | -7.3333 | 15 | 0 | 200% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.2080. - EXS Excavate Structure | 375.37 | 127.5 | -247.87 | 294.4% | 125 | 125 | 49.5% | 63.1188 | -312.2512 | 758.2474 | 375.37 | -94.41% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 340.7100. - IMP Interior Mech/Piping | 28.07 | 25 | -3.07 | 112.3% | 45 | 45 | 64.29% | 16.0714 | -11.9986 | 43.6644 | 28.07 | 87.72% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2030. - D Demolition | 5.87 | 45 | 39.13 | 13.04% | 0 | 15 | 0% | 45 | 39.13 | 45 | 5.87 | 187% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6200. - IN Insulation | 91.08 | 48.75 | -42.33 | 186.8% | 146.25 | 146.25 | 75% | 36.5625 | -54.5175 | 121.44 | 91.08 | 13.17% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.2010. - RG Grading (DO NOT USE) | 8.57 | 4.5 | -4.07 | 190.4% | 4 | 4 | 47.06% | 2.1176 | -6.4524 | 18.2112 | 8.57 | 9.556% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.2800. - BFST Backfill (DO NOT USE) | 62.53 | 70 | 7.47 | 89.33% | 60 | 60 | 46.15% | 32.3077 | -30.2223 | 135.4817 | 62.53 | 110.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.0000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 170.2300. - WPL Water Pipe Laying (DO NOT USE) | 11.16 | -2 | -13.16 |  | 0 | -6 | 0% | -2 | -13.16 | 11.16 | 11.16 | 758% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.7100. - IMP Interior Mech/Piping | 56.56 | 34 | -22.56 | 166.4% | 63 | 63 | 64.95% | 22.0825 | -34.4775 | 87.0844 | 56.56 | 33.65% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.6500. - P Painting | 5.47 | 30 | 24.53 | 18.23% | 0 | 60 | 0% | 30 | 24.53 | 30 | 5.47 | 181.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5310. - Fab Shop Misc Metals Fabrication | 747.31 | 512 | -235.31 | 146% | 484 | 484 | 50.52% | 258.6446 | -488.6654 | 1479.3376 | 747.31 | 54.04% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.6500. - P Painting | 126.81 | 20 | -106.81 | 634% | 60 | 60 | 75% | 15 | -111.81 | 169.08 | 126.81 | -434% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5320. - Fab Shop Misc Metals Coatings | 17.5 | 120 | 102.5 | 14.58% | 103 | 103 | 50% | 60 | 42.5 | 35 | 17.5 | 185.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.3000. - CNC Concrete Work | 3 | 12 | 9 | 25% | 24 | 24 | 66.67% | 8 | 5 | 4.5 | 3 | 175% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1705. - FS Estimator/Change Orders/Scheduling | 39.52 | 1 | -38.52 | 3952% | 0 | 0 | 0% | 1 | -38.52 | 39.52 | 39.52 | -3752% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 330.5100. - W Welding | 1 | 44 | 43 | 2.273% | 2 | 2 | 33.33% | 14.6667 | 13.6667 | 3 | 1 | 197.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 550.2010. - RG Grading (DO NOT USE) | 40.82 | 43.5 | 2.68 | 93.84% | 51 | 51 | 53.97% | 23.4762 | -17.3438 | 75.6371 | 40.82 | 106.2% |  | 2024-03-15
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1510. - S Surveying | 4 | 60 | 56 | 6.667% | 1 | 20 | 5% | 3 | -1 | 80 | 60 | 100% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1702. - FS People Superintendent | 16 | 44.68 | 28.68 | 35.81% | 2.234 | 44.68 | 5% | 2.234 | -13.766 | 320 | 46 | 97.05% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1703. - FS Job Site Superintendent | 16 | 67 | 51 | 23.88% | 3.35 | 67 | 5% | 3.35 | -12.65 | 320 | 166 | -47.76% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1700. - FS Project Manager | 58 | 53.47 | -4.53 | 108.5% | 2.674 | 53.47 | 5.001% | 2.674 | -55.326 | 1159.7831 | 136 | -54.35% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 129.15 | 47.66 | -81.49 | 271% | 2.383 | 47.66 | 8.659% | 4.127 | -125.023 | 1491.4847 | 127.65 | -67.83% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 200.1600. - TC Traffic Control | 0.75 | 10 | 9.25 | 7.5% | 0.1 | 10 | 1% | 0.1 | -0.65 | 75 | 10 | 100% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1706. - FS Executive | 1 | 1 | 0 | 100% | 0.05 | 1 | 5% | 0.05 | -0.95 | 20 | 1 | 100% |  | 2025-10-31
2125. - Price WWTP Nutrient Upgrades | 650.7100. - IMP Interior Mech/Piping | 828.84 | 589 | -239.84 | 140.7% | 0 | 1440 | 0% | 589 | -239.84 | 828.84 | 554 | 105.9%
2125. - Price WWTP Nutrient Upgrades | 600.6500. - P Painting | 10 | 50 | 40 | 20% | 0 | 100 | 0% | 50 | 40 | 50 | 50 | 100%
2125. - Price WWTP Nutrient Upgrades | 600.3000. - CNC Concrete Work | 7 | 10 | 3 | 70% | 0 | 30 | 0% | 10 | 3 | 10 | 10 | 100%
2125. - Price WWTP Nutrient Upgrades | 500.7600. - MEQ Mechanical Equipment | 500.25 | 30 | -470.25 | 1668% | 0 | 80 | 0% | 30 | -470.25 | 500.25 | 30 | 100%
2125. - Price WWTP Nutrient Upgrades | 200.3000. - Unknown Phase | 403.29 | 97 | -306.29 | 415.8% | 0 | 252 | 0% | 97 | -306.29 | 403.29 | 80 | 117.5%
2125. - Price WWTP Nutrient Upgrades | 600.5000. - MET Metals | 33.5 | 62 | 28.5 | 54.03% | 0 | 56 | 0% | 62 | 28.5 | 62 | 52 | 116.1%
2125. - Price WWTP Nutrient Upgrades | 750.7600. - MEQ Mechanical Equipment | 112.46 | 80 | -32.46 | 140.6% | 0 | 100 | 0% | 80 | -32.46 | 112.46 | 80 | 100%
2125. - Price WWTP Nutrient Upgrades | 800.1930. - MC Misc Cleanup | 188.86 | 125 | -63.86 | 151.1% | 0 | 100 | 0% | 125 | -63.86 | 188.86 | 125 | 100%
2125. - Price WWTP Nutrient Upgrades | 300.7100. - IMP Interior Mech/Piping | 647 | 315 | -332 | 205.4% | 0 | 500 | 0% | 315 | -332 | 647 | 305 | 103.2%
2125. - Price WWTP Nutrient Upgrades | 200.2030. - Unknown Phase | 543.76 | 661.51 | 117.75 | 82.2% | 0 | 966.02 | 0% | 661.51 | 117.75 | 661.51 | 644.51 | 102.6%
2125. - Price WWTP Nutrient Upgrades | 900.9012. - Re-Work Mechanical | 5.35 | 0.4 | -4.95 | 1338% | 0 | 0.4 | 0% | 0.4 | -4.95 | 5.35 | 0.2 | 150%
2125. - Price WWTP Nutrient Upgrades | 650.7500. - PUMP Pumps/Motors | 0 | 50 | 50 | 0% | 0 | 150 | 0% | 50 | 50 | 50 | 50 | 100%
2125. - Price WWTP Nutrient Upgrades | 160.7100. - IMP Interior Mech/Piping | 30.09 | 240 | 209.91 | 12.54% | 0 | 360 | 0% | 240 | 209.91 | 240 | 240 | 100%
2125. - Price WWTP Nutrient Upgrades | 650.5000. - MET Metals | 145.01 | 224 | 78.99 | 64.74% | 0 | 122 | 0% | 224 | 78.99 | 224 | 224 | 100%
2125. - Price WWTP Nutrient Upgrades | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 17.5 | 0 | -17.5 |  | 0 | 0 | 0% | 0 | -17.5 | 17.5 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 900.9015. - Re-Work Concrete | 0 | 0.4 | 0.4 | 0% | 0 | 0.4 | 0% | 0.4 | 0.4 | 0.4 | 0.2 | 150%
2125. - Price WWTP Nutrient Upgrades | 510.7600. - MEQ Mechanical Equipment | 304.8 | 80 | -224.8 | 381% | 0 | 120 | 0% | 80 | -224.8 | 304.8 | 80 | 100%
2125. - Price WWTP Nutrient Upgrades | 150.1230. - T Transporting | 33.94 | 205 | 171.06 | 16.56% | 0 | 205 | 0% | 205 | 171.06 | 205 | 200 | 102.4%
2125. - Price WWTP Nutrient Upgrades | 650.6500. - P Painting | 243.13 | 260 | 16.87 | 93.51% | 0 | 520 | 0% | 260 | 16.87 | 260 | 250 | 103.8%
2125. - Price WWTP Nutrient Upgrades | 160.5000. - Unknown Phase | 31.67 | 5 | -26.67 | 633.4% | 0 | 15 | 0% | 5 | -26.67 | 31.67 | 0 | 200%
2125. - Price WWTP Nutrient Upgrades | 100.1510. - S Surveying | 10.5 | 40 | 29.5 | 26.25% | 0 | 20 | 0% | 40 | 29.5 | 40 | 40 | 100%
2125. - Price WWTP Nutrient Upgrades | 900.9055. - Re-Work Finishes | 0 | 0.2 | 0.2 | 0% | 0 | 0.2 | 0% | 0.2 | 0.2 | 0.2 | 0.1 | 150%
2125. - Price WWTP Nutrient Upgrades | 600.7600. - MEQ Mechanical Equipment | 97.72 | 40.5 | -57.22 | 241.3% | 0 | 72 | 40.89% | 16.56 | -81.16 | 238.9891 | 40.5 | 100%
2125. - Price WWTP Nutrient Upgrades | 210.7100. - IMP Interior Mech/Piping | 46.86 | 10 | -36.86 | 468.6% | 0 | 30 | 0% | 10 | -36.86 | 46.86 | 10 | 100%
2125. - Price WWTP Nutrient Upgrades | 100.1702. - FS People Superintendent | 20.52 | 0 | -20.52 |  | 0 | 0 | 0% | 0 | -20.52 | 20.52 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 100.1704. - FS Quality Control/Assurance | 3.5 | 0 | -3.5 |  | 0 | 0 | 0% | 0 | -3.5 | 3.5 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 700.5100. - W Welding | 162.77 | 80 | -82.77 | 203.5% | 0 | 40 | 0% | 80 | -82.77 | 162.77 | 80 | 100%
2125. - Price WWTP Nutrient Upgrades | 200.7100. - IMP Interior Mech/Piping | 82.04 | 10 | -72.04 | 820.4% | 0 | 30 | 0% | 10 | -72.04 | 82.04 | 10 | 100%
2125. - Price WWTP Nutrient Upgrades | 750.5100. - W Welding | 42.08 | 100 | 57.92 | 42.08% | 0 | 50 | 0% | 100 | 57.92 | 100 | 100 | 100%
2125. - Price WWTP Nutrient Upgrades | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 700.7600. - MEQ Mechanical Equipment | 24.5 | 108 | 83.5 | 22.69% | 0 | 222 | 0% | 108 | 83.5 | 108 | 108 | 100%
2125. - Price WWTP Nutrient Upgrades | 800.1940. - PL Punch List Work | 479.03 | 125 | -354.03 | 383.2% | 0 | 100 | 0% | 125 | -354.03 | 479.03 | 125 | 100%
2125. - Price WWTP Nutrient Upgrades | 210.3000. - CNC Concrete Work | 1566.72 | 532.5 | -1034.22 | 294.2% | 0 | 1332.5 | 0% | 532.5 | -1034.22 | 1566.72 | 0 | 200%
2125. - Price WWTP Nutrient Upgrades | 700.5000. - MET Metals | 8.74 | 8 | -0.74 | 109.2% | 0 | 4 | 0% | 8 | -0.74 | 8.74 | 8 | 100%
2125. - Price WWTP Nutrient Upgrades | 200.5000. - MET Metals | 12.32 | 102 | 89.68 | 12.08% | 0 | 55 | 0% | 102 | 89.68 | 102 | 92 | 109.8%
2125. - Price WWTP Nutrient Upgrades | 400.3000. - CNC Concrete Work | 391.9 | 157.5 | -234.4 | 248.8% | 0 | 242.5 | 0% | 157.5 | -234.4 | 391.9 | -134 | 285.1%
2125. - Price WWTP Nutrient Upgrades | 700.6500. - P Painting | 8.66 | 85 | 76.34 | 10.19% | 0 | 110 | 0% | 85 | 76.34 | 85 | 40 | 152.9%
2226. - Tooele Berra Wellhouse | 160.5320. - Fab Shop Misc Metals Coatings | 26.78 | 40 | 13.22 | 66.95% | 0 | 40 | 0% | 40 | 13.22 | 40 | 40 | 100%
2226. - Tooele Berra Wellhouse | 500.3000. - CNC Concrete Work | 13.15 | 36 | 22.85 | 36.53% | 0 | 108 | 0% | 36 | 22.85 | 36 | 36 | 100%
2226. - Tooele Berra Wellhouse | 300.7100. - IMP Interior Mech/Piping | 511.87 | 257.5 | -254.37 | 198.8% | 0 | 420.75 | 0% | 257.5 | -254.37 | 511.87 | 257.5 | 100%
2226. - Tooele Berra Wellhouse | 300.7500. - PUMP Pumps/Motors | 10.58 | 100 | 89.42 | 10.58% | 0 | 150 | 0% | 100 | 89.42 | 100 | 100 | 100%
2226. - Tooele Berra Wellhouse | 900.9015. - Re-Work Concrete | 6 | 0.2 | -5.8 | 3000% | 0 | 0.4 | 0% | 0.2 | -5.8 | 6 | 0.2 | 100%
2226. - Tooele Berra Wellhouse | 300.5000. - MET Metals | 12.52 | 123.5 | 110.98 | 10.14% | 0 | 149.5 | 0% | 123.5 | 110.98 | 123.5 | 123.5 | 100%
2226. - Tooele Berra Wellhouse | 300.7400. - HVAC HVAC | 3.5 | 25 | 21.5 | 14% | 0 | 30 | 0% | 25 | 21.5 | 25 | 25 | 100%
2226. - Tooele Berra Wellhouse | 160.5110. - Fab Shop Pipe Fabrication | 408.61 | 364 | -44.61 | 112.3% | 0 | 364 | 0% | 364 | -44.61 | 408.61 | 364 | 100%
2226. - Tooele Berra Wellhouse | 400.7900. - ELC Electrical | 48.66 | 20 | -28.66 | 243.3% | 0 | 60 | 0% | 20 | -28.66 | 48.66 | 20 | 100%
2226. - Tooele Berra Wellhouse | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2226. - Tooele Berra Wellhouse | 200.2710. - FWF Flowable Fill | 27.18 | 40 | 12.82 | 67.95% | 0 | 80 | 0% | 40 | 12.82 | 40 | 40 | 100%
2226. - Tooele Berra Wellhouse | 160.5310. - Fab Shop Misc Metals Fabrication | 100.6 | 52 | -48.6 | 193.5% | 0 | 52 | 0% | 52 | -48.6 | 100.6 | 52 | 100%
2226. - Tooele Berra Wellhouse | 300.7600. - MEQ Mechanical Equipment | 34.67 | 1 | -33.67 | 3467% | 0 | 3 | 0% | 1 | -33.67 | 34.67 | 1 | 100%
2226. - Tooele Berra Wellhouse | 300.6100. - F Framing | 8.27 | 5 | -3.27 | 165.4% | 0 | 15 | 0% | 5 | -3.27 | 8.27 | 5 | 100%
2226. - Tooele Berra Wellhouse | 300.2800. - BFST Backfill (DO NOT USE) | 1391.81 | 70 | -1321.81 | 1988% | 0 | 60 | 0% | 70 | -1321.81 | 1391.81 | 70 | 100%
2226. - Tooele Berra Wellhouse | 100.1702. - FS People Superintendent | 315.79 | 0 | -315.79 |  | 0 | 0 | 0% | 0 | -315.79 | 315.79 | 0 | 0%
2226. - Tooele Berra Wellhouse | 900.9020. - Re-Work Fab | 4.6 | 0.4 | -4.2 | 1150% | 0 | 0.2 | 0% | 0.4 | -4.2 | 4.6 | 0.4 | 100%
2226. - Tooele Berra Wellhouse | 100.1510. - S Surveying | 372.46 | 160 | -212.46 | 232.8% | 0 | 80 | 0% | 160 | -212.46 | 372.46 | 160 | 100%
2226. - Tooele Berra Wellhouse | 300.2010. - RG Grading (DO NOT USE) | 278.45 | 90 | -188.45 | 309.4% | 0 | 98.5 | 0% | 90 | -188.45 | 278.45 | 90 | 100%
2226. - Tooele Berra Wellhouse | 250.2300. - WPL Water Pipe Laying (DO NOT USE) | 869.21 | 1695.75 | 826.54 | 51.26% | 0 | 1182.25 | 0% | 1695.75 | 826.54 | 1695.75 | 1685.5 | 100.6%
2226. - Tooele Berra Wellhouse | 250.5100. - W Welding | 128.54 | 20 | -108.54 | 642.7% | 0 | 10 | 0% | 20 | -108.54 | 128.54 | 20 | 100%
2226. - Tooele Berra Wellhouse | 400.7100. - IMP Interior Mech/Piping | 125.42 | 63 | -62.42 | 199.1% | 0 | 106 | 0% | 63 | -62.42 | 125.42 | 63 | 100%
2226. - Tooele Berra Wellhouse | 300.6300. - DAW Doors & Windows | 57.74 | 60 | 2.26 | 96.23% | 0 | 180 | 0% | 60 | 2.26 | 60 | 60 | 100%
2226. - Tooele Berra Wellhouse | 300.3000. - CNC Concrete Work | 811 | 285 | -526 | 284.6% | 0 | 621.5 | 0% | 285 | -526 | 811 | 285 | 100%
2226. - Tooele Berra Wellhouse | 700.2610. - PT Pressure Test/Chlorinating | 161.43 | 35 | -126.43 | 461.2% | 0 | 40 | 0% | 35 | -126.43 | 161.43 | 35 | 100%
2226. - Tooele Berra Wellhouse | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 11 | 0 | -11 |  | 0 | 0 | 0% | 0 | -11 | 11 | 0 | 0%
2226. - Tooele Berra Wellhouse | 300.2080. - EXS Excavate Structure | 332.38 | 103.5 | -228.88 | 321.1% | 0 | 111 | 0% | 103.5 | -228.88 | 332.38 | 103.5 | 100%
2226. - Tooele Berra Wellhouse | 185.7900. - ELC Electrical | 20 | 0 | -20 |  | 0 | 0 | 0% | 0 | -20 | 20 | 0 | 0%
2226. - Tooele Berra Wellhouse | 500.2010. - RG Grading (DO NOT USE) | 897.08 | 252 | -645.08 | 356% | 0 | 217 | 0% | 252 | -645.08 | 897.08 | 252 | 100%
2226. - Tooele Berra Wellhouse | 160.5015. - Fab Shop Transport | 0 | 20 | 20 | 0% | 0 | 20 | 0% | 20 | 20 | 20 | 20 | 100%
2226. - Tooele Berra Wellhouse | 800.1700. - FS Project Manager | 16.48 | 140 | 123.52 | 11.77% | 0 | 140 | 0% | 140 | 123.52 | 140 | 140 | 100%
2226. - Tooele Berra Wellhouse | 100.1700. - FS Project Manager | 1 | 0 | -1 |  | 0 | 0 | 0% | 0 | -1 | 1 | 0 | 0%
2226. - Tooele Berra Wellhouse | 200.3000. - Unknown Phase | 41.2 | 10 | -31.2 | 412% | 0 | 20 | 0% | 10 | -31.2 | 41.2 | 10 | 100%
2226. - Tooele Berra Wellhouse | 200.2300. - Unknown Phase | 2141.57 | 314 | -1827.57 | 682% | 0 | 96 | 0% | 314 | -1827.57 | 2141.57 | 314 | 100%
2226. - Tooele Berra Wellhouse | 100.1703. - FS Job Site Superintendent | 569.59 | 0 | -569.59 |  | 0 | 0 | 0% | 0 | -569.59 | 569.59 | 0 | 0%
2226. - Tooele Berra Wellhouse | 150.2750. - Unknown Phase | 298.75 | 66.01 | -232.74 | 452.6% | 0 | 66.01 | 0% | 66.01 | -232.74 | 298.75 | 66.01 | 100%
2226. - Tooele Berra Wellhouse | 150.2760. - Unknown Phase | 41.14 | 105 | 63.86 | 39.18% | 0 | 105 | 0% | 105 | 63.86 | 105 | 105 | 100%
2226. - Tooele Berra Wellhouse | 800.1940. - PL Punch List Work | 140.7 | 250 | 109.3 | 56.28% | 0 | 200 | 0% | 250 | 109.3 | 250 | 250 | 100%
2226. - Tooele Berra Wellhouse | 150.1230. - T Transporting | 351.74 | 200 | -151.74 | 175.9% | 0 | 200 | 0% | 200 | -151.74 | 351.74 | 200 | 100%
2226. - Tooele Berra Wellhouse | 160.5120. - Fab Shop Pipe Linings & Coatings | 401.53 | 380 | -21.53 | 105.7% | 0 | 380 | 0% | 380 | -21.53 | 401.53 | 380 | 100%
2226. - Tooele Berra Wellhouse | 900.9005. - Re-Work Surveying | 4 | 0 | -4 |  | 0 | 0 | 0% | 0 | -4 | 4 | 0 | 0%
2226. - Tooele Berra Wellhouse | 300.6500. - P Painting | 929.96 | 200 | -729.96 | 465% | 0 | 400 | 0% | 200 | -729.96 | 929.96 | 200 | 100%
2226. - Tooele Berra Wellhouse | 250.2710. - FWF Flowable Fill | 4.38 | 20 | 15.62 | 21.9% | 0 | 40 | 0% | 20 | 15.62 | 20 | 20 | 100%
2226. - Tooele Berra Wellhouse | 250.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 18.52 | 80 | 61.48 | 23.15% | 0 | 40 | 0% | 80 | 61.48 | 80 | 80 | 100%
2226. - Tooele Berra Wellhouse | 200.1000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2226. - Tooele Berra Wellhouse | 300.6900. - EF Roofing | 18.12 | 10 | -8.12 | 181.2% | 0 | 30 | 0% | 10 | -8.12 | 18.12 | 10 | 100%
2317. - CUWCD CWP Wellhouse 17 | 200.2800. - Unknown Phase | 589.72 | 195 | -394.72 | 302.4% | 33 | 165 | 9.167% | 17.875 | -571.845 | 6433.3091 | 589.72 | -102.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 400.3000. - CNC Concrete Work | 279.05 | 190.02 | -89.03 | 146.9% | 483.2 | 530.2 | 100% | 190.02 | -89.03 | 279.05 | 279.05 | 53.15% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9100. - Job Related Equipment Repairs | 5 | 1 | -4 | 500% | 1 | 1 | 100% | 1 | -4 | 5 | 5 | -300% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5320. - Fab Shop Misc Metals Coatings | 15.25 | 240 | 224.75 | 6.354% | 1 | 480 | 100% | 240 | 224.75 | 15.25 | 15.25 | 193.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2710. - FWF Flowable Fill | 12.06 | 1.78 | -10.28 | 677.5% | 0.712 | 3.56 | 13.33% | 0.23733 | -11.8227 | 90.45 | 12.06 | -477.5% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 419.06 | 37.5 | -381.56 | 1117% | 37.5 | 37.5 | 100% | 37.5 | -381.56 | 419.06 | 406.56 | -884.2% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9055. - Re-Work Finishes | 0 | 0.1 | 0.1 | 0% | 0 | 0.2 | 0% | 0.1 | 0.1 | 0.1 | 0 | 200% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5310. - Fab Shop Misc Metals Fabrication | 38.15 | 507 | 468.85 | 7.525% | 1 | 253.5 | 100% | 507 | 468.85 | 38.15 | 38.15 | 192.5% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.7600. - MEQ Mechanical Equipment | 0 | 65 | 65 | 0% | 110 | 110 | 100% | 65 | 65 | 0 | 0 | 200% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.6300. - DAW Doors & Windows | 79.35 | 30 | -49.35 | 264.5% | 60 | 60 | 100% | 30 | -49.35 | 79.35 | 79.35 | -64.5% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 31.66 | 162.5 | 130.84 | 19.48% | 135 | 135 | 100% | 162.5 | 130.84 | 31.66 | 31.66 | 180.5% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2070. - RGC Rough Grade Cut | 34.07 | 96.66 | 62.59 | 35.25% | 106 | 106 | 100% | 96.66 | 62.59 | 34.07 | 34.07 | 164.8% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.2800. - BFST Backfill (DO NOT USE) | 268.76 | 175 | -93.76 | 153.6% | 150 | 150 | 100% | 175 | -93.76 | 268.76 | 268.76 | 46.42% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9020. - Re-Work Fab | 67.22 | 0.4 | -66.82 | 16805% | 0 | 0.2 | 0% | 0.4 | -66.82 | 67.22 | 67.22 | -16605% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1650. - SB Signage | 2.5 | 10 | 7.5 | 25% | 15 | 15 | 100% | 10 | 7.5 | 2.5 | 2.5 | 175% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1702. - FS People Superintendent | 640.89 | 291.32 | -349.57 | 220% | 117.6 | 291.32 | 98% | 285.4936 | -355.3964 | 653.9694 | 650.89 | -23.43% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.7900. - ELC Electrical | 473.53 | 144.76 | -328.77 | 327.1% | 144.75 | 144.75 | 100% | 144.76 | -328.77 | 473.53 | 473.53 | -127.1% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 800.1940. - PL Punch List Work | 48.63 | 250 | 201.37 | 19.45% | 130 | 200 | 65% | 162.5 | 113.87 | 74.8154 | 76.27 | 169.5% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 1010.53 | 296.86 | -713.67 | 340.4% | 199.72 | 233.72 | 100% | 296.86 | -713.67 | 1010.53 | 1023.03 | -144.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 800.1700. - FS Project Manager | 41.75 | 400 | 358.25 | 10.44% | 400 | 400 | 100% | 400 | 358.25 | 41.75 | 41.75 | 189.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.2080. - EXS Excavate Structure | 328.75 | 408.75 | 80 | 80.43% | 400 | 400 | 100% | 408.75 | 80 | 328.75 | 328.75 | 119.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.5000. - MET Metals | 122.14 | 25 | -97.14 | 488.6% | 40 | 40 | 240.7% | 60.1852 | -61.9548 | 50.7351 | 122.14 | -288.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1704. - FS Quality Control/Assurance | 453.24 | 58.23 | -395.01 | 778.4% | 100 | 58.23 | 100% | 58.23 | -395.01 | 453.24 | 463.24 | -595.5% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.7100. - IMP Interior Mech/Piping | 331.55 | 85 | -246.55 | 390.1% | 100 | 100 | 100% | 85 | -246.55 | 331.55 | 331.55 | -190.1% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.1650. - SB Signage | 11.25 | 5 | -6.25 | 225% | 10 | 10 | 100% | 5 | -6.25 | 11.25 | 1 | 180% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.6100. - F Framing | 21.52 | 20 | -1.52 | 107.6% | 20 | 20 | 100% | 20 | -1.52 | 21.52 | 21.52 | 92.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1510. - S Surveying | 1024.14 | 212 | -812.14 | 483.1% | 252.45 | 106 | 100% | 212 | -812.14 | 1024.14 | 1024.14 | -283.1% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9015. - Re-Work Concrete | 2 | 0.2 | -1.8 | 1000% | 0 | 0.4 | 0% | 0.2 | -1.8 | 2 | 2 | -800% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 502.84 | 372.02 | -130.82 | 135.2% | 78.4 | 372.018 | 98% | 364.5796 | -138.2604 | 513.102 | 508.34 | 63.36% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1700. - FS Project Manager | 840.75 | 400.64 | -440.11 | 209.9% | 181.055 | 400.64 | 98% | 392.6272 | -448.1228 | 857.9082 | 844.75 | -10.85% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.3000. - CNC Concrete Work | 474.11 | 385 | -89.11 | 123.1% | 930 | 930 | 100% | 385 | -89.11 | 474.11 | 474.11 | 76.85% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1703. - FS Job Site Superintendent | 1056.68 | 596.54 | -460.14 | 177.1% | 519.4 | 596.54 | 98% | 584.6092 | -472.0708 | 1078.2449 | 1058.38 | 22.58% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5110. - Fab Shop Pipe Fabrication | 547.95 | 0 | -547.95 |  | 0 | 0 | 0% | 0 | -547.95 | 547.95 | 547.95 | 0% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 400.2010. - RG Grading (DO NOT USE) | 320.1 | 223.29 | -96.81 | 143.4% | 267.6 | 270.6 | 100% | 223.29 | -96.81 | 320.1 | 325.1 | 54.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9012. - Re-Work Mechanical | 86.75 | 0.2 | -86.55 | 43375% | 0 | 0.4 | 0% | 0.2 | -86.55 | 86.75 | 73.33 | -36465% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.5100. - W Welding | 372.51 | 160 | -212.51 | 232.8% | 60 | 80 | 100% | 160 | -212.51 | 372.51 | 372.51 | -32.82% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2040. - LR Landscaping/Restoration | 0 | 44.63 | 44.63 | 0% | 50 | 44.62 | 100% | 44.63 | 44.63 | 0 | 2.42 | 194.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2610. - PT Pressure Test/Chlorinating | 216.99 | 122.5 | -94.49 | 177.1% | 140 | 140 | 100% | 122.5 | -94.49 | 216.99 | 216.99 | 22.87% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 800.1930. - MC Misc Cleanup | 3.5 | 125 | 121.5 | 2.8% | 60 | 100 | 60% | 75 | 71.5 | 5.8333 | 23.5 | 181.2% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.3000. - Unknown Phase | 366.99 | 198 | -168.99 | 185.3% | 513 | 513 | 100% | 198 | -168.99 | 366.99 | 366.99 | 14.65% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.7100. - IMP Interior Mech/Piping | 708.42 | 203 | -505.42 | 349% | 470.25 | 489 | 95% | 192.85 | -515.57 | 745.7053 | 708.42 | -149% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9010. - Re-Work Pipe | 31.51 | 0.2 | -31.31 | 15755% | 0 | 0.4 | 0% | 0.2 | -31.31 | 31.51 | 31.51 | -15555% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.6200. - IN Insulation | 45.09 | 8 | -37.09 | 563.6% | 39.6 | 16 | 99% | 7.92 | -37.17 | 45.5455 | 47.19 | -389.9% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.6400. - DRY Drywall & Metal Studs | 69.51 | 34 | -35.51 | 204.4% | 68 | 68 | 100% | 34 | -35.51 | 69.51 | 69.51 | -4.441% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.1230. - T Transporting | 175.02 | 152 | -23.02 | 115.1% | 152 | 152 | 100% | 152 | -23.02 | 175.02 | 225.25 | 51.81% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 400.2000. - SWC Site Work Complete (DO NOT USE) | 616.94 | 101.04 | -515.9 | 610.6% | 25 | 84.77 | 100% | 101.04 | -515.9 | 616.94 | 611.94 | -405.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5120. - Fab Shop Pipe Linings & Coatings | 565.19 | 0 | -565.19 |  | 0 | 0 | 0% | 0 | -565.19 | 565.19 | 565.19 | 0% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2030. - Unknown Phase | 6.5 | 11.25 | 4.75 | 57.78% | 15 | 15 | 100% | 11.25 | 4.75 | 6.5 | 11.25 | 100% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9005. - Re-Work Surveying | 6 | 2 | -4 | 300% | 0 | 1 | 0% | 2 | -4 | 6 | 6 | -100% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.2760. - Unknown Phase | 385.94 | 387.72 | 1.78 | 99.54% | 387 | 388 | 100% | 387.72 | 1.78 | 385.94 | 361.54 | 106.8% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.2750. - Unknown Phase | 323.76 | 267.33 | -56.43 | 121.1% | 258.06 | 267.59 | 94.38% | 252.3091 | -71.4509 | 343.0346 | 307.91 | 84.82% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.2710. - FWF Flowable Fill | 52.04 | 0.14 | -51.9 | 37171% | 1 | 1.12 | 100% | 0.14 | -51.9 | 52.04 | 52.04 | -36971% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2300. - Unknown Phase | 774.65 | 590.09 | -184.56 | 131.3% | 319.65 | 438.25 | 100% | 590.09 | -184.56 | 774.65 | 772.55 | 69.08% |  | 2025-12-30
2232. - Syracuse Secondary Reservoir | 400.2410. - IS Irrigation Services (DO NOT USE) | 84.02 | 175 | 90.98 | 48.01% | 840 | 210 | 218.2% | 381.8182 | 297.7982 | 38.5092 | 175 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.7900. - ELC Electrical | 160.5 | 272 | 111.5 | 59.01% | 306 | 204 | 64.29% | 174.8571 | 14.3571 | 249.6667 | 272 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.6300. - DAW Doors & Windows | 2 | 20 | 18 | 10% | 80 | 40 | 133.3% | 26.6667 | 24.6667 | 1.5 | 20 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2030. - D Demolition | 290.16 | 57.68 | -232.48 | 503.1% | 78.48 | 39.24 | 80.97% | 46.7058 | -243.4542 | 358.3372 | 57.68 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 310.2030. - D Demolition | 41.19 | 145 | 103.81 | 28.41% | 300 | 100 | 122.4% | 177.551 | 136.361 | 33.6385 | 145 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 360.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 14.21 | 110.05 | 95.84 | 12.91% | 75 | 75 | 40.54% | 44.6137 | 30.4037 | 35.0523 | 110.05 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5320. - Fab Shop Misc Metals Coatings | 2 | 24 | 22 | 8.333% | 24 | 24 | 50% | 12 | 10 | 4 | 24 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.2080. - EXS Excavate Structure | -188.17 | 582.5 | 770.67 | -32.3% | 140 | 140 | 19.38% | 112.872 | 301.042 | -971.0916 | 582.5 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 330.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 1573.06 | 1289.01 | -284.05 | 122% | 1364 | 682 | 69.2% | 892.0349 | -681.0251 | 2273.1063 | 1289.01 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.6200. - IN Insulation | 1 | 2 | 1 | 50% | 8 | 4 | 133.3% | 2.6667 | 1.6667 | 0.75 | 2 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2080. - EXS Excavate Structure | 8176.36 | 1176.32 | -7000.04 | 695.1% | 838.88 | 850.88 | 42% | 494.0874 | -7682.2726 | 19466.2242 | 1158.32 | 101.5% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.7500. - PUMP Pumps/Motors | 11.38 | 60 | 48.62 | 18.97% | 144 | 120 | 80% | 48 | 36.62 | 14.225 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9040. - Re-Work Drivers | 4 | 0.1 | -3.9 | 4000% | 0 | 0.1 | 0% | 0.1 | -3.9 | 4 | 0.1 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.7100. - IMP Interior Mech/Piping | 127.13 | 60 | -67.13 | 211.9% | 225 | 90 | 150% | 90 | -37.13 | 84.7533 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 260.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 0 | 208 | 208 | 0% | 0 | 132 | 0% | 208 | 208 | 208 | 208 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.7100. - IMP Interior Mech/Piping | 117.29 | 80 | -37.29 | 146.6% | 120 | 120 | 60% | 48 | -69.29 | 195.4833 | 80 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 310.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 3713.4 | 1364.07 | -2349.33 | 272.2% | 2283.99 | 789.33 | 110.5% | 1507.4135 | -2205.9865 | 3360.284 | 1305.47 | 104.3% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9015. - Re-Work Concrete | 108.09 | 0.2 | -107.89 | 54045% | 0 | 0.4 | 0% | 0.2 | -107.89 | 108.09 | 0.2 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 400.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 123.05 | 226.01 | 102.96 | 54.44% | 452 | 113 | 133.3% | 301.3378 | 178.2878 | 92.2902 | 226.01 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5110. - Fab Shop Pipe Fabrication | 962.67 | 150 | -812.67 | 641.8% | 195 | 150 | 65% | 97.5 | -865.17 | 1481.0308 | 150 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2500. - MH Manholes (DO NOT USE) | 414.82 | 70 | -344.82 | 592.6% | 192 | 160 | 83.48% | 58.4348 | -356.3852 | 496.9198 | 70 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9012. - Re-Work Mechanical | 10.42 | 0.2 | -10.22 | 5210% | 1.96 | 0.4 | 2827% | 5.6533 | -4.7667 | 0.36863 | 0.2 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.7100. - IMP Interior Mech/Piping | 624.21 | 482.68 | -141.53 | 129.3% | 950.317 | 559.01 | 91.23% | 440.3412 | -183.8688 | 684.2278 | 482.68 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 240.2010. - RG Grading (DO NOT USE) | 16.26 | 36.58 | 20.32 | 44.45% | 73.14 | 36.57 | 99.99% | 36.575 | 20.315 | 16.2622 | 36.58 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2800. - Unknown Phase | 1303.03 | 175 | -1128.03 | 744.6% | 165 | 150 | 50.77% | 88.8462 | -1214.1838 | 2566.5742 | 175 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2070. - RGC Rough Grade Cut | 191.88 | 30 | -161.88 | 639.6% | 48 | 94.23 | 80% | 24 | -167.88 | 239.85 | 30 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 260.5100. - W Welding | 0 | 40 | 40 | 0% | 40 | 20 | 66.67% | 26.6667 | 26.6667 | 0 | 40 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1510. - S Surveying | 3863.2 | 800 | -3063.2 | 482.9% | 1320 | 800 | 82.5% | 660 | -3203.2 | 4682.6667 | 800 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1702. - FS People Superintendent | 1415.57 | 0 | -1415.57 |  | 0 | 0 | 0% | 0 | -1415.57 | 1415.57 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 380.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 55.93 | 72 | 16.07 | 77.68% | 108 | 36 | 100% | 72 | 16.07 | 55.93 | 72 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 4 | 278.8 | 274.8 | 1.435% | 165 | 214 | 61.11% | 170.3778 | 166.3778 | 6.5455 | 120 | 157% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.5100. - W Welding | 168.55 | 40 | -128.55 | 421.4% | 30 | 20 | 50% | 20 | -148.55 | 337.1 | 40 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.2760. - Unknown Phase | 5273.49 | 4589.17 | -684.32 | 114.9% | 15569.178 | 4589.17 | 191.3% | 8778.8525 | 3505.3625 | 2756.7318 | 4579.17 | 100.2% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 350.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 127.21 | 30.01 | -97.2 | 423.9% | 16.5 | 15 | 36.67% | 11.0034 | -116.2066 | 346.9441 | 30.01 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 270.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 394.68 | 155 | -239.68 | 254.6% | 133 | 95 | 53.2% | 82.46 | -312.22 | 741.8797 | 155 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.5000. - MET Metals | 0 | 9 | 9 | 0% | 25.2 | 18 | 93.33% | 8.4 | 8.4 | 0 | 9 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9100. - Job Related Equipment Repairs | 125.15 | 1 | -124.15 | 12515% | 0 | 1 | 0% | 1 | -124.15 | 125.15 | 1 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.3010. - WP Winter Protection | 513.08 | 0 | -513.08 |  | 0 | 0 | 0% | 0 | -513.08 | 513.08 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2020. - CG Clearing/Grubbing | 97.01 | 41.4 | -55.61 | 234.3% | 35.88 | 27.6 | 52% | 21.528 | -75.482 | 186.5577 | 41.4 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 400.2310. - WS Water Services (DO NOT USE) | 326.27 | 125 | -201.27 | 261% | 600 | 150 | 218.2% | 272.7273 | -53.5427 | 149.5404 | 125 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 600.2000. - SWC Site Work Complete (DO NOT USE) | 872.33 | 391.48 | -480.85 | 222.8% | 1644.36 | 411.09 | 204.9% | 802.0908 | -70.2392 | 425.7619 | 391.48 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5310. - Fab Shop Misc Metals Fabrication | 2899.65 | 135 | -2764.65 | 2148% | 135 | 135 | 51.85% | 70 | -2829.65 | 5592.1821 | 135 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.1520. - TEST Testing 3rd Party Soils/Concrete/Welding/Special | 7.97 | 100 | 92.03 | 7.97% | 380 | 100 | 190% | 190 | 182.03 | 4.1947 | 100 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9055. - Re-Work Finishes | 10.85 | 0.1 | -10.75 | 10850% | 0 | 0.2 | 0% | 0.1 | -10.75 | 10.85 | 250 | -249800% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.3000. - CNC Concrete Work | 158.62 | 10 | -148.62 | 1586% | 30 | 30 | 75% | 7.5 | -151.12 | 211.4933 | 10 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.6100. - F Framing | 41.39 | 0 | -41.39 |  | 0 | 0 | 0% | 0 | -41.39 | 41.39 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1076.44 | 0 | -1076.44 |  | 0 | 0 | 0% | 0 | -1076.44 | 1076.44 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 775.43 | 827 | 51.57 | 93.76% | 634 | 634 | 43.87% | 362.8385 | -412.5915 | 1767.3997 | 827 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 240.3000. - CNC Concrete Work | 114.09 | 32.37 | -81.72 | 352.5% | 97.11 | 97.11 | 75% | 24.2775 | -89.8125 | 152.12 | 32.37 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2020. - Unknown Phase | 563.75 | 90 | -473.75 | 626.4% | 80 | 80 | 47.06% | 42.3529 | -521.3971 | 1197.9688 | 90 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 743.22 | 50 | -693.22 | 1486% | 60 | 60 | 54.55% | 27.2727 | -715.9473 | 1362.57 | 50 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 55.37 | 150 | 94.63 | 36.91% | 285 | 150 | 95% | 142.5 | 87.13 | 58.2842 | 150 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.2800. - BFST Backfill (DO NOT USE) | 98.11 | 35 | -63.11 | 280.3% | 45 | 30 | 69.23% | 24.2308 | -73.8792 | 141.7144 | 35 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.2800. - BFST Backfill (DO NOT USE) | 1196.23 | 140 | -1056.23 | 854.4% | 132 | 120 | 50.77% | 71.0769 | -1125.1531 | 2356.2106 | 140 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1700. - FS Project Manager | 611.78 | 2 | -609.78 | 30589% | 0 | 2 | 0% | 2 | -609.78 | 611.78 | 0 | 200% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.2750. - Unknown Phase | 8373.26 | 1681.93 | -6691.33 | 497.8% | 3190.689 | 1681.96 | 96.02% | 1614.994 | -6758.266 | 8720.303 | 1679.28 | 100.2% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 700.2610. - PT Pressure Test/Chlorinating | 129.13 | 321 | 191.87 | 40.23% | 2220 | 444 | 290.2% | 931.5294 | 802.3994 | 44.4975 | 321 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 800.1930. - MC Misc Cleanup | 363.6 | 250 | -113.6 | 145.4% | 950 | 200 | 211.1% | 527.7778 | 164.1778 | 172.2316 | 250 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1000. - GR General Requirements | 0 | 1 | 1 | 0% | 3 | 1 | 0% | 1 | 1 | 1 | 0 | 200% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 370.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 0 | 222.01 | 222.01 | 0% | 131 | 131 | 37.11% | 82.3887 | 82.3887 | 0 | 222.01 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1704. - FS Quality Control/Assurance | 7.5 | 0 | -7.5 |  | 0 | 0 | 0% | 0 | -7.5 | 7.5 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.1230. - T Transporting | 1810.18 | 500 | -1310.18 | 362% | 950 | 500 | 95% | 475 | -1335.18 | 1905.4526 | 500 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 700.3000. - CNC Concrete Work | 99.08 | 6 | -93.08 | 1651% | 54 | 18 | 225% | 13.5 | -85.58 | 44.0356 | 6 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2010. - RG Grading (DO NOT USE) | 2374.58 | 1577.5 | -797.08 | 150.5% | 1740 | 1740 | 52.45% | 827.3851 | -1547.1949 | 4527.3961 | 1577.5 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 240.2800. - BFST Backfill (DO NOT USE) | 1438.28 | 60 | -1378.28 | 2397% | 120 | 60 | 100% | 60 | -1378.28 | 1438.28 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 250.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 0 | 173 | 173 | 0% | 117 | 117 | 40.34% | 69.7966 | 69.7966 | 0 | 173 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 600.3000. - CNC Concrete Work | 859 | 575.79 | -283.21 | 149.2% | 5342.95 | 1068.59 | 324.9% | 1870.8675 | 1011.8675 | 264.3713 | 575.79 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 180.6100. - F Framing | 68.73 | 0 | -68.73 |  | 0 | 0 | 0% | 0 | -68.73 | 68.73 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.7600. - MEQ Mechanical Equipment | 34.81 | 45 | 10.19 | 77.36% | 180 | 90 | 133.3% | 60 | 25.19 | 26.1075 | 45 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 280.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 83.48 | 78.01 | -5.47 | 107% | 46.8 | 39 | 39.96% | 31.1747 | -52.3053 | 208.8962 | 78.01 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 800.1700. - FS Project Manager | 5 | 50 | 45 | 10% | 242.5 | 50 | 242.5% | 121.25 | 116.25 | 2.0619 | 50 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 320.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 3666.99 | 1507.39 | -2159.6 | 243.3% | 1505.7 | 836.5 | 64.24% | 968.3377 | -2698.6523 | 5708.3225 | 1507.39 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.3000. - CNC Concrete Work | 40.14 | 33 | -7.14 | 121.6% | 198 | 66 | 200% | 66 | 25.86 | 20.07 | 33 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.2800. - BFST Backfill (DO NOT USE) | 88.29 | 70 | -18.29 | 126.1% | 120 | 60 | 92.31% | 64.6154 | -23.6746 | 95.6475 | 70 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 340.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 50.04 | 53.34 | 3.3 | 93.81% | 42.688 | 26.68 | 53.35% | 28.4551 | -21.5849 | 93.8016 | 53.34 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2600. - DW Dewatering | 27306.01 | 7011.4 | -20294.61 | 389.5% | 2966.4 | 1854 | 33.47% | 2346.8347 | -24959.1753 | 81579.3965 | 7011.4 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.2500. - MH Manholes (DO NOT USE) | 288.95 | 17.5 | -271.45 | 1651% | 80 | 40 | 139.1% | 24.3478 | -264.6022 | 207.6828 | 17.5 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5120. - Fab Shop Pipe Linings & Coatings | 907.39 | 110 | -797.39 | 824.9% | 143 | 110 | 106.4% | 117.05 | -790.34 | 852.7373 | 110 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.2080. - EXS Excavate Structure | 49.48 | 41.25 | -8.23 | 120% | 40 | 40 | 49.23% | 20.3077 | -29.1723 | 100.5062 | 41.25 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.3000. - Unknown Phase | 0 | 0 | 0 |  | 12407.3 | 0 | 71.84% | 0 | 0 | 0 | 4864.1 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2600. - DW Dewatering | 42.34 | 788.16 | 745.82 | 5.372% | 945.78 | 315.26 | 85.71% | 675.5596 | 633.2196 | 49.3971 | 788.16 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 80 | 80 | 0% | 160 | 40 | 133.3% | 106.6667 | 106.6667 | 0 | 80 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.1600. - TC Traffic Control | 468.33 | 1955 | 1486.67 | 23.96% | 990 | 465 | 41.25% | 806.4375 | 338.1075 | 1135.3455 | 1950 | 100.3% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1703. - FS Job Site Superintendent | 1926.35 | 0 | -1926.35 |  | 0 | 0 | 0% | 0 | -1926.35 | 1926.35 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5015. - Fab Shop Transport | 5.17 | 20 | 14.83 | 25.85% | 50 | 20 | 125% | 25 | 19.83 | 4.136 | 20 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 6027.32 | 2752.03 | -3275.29 | 219% | 3281.58 | 2187.72 | 66.43% | 1828.2315 | -4199.0885 | 9072.9021 | 2752.03 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 600.2930. - AP Asphalt Prep (DO NOT USE) | 2587.08 | 107.64 | -2479.44 | 2403% | 430.56 | 107.64 | 200% | 215.28 | -2371.8 | 1293.54 | 107.64 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 390.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 9.86 | 60 | 50.14 | 16.43% | 90 | 30 | 100% | 60 | 50.14 | 9.86 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9010. - Re-Work Pipe | 654.55 | 0.2 | -654.35 | 327275% | 1.94 | 0.4 | 323.3% | 0.64667 | -653.9033 | 202.4381 | 0.2 | 100% |  | 2024-04-01
2406. - DR Horton Viridian Wellhouse | 100.1704. - FS Quality Control/Assurance | 24.5 | 36.98 | 12.48 | 66.25% | 0 | 36.98 | 0% | 36.98 | 12.48 | 36.98 | 24.5 | 133.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 160.5000. - Unknown Phase | 7.5 | 150 | 142.5 | 5% | 1 | 150 | 100% | 150 | 142.5 | 7.5 | 7.5 | 195% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2075. - FG Finish Grade | 194.46 | 82.24 | -112.22 | 236.5% | 61.19 | 82.04 | 100% | 82.24 | -112.22 | 194.46 | 194.46 | -36.45% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1510. - S Surveying | 51.16 | 30 | -21.16 | 170.5% | 0 | 10 | 0% | 30 | -21.16 | 51.16 | 51.16 | 29.47% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2240. - PCS Precast Structures | 28.49 | 27.5 | -0.99 | 103.6% | 0 | 40 | 0% | 27.5 | -0.99 | 28.49 | 28.49 | 96.4% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.7100. - IMP Interior Mech/Piping | 370.03 | 316 | -54.03 | 117.1% | 589.5 | 598.5 | 100% | 316 | -54.03 | 370.03 | 370.03 | 82.9% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2120. - DIP Ductile Iron Pipe | 331.06 | 417.72 | 86.66 | 79.25% | 0 | 237.74 | 0% | 417.72 | 86.66 | 417.72 | 331.06 | 120.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.4000. - MAS Masonry | 13.49 | 24.6 | 11.11 | 54.84% | 0 | 186.95 | 0% | 24.6 | 11.11 | 24.6 | 13.49 | 145.2% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2085. - BFST Backfill Structure | 35.6 | 141.68 | 106.08 | 25.13% | 0 | 92.7 | 0% | 141.68 | 106.08 | 141.68 | 35.6 | 174.9% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1200. - HOOK Hook Truck Dumpster Transporting | 26.72 | 30 | 3.28 | 89.07% | 47 | 30 | 100% | 30 | 3.28 | 26.72 | 26.72 | 110.9% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 800.1940. - PL Punch List Work | 142.7 | 90 | -52.7 | 158.6% | 38 | 135 | 100% | 90 | -52.7 | 142.7 | 142.7 | 41.44% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 38.13 | 113.01 | 74.88 | 33.74% | 0 | 55 | 0% | 113.01 | 74.88 | 113.01 | 38.13 | 166.3% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6800. - CLK Caulking | 99.14 | 40 | -59.14 | 247.8% | 80 | 80 | 100% | 40 | -59.14 | 99.14 | 99.14 | -47.85% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.7900. - ELC Electrical | 54.31 | 97.45 | 43.14 | 55.73% | 1 | 118 | 100% | 97.45 | 43.14 | 54.31 | 54.31 | 144.3% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.5000. - MET Metals | 62.28 | 58.56 | -3.72 | 106.4% | 107.84 | 107.84 | 100% | 58.56 | -3.72 | 62.28 | 62.28 | 93.65% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 161.2090. - MTL Materials | 3.75 | 32 | 28.25 | 11.72% | 1 | 33 | 100% | 32 | 28.25 | 3.75 | 3.75 | 188.3% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1702. - FS People Superintendent | 207.82 | 186.95 | -20.87 | 111.2% | 1 | 186.95 | 100% | 186.95 | -20.87 | 207.82 | 207.82 | 88.84% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 150.1230. - T Transporting | 86.35 | 100 | 13.65 | 86.35% | 100 | 100 | 100% | 100 | 13.65 | 86.35 | 86.35 | 113.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 900.9015. - Re-Work Concrete | 122.62 | 0.2 | -122.42 | 61310% | 0.4 | 0.4 | 100% | 0.2 | -122.42 | 122.62 | 122.62 | -61110% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.3000. - Unknown Phase | 420.34 | 145.1 | -275.24 | 289.7% | 768.91 | 777.91 | 100% | 145.1 | -275.24 | 420.34 | 420.34 | -89.69% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 900.9012. - Re-Work Mechanical | 10 | 0.2 | -9.8 | 5000% | 0.6 | 0.6 | 100% | 0.2 | -9.8 | 10 | 10 | -4800% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 263.92 | 239.1 | -24.82 | 110.4% | 0.95 | 239.1 | 95% | 227.145 | -36.775 | 277.8105 | 263.92 | 89.62% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 150.2750. - Unknown Phase | 154.94 | 419.52 | 264.58 | 36.93% | 167.55 | 190.88 | 100% | 419.52 | 264.58 | 154.94 | 154.94 | 163.1% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 150.2760. - Unknown Phase | 3.13 | 58.41 | 55.28 | 5.359% | 53.08 | 53.08 | 100% | 58.41 | 55.28 | 3.13 | 3.13 | 194.6% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6000. - IF Interior Finishes | 49.3 | 0.5 | -48.8 | 9860% | 1.5 | 1.5 | 100% | 0.5 | -48.8 | 49.3 | 49.3 | -9660% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6300. - DAW Doors & Windows | 30.3 | 50 | 19.7 | 60.6% | 150 | 150 | 100% | 50 | 19.7 | 30.3 | 30.3 | 139.4% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1703. - FS Job Site Superintendent | 990.24 | 384.2 | -606.04 | 257.7% | 0.95 | 384.2 | 105.6% | 405.5444 | -584.6956 | 938.1221 | 990.24 | -57.74% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1700. - FS Project Manager | 682 | 264.59 | -417.41 | 257.8% | 0.95 | 264.59 | 95% | 251.3605 | -430.6395 | 717.8947 | 682 | -57.76% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 900.9010. - Re-Work Pipe | 44.01 | 0.2 | -43.81 | 22005% | 0.6 | 0.6 | 100% | 0.2 | -43.81 | 44.01 | 44.01 | -21805% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2150. - PSR Pipe w/ Slide Rail | 10 | 39.6 | 29.6 | 25.25% | 0 | 42 | 0% | 39.6 | 29.6 | 39.6 | 10 | 174.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6200. - IN Insulation | 13.57 | 4 | -9.57 | 339.2% | 0 | 12 | 0% | 4 | -9.57 | 13.57 | 13.57 | -139.2% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2140. - SVR Services | 51.02 | 27.1 | -23.92 | 188.3% | 0 | 21 | 0% | 27.1 | -23.92 | 51.02 | 51.02 | 11.73% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1201. - HOOK Hook Truck Conex, Skid Transporting | 2 | 5 | 3 | 40% | 5 | 5 | 100% | 5 | 3 | 2 | 2 | 160% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2080. - EXS Excavate Structure | 197.61 | 29.92 | -167.69 | 660.5% | 0 | 37.73 | 0% | 29.92 | -167.69 | 197.61 | 197.61 | -460.5% |  | 2025-05-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.2080. - EXS Excavate Structure | 450.98 | 30 | -420.98 | 1503% | 40 | 40 | 100% | 30 | -420.98 | 450.98 | 453.98 | -1313% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.2085. - BFST Backfill Structure | 462.46 | 60 | -402.46 | 770.8% | 40 | 40 | 100% | 60 | -402.46 | 462.46 | 462.46 | -570.8% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 800.1940. - PL Punch List Work | 29.34 | 410 | 380.66 | 7.156% | 0 | 840 | 0% | 410 | 380.66 | 410 | 410 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.3000. - CNC Concrete Work | 350 | 80.36 | -269.64 | 435.5% | 310.848 | 388.56 | 80% | 64.288 | -285.712 | 437.5 | 354 | -240.5% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2120. - DIP Ductile Iron Pipe | 511.44 | 847.7 | 336.26 | 60.33% | 434.817 | 511.55 | 85% | 720.5447 | 209.1047 | 601.6944 | 847.7 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 550.3000. - CNC Concrete Work | 1118.67 | 173.79 | -944.88 | 643.7% | 673.013 | 897.35 | 75% | 130.3427 | -988.3273 | 1491.5581 | 1069.55 | -415.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1200. - HOOK Hook Truck Dumpster Transporting | 28.37 | 56.25 | 27.88 | 50.44% | 0 | 56.25 | 0% | 56.25 | 27.88 | 56.25 | 34.85 | 138% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.7900. - ELC Electrical | 222.92 | 236.25 | 13.33 | 94.36% | 81 | 180 | 45% | 106.3128 | -116.6072 | 495.3765 | 260.79 | 89.61% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.2120. - DIP Ductile Iron Pipe | 128.11 | 10 | -118.11 | 1281% | 18 | 30 | 61.25% | 6.125 | -121.985 | 209.1592 | 114.98 | -949.8% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.7100. - IMP Interior Mech/Piping | 4 | 41.25 | 37.25 | 9.697% | 60 | 60 | 100% | 41.25 | 37.25 | 4 | 4 | 190.3% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.6300. - DAW Doors & Windows | 4 | 50 | 46 | 8% | 0 | 105 | 0% | 50 | 46 | 50 | 50 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 550.2085. - BFST Backfill Structure | 389.08 | 240 | -149.08 | 162.1% | 120 | 160 | 75% | 180 | -209.08 | 518.7733 | 240 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2065. - SFC SWPPP | 0.5 | 25 | 24.5 | 2% | 13 | 26 | 50% | 12.5 | 12 | 1 | 25 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 700.7100. - IMP Interior Mech/Piping | 241.85 | 157.85 | -84 | 153.2% | 0 | 124 | 0% | 157.85 | -84 | 241.85 | 0 | 200% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.7100. - IMP Interior Mech/Piping | 4.29 | 19 | 14.71 | 22.58% | 0 | 57 | 0% | 19 | 14.71 | 19 | 19 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.2080. - EXS Excavate Structure | 263.09 | 70 | -193.09 | 375.8% | 108 | 120 | 90% | 63 | -200.09 | 292.3222 | 277.09 | -195.8% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1702. - FS People Superintendent | 671.28 | 1001 | 329.72 | 67.06% | 500 | 1001 | 50% | 500.5 | -170.78 | 1342.56 | 1001.28 | 99.97% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1510. - S Surveying | 1057.13 | 750 | -307.13 | 141% | 200 | 250 | 80% | 600 | -457.13 | 1321.4125 | 1025.81 | 63.23% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.7100. - IMP Interior Mech/Piping | 3 | 60 | 57 | 5% | 40 | 80 | 50% | 30 | 27 | 6 | 60 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 800.1930. - MC Misc Cleanup | 19.46 | 175 | 155.54 | 11.12% | 0 | 412.5 | 0% | 175 | 155.54 | 175 | 175 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.6100. - F Framing | 54.2 | 40 | -14.2 | 135.5% | 0 | 60 | 0% | 40 | -14.2 | 54.2 | 40 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.3000. - CNC Concrete Work | 1200.56 | 834.42 | -366.14 | 143.9% | 2353.6 | 2353.6 | 100% | 834.42 | -366.14 | 1200.56 | 1200.56 | 56.12% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.1800. - PH Potholing | 11 | 6 | -5 | 183.3% | 8.1 | 9 | 90% | 5.4 | -5.6 | 12.2222 | 11 | 16.67% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1704. - FS Quality Control/Assurance | 227.5 | 501 | 273.5 | 45.41% | 250 | 501 | 50% | 250.5 | 23 | 455 | 500 | 100.2% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.2130. - PVC Pipe | 93.28 | 755.96 | 662.68 | 12.34% | 400.69 | 400.69 | 100% | 755.96 | 662.68 | 93.28 | 90.28 | 188.1% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.2080. - EXS Excavate Structure | 1453.44 | 300 | -1153.44 | 484.5% | 300 | 300 | 100% | 300 | -1153.44 | 1453.44 | 1451.44 | -283.8% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.7600. - MEQ Mechanical Equipment | 53.2 | 15 | -38.2 | 354.7% | 30 | 30 | 100% | 15 | -38.2 | 53.2 | 53.2 | -154.7% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 550.2080. - EXS Excavate Structure | 401.91 | 60 | -341.91 | 669.9% | 80 | 80 | 100% | 60 | -341.91 | 401.91 | 410.04 | -483.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1700. - FS Project Manager | 1191.73 | 2251 | 1059.27 | 52.94% | 0 | 2251 | 0% | 2251 | 1059.27 | 2251 | 1430.98 | 136.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 260.2210. - RCP Reinforced Concrete Pipe | 57.34 | 0 | -57.34 |  | 0 | 0 | 0% | 0 | -57.34 | 57.34 | 0 | 0% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 503.54 | 501 | -2.54 | 100.5% | 250 | 501 | 50% | 250.5 | -253.04 | 1007.08 | 571.35 | 85.96% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 300.6500. - P Painting | 2.5 | 0 | -2.5 |  | 0 | 0 | 0% | 0 | -2.5 | 2.5 | 2.5 | 0% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 150.2750. - Unknown Phase | 587.69 | 592.98 | 5.29 | 99.11% | 174.35 | 348.7 | 50% | 296.49 | -291.2 | 1175.38 | 588.95 | 100.7% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1703. - FS Job Site Superintendent | 1690.85 | 3001 | 1310.15 | 56.34% | 1500 | 3001 | 50% | 1500.5 | -190.35 | 3381.7 | 3000 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.3000. - CNC Concrete Work | 449.34 | 130 | -319.34 | 345.6% | 140 | 140 | 100% | 130 | -319.34 | 449.34 | 449.34 | -145.6% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.3000. - CNC Concrete Work | 624.51 | 179.06 | -445.45 | 348.8% | 641.546 | 754.76 | 85% | 152.201 | -472.309 | 734.7176 | 559.45 | -112.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 150.1230. - T Transporting | 355.34 | 170 | -185.34 | 209% | 75 | 170 | 50% | 85 | -270.34 | 710.68 | 397.19 | -33.64% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2150. - PSR Pipe w/ Slide Rail | 213.21 | 272.5 | 59.29 | 78.24% | 280 | 280 | 100% | 272.5 | 59.29 | 213.21 | 237.34 | 112.9% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.6300. - DAW Doors & Windows | 27.66 | 20 | -7.66 | 138.3% | 57 | 60 | 95% | 19 | -8.66 | 29.1158 | 41.66 | -8.3% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 200.2065. - SFC SWPPP | 265.87 | 50 | -215.87 | 531.7% | 25.5 | 51 | 50% | 25 | -240.87 | 531.74 | 307.75 | -415.5% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.7900. - ELC Electrical | 53.17 | 0 | -53.17 |  | 0 | 0 | 0% | 0 | -53.17 | 53.17 | 53.17 | 0% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.7600. - MEQ Mechanical Equipment | 0 | 20 | 20 | 0% | 20 | 20 | 100% | 20 | 20 | 0 | 0 | 200% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.2085. - BFST Backfill Structure | 1513.51 | 750 | -763.51 | 201.8% | 593.75 | 625 | 95% | 712.5 | -801.01 | 1593.1684 | 1587.99 | -11.73% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.5000. - MET Metals | 15.32 | 130 | 114.68 | 11.78% | 72.75 | 291 | 25% | 32.5 | 17.18 | 61.28 | 130 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.2130. - PVC Pipe | 438.92 | 787.86 | 348.94 | 55.71% | 137.424 | 458.08 | 30% | 236.358 | -202.562 | 1463.0667 | 787.86 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 150.2760. - Unknown Phase | 127.03 | 578.5 | 451.47 | 21.96% | 113.1 | 565.5 | 20% | 115.7 | -11.33 | 635.15 | 487.03 | 115.8% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2210. - RCP Reinforced Concrete Pipe | 1015 | 629.6 | -385.4 | 161.2% | 334.36 | 417.95 | 80% | 503.68 | -511.32 | 1268.75 | 942.25 | 50.34% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.2085. - BFST Backfill Structure | 445.15 | 150 | -295.15 | 296.8% | 100 | 100 | 100% | 150 | -295.15 | 445.15 | 439.84 | -93.23% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2130. - PVC Pipe | 219.03 | 256.5 | 37.47 | 85.39% | 145.775 | 171.5 | 85% | 218.025 | -1.005 | 257.6824 | 256.5 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.6100. - F Framing | 19.56 | 2.56 | -17 | 764.1% | 5.12 | 5.12 | 100% | 2.56 | -17 | 19.56 | 19.56 | -564.1% |  | 2026-08-31
2508. - Turner Dam & Joint Diversion Rehab | 500.3000. - CNC Concrete Work | 741.55 | 40 | -701.55 | 1854% | 51 | 60 | 85% | 34 | -707.55 | 872.4118 | 690.3 | -1526%
2508. - Turner Dam & Joint Diversion Rehab | 500.2030. - D Demolition | 0 | 104 | 104 | 0% | 73.6 | 92 | 80% | 83.2 | 83.2 | 0 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 250.7600. - MEQ Mechanical Equipment | 611.95 | 542.5 | -69.45 | 112.8% | 645 | 1290 | 50% | 271.25 | -340.7 | 1223.9 | 1077.85 | 1.318%
2508. - Turner Dam & Joint Diversion Rehab | 600.2070. - RGC Rough Grade Cut | 5.5 | 209 | 203.5 | 2.632% | 27.5 | 110 | 0% | 209 | 203.5 | 209 | 5.5 | 197.4%
2508. - Turner Dam & Joint Diversion Rehab | 400.2600. - DW Dewatering | 3.77 | 35 | 31.23 | 10.77% | 90 | 90 | 100% | 35 | 31.23 | 3.77 | 19.35 | 144.7%
2508. - Turner Dam & Joint Diversion Rehab | 600.2075. - FG Finish Grade | 1429.97 | 40.26 | -1389.71 | 3552% | 0 | 51.56 | 0% | 40.26 | -1389.71 | 1429.97 | 1147.78 | -2651%
2508. - Turner Dam & Joint Diversion Rehab | 600.1940. - PL Punch List Work | 28.05 | 60 | 31.95 | 46.75% | 0 | 80 | 0% | 60 | 31.95 | 60 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 260.2080. - EXS Excavate Structure | 621.43 | 150 | -471.43 | 414.3% | 0 | 90 | 0% | 150 | -471.43 | 621.43 | 621.43 | -214.3%
2508. - Turner Dam & Joint Diversion Rehab | 300.2030. - D Demolition | 0 | 80 | 80 | 0% | 60 | 60 | 100% | 80 | 80 | 0 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 600.5000. - MET Metals | 10.28 | 5 | -5.28 | 205.6% | 0 | 15 | 0% | 5 | -5.28 | 10.28 | 200 | -3800%
2508. - Turner Dam & Joint Diversion Rehab | 150.2760. - Unknown Phase | 205.15 | 206.94 | 1.79 | 99.14% | 104.234 | 109.72 | 95% | 196.593 | -8.557 | 215.9474 | 205.3 | 100.8%
2508. - Turner Dam & Joint Diversion Rehab | 350.2075. - FG Finish Grade | 503.83 | 312.01 | -191.82 | 161.5% | 315.56 | 315.56 | 100% | 312.01 | -191.82 | 503.83 | 483.01 | 45.19%
2508. - Turner Dam & Joint Diversion Rehab | 900.9100. - Job Related Equipment Repairs | 5.57 | 1 | -4.57 | 557% | 0.4 | 1 | 40% | 0.4 | -5.17 | 13.925 | 5.57 | -357%
2508. - Turner Dam & Joint Diversion Rehab | 100.1706. - FS Executive | 3.5 | 1 | -2.5 | 350% | 0.35 | 1 | 35% | 0.35 | -3.15 | 10 | 3.5 | -150%
2508. - Turner Dam & Joint Diversion Rehab | 300.7600. - MEQ Mechanical Equipment | 0 | 45 | 45 | 0% | 67.5 | 90 | 75% | 33.75 | 33.75 | 0 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 600.2600. - DW Dewatering | 16.26 | 108.9 | 92.64 | 14.93% | 0 | 58 | 0% | 108.9 | 92.64 | 108.9 | 8.48 | 192.2%
2508. - Turner Dam & Joint Diversion Rehab | 350.2240. - PCS Precast Structures | 212.37 | 175 | -37.37 | 121.4% | 110 | 110 | 100% | 175 | -37.37 | 212.37 | 212.37 | 78.65%
2508. - Turner Dam & Joint Diversion Rehab | 100.1200. - HOOK Hook Truck Dumpster Transporting | 2.15 | 15 | 12.85 | 14.33% | 7.5 | 15 | 75% | 11.25 | 9.1 | 2.8667 | 11.72 | 121.9%
2508. - Turner Dam & Joint Diversion Rehab | 500.3010. - WP Winter Protection | 1.58 | 403 | 401.42 | 0.3921% | 9 | 18 | 50% | 201.5 | 199.92 | 3.16 | 1.58 | 199.6%
2508. - Turner Dam & Joint Diversion Rehab | 350.2050. - RW Retaining Walls | 48.43 | 23.36 | -25.07 | 207.3% | 23.36 | 23.36 | 100% | 23.36 | -25.07 | 48.43 | 48.43 | -7.32%
2508. - Turner Dam & Joint Diversion Rehab | 600.2140. - SVR Services | 0 | 91 | 91 | 0% | 0 | 46 | 0% | 91 | 91 | 91 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 350.3000. - CNC Concrete Work | 403.7 | 34.13 | -369.57 | 1183% | 189.8 | 189.8 | 100% | 34.13 | -369.57 | 403.7 | 403.7 | -982.8%
2508. - Turner Dam & Joint Diversion Rehab | 300.5000. - MET Metals | 105.37 | 21 | -84.37 | 501.8% | 1.008 | 50.4 | 23.47% | 4.9288 | -100.4412 | 448.9449 | 77.9 | -171%
2508. - Turner Dam & Joint Diversion Rehab | 100.1702. - FS People Superintendent | 425.17 | 160.77 | -264.4 | 264.5% | 112.539 | 160.77 | 70% | 112.539 | -312.631 | 607.3857 | 457.67 | -84.67%
2508. - Turner Dam & Joint Diversion Rehab | 100.1510. - S Surveying | 102.22 | 60 | -42.22 | 170.4% | 19 | 20 | 95% | 57 | -45.22 | 107.6 | 90.92 | 48.47%
2508. - Turner Dam & Joint Diversion Rehab | 400.7600. - MEQ Mechanical Equipment | 47.7 | 100 | 52.3 | 47.7% | 204 | 240 | 85% | 85 | 37.3 | 56.1176 | 100.7 | 99.3%
2508. - Turner Dam & Joint Diversion Rehab | 300.3000. - CNC Concrete Work | 30.71 | 50.66 | 19.95 | 60.62% | 223.04 | 223.04 | 100% | 50.66 | 19.95 | 30.71 | 30.71 | 139.4%
2508. - Turner Dam & Joint Diversion Rehab | 400.5000. - MET Metals | 41.96 | 7.5 | -34.46 | 559.5% | 22.5 | 22.5 | 100% | 7.5 | -34.46 | 41.96 | 44.96 | -399.5%
2508. - Turner Dam & Joint Diversion Rehab | 665.5000. - MET Metals | 3.25 | 2 | -1.25 | 162.5% | 0 | 4 | 0% | 2 | -1.25 | 3.25 | 4 | 0%
2508. - Turner Dam & Joint Diversion Rehab | 420.7600. - MEQ Mechanical Equipment | 338.71 | 60 | -278.71 | 564.5% | 0 | 116 | 0% | 60 | -278.71 | 338.71 | 346.71 | -377.9%
2508. - Turner Dam & Joint Diversion Rehab | 100.1704. - FS Quality Control/Assurance | 7 | 60.68 | 53.68 | 11.54% | 21.238 | 60.68 | 35% | 21.238 | 14.238 | 20 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 250.2030. - D Demolition | 0 | 28 | 28 | 0% | 18.9 | 21 | 90% | 25.2 | 25.2 | 0 | 1.24 | 195.6%
2508. - Turner Dam & Joint Diversion Rehab | 350.2020. - CG Clearing/Grubbing | 28.73 | 10 | -18.73 | 287.3% | 10 | 10 | 100% | 10 | -18.73 | 28.73 | 28.73 | -87.3%
2508. - Turner Dam & Joint Diversion Rehab | 600.1930. - MC Misc Cleanup | 13.93 | 20 | 6.07 | 69.65% | 32 | 80 | 0% | 20 | 6.07 | 20 | 14.48 | 127.6%
2508. - Turner Dam & Joint Diversion Rehab | 600.2595. - CD Coffer Dams | 3 | 118 | 115 | 2.542% | 0 | 60 | 0% | 118 | 115 | 118 | 3 | 197.5%
2508. - Turner Dam & Joint Diversion Rehab | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 452.99 | 196.29 | -256.7 | 230.8% | 137.403 | 196.29 | 70% | 137.403 | -315.587 | 647.1286 | 446.66 | -27.55%
2508. - Turner Dam & Joint Diversion Rehab | 100.1700. - FS Project Manager | 416 | 191.9 | -224.1 | 216.8% | 134.33 | 191.9 | 70% | 134.33 | -281.67 | 594.2857 | 431.5 | -24.86%
2508. - Turner Dam & Joint Diversion Rehab | 100.1703. - FS Job Site Superintendent | 935.49 | 238.89 | -696.6 | 391.6% | 164.395 | 236.85 | 70% | 167.223 | -768.267 | 1336.4143 | 877.33 | -167.3%
2508. - Turner Dam & Joint Diversion Rehab | 420.5000. - MET Metals | 459.96 | 0 | -459.96 |  | 0 | 0 | 0% | 0 | -459.96 | 459.96 | 488.81 | 0%
2508. - Turner Dam & Joint Diversion Rehab | 350.2210. - RCP Reinforced Concrete Pipe | 0 | 20 | 20 | 0% | 12.5 | 12.5 | 100% | 20 | 20 | 0 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 450.5000. - MET Metals | 35.55 | 54 | 18.45 | 65.83% | 64 | 64 | 0% | 54 | 18.45 | 54 | 35.55 | 134.2%
2508. - Turner Dam & Joint Diversion Rehab | 350.2085. - BFST Backfill Structure | 266.75 | 87 | -179.75 | 306.6% | 81 | 81 | 100% | 87 | -179.75 | 266.75 | 268.75 | -108.9%
2508. - Turner Dam & Joint Diversion Rehab | 250.3000. - CNC Concrete Work | 203.16 | 10 | -193.16 | 2032% | 40.5 | 45 | 90% | 9 | -194.16 | 225.7333 | 268.16 | -2482%
2508. - Turner Dam & Joint Diversion Rehab | 350.7600. - MEQ Mechanical Equipment | 0 | 35 | 35 | 0% | 0.5 | 50 | 1% | 0.35 | 0.35 | 0 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 150.2750. - Unknown Phase | 455.31 | 298.38 | -156.93 | 152.6% | 142.367 | 149.86 | 95% | 283.461 | -171.849 | 479.2737 | 469.26 | 42.73%
2508. - Turner Dam & Joint Diversion Rehab | 350.2070. - RGC Rough Grade Cut | 39.49 | 113.6 | 74.11 | 34.76% | 64.8 | 64.8 | 100% | 113.6 | 74.11 | 39.49 | 29.49 | 174%
2508. - Turner Dam & Joint Diversion Rehab | 620.2075. - FG Finish Grade | 0 | 322.1 | 322.1 | 0% | 0 | 268.41 | 0% | 322.1 | 322.1 | 322.1 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 300.2085. - BFST Backfill Structure | 36.58 | 4.5 | -32.08 | 812.9% | 9 | 9 | 100% | 4.5 | -32.08 | 36.58 | 36.58 | -612.9%
2508. - Turner Dam & Joint Diversion Rehab | 600.2750. - H Hauling | 206.97 | 191.8 | -15.17 | 107.9% | 0 | 119.86 | 0% | 191.8 | -15.17 | 206.97 | 189.12 | 101.4%
2508. - Turner Dam & Joint Diversion Rehab | 250.2595. - CD Coffer Dams | 2077 | 197 | -1880 | 1054% | 60 | 100 | 60% | 118.2 | -1958.8 | 3461.6667 | 2077 | -854.3%
2508. - Turner Dam & Joint Diversion Rehab | 150.1230. - T Transporting | 488.07 | 175 | -313.07 | 278.9% | 60 | 175 | 80% | 140 | -348.07 | 610.0875 | 492.66 | -81.52%
2508. - Turner Dam & Joint Diversion Rehab | 600.3000. - CNC Concrete Work | 424.14 | 213.03 | -211.11 | 199.1% | 0 | 639.09 | 0% | 213.03 | -211.11 | 424.14 | 50 | 176.5%
2508. - Turner Dam & Joint Diversion Rehab | 250.5000. - MET Metals | 2 | 49 | 47 | 4.082% | 0.88 | 88 | 1% | 0.49 | -1.51 | 200 | 49 | 100%
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1704. - FS Quality Control/Assurance | 116.5 | 147.24 | 30.74 | 79.12% | 87.744 | 146.24 | 57.5% | 84.663 | -31.837 | 202.6087 | 170.5 | 84.2% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 205.2170. - HDPE Fusion Pipe <15' Depth | 3363.33 | 3818.07 | 454.74 | 88.09% | 402.6 | 746 | 55% | 2099.9385 | -1263.3915 | 6115.1455 | 4085.95 | 92.98% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 130.99 | 454.26 | 323.27 | 28.84% | 271.956 | 453.26 | 60% | 272.556 | 141.566 | 218.3167 | 447.99 | 101.4% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1700. - FS Project Manager | 238.5 | 484.4 | 245.9 | 49.24% | 290.04 | 483.4 | 60% | 290.64 | 52.14 | 397.5 | 441 | 109% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 300.5100. - W Welding | 288.27 | 0 | -288.27 |  | 0 | 0 | 0% | 0 | -288.27 | 288.27 | 288.27 | 0% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 150.2750. - Unknown Phase | 881.86 | 2207.08 | 1325.22 | 39.96% | 605 | 15250 | 55% | 1213.894 | 332.034 | 1603.3818 | 1985.4 | 110% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1703. - FS Job Site Superintendent | 510.48 | 571.11 | 60.63 | 89.38% | 342.066 | 570.11 | 60% | 342.666 | -167.814 | 850.8 | 670.7 | 82.56% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2170. - HDPE Fusion Pipe <15' Depth | 8943.76 | 7302.58 | -1641.18 | 122.5% | 4009.5 | 7290 | 55% | 4016.419 | -4927.341 | 16261.3818 | 11028.27 | 48.98% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1510. - S Surveying | 387.81 | 313 | -74.81 | 123.9% | 55 | 100 | 55% | 172.15 | -215.66 | 705.1091 | 491.29 | 43.04% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 150.1230. - T Transporting | 137.52 | 152 | 14.48 | 90.47% | 82.5 | 150 | 55% | 83.6 | -53.92 | 250.0364 | 207.54 | 63.46% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2075. - FG Finish Grade | 0 | 48 | 48 | 0% | 0 | 7200 | 0% | 48 | 48 | 48 | 50 | 95.83% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1201. - HOOK Hook Truck Conex, Skid Transporting | 1.25 | 10 | 8.75 | 12.5% | 4 | 10 | 40% | 4 | 2.75 | 3.125 | 11.25 | 87.5% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1600. - TC Traffic Control | 35 | 220 | 185 | 15.91% | 84 | 140 | 60% | 132 | 97 | 58.3333 | 85 | 161.4% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 350.2170. - HDPE Fusion Pipe <15' Depth | 1537.83 | 0 | -1537.83 |  | 0 | 0 | 0% | 0 | -1537.83 | 1537.83 | 1593.09 | 0% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1200. - HOOK Hook Truck Dumpster Transporting | 9.98 | 20 | 10.02 | 49.9% | 10 | 20 | 50% | 10 | 0.02 | 19.96 | 59.5 | -97.5% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 160.5000. - Unknown Phase | 27.13 | 0 | -27.13 |  | -21.1 | 0 | 0% | 0 | -27.13 | 27.13 | 27.13 | 0% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 215.2170. - HDPE Fusion Pipe <15' Depth | 60.3 | 1144 | 1083.7 | 5.271% | 6.6 | 22 | 30% | 343.2 | 282.9 | 201 | 660.3 | 142.3% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 210.2170. - HDPE Fusion Pipe <15' Depth | 212.72 | 481.35 | 268.63 | 44.19% | 5.4 | 18 | 45% | 216.6075 | 3.8875 | 472.7111 | 380.45 | 121% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1702. - FS People Superintendent | 336.87 | 378.66 | 41.79 | 88.96% | 226.596 | 377.66 | 60% | 227.196 | -109.674 | 561.45 | 399.95 | 94.38% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2080. - EXS Excavate Structure | 359.55 | 295.04 | -64.51 | 121.9% | 150 | 297 | 100% | 295.04 | -64.51 | 359.55 | 359.55 | 78.14% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.3000. - Unknown Phase | 655.69 | 233 | -422.69 | 281.4% | 432.8 | 573 | 100% | 233 | -422.69 | 655.69 | 655.69 | -81.41% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.2010. - RG Grading (DO NOT USE) | 46.27 | 110 | 63.73 | 42.06% | 160 | 160 | 100% | 110 | 63.73 | 46.27 | 46.27 | 157.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 510.2040. - LR Landscaping/Restoration | 345.74 | 290 | -55.74 | 119.2% | 230 | 230 | 100% | 290 | -55.74 | 345.74 | 345.74 | 80.78% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 150.2750. - Unknown Phase | 1915.69 | 944.06 | -971.63 | 202.9% | 916.24 | 940.66 | 100% | 944.06 | -971.63 | 1915.69 | 1918.19 | -3.185% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 400.2010. - RG Grading (DO NOT USE) | 151.26 | 257.89 | 106.63 | 58.65% | 277.623 | 308.47 | 100% | 257.8928 | 106.6328 | 151.2584 | 151.26 | 141.3% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2610. - PT Pressure Test/Chlorinating | 102.61 | 140 | 37.39 | 73.29% | 160 | 160 | 100% | 140 | 37.39 | 102.61 | 102.61 | 126.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7300. - PLUM Plumbing | 484.83 | 125 | -359.83 | 387.9% | 90 | 150 | 100% | 125 | -359.83 | 484.83 | 484.83 | -187.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9010. - Re-Work Pipe | 8 | 0.2 | -7.8 | 4000% | 0.4 | 0.4 | 100% | 0.2 | -7.8 | 8 | 8 | -3800% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1703. - FS Job Site Superintendent | 2146 | 1049.46 | -1096.54 | 204.5% | 1048.071 | 1049.464 | 98% | 1028.471 | -1117.529 | 2189.7955 | 2159.5 | -5.772% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5120. - Fab Shop Pipe Linings & Coatings | 10746.41 | 220 | -10526.41 | 4885% | 0 | 440 | 0% | 220 | -10526.41 | 10746.41 | 10746.41 | -4685% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9005. - Re-Work Surveying | 20.9 | 2 | -18.9 | 1045% | 1 | 1 | 100% | 2 | -18.9 | 20.9 | 20.9 | -845% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9011. - Unknown Phase | 24.57 | 0 | -24.57 |  | 0 | 0 | 0% | 0 | -24.57 | 24.57 | 24.57 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 150.1230. - T Transporting | 520.91 | 261.5 | -259.41 | 199.2% | 247 | 261.5 | 95% | 248.425 | -272.485 | 548.3263 | 520.91 | 0.7992% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 9738.55 | 1340.9 | -8397.65 | 726.3% | 930.2 | 930.2 | 100% | 1340.9 | -8397.65 | 9738.55 | 9609.41 | -516.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.6200. - IN Insulation | 101.08 | 18.76 | -82.32 | 538.8% | 16 | 48 | 100% | 18.76 | -82.32 | 101.08 | 101.08 | -338.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 310.7900. - ELC Electrical | 15.75 | 0 | -15.75 |  | 0 | 0 | 0% | 0 | -15.75 | 15.75 | 15.75 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.5100. - W Welding | 6425.86 | 790 | -5635.86 | 813.4% | 121.5 | 395 | 100% | 790 | -5635.86 | 6425.86 | 6425.86 | -613.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 510.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 543.9 | 225 | -318.9 | 241.7% | 225 | 225 | 100% | 225 | -318.9 | 543.9 | 586.29 | -60.57% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 310.3000. - CNC Concrete Work | 208.59 | 0 | -208.59 |  | 0 | 0 | 0% | 0 | -208.59 | 208.59 | 208.59 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2040. - LR Landscaping/Restoration | 169.14 | 80.8 | -88.34 | 209.3% | 1 | 80.8 | 100% | 80.8 | -88.34 | 169.14 | 170.14 | -10.57% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9012. - Re-Work Mechanical | 25.95 | 0.2 | -25.75 | 12975% | 0.4 | 0.4 | 100% | 0.2 | -25.75 | 25.95 | 25.95 | -12775% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1500. - VIS Meetings (Vision, Safety, Training) | 40.9 | 0 | -40.9 |  | 0 | 0 | 0% | 0 | -40.9 | 40.9 | 40.9 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7900. - ELC Electrical | 225.87 | 97.5 | -128.37 | 231.7% | 75 | 90 | 100% | 97.5 | -128.37 | 225.87 | 225.87 | -31.66% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5110. - Fab Shop Pipe Fabrication | 5618.23 | 616 | -5002.23 | 912.1% | 0 | 308 | 0% | 616 | -5002.23 | 5618.23 | 5618.23 | -712.1% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.3000. - CNC Concrete Work | 620.94 | 639.81 | 18.87 | 97.05% | 1255.696 | 1569.62 | 100% | 639.808 | 18.868 | 620.942 | 620.94 | 102.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7100. - IMP Interior Mech/Piping | 834.4 | 232 | -602.4 | 359.7% | 570 | 576 | 100% | 232 | -602.4 | 834.4 | 834.4 | -159.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 150.2760. - Unknown Phase | 115.78 | 862.64 | 746.86 | 13.42% | 843.14 | 838.14 | 100% | 862.64 | 746.86 | 115.78 | 109.78 | 187.3% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.6400. - DRY Drywall & Metal Studs | 261.39 | 34 | -227.39 | 768.8% | 64.6 | 68 | 100% | 34 | -227.39 | 261.39 | 261.39 | -568.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 400.2000. - SWC Site Work Complete (DO NOT USE) | 908.33 | 209.91 | -698.42 | 432.7% | 176.928 | 221.16 | 100% | 209.9076 | -698.4224 | 908.3403 | 907.33 | -232.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7600. - MEQ Mechanical Equipment | 69.88 | 105 | 35.12 | 66.55% | 99 | 350 | 100% | 105 | 35.12 | 69.88 | 69.88 | 133.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2300. - Unknown Phase | 1356.6 | 689.72 | -666.88 | 196.7% | 614.9 | 783.04 | 100% | 689.72 | -666.88 | 1356.6 | 1356.6 | 3.311% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.7100. - IMP Interior Mech/Piping | 227.38 | 88 | -139.38 | 258.4% | 70 | 109 | 100% | 88 | -139.38 | 227.38 | 227.38 | -58.39% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.1650. - SB Signage | 49.02 | 10 | -39.02 | 490.2% | 15 | 15 | 100% | 10 | -39.02 | 49.02 | 49.02 | -290.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 600.2030. - D Demolition | 303.44 | 292 | -11.44 | 103.9% | 0 | 219 | 0% | 292 | -11.44 | 303.44 | 303.44 | 96.08% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9055. - Re-Work Finishes | 138.32 | 0.1 | -138.22 | 138320% | 0.2 | 0.2 | 100% | 0.1 | -138.22 | 138.32 | 138.32 | -138120% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.7100. - IMP Interior Mech/Piping | 48.97 | 134.13 | 85.16 | 36.51% | 168.142 | 258.63 | 65% | 87.1845 | 38.2145 | 75.3385 | 228.97 | 29.29% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9020. - Re-Work Fab | 24.05 | 0.4 | -23.65 | 6012% | 0.2 | 0.2 | 100% | 0.4 | -23.65 | 24.05 | 24.05 | -5812% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.5000. - MET Metals | 84.25 | 29 | -55.25 | 290.5% | 8 | 52 | 100% | 29 | -55.25 | 84.25 | 84.25 | -90.52% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.6100. - F Framing | 11.85 | 15 | 3.15 | 79% | 30 | 30 | 100% | 15 | 3.15 | 11.85 | 11.85 | 121% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 1048.43 | 312.26 | -736.17 | 335.8% | 237.951 | 264.39 | 100% | 312.2613 | -736.1687 | 1048.4256 | 1048.43 | -135.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2800. - Unknown Phase | 813.62 | 195 | -618.62 | 417.2% | 165 | 165 | 100% | 195 | -618.62 | 813.62 | 826.12 | -223.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.2800. - BFST Backfill (DO NOT USE) | 1175.42 | 175 | -1000.42 | 671.7% | 0 | 150 | 0% | 175 | -1000.42 | 1175.42 | 1159.42 | -462.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1702. - FS People Superintendent | 2485.35 | 512.76 | -1972.59 | 484.7% | 522.105 | 512.755 | 98% | 502.505 | -1982.845 | 2536.0705 | 2495.35 | -286.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5310. - Fab Shop Misc Metals Fabrication | 1216.38 | 601 | -615.38 | 202.4% | 0 | 300.5 | 0% | 601 | -615.38 | 1216.38 | 1216.38 | -2.393% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2710. - FWF Flowable Fill | 275.5 | 4.04 | -271.46 | 6819% | 3.56 | 7.68 | 100% | 4.04 | -271.46 | 275.5 | 279 | -6706% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1510. - S Surveying | 3313.34 | 355 | -2958.34 | 933.3% | 150 | 175 | 100% | 355 | -2958.34 | 3313.34 | 3313.34 | -733.3% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5320. - Fab Shop Misc Metals Coatings | 0 | 245.5 | 245.5 | 0% | 0 | 491 | 0% | 245.5 | 245.5 | 245.5 | 0 | 200% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.5000. - MET Metals | 110.36 | 26.28 | -84.08 | 419.9% | 75 | 76.92 | 100% | 26.28 | -84.08 | 110.36 | 110.36 | -219.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 550.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 511.03 | 0 | -511.03 |  | 0 | 0 | 0% | 0 | -511.03 | 511.03 | 518.93 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 400.3000. - CNC Concrete Work | 537.43 | 288.35 | -249.08 | 186.4% | 778.6 | 869.56 | 100% | 288.35 | -249.08 | 537.43 | 537.43 | 13.62% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 210.2300. - WPL Water Pipe Laying (DO NOT USE) | 74.45 | 143 | 68.55 | 52.06% | 100 | 100 | 100% | 143 | 68.55 | 74.45 | 74.45 | 147.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1704. - FS Quality Control/Assurance | 1955.48 | 104.63 | -1850.85 | 1869% | 104.633 | 104.633 | 100% | 104.63 | -1850.85 | 1955.48 | 1965.48 | -1679% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.3000. - CNC Concrete Work | 761.15 | 66.33 | -694.82 | 1148% | 1 | 287 | 100% | 66.33 | -694.82 | 761.15 | 761.15 | -947.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.6300. - DAW Doors & Windows | 188.34 | 45 | -143.34 | 418.5% | 85.5 | 90 | 100% | 45 | -143.34 | 188.34 | 188.34 | -218.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9100. - Job Related Equipment Repairs | 54.06 | 1 | -53.06 | 5406% | 0 | 1 | 0% | 1 | -53.06 | 54.06 | 54.06 | -5206% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.1650. - SB Signage | 6.15 | 5 | -1.15 | 123% | 8 | 10 | 100% | 5 | -1.15 | 6.15 | 6.15 | 77% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2500. - MH Manholes (DO NOT USE) | 0 | 42 | 42 | 0% | 1 | 96 | 100% | 42 | 42 | 0 | 0 | 200% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 800.1940. - PL Punch List Work | 647.91 | 265 | -382.91 | 244.5% | 198 | 222 | 99% | 262.35 | -385.56 | 654.4545 | 690.16 | -60.44% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1101. - TF Temporary Office Trailer VanCon | 2 | 0 | -2 |  | 0 | 0 | 0% | 0 | -2 | 2 | 2 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 123.22 | 200 | 76.78 | 61.61% | 165 | 165 | 100% | 200 | 76.78 | 123.22 | 123.22 | 138.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 600.6000. - IF Interior Finishes | 67.41 | 30 | -37.41 | 224.7% | 31 | 90 | 100% | 30 | -37.41 | 67.41 | 67.41 | -24.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 510.2300. - WPL Water Pipe Laying (DO NOT USE) | 73.4 | 0 | -73.4 |  | 0 | 0 | 0% | 0 | -73.4 | 73.4 | 73.4 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.7900. - ELC Electrical | 405.22 | 1090.77 | 685.55 | 37.15% | 661.25 | 661.25 | 100% | 1090.77 | 685.55 | 405.22 | 469.57 | 157% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2600. - DW Dewatering | 1014.35 | 30 | -984.35 | 3381% | 1 | 32 | 66.67% | 20 | -994.35 | 1521.525 | 1014.35 | -3181% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 800.1700. - FS Project Manager | 103.37 | 400 | 296.63 | 25.84% | 380 | 400 | 100% | 400 | 296.63 | 103.37 | 103.37 | 174.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.2000. - SWC Site Work Complete (DO NOT USE) | 197.27 | 0 | -197.27 |  | 0 | 0 | 0% | 0 | -197.27 | 197.27 | 197.27 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1700. - FS Project Manager | 1953.79 | 704.98 | -1248.81 | 277.1% | 710.48 | 704.98 | 98% | 690.88 | -1262.91 | 1993.6644 | 1967.79 | -79.13% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.2080. - EXS Excavate Structure | 35.19 | 237.5 | 202.31 | 14.82% | 0 | 250 | 0% | 237.5 | 202.31 | 237.5 | 53.19 | 177.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 800.1930. - MC Misc Cleanup | 408.7 | 270 | -138.7 | 151.4% | 198 | 230 | 99% | 267.3 | -141.4 | 412.8283 | 380.93 | 58.91% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 2079.97 | 654.65 | -1425.32 | 317.7% | 651.357 | 654.654 | 98% | 641.557 | -1438.413 | 2122.4184 | 2093.47 | -119.8% |  | 2025-12-31
2402. - SLC Little Dell Dam Outlet Works | 100.1703. - FS Job Site Superintendent | 75.26 | 50 | -25.26 | 150.5% | 50 | 50 | 100% | 50 | -25.26 | 75.26 | 75.26 | 49.48% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 100.1700. - FS Project Manager | 172.5 | 25 | -147.5 | 690% | 25 | 25 | 100% | 25 | -147.5 | 172.5 | 172.5 | -490% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 32 | 25 | -7 | 128% | 25 | 25 | 100% | 25 | -7 | 32 | 32 | 72% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 900.9100. - Job Related Equipment Repairs | 10 | 1 | -9 | 1000% | 1 | 1 | 100% | 1 | -9 | 10 | 10 | -800% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 100.1702. - FS People Superintendent | 6.5 | 20 | 13.5 | 32.5% | 20 | 20 | 100% | 20 | 13.5 | 6.5 | 6.5 | 167.5% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 200.7600. - MEQ Mechanical Equipment | 138.27 | 30 | -108.27 | 460.9% | 90 | 90 | 100% | 30 | -108.27 | 138.27 | 138.27 | -260.9% |  | 2024-10-31
2231. - UDOT Bangerter Hwy Aqueduct Protection | 110.1600. - TC Traffic Control | 0 | 1725 | 1725 | 0% | 0 | 225 | 0% | 1725 | 1725 | 1725 | 1725 | 100% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 100.1700. - FS Project Manager | 10 | 20 | 10 | 50% | 0 | 20 | 0% | 20 | 10 | 20 | 10 | 150% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 150.2750. - Unknown Phase | 67.5 | 10 | -57.5 | 675% | 0 | 10 | 0% | 10 | -57.5 | 67.5 | 77.5 | -575% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 200.2000. - Unknown Phase | 81.9 | 30 | -51.9 | 273% | 0 | 30 | 0% | 30 | -51.9 | 81.9 | 81.9 | -73% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 300.3000. - CNC Concrete Work | 0 | 437.5 | 437.5 | 0% | 0 | 875 | 0% | 437.5 | 437.5 | 437.5 | 437.5 | 100% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 150.1230. - T Transporting | 180.73 | 100 | -80.73 | 180.7% | 0 | 100 | 0% | 100 | -80.73 | 180.73 | 230.73 | -30.73% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 900.9600. - Reallocate EQ/FOO costs to actual | 2.5 | 0 | -2.5 |  | 0 | 0 | 0% | 0 | -2.5 | 2.5 | 2.5 | 0% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 100.1600. - TC Traffic Control | 48.5 | 1650 | 1601.5 | 2.939% | 0 | 150 | 0% | 1650 | 1601.5 | 1650 | 48.5 | 197.1% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 200.2030. - Unknown Phase | 0 | 25 | 25 | 0% | 0 | 30 | 0% | 25 | 25 | 25 | 0 | 200% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 300.7100. - IMP Interior Mech/Piping | 17.25 | 1662.51 | 1645.26 | 1.038% | 0 | 2482.51 | 0% | 1662.51 | 1645.26 | 1662.51 | 1667.25 | 99.71% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 200.7100. - IMP Interior Mech/Piping | 301.79 | 110 | -191.79 | 274.4% | 0 | 210 | 0% | 110 | -191.79 | 301.79 | 301.79 | -74.35% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 900.9100. - Job Related Equipment Repairs | 0 | 1 | 1 | 0% | 0 | 1 | 0% | 1 | 1 | 1 | 0 | 200% |  | 2026-04-30
2515. - UWCD Steinaker Service Canal Gate Rahab | 150.1230. - T Transporting | 57.23 | 40 | -17.23 | 143.1% | 20 | 40 | 50% | 20 | -37.23 | 114.46 | 57.23 | 56.93% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1700. - FS Project Manager | 42 | 12.83 | -29.17 | 327.4% | 6.415 | 12.83 | 50% | 6.415 | -35.585 | 84 | 42 | -127.4% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 0 | 11.77 | 11.77 | 0% | 0 | 11.77 | 0% | 11.77 | 11.77 | 11.77 | 0 | 200% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1703. - FS Job Site Superintendent | 235.61 | 15.92 | -219.69 | 1480% | 7.96 | 15.92 | 50% | 7.96 | -227.65 | 471.22 | 235.61 | -1280% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 300.7600. - MEQ Mechanical Equipment | 186.21 | 40 | -146.21 | 465.5% | 0 | 60 | 0% | 40 | -146.21 | 186.21 | 186.21 | -265.5% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 200.7600. - MEQ Mechanical Equipment | 0 | 30 | 30 | 0% | 30 | 30 | 100% | 30 | 30 | 0 | 0 | 200% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1702. - FS People Superintendent | 15 | 10.92 | -4.08 | 137.4% | 0 | 10.92 | 0% | 10.92 | -4.08 | 15 | 15 | 62.64% |  | 2026-04-15
2318. - CUWCD CWP Wellhouse 7 | 200.2080. - EXS Excavate Structure | 200.19 | 171.25 | -28.94 | 116.9% | 0 | 150 | 0% | 171.25 | -28.94 | 200.19 | 200.19 | 83.1% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 150.2750. - Unknown Phase | 695.8 | 500.21 | -195.59 | 139.1% | 489.54 | 500.21 | 99.9% | 499.6996 | -196.1004 | 696.5107 | 685.55 | 62.95% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 400.2010. - RG Grading (DO NOT USE) | 752.75 | 220.25 | -532.5 | 341.8% | 263.5 | 263.5 | 100% | 220.25 | -532.5 | 752.75 | 752.75 | -141.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2300. - Unknown Phase | 309.07 | 402.86 | 93.79 | 76.72% | 302.44 | 302.44 | 100% | 402.86 | 93.79 | 309.07 | 309.07 | 123.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1703. - FS Job Site Superintendent | 1132.48 | 622.24 | -510.24 | 182% | 421.4 | 622.239 | 98% | 609.7952 | -522.6848 | 1155.5918 | 1140.48 | 16.71% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2040. - LR Landscaping/Restoration | 120.15 | 44.92 | -75.23 | 267.5% | 40 | 44.92 | 100% | 44.92 | -75.23 | 120.15 | 120.15 | -67.48% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7300. - PLUM Plumbing | 131.63 | 125 | -6.63 | 105.3% | 150 | 150 | 100% | 125 | -6.63 | 131.63 | 131.63 | 94.7% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5120. - Fab Shop Pipe Linings & Coatings | 516.79 | 0 | -516.79 |  | 0 | 0 | 0% | 0 | -516.79 | 516.79 | 516.79 | 0% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9005. - Re-Work Surveying | 8 | 2 | -6 | 400% | 0 | 1 | 0% | 2 | -6 | 8 | 8 | -200% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.7100. - IMP Interior Mech/Piping | 281.69 | 150 | -131.69 | 187.8% | 196 | 200 | 98% | 147 | -134.69 | 287.4388 | 281.69 | 12.21% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.6300. - DAW Doors & Windows | 21.8 | 30 | 8.2 | 72.67% | 60 | 60 | 100% | 30 | 8.2 | 21.8 | 21.8 | 127.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2610. - PT Pressure Test/Chlorinating | 124.3 | 122.5 | -1.8 | 101.5% | 140 | 140 | 100% | 122.5 | -1.8 | 124.3 | 124.3 | 98.53% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.6200. - IN Insulation | 35.04 | 8 | -27.04 | 438% | 15.84 | 16 | 99% | 7.92 | -27.12 | 35.3939 | 31.04 | -188% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.3000. - CNC Concrete Work | 447.49 | 385 | -62.49 | 116.2% | 930 | 930 | 100% | 385 | -62.49 | 447.49 | 447.49 | 83.77% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7500. - PUMP Pumps/Motors | 10.38 | 20 | 9.62 | 51.9% | 40 | 40 | 100% | 20 | 9.62 | 10.38 | 10.38 | 148.1% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7100. - IMP Interior Mech/Piping | 816.63 | 178 | -638.63 | 458.8% | 399 | 414 | 95% | 169.1 | -647.53 | 859.6105 | 816.63 | -258.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9012. - Re-Work Mechanical | 63.85 | 0.2 | -63.65 | 31925% | 0 | 0.4 | 0% | 0.2 | -63.65 | 63.85 | 63.85 | -31725% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.3000. - Unknown Phase | 341.95 | 222 | -119.95 | 154% | 32500 | 561 | 91.42% | 202.9563 | -138.9937 | 374.0356 | 341.95 | 45.97% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.5100. - W Welding | 135.81 | 80 | -55.81 | 169.8% | 40 | 40 | 100% | 80 | -55.81 | 135.81 | 135.81 | 30.24% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5110. - Fab Shop Pipe Fabrication | 879.06 | 0 | -879.06 |  | 0 | 0 | 0% | 0 | -879.06 | 879.06 | 879.06 | 0% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.1600. - TC Traffic Control | 19 | 30 | 11 | 63.33% | 0 | 20 | 100% | 30 | 11 | 19 | 19 | 136.7% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 150.2760. - Unknown Phase | 264.41 | 609.14 | 344.73 | 43.41% | 578.683 | 609.14 | 95% | 578.683 | 314.273 | 278.3263 | 274.66 | 154.9% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2710. - FWF Flowable Fill | 30.23 | 1.78 | -28.45 | 1698% | 200 | 3.56 | 100% | 1.78 | -28.45 | 30.23 | 30.23 | -1498% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 150.1230. - T Transporting | 120.41 | 152 | 31.59 | 79.22% | 144.4 | 152 | 95% | 144.4 | 23.99 | 126.7474 | 130.41 | 114.2% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 400.2000. - SWC Site Work Complete (DO NOT USE) | 704.54 | 229.83 | -474.71 | 306.5% | 195.29 | 195.29 | 100% | 229.83 | -474.71 | 704.54 | 704.54 | -106.5% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2030. - Unknown Phase | 6.5 | 11.25 | 4.75 | 57.78% | 15 | 15 | 100% | 11.25 | 4.75 | 6.5 | 6.5 | 142.2% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7600. - MEQ Mechanical Equipment | 3.5 | 65 | 61.5 | 5.385% | 110 | 110 | 100% | 65 | 61.5 | 3.5 | 3.5 | 194.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.6400. - DRY Drywall & Metal Studs | 26.86 | 34 | 7.14 | 79% | 68 | 68 | 100% | 34 | 7.14 | 26.86 | 26.86 | 121% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9055. - Re-Work Finishes | 7.52 | 0.1 | -7.42 | 7520% | 0 | 0.2 | 0% | 0.1 | -7.42 | 7.52 | 7.52 | -7320% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 2.03 | 26.25 | 24.22 | 7.733% | 0 | 26.25 | 0% | 26.25 | 24.22 | 26.25 | 2.03 | 192.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.2800. - BFST Backfill (DO NOT USE) | 123.2 | 175 | 51.8 | 70.4% | 150 | 150 | 100% | 175 | 51.8 | 123.2 | 127.2 | 127.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5310. - Fab Shop Misc Metals Fabrication | 122.15 | 477 | 354.85 | 25.61% | 1 | 238.5 | 100% | 477 | 354.85 | 122.15 | 122.15 | 174.4% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 800.1940. - PL Punch List Work | 70.42 | 250 | 179.58 | 28.17% | 130 | 200 | 65% | 162.5 | 92.08 | 108.3385 | 96.04 | 161.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 50.05 | 102.5 | 52.45 | 48.83% | 87 | 87 | 100% | 102.5 | 52.45 | 50.05 | 50.05 | 151.2% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 400.3000. - CNC Concrete Work | 94.47 | 230.4 | 135.93 | 41% | 668.2 | 683.2 | 100% | 230.4 | 135.93 | 94.47 | 94.47 | 159% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9020. - Re-Work Fab | 38.6 | 0.4 | -38.2 | 9650% | 0 | 0.2 | 0% | 0.4 | -38.2 | 38.6 | 38.6 | -9450% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.5000. - MET Metals | 5 | 20 | 15 | 25% | 2000 | 35 | 100% | 20 | 15 | 5 | 5 | 175% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.6100. - F Framing | 40.6 | 20 | -20.6 | 203% | 20 | 20 | 100% | 20 | -20.6 | 40.6 | 40.6 | -3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.7900. - ELC Electrical | 140.3 | 98.82 | -41.48 | 142% | 103.14 | 103.14 | 100% | 98.82 | -41.48 | 140.3 | 140.3 | 58.02% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5320. - Fab Shop Misc Metals Coatings | 3.15 | 230 | 226.85 | 1.37% | 1 | 460 | 100% | 230 | 226.85 | 3.15 | 3.15 | 198.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 800.1930. - MC Misc Cleanup | 5.38 | 125 | 119.62 | 4.304% | 65 | 100 | 65% | 81.25 | 75.87 | 8.2769 | 25.38 | 179.7% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1650. - SB Signage | 2.5 | 10 | 7.5 | 25% | 15 | 15 | 100% | 10 | 7.5 | 2.5 | 2.5 | 175% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1702. - FS People Superintendent | 720.58 | 303.31 | -417.27 | 237.6% | 98 | 303.314 | 98% | 297.2438 | -423.3362 | 735.2857 | 728.08 | -40.04% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 500.2030. - D Demolition | 6.43 | 52 | 45.57 | 12.37% | 0 | 52 | 0% | 52 | 45.57 | 52 | 6.43 | 187.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 500.7900. - ELC Electrical | 159.43 | 495.49 | 336.06 | 32.18% | 0 | 253.99 | 51.66% | 255.9803 | 96.5503 | 308.6018 | 159.43 | 167.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1704. - FS Quality Control/Assurance | 482.25 | 60.8 | -421.45 | 793.2% | 320 | 60.798 | 100% | 60.8 | -421.45 | 482.25 | 492.25 | -609.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1510. - S Surveying | 1226.7 | 200 | -1026.7 | 613.4% | 100 | 100 | 100% | 200 | -1026.7 | 1226.7 | 1226.7 | -413.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.5000. - MET Metals | 67.48 | 25 | -42.48 | 269.9% | 75 | 75 | 100% | 25 | -42.48 | 67.48 | 67.48 | -69.92% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9100. - Job Related Equipment Repairs | 51.19 | 1 | -50.19 | 5119% | 0 | 1 | 0% | 1 | -50.19 | 51.19 | 51.19 | -4919% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 800.1700. - FS Project Manager | 44.97 | 400 | 355.03 | 11.24% | 400 | 400 | 100% | 400 | 355.03 | 44.97 | 44.97 | 188.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.2080. - EXS Excavate Structure | 438.83 | 237.5 | -201.33 | 184.8% | 250 | 250 | 100% | 237.5 | -201.33 | 438.83 | 438.83 | 15.23% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 1139.61 | 413.86 | -725.75 | 275.4% | 279.8 | 295.8 | 100% | 413.86 | -725.75 | 1139.61 | 1139.61 | -75.36% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 484.28 | 387.63 | -96.65 | 124.9% | 686 | 387.634 | 98% | 379.8774 | -104.4026 | 494.1633 | 490.78 | 73.39% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2800. - Unknown Phase | 584.37 | 195 | -389.37 | 299.7% | 9000 | 165 | 100% | 195 | -389.37 | 584.37 | 580.37 | -97.63% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1700. - FS Project Manager | 685.75 | 417.54 | -268.21 | 164.2% | 292.04 | 417.537 | 98% | 409.1892 | -276.5608 | 699.7449 | 689.75 | 34.81% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.2030. - Unknown Phase | 41.2 | 20 | -21.2 | 206% | 10 | 10 | 100% | 20 | -21.2 | 41.2 | 41.2 | -6% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.7100. - IMP Interior Mech/Piping | 53.06 | 20 | -33.06 | 265.3% | 60 | 60 | 100% | 20 | -33.06 | 53.06 | 53.06 | -65.3% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.5100. - W Welding | 4 | 46 | 42 | 8.696% | 23 | 23 | 100% | 46 | 42 | 4 | 4 | 191.3% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.6500. - Unknown Phase | 5.5 | 20 | 14.5 | 27.5% | 60 | 60 | 100% | 20 | 14.5 | 5.5 | 5.5 | 172.5% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 800.1940. - PL Punch List Work | 77.07 | 5 | -72.07 | 1541% | 15 | 15 | 100% | 5 | -72.07 | 77.07 | 77.07 | -1341% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 20.75 | 4.45 | -16.3 | 466.3% | 0.445 | 4.45 | 10% | 0.445 | -20.305 | 207.5 | 20.75 | -266.3% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1700. - FS Project Manager | 10.5 | 4.79 | -5.71 | 219.2% | 0.479 | 4.79 | 10% | 0.479 | -10.021 | 105 | 10.5 | -19.21% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1703. - FS Job Site Superintendent | 30.84 | 5.78 | -25.06 | 533.6% | 0.578 | 5.78 | 10% | 0.578 | -30.262 | 308.4 | 30.84 | -333.6% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 800.1930. - MC Misc Cleanup | 4.38 | 5 | 0.62 | 87.6% | 15 | 15 | 100% | 5 | 0.62 | 4.38 | 4.38 | 112.4% |  | 2025-12-31
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 150.1230. - T Transporting | 225.29 | 130 | -95.29 | 173.3% | 130 | 130 | 50% | 65 | -160.29 | 450.58 | 130 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.5100. - W Welding | 341.99 | 190 | -151.99 | 180% | 60 | 110 | 33.33% | 63.3333 | -278.6567 | 1025.97 | 120 | 136.8% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.3000. - CNC Concrete Work | 622.46 | 80 | -542.46 | 778.1% | 180 | 240 | 75% | 60 | -562.46 | 829.9467 | 60 | 125% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 250.7100. - IMP Interior Mech/Piping | 165.33 | 340 | 174.67 | 48.63% | 540 | 540 | 61.36% | 208.6364 | 43.3064 | 269.4267 | 340 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 350.6200. - IN Insulation | 9 | 30 | 21 | 30% | 90 | 90 | 75% | 22.5 | 13.5 | 12 | 30 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 20 | 48 | 28 | 41.67% | 30 | 30 | 38.46% | 18.4615 | -1.5385 | 52 | 48 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 39.28 | 0 | -39.28 |  | 0 | 0 | 0% | 0 | -39.28 | 39.28 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1700. - FS Project Manager | 17.5 | 0 | -17.5 |  | 0 | 0 | 0% | 0 | -17.5 | 17.5 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 150.2750. - Unknown Phase | 36.37 | 10 | -26.37 | 363.7% | 10 | 10 | 50% | 5 | -31.37 | 72.74 | 10 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 200.3000. - Unknown Phase | 740.69 | 1880 | 1139.31 | 39.4% | 2200 | 1880 | 49.66% | 933.5909 | 192.9009 | 1491.5497 | 2200 | 82.98% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 350.5000. - MET Metals | 7.92 | 34 | 26.08 | 23.29% | 30 | 30 | 46.88% | 15.9375 | 8.0175 | 16.896 | 34 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1703. - FS Job Site Superintendent | 239.65 | 0 | -239.65 |  | 0 | 0 | 0% | 0 | -239.65 | 239.65 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.5000. - MET Metals | 88.34 | 102 | 13.66 | 86.61% | 90 | 90 | 46.88% | 47.8125 | -40.5275 | 188.4587 | 102 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 160.1230. - T Transporting | 350.25 | 50 | -300.25 | 700.5% | 0 | 50 | 0% | 50 | -300.25 | 350.25 | 50 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 160.5310. - Fab Shop Misc Metals Fabrication | 10527.09 | 173 | -10354.09 | 6085% | 0 | 173 | 0% | 173 | -10354.09 | 10527.09 | 0 | 200% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 165.7100. - IMP Interior Mech/Piping | 0 | 0 | 0 |  | 0 | 133 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 160.5320. - Fab Shop Misc Metals Coatings | 140.43 | 52 | -88.43 | 270.1% | 0 | 156 | 0% | 52 | -88.43 | 140.43 | 0 | 200% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 200.7100. - IMP Interior Mech/Piping | 146.8 | 800.52 | 653.72 | 18.34% | 1410 | 1263.3 | 61.2% | 489.9417 | 343.1417 | 239.8578 | 918.32 | 85.28% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 900.9100. - Job Related Equipment Repairs | 2 | 1 | -1 | 200% | 1 | 1 | 50% | 0.5 | -1.5 | 4 | 1 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 134.63 | 288 | 153.37 | 46.75% | 180 | 180 | 38.46% | 110.7692 | -23.8608 | 350.038 | 288 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1702. - FS People Superintendent | 111.1 | 0 | -111.1 |  | 0 | 0 | 0% | 0 | -111.1 | 111.1 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.2080. - EXS Excavate Structure | 95.86 | 288 | 192.14 | 33.28% | 180 | 180 | 38.46% | 110.7692 | 14.9092 | 249.236 | 288 | 100% |  | 2023-11-06
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 526.55 | 2470 | 1943.45 | 21.32% | 1253 | 1253 | 33.66% | 831.2947 | 304.7447 | 1564.5217 | 2470 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2800. - BFST Backfill (DO NOT USE) | 205.51 | 30 | -175.51 | 685% | 30 | 30 | 50% | 15 | -190.51 | 411.02 | 30 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 195.51 | 156 | -39.51 | 125.3% | 234 | 234 | 60% | 93.6 | -101.91 | 325.85 | 156 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.6500. - P Painting | 732.48 | 120 | -612.48 | 610.4% | 240 | 240 | 66.67% | 80 | -652.48 | 1098.72 | 120 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9020. - Re-Work Fab | 364.72 | 0.4 | -364.32 | 91180% | 0.2 | 0.2 | 33.33% | 0.13333 | -364.5867 | 1094.16 | 0.4 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2600. - DW Dewatering | 23.5 | 562.5 | 539 | 4.178% | 500 | 500 | 47.06% | 264.7059 | 241.2059 | 49.9375 | 562.5 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.7100. - IMP Interior Mech/Piping | 355.63 | 140 | -215.63 | 254% | 210 | 210 | 60% | 84 | -271.63 | 592.7167 | 140 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2750. - H Hauling | 2 | 7.28 | 5.28 | 27.47% | 7.28 | 7.28 | 50% | 3.64 | 1.64 | 4 | 7.28 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 410.2000. - SWC Site Work Complete (DO NOT USE) | 50.76 | 27.5 | -23.26 | 184.6% | 30 | 30 | 52.17% | 14.3478 | -36.4122 | 97.29 | 27.5 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 600.5000. - MET Metals | 9.5 | 10 | 0.5 | 95% | 12 | 12 | 54.55% | 5.4545 | -4.0455 | 17.4167 | 10 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.5100. - W Welding | 3272.95 | 2127.5 | -1145.45 | 153.8% | 1030 | 1030 | 32.89% | 699.7336 | -2573.2164 | 9951.2177 | 2127.5 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2750. - H Hauling | 259.32 | 79.37 | -179.95 | 326.7% | 79.37 | 79.37 | 50% | 39.685 | -219.635 | 518.64 | 79.37 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.5000. - MET Metals | 119.3 | 279 | 159.7 | 42.76% | 266 | 266 | 63.18% | 176.2803 | 56.9803 | 188.8169 | 155 | 144.4% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2080. - EXS Excavate Structure | 13.48 | 332 | 318.52 | 4.06% | 140 | 140 | 29.66% | 98.4746 | 84.9946 | 45.4469 | 332 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2750. - H Hauling | 6 | 974.53 | 968.53 | 0.6157% | 974.53 | 974.53 | 50% | 487.265 | 481.265 | 12 | 974.53 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.7100. - IMP Interior Mech/Piping | 397.77 | 170 | -227.77 | 234% | 255 | 255 | 60% | 102 | -295.77 | 662.95 | 170 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.5100. - W Welding | 311.91 | 443.75 | 131.84 | 70.29% | 210 | 210 | 32.12% | 142.543 | -169.367 | 971.0055 | 443.75 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 310.2300. - WPL Water Pipe Laying (DO NOT USE) | 5 | 400 | 395 | 1.25% | 475 | 475 | 54.29% | 217.1429 | 212.1429 | 9.2105 | 400 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2030. - D Demolition | 96.14 | 120 | 23.86 | 80.12% | 125 | 125 | 51.02% | 61.2245 | -34.9155 | 188.4344 | 120 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.7900. - ELC Electrical | 67.28 | 25 | -42.28 | 269.1% | 20 | 20 | 44.44% | 11.1111 | -56.1689 | 151.38 | 25 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2800. - BFST Backfill (DO NOT USE) | 1277.73 | 325 | -952.73 | 393.1% | 300 | 300 | 48% | 156 | -1121.73 | 2661.9375 | 325 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2030. - D Demolition | 358.14 | 582 | 223.86 | 61.54% | 380 | 380 | 39.5% | 229.896 | -128.244 | 906.6597 | 582 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 320.2300. - WPL Water Pipe Laying (DO NOT USE) | 5.22 | 160 | 154.78 | 3.263% | 140 | 140 | 46.67% | 74.6667 | 69.4467 | 11.1857 | 160 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1510. - S Surveying | 3983.15 | 1000 | -2983.15 | 398.3% | 500 | 500 | 33.33% | 333.3333 | -3649.8167 | 11949.45 | 1000 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2760. - HO Haul Off | 69.09 | 173 | 103.91 | 39.94% | 173 | 173 | 50% | 86.5 | 17.41 | 138.18 | 173 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.7900. - ELC Electrical | 1.5 | 25 | 23.5 | 6% | 20 | 20 | 44.44% | 11.1111 | 9.6111 | 3.375 | 25 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2800. - BFST Backfill (DO NOT USE) | 132.63 | 500 | 367.37 | 26.53% | 375 | 375 | 42.86% | 214.2857 | 81.6557 | 309.47 | 500 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2800. - BFST Backfill (DO NOT USE) | 941.89 | 235 | -706.89 | 400.8% | 210 | 210 | 47.19% | 110.8989 | -830.9911 | 1995.9098 | 235 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 160.5010. - Fab Shop Steel Materials | 11034.55 | 0 | -11034.55 |  | 0 | 0 | 466.7% | 0 | -11034.55 | 2364.5464 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9100. - Job Related Equipment Repairs | 0 | 5 | 5 | 0% | 1 | 1 | 50% | 2.5 | 2.5 | 0 | 1 | 180% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.5000. - MET Metals | 4.7 | 50 | 45.3 | 9.4% | 75 | 75 | 60% | 30 | 25.3 | 7.8333 | 50 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.3000. - CNC Concrete Work | 508.83 | 514 | 5.17 | 98.99% | 1080 | 1080 | 67.92% | 349.1321 | -159.6979 | 749.1108 | 510 | 100.8% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2080. - EXS Excavate Structure | 53.36 | 10 | -43.36 | 533.6% | 10 | 10 | 50% | 5 | -48.36 | 106.72 | 10 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2080. - EXS Excavate Structure | 519.23 | 2800 | 2280.77 | 18.54% | 600 | 600 | 17.65% | 494.1176 | -25.1124 | 2942.3033 | 2800 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1702. - FS People Superintendent | 1185.69 | 4 | -1181.69 | 29642% | -13.63 | 0 | 0% | 4 | -1181.69 | 1185.69 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2030. - D Demolition | 0 | 45 | 45 | 0% | 30 | 30 | 50% | 22.5 | 22.5 | 0 | 30 | 133.3% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 4 | 80 | 76 | 5% | 40 | 40 | 33.33% | 26.6667 | 22.6667 | 12 | 80 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.3000. - CNC Concrete Work | 231.72 | 50 | -181.72 | 463.4% | 140 | 140 | 73.68% | 36.8421 | -194.8779 | 314.4771 | 50 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 410.2300. - WPL Water Pipe Laying (DO NOT USE) | 21.9 | 150 | 128.1 | 14.6% | 225 | 225 | 60% | 90 | 68.1 | 36.5 | 150 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 180.1600. - TC Traffic Control | 183.1 | 0 | -183.1 |  | 0 | 0 | 0% | 0 | -183.1 | 183.1 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2760. - HO Haul Off | 137.55 | 110.67 | -26.88 | 124.3% | 110.67 | 110.67 | 50% | 55.335 | -82.215 | 275.1 | 110.67 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9010. - Re-Work Pipe | 142.32 | 1 | -141.32 | 14232% | 0.4 | 0.4 | 66.67% | 0.66667 | -141.6533 | 213.48 | 0.2 | 180% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.7100. - IMP Interior Mech/Piping | 36.3 | 10 | -26.3 | 363% | 20 | 20 | 66.67% | 6.6667 | -29.6333 | 54.45 | 10 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 210.2010. - RG Grading (DO NOT USE) | 611.31 | 456.1 | -155.21 | 134% | 0 | 0 | 0% | 456.1 | -155.21 | 611.31 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 800.1930. - MC Misc Cleanup | 283.05 | 375 | 91.95 | 75.48% | 450 | 450 | 54.55% | 204.5455 | -78.5045 | 518.925 | 375 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2080. - EXS Excavate Structure | 244.96 | 1037 | 792.04 | 23.62% | 295 | 295 | 22.15% | 229.6659 | -15.2941 | 1106.0567 | 1037 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2080. - EXS Excavate Structure | 117.19 | 746 | 628.81 | 15.71% | 175 | 175 | 19.42% | 144.8946 | 27.7046 | 603.3611 | 726 | 102.7% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.3000. - Unknown Phase | 125.58 | 248 | 122.42 | 50.64% | 440 | 440 | 66.67% | 165.3333 | 39.7533 | 188.37 | 220 | 111.3% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2000. - Unknown Phase | 25.45 | 250 | 224.55 | 10.18% | 250 | 250 | 50% | 125 | 99.55 | 50.9 | 250 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2610. - PT Pressure Test/Chlorinating | 112.8 | 30 | -82.8 | 376% | 20 | 20 | 40% | 12 | -100.8 | 282 | 30 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2000. - SWC Site Work Complete (DO NOT USE) | 67.36 | 13.75 | -53.61 | 489.9% | 15 | 15 | 52.17% | 7.1739 | -60.1861 | 129.1067 | 13.75 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 210.2300. - WPL Water Pipe Laying (DO NOT USE) | 515.61 | 360 | -155.61 | 143.2% | 540 | 540 | 60% | 216 | -299.61 | 859.35 | 360 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.1230. - T Transporting | 1089.55 | 520 | -569.55 | 209.5% | 900 | 500 | 90% | 468 | -621.55 | 1210.6111 | 500 | 103.8% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9005. - Re-Work Surveying | 36 | 10 | -26 | 360% | 1 | 1 | 33.33% | 3.3333 | -32.6667 | 108 | 2 | 180% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 160.5120. - Fab Shop Pipe Linings & Coatings | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1700. - FS Project Manager | 47.5 | 18 | -29.5 | 263.9% | -12.75 | 0 | 0% | 18 | -29.5 | 47.5 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 769.25 | 2331.5 | 1562.25 | 32.99% | 1202 | 1202 | 34.02% | 793.1125 | 23.8625 | 2261.3518 | 2331.5 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.5100. - W Welding | 193.71 | 305 | 111.29 | 63.51% | 140 | 140 | 31.46% | 95.9551 | -97.7549 | 615.7211 | 305 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 800.1940. - PL Punch List Work | 480.28 | 155 | -325.28 | 309.9% | 290.72 | 300 | 60.48% | 93.744 | -386.536 | 794.1138 | 150 | 103.2% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1085.5 | 4 | -1081.5 | 27138% | 0 | 0 | 0% | 4 | -1081.5 | 1085.5 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 310.2000. - SWC Site Work Complete (DO NOT USE) | 16.5 | 27.5 | 11 | 60% | 30 | 30 | 52.17% | 14.3478 | -2.1522 | 31.625 | 27.5 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.1600. - TC Traffic Control | 76.05 | 18700 | 18623.95 | 0.4067% | 300 | 300 | 1.579% | 295.2632 | 219.2132 | 4816.5 | 18700 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 420.2000. - SWC Site Work Complete (DO NOT USE) | 21 | 82.5 | 61.5 | 25.45% | 90 | 90 | 52.17% | 43.0435 | 22.0435 | 40.25 | 82.5 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2760. - HO Haul Off | 17.07 | 1104 | 1086.93 | 1.546% | 1104 | 1104 | 50% | 552 | 534.93 | 34.14 | 1104 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.2750. - Unknown Phase | 795.66 | -78.34 | -874 |  | 0 | 3 | 0% | -78.34 | -874 | 795.66 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2300. - Unknown Phase | 11960.95 | 7775.19 | -4185.76 | 153.8% | 4820.67 | 4820.67 | 37.72% | 2932.8088 | -9028.1412 | 31709.7582 | 7775.19 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1703. - FS Job Site Superintendent | 485.37 | 4 | -481.37 | 12134% | 0 | 0 | 0% | 4 | -481.37 | 485.37 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2760. - HO Haul Off | 30.39 | 12 | -18.39 | 253.3% | 12 | 12 | 50% | 6 | -24.39 | 60.78 | 12 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 40.09 | 40 | -0.09 | 100.2% | 80 | 80 | 66.67% | 26.6667 | -13.4233 | 60.135 | 40 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.6200. - IN Insulation | 3.28 | 25 | 21.72 | 13.12% | 50 | 50 | 66.67% | 16.6667 | 13.3867 | 4.92 | 25 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2050. - RW Retaining Walls | 291.8 | 100 | -191.8 | 291.8% | 100 | 100 | 51.5% | 51.5 | -240.3 | 566.6019 | 100 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.6500. - Unknown Phase | 108.88 | 25 | -83.88 | 435.5% | 50 | 50 | 66.67% | 16.6667 | -92.2133 | 163.32 | 25 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 420.2300. - WPL Water Pipe Laying (DO NOT USE) | 42.21 | 270 | 227.79 | 15.63% | 240 | 240 | 47.06% | 127.0588 | 84.8488 | 89.6963 | 270 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2750. - H Hauling | 4.5 | 94.3 | 89.8 | 4.772% | 94.3 | 94.3 | 50% | 47.15 | 42.65 | 9 | 94.3 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.5010. - FAB Shop Steel Materials (DO NOT USE) | 3073.42 | 0 | -3073.42 |  | 0 | 0 | 0% | 0 | -3073.42 | 3073.42 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2010. - RG Grading (DO NOT USE) | 570.96 | 440 | -130.96 | 129.8% | 319.99 | 319.99 | 42.1% | 185.2598 | -385.7002 | 1356.0545 | 440 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2610. - PT Pressure Test/Chlorinating | 64.2 | 45 | -19.2 | 142.7% | 30 | 30 | 40% | 18 | -46.2 | 160.5 | 45 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.6500. - P Painting | 526.58 | 120 | -406.58 | 438.8% | 240 | 240 | 66.67% | 80 | -446.58 | 789.87 | 120 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2610. - PT Pressure Test/Chlorinating | 258.17 | 300 | 41.83 | 86.06% | 200 | 200 | 40% | 120 | -138.17 | 645.425 | 300 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 320.2000. - SWC Site Work Complete (DO NOT USE) | 105.33 | 55 | -50.33 | 191.5% | 60 | 60 | 52.17% | 28.6957 | -76.6343 | 201.8825 | 55 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 410.3000. - CNC Concrete Work | 103 | 70 | -33 | 147.1% | 120 | 120 | 66.67% | 46.6667 | -56.3333 | 154.5 | 60 | 114.3% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 238.57 | 240 | 1.43 | 99.4% | 120 | 120 | 33.33% | 80 | -158.57 | 715.71 | 240 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2750. - H Hauling | 344.24 | 104.34 | -239.9 | 329.9% | 104.34 | 104.34 | 50% | 52.17 | -292.07 | 688.48 | 104.34 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2060. - FE Fencing | 16.07 | 29.62 | 13.55 | 54.25% | 44.44 | 44.44 | 60.01% | 17.7736 | 1.7036 | 26.7809 | 29.62 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.5000. - MET Metals | 66.42 | 140 | 73.58 | 47.44% | 248 | 248 | 63.92% | 89.4845 | 23.0645 | 103.9152 | 140 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.3000. - CNC Concrete Work | 775.76 | 555.83 | -219.93 | 139.6% | 1195.39 | 1195.39 | 68.26% | 379.4119 | -396.3481 | 1136.4713 | 555.83 | 100% |  | 2024-03-04
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.3000. - CNC Concrete Work | 104.02 | 40 | -64.02 | 260% | 0 | 80 | 0% | 40 | -64.02 | 104.02 | 40 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.2800. - Unknown Phase | 7.6 | 70 | 62.4 | 10.86% | 0 | 60 | 0% | 70 | 62.4 | 70 | 70 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 350.5100. - W Welding | 17 | 120 | 103 | 14.17% | 0 | 60 | 0% | 120 | 103 | 120 | 120 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2610. - PT Pressure Test/Chlorinating | 6.33 | 4.84 | -1.49 | 130.8% | 0 | 10 | 0% | 4.84 | -1.49 | 6.33 | 8.75 | 19.21% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 40 | 40 | 0% | 0 | 50 | 0% | 40 | 40 | 40 | 40 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.2610. - PT Pressure Test/Chlorinating | 79.94 | 21.73 | -58.21 | 367.9% | 0 | 20 | 0% | 21.73 | -58.21 | 79.94 | 17.5 | 119.5% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1700. - FS Project Manager | 34 | 0 | -34 |  | 0 | 0 | 0% | 0 | -34 | 34 | 0 | 0% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1510. - S Surveying | 111.79 | 40 | -71.79 | 279.5% | 0 | 20 | 0% | 40 | -71.79 | 111.79 | 40 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.2910. - MP Milling/Pulverize | 6.42 | 6.47 | 0.05 | 99.23% | 0 | 3.1 | 0% | 6.47 | 0.05 | 6.47 | 5.21 | 119.5% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 600.2930. - AP Asphalt Prep (DO NOT USE) | 151.85 | 66.83 | -85.02 | 227.2% | 0 | 114.16 | 0% | 66.83 | -85.02 | 151.85 | 98.46 | 52.67% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 800.1930. - MC Misc Cleanup | 11.32 | 250 | 238.68 | 4.528% | 0 | 300 | 0% | 250 | 238.68 | 250 | 250 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 800.1940. - PL Punch List Work | 17.23 | 100 | 82.77 | 17.23% | 0 | 200 | 0% | 100 | 82.77 | 100 | 100 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 166.94 | 309.84 | 142.9 | 53.88% | 0 | 287 | 0% | 309.84 | 142.9 | 309.84 | 527 | 29.91% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1702. - FS People Superintendent | 46 | 0 | -46 |  | 0 | 0 | 0% | 0 | -46 | 46 | 0 | 0% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 150.1230. - T Transporting | 247.96 | 150 | -97.96 | 165.3% | 0 | 150 | 0% | 150 | -97.96 | 247.96 | 150 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 94.47 | 597 | 502.53 | 15.82% | 0 | 282 | 0% | 597 | 502.53 | 597 | 597 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.1600. - TC Traffic Control | 128.66 | 385 | 256.34 | 33.42% | 0 | 185 | 0% | 385 | 256.34 | 385 | 385 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2030. - D Demolition | 22.96 | 33.24 | 10.28 | 69.07% | 0 | 60 | 0% | 33.24 | 10.28 | 33.24 | 60 | 19.49% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.2300. - Unknown Phase | 9 | 261.59 | 252.59 | 3.44% | 0 | 90 | 0% | 261.59 | 252.59 | 261.59 | 60 | 177.1% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 556.98 | 448.56 | -108.42 | 124.2% | 0 | 336.75 | 0% | 448.56 | -108.42 | 556.98 | 375.75 | 116.2% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 150.2750. - Unknown Phase | 144.31 | 343.73 | 199.42 | 41.98% | 0 | 187.09 | 0% | 343.73 | 199.42 | 343.73 | 187.09 | 145.6% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.2910. - MP Milling/Pulverize | 24.88 | 48.03 | 23.15 | 51.8% | 0 | 47 | 0% | 48.03 | 23.15 | 48.03 | 48.03 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1703. - FS Job Site Superintendent | 177.4 | 0 | -177.4 |  | 0 | 0 | 0% | 0 | -177.4 | 177.4 | 0 | 0% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 150.2760. - Unknown Phase | 426.97 | 125.72 | -301.25 | 339.6% | 0 | 150 | 0% | 125.72 | -301.25 | 426.97 | 150 | 80.69% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 900.9015. - Re-Work Concrete | 0 | 0.6 | 0.6 | 0% | 0 | 0.4 | 0% | 0.6 | 0.6 | 0.6 | 0.2 | 166.7% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 350.3000. - CNC Concrete Work | 42.32 | 4.5 | -37.82 | 940.4% | 0 | 6 | 0% | 4.5 | -37.82 | 42.32 | 4.5 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2910. - MP Milling/Pulverize | 0 | 16.11 | 16.11 | 0% | 0 | 14.76 | 0% | 16.11 | 16.11 | 16.11 | 24.8 | 46.06% |  | 2023-09-29
2409. - JVWCD 2024 Vault Improvement Project | 500.7100. - IMP Interior Mech/Piping | 789.83 | 316.5 | -473.33 | 249.6% | 405.6 | 507 | 80% | 253.2 | -536.63 | 987.2875 | 783.43 | -47.53% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1230. - T Transporting | 39.08 | 30 | -9.08 | 130.3% | 30 | 30 | 100% | 30 | -9.08 | 39.08 | 39.08 | 69.73% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1702. - FS People Superintendent | 318.89 | 139.74 | -179.15 | 228.2% | 0.66 | 138.74 | 40.5% | 56.5947 | -262.2953 | 787.3827 | 342.39 | -45.02% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2760. - HO Haul Off | 2 | 2.5 | 0.5 | 80% | 2.5 | 2.5 | 100% | 2.5 | 0.5 | 2 | 2 | 120% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 180.2920. - SC Saw Cutting/Coring | 14 | 2 | -12 | 700% | 0 | 4 | 0% | 2 | -12 | 14 | 14 | -500% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2390. - WSP Welded Steel Pipe | 16.38 | 127.34 | 110.96 | 12.86% | 116.22 | 116.22 | 100% | 127.34 | 110.96 | 16.38 | 16.38 | 187.1% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.2030. - D Demolition | 59.8 | 195.3 | 135.5 | 30.62% | 241.587 | 268.43 | 90% | 175.77 | 115.97 | 66.4444 | 52.75 | 173% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.5000. - MET Metals | 8 | 10 | 2 | 80% | 30 | 30 | 100% | 10 | 2 | 8 | 8 | 120% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 900.9010. - Re-Work Pipe | 17.22 | 0.4 | -16.82 | 4305% | 0 | 0.4 | 0% | 0.4 | -16.82 | 17.22 | 17.22 | -4105% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2180. - CATH Cathodic Protection | 1 | 10 | 9 | 10% | 18 | 18 | 100% | 10 | 9 | 1 | 1 | 190% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.1200. - HOOK Hook Truck Dumpster Transporting | 29.37 | 2.5 | -26.87 | 1175% | 2.25 | 2.5 | 90% | 2.25 | -27.12 | 32.6333 | 21 | -640% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.3000. - Unknown Phase | 12.52 | 19.81 | 7.29 | 63.2% | 50.12 | 50.12 | 100% | 19.81 | 7.29 | 12.52 | 12.52 | 136.8% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 900.9005. - Re-Work Surveying | 8.8 | 4 | -4.8 | 220% | 0 | 1 | 0% | 4 | -4.8 | 8.8 | 8.8 | -20% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1600. - TC Traffic Control | 427.76 | 750 | 322.24 | 57.03% | 32 | 40 | 80% | 600 | 172.24 | 534.7 | 373.46 | 150.2% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2075. - FG Finish Grade | 30.87 | 25.52 | -5.35 | 121% | 20.32 | 20.32 | 97.22% | 24.8096 | -6.0604 | 31.7539 | 30.87 | 79.04% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1704. - FS Quality Control/Assurance | 44 | 28.45 | -15.55 | 154.7% | 0.66 | 27.45 | 40.5% | 11.5222 | -32.4778 | 108.642 | 48 | 31.28% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.1600. - TC Traffic Control | 195.44 | 15 | -180.44 | 1303% | 30 | 30 | 100% | 15 | -180.44 | 195.44 | 198.94 | -1126% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2750. - H Hauling | 10 | 11.25 | 1.25 | 88.89% | 11.25 | 11.25 | 100% | 11.25 | 1.25 | 10 | 10 | 111.1% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.5000. - MET Metals | 24.37 | 21 | -3.37 | 116% | 30 | 38 | 100% | 21 | -3.37 | 24.37 | 24.37 | 83.95% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2610. - PT Pressure Test/Chlorinating | 1 | 10 | 9 | 10% | 10 | 10 | 100% | 10 | 9 | 1 | 1 | 190% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.1600. - TC Traffic Control | 329.56 | 0 | -329.56 |  | 0 | 0 | 0% | 0 | -329.56 | 329.56 | 294.48 | 0% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1230. - T Transporting | 112.51 | 30 | -82.51 | 375% | 24 | 30 | 80% | 24 | -88.51 | 140.6375 | 112.51 | -175% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1700. - FS Project Manager | 178.18 | 187.28 | 9.1 | 95.14% | 51.81 | 186.277 | 65.36% | 122.4034 | -55.7766 | 272.6195 | 195.93 | 95.38% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.3000. - CNC Concrete Work | 1 | 19.48 | 18.48 | 5.133% | 49.15 | 49.15 | 100% | 19.48 | 18.48 | 1 | 1 | 194.9% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.5000. - MET Metals | 31.91 | 24 | -7.91 | 133% | 60 | 64 | 100% | 24 | -7.91 | 31.91 | 31.91 | 67.04% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 629.34 | 192.05 | -437.29 | 327.7% | 0.66 | 191.048 | 40.5% | 77.7802 | -551.5598 | 1553.9259 | 644.09 | -135.4% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2750. - H Hauling | 13.23 | 21.6 | 8.37 | 61.25% | 21.42 | 21.42 | 100% | 21.6 | 8.37 | 13.23 | 13.23 | 138.8% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.5100. - W Welding | 27.3 | 20 | -7.3 | 136.5% | 9 | 10 | 90% | 18 | -9.3 | 30.3333 | 27.3 | 63.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2710. - FWF Flowable Fill | 2 | 5 | 3 | 40% | 10 | 10 | 100% | 5 | 3 | 2 | 2 | 160% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1703. - FS Job Site Superintendent | 473.34 | 280.84 | -192.5 | 168.5% | 0.66 | 279.838 | 40.5% | 113.7402 | -359.5998 | 1168.7407 | 411.81 | 53.36% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.1230. - T Transporting | 287.86 | 60 | -227.86 | 479.8% | 54 | 60 | 90% | 54 | -233.86 | 319.8444 | 299.01 | -298.3% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.5100. - W Welding | 84.06 | 133.34 | 49.28 | 63.04% | 53.336 | 66.67 | 80% | 106.672 | 22.612 | 105.075 | 84.06 | 137% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2760. - HO Haul Off | 135.74 | 8.63 | -127.11 | 1573% | 10.63 | 10.63 | 100% | 8.63 | -127.11 | 135.74 | 135.74 | -1373% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2760. - HO Haul Off | 59.09 | 21 | -38.09 | 281.4% | 16.8 | 21 | 80% | 16.8 | -42.29 | 73.8625 | 59.09 | -81.38% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.5000. - MET Metals | 35.13 | 15 | -20.13 | 234.2% | 10.8 | 12 | 84.44% | 12.6667 | -22.4633 | 41.6013 | 35.33 | -35.53% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.5000. - MET Metals | 91.8 | 40 | -51.8 | 229.5% | 48 | 60 | 80% | 32 | -59.8 | 114.75 | 93.03 | -32.57% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.3000. - CNC Concrete Work | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2030. - D Demolition | 111.18 | 105.86 | -5.32 | 105% | 69.61 | 69.61 | 100% | 105.86 | -5.32 | 111.18 | 111.18 | 94.97% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2760. - HO Haul Off | 40.46 | 8.88 | -31.58 | 455.6% | 8.88 | 8.88 | 100% | 8.88 | -31.58 | 40.46 | 40.46 | -255.6% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.7100. - IMP Interior Mech/Piping | 140.76 | 48 | -92.76 | 293.2% | 30 | 30 | 100% | 48 | -92.76 | 140.76 | 140.76 | -93.25% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 180.2910. - MP Milling/Pulverize | 15.12 | 13 | -2.12 | 116.3% | 0 | 15 | 0% | 13 | -2.12 | 15.12 | 15.12 | 83.69% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.7100. - IMP Interior Mech/Piping | 297.38 | 152 | -145.38 | 195.6% | 102.6 | 114 | 90% | 136.8 | -160.58 | 330.4222 | 297.38 | 4.355% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.1230. - T Transporting | 55.31 | 30 | -25.31 | 184.4% | 30 | 30 | 100% | 30 | -25.31 | 55.31 | 55.31 | 15.63% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.7100. - IMP Interior Mech/Piping | 206.88 | 48 | -158.88 | 431% | 30 | 30 | 100% | 48 | -158.88 | 206.88 | 206.88 | -231% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2030. - Unknown Phase | 107.37 | 143.04 | 35.67 | 75.06% | 71.58 | 71.58 | 100% | 143.04 | 35.67 | 107.37 | 107.37 | 124.9% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2390. - WSP Welded Steel Pipe | 15.11 | 116.83 | 101.72 | 12.93% | 111.5 | 111.5 | 100% | 116.83 | 101.72 | 15.11 | 15.11 | 187.1% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1930. - MC Misc Cleanup | 3 | 20 | 17 | 15% | 16 | 20 | 80% | 16 | 13 | 3.75 | 13 | 135% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2030. - D Demolition | 108.68 | 25 | -83.68 | 434.7% | 45 | 45 | 100% | 25 | -83.68 | 108.68 | 108.68 | -234.7% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1600. - TC Traffic Control | 167.23 | 0 | -167.23 |  | 0 | 0 | 0% | 0 | -167.23 | 167.23 | 167.23 | 0% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.2120. - DIP Ductile Iron Pipe | 0 | -4.8 | -4.8 |  | 21.6 | 24 | 90% | -4.32 | -4.32 | 0 | 0 | 200% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.5100. - W Welding | 14.12 | 20 | 5.88 | 70.6% | 10 | 10 | 100% | 20 | 5.88 | 14.12 | 14.12 | 129.4% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1930. - MC Misc Cleanup | 10 | 20 | 10 | 50% | 20 | 20 | 100% | 20 | 10 | 10 | 10 | 150% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2075. - FG Finish Grade | 13.87 | 31.84 | 17.97 | 43.56% | 26.56 | 26.56 | 100% | 31.84 | 17.97 | 13.87 | 13.87 | 156.4% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2090. - MTL Materials | 44.6 | 35 | -9.6 | 127.4% | 0 | 30 | 0% | 35 | -9.6 | 44.6 | 13.6 | 161.1% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2030. - D Demolition | 188.94 | 203.11 | 14.17 | 93.02% | 189.621 | 210.69 | 90% | 182.799 | -6.141 | 209.9333 | 195.99 | 103.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.3000. - CNC Concrete Work | 41.2 | 90.5 | 49.3 | 45.52% | 60.35 | 221 | 59.46% | 53.8096 | 12.6096 | 69.2925 | 41.2 | 154.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2710. - FWF Flowable Fill | 23.54 | 3 | -20.54 | 784.7% | 6 | 6 | 100% | 3 | -20.54 | 23.54 | 23.54 | -584.7% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1940. - PL Punch List Work | 20.86 | 10 | -10.86 | 208.6% | 30 | 30 | 100% | 10 | -10.86 | 20.86 | 20.86 | -8.6% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2390. - WSP Welded Steel Pipe | 127.55 | 13.75 | -113.8 | 927.6% | 16 | 20 | 80% | 11 | -116.55 | 159.4375 | 127.55 | -727.6% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1200. - HOOK Hook Truck Dumpster Transporting | 9.75 | 2.5 | -7.25 | 390% | 2 | 2.5 | 80% | 2 | -7.75 | 12.1875 | 9.75 | -190% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.2760. - HO Haul Off | 9.77 | 11 | 1.23 | 88.82% | 20.8 | 26 | 80% | 8.8 | -0.97 | 12.2125 | 9.77 | 111.2% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 900.9012. - Re-Work Mechanical | 0 | 0.4 | 0.4 | 0% | 0 | 0.4 | 0% | 0.4 | 0.4 | 0.4 | 0 | 200% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2180. - CATH Cathodic Protection | 18.5 | 72.5 | 54 | 25.52% | 92.5 | 92.5 | 100% | 72.5 | 54 | 18.5 | 18.5 | 174.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.5100. - W Welding | 10.3 | 35.82 | 25.52 | 28.75% | 16.66 | 16.66 | 100% | 35.82 | 25.52 | 10.3 | 10.3 | 171.2% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2390. - WSP Welded Steel Pipe | 19.67 | 87.5 | 67.83 | 22.48% | 50.5 | 120.5 | 74.26% | 64.9816 | 45.3116 | 26.4863 | 19.67 | 177.5% |  | 2026-04-01
2302. - Payson Well #2 Reconstruction | 800.1700. - FS Project Manager | 2 | 40 | 38 | 5% | 40 | 40 | 50% | 20 | 18 | 4 | 40 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 900.9010. - Re-Work Pipe | 3.36 | 0.2 | -3.16 | 1680% | 0.4 | 0.4 | 66.67% | 0.13333 | -3.2267 | 5.04 | 0.2 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 103.46 | 152.5 | 49.04 | 67.84% | 105 | 105 | 40.78% | 62.1845 | -41.2755 | 253.7233 | 152.5 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 357.14 | 0 | -357.14 |  | 0 | 0 | 0% | 0 | -357.14 | 357.14 | 0 | 0% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 900.9005. - Re-Work Surveying | 2 | 2 | 0 | 100% | 1 | 1 | 33.33% | 0.66667 | -1.3333 | 6 | 2 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.2080. - EXS Excavate Structure | 13.5 | 15 | 1.5 | 90% | 0 | 0 | 0% | 15 | 1.5 | 15 | 15 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.1230. - T Transporting | 43.49 | 75 | 31.51 | 57.99% | 75 | 75 | 50% | 37.5 | -5.99 | 86.98 | 75 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1703. - FS Job Site Superintendent | 396.35 | 42 | -354.35 | 943.7% | 0 | 42 | 0% | 42 | -354.35 | 396.35 | 0 | 200% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 200.2800. - Unknown Phase | 0 | 17.5 | 17.5 | 0% | 0 | 0 | 0% | 17.5 | 17.5 | 17.5 | 17.5 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.2750. - Unknown Phase | 214.64 | 29.11 | -185.53 | 737.3% | 29.11 | 29.11 | 50% | 14.555 | -200.085 | 429.28 | 29.11 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1700. - FS Project Manager | 275 | 24 | -251 | 1146% | 3 | 24 | 50% | 12 | -263 | 550 | 3 | 187.5% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 800.1930. - MC Misc Cleanup | 59.07 | 50 | -9.07 | 118.1% | 40 | 40 | 44.44% | 22.2222 | -36.8478 | 132.9075 | 50 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 400.2060. - FE Fencing | 15.7 | 30 | 14.3 | 52.33% | 30 | 30 | 50% | 15 | -0.7 | 31.4 | 30 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 200.2010. - RG Grading (DO NOT USE) | 120.22 | 43.5 | -76.72 | 276.4% | 0 | 0 | 0% | 43.5 | -76.72 | 120.22 | 43.5 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.3000. - CNC Concrete Work | 270.52 | 210 | -60.52 | 128.8% | 543 | 543 | 72.11% | 151.4343 | -119.0857 | 375.141 | 210 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.6500. - P Painting | 83.64 | 50 | -33.64 | 167.3% | 150 | 150 | 75% | 37.5 | -46.14 | 111.52 | 50 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 800.1940. - PL Punch List Work | 120.06 | 75 | -45.06 | 160.1% | 60 | 60 | 44.44% | 33.3333 | -86.7267 | 270.135 | 75 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.7100. - IMP Interior Mech/Piping | 278.01 | 141.34 | -136.67 | 196.7% | 233 | 233 | 62.24% | 87.9741 | -190.0359 | 446.6535 | 141.34 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 50 | 50 | 0% | 60 | 60 | 54.55% | 27.2727 | 27.2727 | 0 | 50 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 200.2030. - Unknown Phase | 36.39 | 84 | 47.61 | 43.32% | 0 | 0 | 0% | 84 | 47.61 | 84 | 84 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.2760. - Unknown Phase | 85.77 | 80 | -5.77 | 107.2% | 80 | 80 | 50% | 40 | -45.77 | 171.54 | 80 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1510. - S Surveying | 169.26 | 100 | -69.26 | 169.3% | 50 | 50 | 33.33% | 33.3333 | -135.9267 | 507.78 | 100 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.7500. - PUMP Pumps/Motors | 0.5 | 20 | 19.5 | 2.5% | 30 | 30 | 60% | 12 | 11.5 | 0.83333 | 20 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 500.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 142.04 | 175.95 | 33.91 | 80.73% | 211.2 | 211.2 | 54.55% | 95.9851 | -46.0549 | 260.373 | 175.95 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.5000. - MET Metals | 4.5 | 24 | 19.5 | 18.75% | 37 | 37 | 60.66% | 14.5574 | 10.0574 | 7.4189 | 24 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 400.3000. - CNC Concrete Work | 21 | 32 | 11 | 65.62% | 66 | 66 | 67.35% | 21.551 | 0.55102 | 31.1818 | 32 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.2010. - RG Grading (DO NOT USE) | 36.7 | 78.75 | 42.05 | 46.6% | 70 | 30 | 47.06% | 37.0588 | 0.35882 | 77.9875 | 78.75 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 900.9012. - Re-Work Mechanical | 6 | 0.2 | -5.8 | 3000% | 0.4 | 0.4 | 66.67% | 0.13333 | -5.8667 | 9 | 0.2 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 160.5310. - Fab Shop Misc Metals Fabrication | 5 | 40 | 35 | 12.5% | 40 | 40 | 50% | 20 | 15 | 10 | 40 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1702. - FS People Superintendent | 159.07 | 0 | -159.07 |  | 0 | 0 | 0% | 0 | -159.07 | 159.07 | 0 | 0% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.7600. - MEQ Mechanical Equipment | 78.26 | 80 | 1.74 | 97.82% | 120 | 120 | 60% | 48 | -30.26 | 130.4333 | 80 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.6300. - DAW Doors & Windows | 26.65 | 20 | -6.65 | 133.2% | 60 | 60 | 75% | 15 | -11.65 | 35.5333 | 20 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.2800. - BFST Backfill (DO NOT USE) | 0 | 80 | 80 | 0% | 0 | 0 | 0% | 80 | 80 | 80 | 80 | 100% |  | 2024-03-15
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1700. - FS Project Manager | 158.37 | 50 | -108.37 | 316.7% | 0 | 50 | 0% | 50 | -108.37 | 158.37 | 50 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.2930. - AP Asphalt Prep (DO NOT USE) | 17.5 | 27.5 | 10 | 63.64% | 0 | 30 | 0% | 27.5 | 10 | 27.5 | 27.5 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.6500. - P Painting | 1451.87 | 135 | -1316.87 | 1075% | 1 | 405 | 0.5556% | 0.75 | -1451.12 | 261336.6 | 135 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 800.1930. - MC Misc Cleanup | 24.18 | 125 | 100.82 | 19.34% | 0 | 100 | 0% | 125 | 100.82 | 125 | 125 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 310.3000. - CNC Concrete Work | 129.12 | 0 | -129.12 |  | 0 | 0 | 0% | 0 | -129.12 | 129.12 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 8 | 0 | -8 |  | 0 | 0 | 0% | 0 | -8 | 8 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1703. - FS Job Site Superintendent | 42.24 | 0 | -42.24 |  | 0 | 0 | 0% | 0 | -42.24 | 42.24 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2030. - Unknown Phase | 27.54 | 22 | -5.54 | 125.2% | 0 | 27 | 0% | 22 | -5.54 | 27.54 | 22 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1220. - TD Tempoary Toilets for Job Site | 31.02 | 0 | -31.02 |  | 0 | 0 | 0% | 0 | -31.02 | 31.02 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2080. - EXS Excavate Structure | 271.06 | 904 | 632.94 | 29.98% | 0 | 328 | 0% | 904 | 632.94 | 904 | 129 | 185.7% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.3000. - Unknown Phase | 498.37 | 197 | -301.37 | 253% | 0 | 433 | 0% | 197 | -301.37 | 498.37 | 172 | 112.7% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 150.2760. - Unknown Phase | 238.08 | 108 | -130.08 | 220.4% | 0 | 108 | 0% | 108 | -130.08 | 238.08 | 50 | 153.7% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 150.1230. - T Transporting | 395.53 | 150 | -245.53 | 263.7% | 0 | 150 | 0% | 150 | -245.53 | 395.53 | 300 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.7900. - ELC Electrical | 624.36 | 125 | -499.36 | 499.5% | 0 | 150 | 0% | 125 | -499.36 | 624.36 | 125 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 310.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 150.2750. - Unknown Phase | 374.14 | 104.5 | -269.64 | 358% | 0 | 104.5 | 0% | 104.5 | -269.64 | 374.14 | 40.5 | 161.2% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.3000. - CNC Concrete Work | 434.09 | 129 | -305.09 | 336.5% | 0 | 303 | 0% | 129 | -305.09 | 434.09 | 109 | 115.5% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.3000. - CNC Concrete Work | 1091.19 | 115 | -976.19 | 948.9% | 0 | 285 | 0% | 115 | -976.19 | 1091.19 | 100 | 113% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.2800. - BFST Backfill (DO NOT USE) | 289.52 | 70 | -219.52 | 413.6% | 0 | 60 | 0% | 70 | -219.52 | 289.52 | 70 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.7600. - MEQ Mechanical Equipment | 4.23 | 14 | 9.77 | 30.21% | 0 | 28 | 0% | 14 | 9.77 | 14 | 14 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.2000. - SWC Site Work Complete (DO NOT USE) | 468.43 | 85 | -383.43 | 551.1% | 0 | 80 | 0% | 85 | -383.43 | 468.43 | 85 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 210.2000. - SWC Site Work Complete (DO NOT USE) | 325.71 | 178 | -147.71 | 183% | 0 | 236 | 0% | 178 | -147.71 | 325.71 | 0 | 200% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 160.5310. - Fab Shop Misc Metals Fabrication | 51.87 | 0 | -51.87 |  | 0 | 0 | 0% | 0 | -51.87 | 51.87 | 33.24 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.7400. - HVAC HVAC | 3.5 | 5 | 1.5 | 70% | 0 | 15 | 0% | 5 | 1.5 | 5 | 5 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.5100. - W Welding | 3 | 20 | 17 | 15% | 0 | 10 | 0% | 20 | 17 | 20 | 20 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2020. - Unknown Phase | 89.71 | 30 | -59.71 | 299% | 1 | 30 | 3.333% | 1 | -88.71 | 2691.3 | 30 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.5000. - MET Metals | 1.5 | 5 | 3.5 | 30% | 0 | 15 | 0% | 5 | 3.5 | 5 | 5 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1510. - S Surveying | 50.5 | 110 | 59.5 | 45.91% | 0 | 55 | 0% | 110 | 59.5 | 110 | 100 | 109.1% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2800. - Unknown Phase | 249.16 | 35 | -214.16 | 711.9% | 0 | 30 | 0% | 35 | -214.16 | 249.16 | 35 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1702. - FS People Superintendent | 120.78 | 0 | -120.78 |  | 0 | 0 | 0% | 0 | -120.78 | 120.78 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.6900. - EF Roofing | 27.31 | 0 | -27.31 |  | 0 | 0 | 0% | 0 | -27.31 | 27.31 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.5000. - MET Metals | 14 | 0 | -14 |  | 0 | 0 | 0% | 0 | -14 | 14 | 847.5 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.6300. - DAW Doors & Windows | 73.42 | 64 | -9.42 | 114.7% | 0 | 128 | 0% | 64 | -9.42 | 73.42 | 64 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 1006.68 | 320 | -686.68 | 314.6% | 0 | 330 | 0% | 320 | -686.68 | 1006.68 | 505.69 | 41.97% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 800.1940. - PL Punch List Work | 488.62 | 150 | -338.62 | 325.7% | 1 | 120 | 0.7407% | 1.1111 | -487.5089 | 65963.7 | 150 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 161.3000. - CNC Concrete Work | 88.35 | 1844 | 1755.65 | 4.791% | 0 | 160 | 0% | 1844 | 1755.65 | 1844 | 1844 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2060. - Unknown Phase | 5 | 20 | 15 | 25% | 0 | 40 | 0% | 20 | 15 | 20 | 20 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2070. - RGC Rough Grade Cut | 13.68 | 30 | 16.32 | 45.6% | 0 | 30 | 0% | 30 | 16.32 | 30 | 30 | 100% |  | 2023-06-30
2314. - JVWCD AC Mitigation Project | 800.1940. - PL Punch List Work | 23.72 | 50 | 26.28 | 47.44% | 0 | 150 | 0% | 50 | 26.28 | 50 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2930. - AP Asphalt Prep (DO NOT USE) | 16.13 | 120 | 103.87 | 13.44% | 0 | 120 | 0% | 120 | 103.87 | 120 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 100.1702. - FS People Superintendent | 85.92 | 0 | -85.92 |  | 0 | 0 | 0% | 0 | -85.92 | 85.92 | 0 | 0% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 180.2920. - SC Saw Cutting/Coring | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 900.9010. - Re-Work Pipe | 0 | 0.2 | 0.2 | 0% | 0 | 0.4 | 0% | 0.2 | 0.2 | 0.2 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.1600. - TC Traffic Control | 314.93 | 2970 | 2655.07 | 10.6% | 0 | 300 | 0% | 2970 | 2655.07 | 2970 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 900.9100. - Job Related Equipment Repairs | 0 | 1 | 1 | 0% | 0 | 1 | 0% | 1 | 1 | 1 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 900.9005. - Re-Work Surveying | 156.65 | 2 | -154.65 | 7832% | 0 | 1 | 0% | 2 | -154.65 | 156.65 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 100.1700. - FS Project Manager | 58.5 | 110 | 51.5 | 53.18% | 0 | 110 | 0% | 110 | 51.5 | 110 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 390.93 | 841 | 450.07 | 46.48% | 0 | 855 | 0% | 841 | 450.07 | 841 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2800. - Unknown Phase | 35.69 | 166 | 130.31 | 21.5% | 0 | 122 | 0% | 166 | 130.31 | 166 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 100.1703. - FS Job Site Superintendent | 194.35 | 2 | -192.35 | 9718% | 0 | 2 | 0% | 2 | -192.35 | 194.35 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.2080. - EXS Excavate Structure | 42.35 | 192 | 149.65 | 22.06% | 0 | 120 | 0% | 192 | 149.65 | 192 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 150.2760. - Unknown Phase | 18.5 | 58.5 | 40 | 31.62% | 0 | 58.5 | 0% | 58.5 | 40 | 58.5 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2080. - EXS Excavate Structure | 0 | 233 | 233 | 0% | 0 | 151 | 0% | 233 | 233 | 233 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 150.2750. - Unknown Phase | 22.97 | 34.68 | 11.71 | 66.23% | 0 | 34.68 | 0% | 34.68 | 11.71 | 34.68 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2300. - Unknown Phase | 7.22 | -454.75 | -461.97 |  | 0 | 129 | 0% | -454.75 | -461.97 | 7.22 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 62.44 | 246 | 183.56 | 25.38% | 0 | 300 | 0% | 246 | 183.56 | 246 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.1600. - TC Traffic Control | 116.74 | 1908 | 1791.26 | 6.118% | 0 | 208 | 0% | 1908 | 1791.26 | 1908 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.2930. - AP Asphalt Prep (DO NOT USE) | 8.74 | 300 | 291.26 | 2.913% | 0 | 300 | 0% | 300 | 291.26 | 300 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 150.1230. - T Transporting | 67.34 | 165 | 97.66 | 40.81% | 0 | 165 | 0% | 165 | 97.66 | 165 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 300.2800. - BFST Backfill (DO NOT USE) | 76.75 | 0 | -76.75 |  | 0 | 0 | 0% | 0 | -76.75 | 76.75 | 0 | 0% |  | 2024-05-31
2305. - Highland Well #4 Improvements | 200.3000. - Unknown Phase | 752.68 | 311.01 | -441.67 | 242% | 524 | 615.92 | 65.91% | 204.9928 | -547.6872 | 1141.9477 | 271.7 | 112.6% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2010. - RG Grading (DO NOT USE) | 0 | 242.95 | 242.95 | 0% | 123 | 125.62 | 33.88% | 82.3219 | 82.3219 | 0 | 240 | 101.2% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.1510. - S Surveying | 451.6 | 120 | -331.6 | 376.3% | 60 | 60 | 33.33% | 40 | -411.6 | 1354.8 | 120 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2610. - PT Pressure Test/Chlorinating | 46.12 | 17.5 | -28.62 | 263.5% | 20 | 20 | 54.05% | 9.4595 | -36.6605 | 85.322 | 17.5 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9015. - Re-Work Concrete | 65.4 | 0.2 | -65.2 | 32700% | 0 | 0 | 0% | 0.2 | -65.2 | 65.4 | 0.2 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.1700. - FS Project Manager | 4 | 60 | 56 | 6.667% | 60 | 60 | 50% | 30 | 26 | 8 | 60 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9012. - Re-Work Mechanical | 18 | 0.2 | -17.8 | 9000% | 0 | 0 | 0% | 0.2 | -17.8 | 18 | 0.2 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 150.2750. - Unknown Phase | 86.5 | 32.66 | -53.84 | 264.8% | 51 | 55.27 | 60% | 19.596 | -66.904 | 144.1667 | 30.17 | 107.6% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 160.5110. - Fab Shop Pipe Fabrication | 13.53 | 10 | -3.53 | 135.3% | -10 | 10 | 0% | 10 | -3.53 | 13.53 | 0 | 200% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.6300. - DAW Doors & Windows | 141.33 | 32 | -109.33 | 441.7% | 96 | 96 | 75% | 24 | -117.33 | 188.44 | 32 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2080. - EXS Excavate Structure | 3 | 67.85 | 64.85 | 4.422% | 60 | 69.42 | 50% | 33.925 | 30.925 | 6 | 60 | 111.6% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 399.31 | 0 | -399.31 |  | 0 | 0 | 0% | 0 | -399.31 | 399.31 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1700. - FS Project Manager | 286.68 | 0 | -286.68 |  | 0 | 0 | 0% | 0 | -286.68 | 286.68 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2300. - Unknown Phase | 209.94 | 562.25 | 352.31 | 37.34% | 1 | 254 | 0.3906% | 2.1963 | -207.7437 | 53744.64 | 255 | 154.6% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1703. - FS Job Site Superintendent | 640.85 | 0 | -640.85 |  | 0 | 0 | 0% | 0 | -640.85 | 640.85 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 150.2760. - Unknown Phase | 75.6 | 144.14 | 68.54 | 52.45% | 72 | 82.14 | 34.95% | 50.379 | -25.221 | 216.3 | 134 | 107% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.1600. - TC Traffic Control | 80.94 | 165 | 84.06 | 49.05% | 1 | 23.5 | 1.205% | 1.988 | -78.952 | 6718.02 | 82.5 | 150% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2900. - ASPH Asphalt | 40.8 | 13.75 | -27.05 | 296.7% | 1 | 1 | 7.143% | 0.98214 | -39.8179 | 571.2 | 13.75 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.3100. - CNC Rebar | 39.75 | 29 | -10.75 | 137.1% | 24 | 39 | 50% | 14.5 | -25.25 | 79.5 | 24 | 117.2% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9010. - Re-Work Pipe | 12.02 | 0.2 | -11.82 | 6010% | 0 | 0 | 0% | 0.2 | -11.82 | 12.02 | 0.2 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 150.1230. - T Transporting | 130.74 | 75 | -55.74 | 174.3% | 75 | 75 | 50% | 37.5 | -93.24 | 261.48 | 75 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2110. - Unknown Phase | 0 | 16 | 16 | 0% | 16 | 16 | 50% | 8 | 8 | 0 | 0 | 200% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1702. - FS People Superintendent | 203.9 | 0 | -203.9 |  | 0 | 0 | 0% | 0 | -203.9 | 203.9 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.6500. - Unknown Phase | 605.53 | 150 | -455.53 | 403.7% | 300 | 300 | 66.67% | 100 | -505.53 | 908.295 | 150 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2500. - MH Manholes (DO NOT USE) | 12 | 29.26 | 17.26 | 41.01% | 33 | 25 | 49.25% | 14.4116 | 2.4116 | 24.3636 | 33.76 | 84.62% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.5100. - W Welding | 19.55 | 8 | -11.55 | 244.4% | 18 | 18 | 69.23% | 5.5385 | -14.0115 | 28.2389 | 8 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.7100. - IMP Interior Mech/Piping | 120.79 | 217.25 | 96.46 | 55.6% | 327 | 362 | 62.29% | 135.3157 | 14.5257 | 193.9289 | 198.91 | 108.4% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 146.44 | 271.42 | 124.98 | 53.95% | 133 | 141.72 | 34.37% | 93.2787 | -53.1613 | 426.1074 | 254 | 106.4% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.7600. - MEQ Mechanical Equipment | 28.21 | 50 | 21.79 | 56.42% | 150 | 150 | 75% | 37.5 | 9.29 | 37.6133 | 50 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 800.1940. - PL Punch List Work | 16.71 | 150 | 133.29 | 11.14% | 120 | 120 | 44.44% | 66.6667 | 49.9567 | 37.5975 | 150 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2020. - Unknown Phase | 19.7 | 60 | 40.3 | 32.83% | 21 | 21 | 25.93% | 15.5556 | -4.1444 | 75.9857 | 60 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.7400. - HVAC HVAC | 2.65 | 50 | 47.35 | 5.3% | 1 | 1 | 1.961% | 0.98039 | -1.6696 | 135.15 | 50 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.5000. - MET Metals | 36 | 20 | -16 | 180% | 45 | 45 | 69.23% | 13.8462 | -22.1538 | 52 | 20 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | -80 | -80 |  | 40 | -40 | 0% | -80 | -80 | 0 | 0 | 200% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 160.5310. - Fab Shop Misc Metals Fabrication | 6 | 6 | 0 | 100% | 6 | 6 | 50% | 3 | -3 | 12 | 6 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9055. - Re-Work Finishes | 14.59 | 0.1 | -14.49 | 14590% | 0 | 0 | 0% | 0.1 | -14.49 | 14.59 | 0.1 | 100% |  | 2023-12-31
2303. - Provo River Trail 2230 N Improvements | 200.2070. - RGC Rough Grade Cut | 1 | 232.3 | 231.3 | 0.4305% | 0 | 335.96 | 0% | 232.3 | 231.3 | 232.3 | 232.3 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2020. - Unknown Phase | 14.28 | 228 | 213.72 | 6.263% | 0 | 81.6 | 0% | 228 | 213.72 | 228 | 80 | 164.9% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 150.2760. - Unknown Phase | 321.31 | 783.33 | 462.02 | 41.02% | 0 | 783.33 | 0% | 783.33 | 462.02 | 783.33 | 772.33 | 101.4% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 900.9100. - Job Related Equipment Repairs | 31 | 1 | -30 | 3100% | 0 | 1 | 0% | 1 | -30 | 31 | 1 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2310. - WS Water Services (DO NOT USE) | 17.37 | 89 | 71.63 | 19.52% | 0 | 110 | 0% | 89 | 71.63 | 89 | 89 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2080. - EXS Excavate Structure | 8.25 | 20 | 11.75 | 41.25% | 0 | 20 | 0% | 20 | 11.75 | 20 | 20 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 900.9055. - Re-Work Finishes | 0 | 0.1 | 0.1 | 0% | 0 | 0.2 | 0% | 0.1 | 0.1 | 0.1 | 0.1 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1510. - S Surveying | 723.45 | 200 | -523.45 | 361.7% | 0 | 100 | 0% | 200 | -523.45 | 723.45 | 200 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 400.3000. - CNC Concrete Work | 497.94 | 11 | -486.94 | 4527% | 0 | 33 | 0% | 11 | -486.94 | 497.94 | 11 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 300.2010. - RG Grading (DO NOT USE) | 60.38 | 101.52 | 41.14 | 59.48% | 0 | 110.63 | 0% | 101.52 | 41.14 | 101.52 | 101.52 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1702. - FS People Superintendent | 31 | 0 | -31 |  | 0 | 0 | 0% | 0 | -31 | 31 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 400.1650. - SB Signage | 25.9 | 150 | 124.1 | 17.27% | 0 | 225 | 0% | 150 | 124.1 | 150 | 150 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2800. - Unknown Phase | 0 | 50 | 50 | 0% | 0 | 60 | 0% | 50 | 50 | 50 | 50 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1704. - FS Quality Control/Assurance | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.1600. - TC Traffic Control | 446.2 | 1175 | 728.8 | 37.97% | 0 | 255 | 0% | 1175 | 728.8 | 1175 | 0 | 200% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2030. - Unknown Phase | 7 | 1198.48 | 1191.48 | 0.5841% | 0 | 0 | 0% | 1198.48 | 1191.48 | 1198.48 | 599.24 | 150% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 6 | 0 | -6 |  | 0 | 0 | 0% | 0 | -6 | 6 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2300. - Unknown Phase | 97.51 | 0 | -97.51 |  | 0 | 0 | 0% | 0 | -97.51 | 97.51 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1703. - FS Job Site Superintendent | 121 | 0 | -121 |  | 0 | 0 | 0% | 0 | -121 | 121 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 150.2750. - Unknown Phase | 261.83 | 287.92 | 26.09 | 90.94% | 0 | 288.2 | 0% | 287.92 | 26.09 | 287.92 | 266.91 | 107.3% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2000. - Unknown Phase | 616.22 | 1096.8 | 480.58 | 56.18% | 0 | 116.16 | 0% | 1096.8 | 480.58 | 1096.8 | 500 | 154.4% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 300.6900. - EF Roofing | 12 | 40 | 28 | 30% | 0 | 60 | 0% | 40 | 28 | 40 | 40 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 150.1230. - T Transporting | 54.32 | 100 | 45.68 | 54.32% | 0 | 100 | 0% | 100 | 45.68 | 100 | 100 | 100% |  | 2023-06-30
2503. - HVSSD Headworks Upgrade | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 350.38 | 154.17 | -196.21 | 227.3% | 54.6 | 154.17 | 91% | 140.2947 | -210.0853 | 385.033 | 350.63 | -27.43% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 800.1940. - PL Punch List Work | 206.53 | 120 | -86.53 | 172.1% | 18 | 180 | 10% | 12 | -194.53 | 2065.3 | 217.54 | 18.72% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1700. - FS Project Manager | 496.75 | 173.26 | -323.49 | 286.7% | 126.4 | 173.26 | 79% | 136.8754 | -359.8746 | 628.7975 | 484.75 | -79.78% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1703. - FS Job Site Superintendent | 201 | 216.7 | 15.7 | 92.75% | 147.9 | 216.7 | 87% | 188.529 | -12.471 | 231.0345 | 205.5 | 105.2% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1510. - S Surveying | 129.24 | 120 | -9.24 | 107.7% | 20 | 40 | 100% | 120 | -9.24 | 129.24 | 129.24 | 92.3% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.5000. - MET Metals | 81.29 | 108 | 26.71 | 75.27% | 162.5 | 257 | 65% | 70.2 | -11.09 | 125.0615 | 105.77 | 102.1% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.7600. - MEQ Mechanical Equipment | 0 | 105 | 105 | 0% | 105 | 105 | 100% | 105 | 105 | 0 | 0 | 200% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1200. - HOOK Hook Truck Dumpster Transporting | 18 | 5 | -13 | 360% | 7 | 5 | 70% | 3.5 | -14.5 | 25.7143 | 18 | -160% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.2085. - BFST Backfill Structure | 391.59 | 20 | -371.59 | 1958% | 20 | 20 | 100% | 20 | -371.59 | 391.59 | 391.59 | -1758% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.3000. - Unknown Phase | 729.71 | 129.84 | -599.87 | 562% | 490 | 573.42 | 100% | 129.84 | -599.87 | 729.71 | 729.71 | -362% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1702. - FS People Superintendent | 136.93 | 144.42 | 7.49 | 94.81% | 108.75 | 144.42 | 87% | 125.6454 | -11.2846 | 157.3908 | 137.93 | 104.5% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 900.9015. - Re-Work Concrete | 10 | 0.2 | -9.8 | 5000% | 0 | 0.6 | 0% | 0.2 | -9.8 | 10 | 10 | -4800% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 150.2750. - Unknown Phase | 75.14 | 34.67 | -40.47 | 216.7% | 30 | 34.67 | 100% | 34.67 | -40.47 | 75.14 | 83.5 | -40.84% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1706. - FS Executive | 2 | 1 | -1 | 200% | 2 | 1 | 100% | 1 | -1 | 2 | 2 | 0% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 150.1230. - T Transporting | 47.87 | 75 | 27.13 | 63.83% | 23.1 | 75 | 77% | 57.75 | 9.88 | 62.1688 | 47.87 | 136.2% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 300.7700. - SEQ Specialized Equipment | 674.32 | 125 | -549.32 | 539.5% | 425 | 300 | 85% | 106.25 | -568.07 | 793.3176 | 674.32 | -339.5% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.2030. - Unknown Phase | 304.09 | 118 | -186.09 | 257.7% | 60 | 228 | 100% | 118 | -186.09 | 304.09 | 294.09 | -49.23% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 150.2760. - Unknown Phase | 14.16 | 5.12 | -9.04 | 276.6% | 10 | 5.12 | 100% | 5.12 | -9.04 | 14.16 | 5.8 | 86.72% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.7100. - IMP Interior Mech/Piping | 22.47 | 18 | -4.47 | 124.8% | 36 | 54 | 90% | 16.2 | -6.27 | 24.9667 | 22.47 | 75.17% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.2075. - FG Finish Grade | 35.78 | 48 | 12.22 | 74.54% | 40 | 56 | 100% | 48 | 12.22 | 35.78 | 35.78 | 125.5% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 400.7700. - SEQ Specialized Equipment | 457.88 | 80 | -377.88 | 572.3% | 165 | 240 | 100% | 80 | -377.88 | 457.88 | 457.88 | -372.4% |  | 2025-10-15
2304. - Park City 9th & 10th Street Stairs & Waterline | 150.1230. - T Transporting | 180.48 | 100 | -80.48 | 180.5% | 0 | 100 | 0% | 100 | -80.48 | 180.48 | 100 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.1600. - TC Traffic Control | 161.7 | 220 | 58.3 | 73.5% | 0 | 60 | 0% | 220 | 58.3 | 220 | 220 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9005. - Re-Work Surveying | 22 | 2 | -20 | 1100% | 0 | 1 | 0% | 2 | -20 | 22 | 2 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2010. - RG Grading (DO NOT USE) | 1558.88 | 120 | -1438.88 | 1299% | 0 | 120 | 0% | 120 | -1438.88 | 1558.88 | 120 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.3000. - Unknown Phase | 1204.3 | 793.75 | -410.55 | 151.7% | 0 | 1595 | 0% | 793.75 | -410.55 | 1204.3 | 805 | 98.58% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2300. - Unknown Phase | 1376.96 | 1253 | -123.96 | 109.9% | 0 | 825 | 0.07299% | 0.9146 | -1376.0454 | 1886435.2 | 815 | 135% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1703. - FS Job Site Superintendent | 349.38 | 10 | -339.38 | 3494% | 0 | 10 | 0% | 10 | -339.38 | 349.38 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 150.2750. - Unknown Phase | 217.37 | 58.93 | -158.44 | 368.9% | 0 | 58.93 | 1.697% | 1 | -216.37 | 12809.6141 | 58.93 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9010. - Re-Work Pipe | 57.26 | 0.2 | -57.06 | 28630% | 0 | 0.4 | 0% | 0.2 | -57.06 | 57.26 | 0.2 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1700. - FS Project Manager | 78.42 | 15 | -63.42 | 522.8% | 0 | 15 | 0% | 15 | -63.42 | 78.42 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 150.2760. - Unknown Phase | 377.02 | 162.5 | -214.52 | 232% | 0 | 162.5 | 0% | 162.5 | -214.52 | 377.02 | 154 | 105.2% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2080. - EXS Excavate Structure | 381.26 | 815 | 433.74 | 46.78% | 0 | 690 | 0% | 815 | 433.74 | 815 | 815 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2040. - LR Landscaping/Restoration | 74.16 | 390 | 315.84 | 19.02% | 0 | 390 | 0% | 390 | 315.84 | 390 | 390 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9015. - Re-Work Concrete | 0 | 0.2 | 0.2 | 0% | 0 | 0.4 | 0% | 0.2 | 0.2 | 0.2 | 0.2 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2610. - PT Pressure Test/Chlorinating | 38.91 | 52.5 | 13.59 | 74.11% | 0 | 60 | 0% | 52.5 | 13.59 | 52.5 | 52.5 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1520. - TEST Testing 3rd Party Soils/Concrete/Welding/Special | 567.3 | 50 | -517.3 | 1135% | 0 | 0 | 0% | 50 | -517.3 | 567.3 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1702. - FS People Superintendent | 360.25 | 4 | -356.25 | 9006% | 0 | 4 | 0% | 4 | -356.25 | 360.25 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.6500. - Unknown Phase | 116.2 | 30 | -86.2 | 387.3% | 0 | 60 | 0% | 30 | -86.2 | 116.2 | 30 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9100. - Job Related Equipment Repairs | 0 | 1 | 1 | 0% | 0 | 1 | 0% | 1 | 1 | 1 | 1 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.6900. - EF Roofing | 1928.65 | 785 | -1143.65 | 245.7% | 0 | 1325 | 46.83% | 367.6098 | -1561.0402 | 4118.4714 | 770 | 101.9% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9055. - Re-Work Finishes | 116.78 | 0.1 | -116.68 | 116780% | 0 | 0.2 | 0% | 0.1 | -116.68 | 116.78 | 0.1 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2070. - RGC Rough Grade Cut | 26.08 | 120 | 93.92 | 21.73% | 0 | 120 | 0% | 120 | 93.92 | 120 | 120 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9020. - Re-Work Fab | 30.64 | 0.4 | -30.24 | 7660% | 0 | 0.2 | 0% | 0.4 | -30.24 | 30.64 | 0.4 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 800.1940. - PL Punch List Work | 324.96 | 30 | -294.96 | 1083% | 0 | 60 | 0% | 30 | -294.96 | 324.96 | 30 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2020. - Unknown Phase | 576.48 | 120 | -456.48 | 480.4% | 0 | 120 | 0% | 120 | -456.48 | 576.48 | 120 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2310. - WS Water Services (DO NOT USE) | 205.11 | 60 | -145.11 | 341.8% | 0 | 60 | 0% | 60 | -145.11 | 205.11 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 160.5320. - Fab Shop Misc Metals Coatings | 541.34 | 210 | -331.34 | 257.8% | 0 | 420 | 0.4762% | 1 | -540.34 | 113681.4 | 210 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 160.5310. - Fab Shop Misc Metals Fabrication | 380.26 | 1053.64 | 673.38 | 36.09% | 0 | 946.82 | 0.15% | 1.5801 | -378.6799 | 253564.9732 | 1053.64 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 8.55 | 6 | -2.55 | 142.5% | 0 | 6 | 0% | 6 | -2.55 | 8.55 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 800.1930. - MC Misc Cleanup | 331.56 | 75 | -256.56 | 442.1% | 0 | 60 | 0% | 75 | -256.56 | 331.56 | 75 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2800. - Unknown Phase | 396.21 | 175 | -221.21 | 226.4% | 0 | 135 | 0% | 175 | -221.21 | 396.21 | 175 | 100% |  | 2023-11-10
2609. - JVWCD JA-1 Internal Buttstraps | 200.5100. - W Welding | 307.46 | 190 | -117.46 | 161.8% | 10 | 13 | 100% | 190 | -117.46 | 307.46 | 203.38 | 92.96% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1702. - FS People Superintendent | 15 | 6.88 | -8.12 | 218% | 6.88 | 6.88 | 100% | 6.88 | -8.12 | 15 | 14 | -3.488% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 200.7100. - IMP Interior Mech/Piping | 52.95 | 35 | -17.95 | 151.3% | 10 | 10 | 100% | 35 | -17.95 | 52.95 | 52.95 | 48.71% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1704. - FS Quality Control/Assurance | 20 | 3.27 | -16.73 | 611.6% | 3.27 | 3.27 | 100% | 3.27 | -16.73 | 20 | 9 | -75.23% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 800.1940. - PL Punch List Work | 2 | 18 | 16 | 11.11% | 1 | 1 | 100% | 18 | 16 | 2 | 5 | 172.2% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 200.3000. - Unknown Phase | 192.5 | 50 | -142.5 | 385% | 10 | 10 | 100% | 50 | -142.5 | 192.5 | 211.25 | -222.5% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 0 | 7.37 | 7.37 | 0% | 7.37 | 7.37 | 100% | 7.37 | 7.37 | 0 | 0 | 200% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1703. - FS Job Site Superintendent | 59.69 | 9.86 | -49.83 | 605.4% | 9.86 | 9.86 | 100% | 9.86 | -49.83 | 59.69 | 58.69 | -395.2% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 150.1230. - T Transporting | 30.21 | 5 | -25.21 | 604.2% | 1 | 1 | 100% | 5 | -25.21 | 30.21 | 26.58 | -331.6% |  | 2026-04-10
2510. - Draper Pump Station #3 Improvements | 400.3000. - CNC Concrete Work | 43.75 | 32.5 | -11.25 | 134.6% | 0 | 136.5 | 0% | 32.5 | -11.25 | 43.75 | 123.75 | -180.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.9000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1200. - HOOK Hook Truck Dumpster Transporting | 0.36 | 5 | 4.64 | 7.2% | 2.5 | 5 | 50% | 2.5 | 2.14 | 0.72 | 5.36 | 92.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.8000. - HP Helical Piers | 0 | 20 | 20 | 0% | 0 | 30 | 0% | 20 | 20 | 20 | 0 | 200% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1702. - FS People Superintendent | 121.5 | 149.49 | 27.99 | 81.28% | 74.245 | 149.49 | 50% | 74.745 | -46.755 | 243 | 151.5 | 98.66% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.2160. - WSP Welded Steel Pipe <15' Depth | 847.74 | 238.42 | -609.32 | 355.6% | 129.408 | 161.76 | 80% | 190.736 | -657.004 | 1059.675 | 927.74 | -189.1% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.2160. - WSP Welded Steel Pipe <15' Depth | 78.75 | 400.28 | 321.53 | 19.67% | 193.08 | 257.44 | 75% | 300.21 | 221.46 | 105 | 118.75 | 170.3% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.7100. - IMP Interior Mech/Piping | 483.03 | 259.58 | -223.45 | 186.1% | 432.225 | 559.5 | 85% | 220.643 | -262.387 | 568.2706 | 683.03 | -63.13% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1704. - FS Quality Control/Assurance | 17 | 58.78 | 41.78 | 28.92% | 28.89 | 58.78 | 50% | 29.39 | 12.39 | 34 | 37 | 137.1% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1510. - S Surveying | 23.83 | 60 | 36.17 | 39.72% | 5 | 20 | 50% | 30 | 6.17 | 47.66 | 33.83 | 143.6% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 188.5 | 162.14 | -26.36 | 116.3% | 80.57 | 162.14 | 50% | 81.07 | -107.43 | 377 | 198.5 | 77.57% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.5100. - W Welding | 40.35 | 28.14 | -12.21 | 143.4% | 14.07 | 14.07 | 100% | 28.14 | -12.21 | 40.35 | 40.35 | 56.61% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1703. - FS Job Site Superintendent | 115.5 | 223.92 | 108.42 | 51.58% | 111.46 | 223.92 | 50% | 111.96 | -3.54 | 231 | 242.5 | 91.7% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.2080. - EXS Excavate Structure | 646.02 | 60.5 | -585.52 | 1068% | 20.375 | 40.75 | 50% | 30.25 | -615.77 | 1292.04 | 726.02 | -1000% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 150.2750. - Unknown Phase | 18.66 | 30.66 | 12 | 60.86% | 15.33 | 30.66 | 50% | 15.33 | -3.33 | 37.32 | 40.66 | 67.38% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.2030. - Unknown Phase | 0 | 8 | 8 | 0% | 6 | 6 | 100% | 8 | 8 | 0 | 10 | 75% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1700. - FS Project Manager | 254.32 | 183.01 | -71.31 | 139% | 88.505 | 183.01 | 50% | 91.505 | -162.815 | 508.64 | 278.32 | 47.92% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.2240. - PCS Precast Structures | 0 | 162.35 | 162.35 | 0% | 0 | 91.52 | 0% | 162.35 | 162.35 | 162.35 | 150 | 107.6% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.1800. - PH Potholing | 7.98 | 10 | 2.02 | 79.8% | 15 | 15 | 100% | 10 | 2.02 | 7.98 | 7.98 | 120.2% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.3000. - Unknown Phase | 254.5 | 48.02 | -206.48 | 530% | 178.56 | 178.56 | 100% | 48.02 | -206.48 | 254.5 | 354.5 | -538.2% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.7100. - IMP Interior Mech/Piping | 1 | 41.25 | 40.25 | 2.424% | 52.5 | 105 | 50% | 20.625 | 19.625 | 2 | 21 | 149.1% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 500.5000. - MET Metals | 49.49 | 0 | -49.49 |  | 0 | 1 | 0% | 0 | -49.49 | 49.49 | 49.49 | 0% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 150.1230. - T Transporting | 233.06 | 100 | -133.06 | 233.1% | 50 | 100 | 50% | 50 | -183.06 | 466.12 | 293.06 | -93.06% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.3000. - CNC Concrete Work | 29 | 27.5 | -1.5 | 105.5% | 60.75 | 121.5 | 50% | 13.75 | -15.25 | 58 | 49 | 21.82% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.2085. - BFST Backfill Structure | 140.23 | 1.5 | -138.73 | 9349% | 1.8 | 3 | 60% | 0.9 | -139.33 | 233.7167 | 180.23 | -11815% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 150.2760. - Unknown Phase | 26.61 | 8.95 | -17.66 | 297.3% | 0 | 8.95 | 0% | 8.95 | -17.66 | 26.61 | 46.61 | -320.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.1600. - TC Traffic Control | 178.45 | 860 | 681.55 | 20.75% | 36 | 60 | 60% | 516 | 337.55 | 297.4167 | 926.45 | 92.27% |  | 2026-03-15
2450. - Fab Shop Jobs 2024 Projects | 408.5970. - FAB Fab Shop Misc. Metals Paint | 0 | 48 | 48 | 0% | 0 | 48 | 0% | 48 | 48 | 48 | 40 | 116.7%
2450. - Fab Shop Jobs 2024 Projects | 408.5960. - FAB Fab Shop Misc. Metals Fabrication | 298.29 | 1183 | 884.71 | 25.21% | 0 | 1183 | 0% | 1183 | 884.71 | 1183 | 912.29 | 122.9%
2450. - Fab Shop Jobs 2024 Projects | 407.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 868 | 210 | -658 | 413.3% | 0 | 210 | 0% | 210 | -658 | 868 | 868 | -213.3%
2450. - Fab Shop Jobs 2024 Projects | 403.5950. - FAB Fab Shop WSP Paint | 61.42 | 5 | -56.42 | 1228% | 0 | 15 | 0% | 5 | -56.42 | 61.42 | 61.42 | -1028%
2450. - Fab Shop Jobs 2024 Projects | 403.5960. - FAB Fab Shop Misc. Metals Fabrication | 5.66 | 0 | -5.66 |  | 0 | 0 | 0% | 0 | -5.66 | 5.66 | 5.66 | 0%
2450. - Fab Shop Jobs 2024 Projects | 404.5960. - FAB Fab Shop Misc. Metals Fabrication | 20 | 80 | 60 | 25% | 0 | 40 | 0% | 80 | 60 | 80 | 20 | 175%
2450. - Fab Shop Jobs 2024 Projects | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 6.39 | 10 | 3.61 | 63.9% | 0 | 10 | 0% | 10 | 3.61 | 10 | 6.39 | 136.1%
2450. - Fab Shop Jobs 2024 Projects | 408.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 1251 | 853 | -398 | 146.7% | 0 | 853 | 0% | 853 | -398 | 1251 | 1233 | 55.45%
2450. - Fab Shop Jobs 2024 Projects | 409.5995. - FAB Fab Shop Change Orders | 102.79 | 0 | -102.79 |  | 0 | 0 | 0% | 0 | -102.79 | 102.79 | 109.79 | 0%
2450. - Fab Shop Jobs 2024 Projects | 409.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 819.76 | 58 | -761.76 | 1413% | 0 | 58 | 0% | 58 | -761.76 | 819.76 | 819.76 | -1213%
2450. - Fab Shop Jobs 2024 Projects | 404.5940. - FAB Fab Shop WSP Fabrication | 184.61 | 210 | 25.39 | 87.91% | 0 | 105 | 0% | 210 | 25.39 | 210 | 184.61 | 112.1%
2450. - Fab Shop Jobs 2024 Projects | 407.5960. - FAB Fab Shop Misc. Metals Fabrication | 517.51 | 767 | 249.49 | 67.47% | 0 | 769 | 0% | 767 | 249.49 | 767 | 517.51 | 132.5%
2450. - Fab Shop Jobs 2024 Projects | 100.5900. - FAB Fab Shop | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2450. - Fab Shop Jobs 2024 Projects | 403.5940. - FAB Fab Shop WSP Fabrication | 113.38 | 80 | -33.38 | 141.7% | 0 | 40 | 0% | 80 | -33.38 | 113.38 | 113.38 | 58.27%
2450. - Fab Shop Jobs 2024 Projects | 404.5995. - FAB Fab Shop Change Orders | 54.24 | 0 | -54.24 |  | 0 | 0 | 0% | 0 | -54.24 | 54.24 | 54.24 | 0%
2450. - Fab Shop Jobs 2024 Projects | 409.5960. - FAB Fab Shop Misc. Metals Fabrication | 496.46 | 710 | 213.54 | 69.92% | 0 | 355 | 0% | 710 | 213.54 | 710 | 496.46 | 130.1%
2450. - Fab Shop Jobs 2024 Projects | 403.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 29.48 | 0 | -29.48 |  | 0 | 0 | 0% | 0 | -29.48 | 29.48 | 29.48 | 0%
2450. - Fab Shop Jobs 2024 Projects | 406.5901. - FAB 2406 Management/Design/QC | 94 | 10 | -84 | 940% | 0 | 68 | 0% | 10 | -84 | 94 | 94 | -740%
2450. - Fab Shop Jobs 2024 Projects | 404.5970. - FAB Fab Shop Misc. Metals Paint | 5.94 | 7 | 1.06 | 84.86% | 0 | 15 | 0% | 7 | 1.06 | 7 | 5.94 | 115.1%
2450. - Fab Shop Jobs 2024 Projects | 404.5935. - FAB Fab Shop Deliveries | 3 | 20 | 17 | 15% | 0 | 20 | 0% | 20 | 17 | 20 | 3 | 185%
2450. - Fab Shop Jobs 2024 Projects | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 16 | 0 | -16 |  | 0 | 0 | 0% | 0 | -16 | 16 | 16 | 0%
2450. - Fab Shop Jobs 2024 Projects | 100.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2450. - Fab Shop Jobs 2024 Projects | 406.5995. - FAB Fab Shop Change Orders | 38.12 | 0 | -38.12 |  | 0 | 0 | 0% | 0 | -38.12 | 38.12 | 38.12 | 0%
2450. - Fab Shop Jobs 2024 Projects | 407.5995. - FAB Fab Shop Change Orders | 304.55 | 0 | -304.55 |  | 0 | 0 | 0% | 0 | -304.55 | 304.55 | 266.12 | 0%
2450. - Fab Shop Jobs 2024 Projects | 408.5940. - FAB Fab Shop WSP Fabrication | 735.23 | 1335 | 599.77 | 55.07% | 0 | 1335 | 0% | 1335 | 599.77 | 1335 | 882.81 | 133.9%
2450. - Fab Shop Jobs 2024 Projects | 406.5960. - FAB Fab Shop Misc. Metals Fabrication | 15.76 | 98 | 82.24 | 16.08% | 0 | 49 | 0% | 98 | 82.24 | 98 | 15.76 | 183.9%
2450. - Fab Shop Jobs 2024 Projects | 403.5970. - FAB Fab Shop Misc. Metals Paint | 2 | 3 | 1 | 66.67% | 0 | 6 | 0% | 3 | 1 | 3 | 2 | 133.3%
2450. - Fab Shop Jobs 2024 Projects | 407.5935. - FAB Fab Shop Deliveries | 4 | 60 | 56 | 6.667% | 0 | 60 | 0% | 60 | 56 | 60 | 4 | 193.3%
2450. - Fab Shop Jobs 2024 Projects | 404.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 283.67 | 65 | -218.67 | 436.4% | 0 | 65 | 0% | 65 | -218.67 | 283.67 | 283.67 | -236.4%
2450. - Fab Shop Jobs 2024 Projects | 404.5950. - FAB Fab Shop WSP Paint | 109.61 | 120 | 10.39 | 91.34% | 0 | 360 | 0% | 120 | 10.39 | 120 | 109.61 | 108.7%
2450. - Fab Shop Jobs 2024 Projects | 409.5970. - FAB Fab Shop Misc. Metals Paint | 65.33 | 261 | 195.67 | 25.03% | 0 | 523 | 0% | 261 | 195.67 | 261 | 65.33 | 175%
2407. - So SLC Lift Station | 150.2760. - Unknown Phase | 431.78 | 256.93 | -174.85 | 168.1% | 484.938 | 229.15 | 90% | 231.237 | -200.543 | 479.7556 | 531.35 | -6.807% |  | 2026-03-31
2407. - So SLC Lift Station | 150.2750. - Unknown Phase | 430.04 | 189.88 | -240.16 | 226.5% | 119.594 | 175.6 | 65% | 123.4225 | -306.6175 | 661.5972 | 412.39 | -17.18% |  | 2026-03-31
2407. - So SLC Lift Station | 900.9010. - Re-Work Pipe | 93.6 | 0.2 | -93.4 | 46800% | 0 | 0.6 | 0% | 0.2 | -93.4 | 93.6 | 93.6 | -46600% |  | 2026-03-31
2407. - So SLC Lift Station | 700.2075. - FG Finish Grade | 120.08 | 165 | 44.92 | 72.78% | 0 | 180.6 | 0% | 165 | 44.92 | 165 | 280 | 30.3% |  | 2026-03-31
2407. - So SLC Lift Station | 600.3000. - CNC Concrete Work | 111.41 | 79.4 | -32.01 | 140.3% | 100.87 | 137.47 | 100% | 79.4 | -32.01 | 111.41 | 118.2 | 51.13% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1703. - FS Job Site Superintendent | 2010.8 | 1327 | -683.8 | 151.5% | 0.87 | 1327 | 87% | 1154.49 | -856.31 | 2311.2644 | 2607.06 | 3.537% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2065. - SFC SWPPP | 10.58 | 142.95 | 132.37 | 7.401% | 107.7 | 168 | 75% | 107.2122 | 96.6322 | 14.1067 | 30.58 | 178.6% |  | 2026-03-31
2407. - So SLC Lift Station | 500.5000. - MET Metals | 185.28 | 206.73 | 21.45 | 89.62% | 39.947 | 159.79 | 25% | 51.6819 | -133.5981 | 741.1281 | 241.28 | 83.29% |  | 2026-03-31
2407. - So SLC Lift Station | 100.9990. - OH Tools/Safety Allocation | 27.34 | 0 | -27.34 |  | 0 | 0 | 75% | 0 | -27.34 | 36.4533 | 27.34 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 400.5000. - MET Metals | 158.3 | 794.35 | 636.05 | 19.93% | 249.914 | 603.29 | 64% | 508.3844 | 350.0844 | 247.3436 | 193.47 | 175.6% |  | 2026-03-31
2407. - So SLC Lift Station | 500.7600. - MEQ Mechanical Equipment | 30.02 | 100 | 69.98 | 30.02% | 0 | 150 | 0% | 100 | 69.98 | 100 | 30.02 | 170% |  | 2026-03-31
2407. - So SLC Lift Station | 400.7500. - PUMP Pumps/Motors | 74.34 | 214.01 | 139.67 | 34.74% | 147 | 125 | 100% | 214.0106 | 139.6706 | 74.3398 | 74.34 | 165.3% |  | 2026-03-31
2407. - So SLC Lift Station | 200.7100. - IMP Interior Mech/Piping | 268.41 | 502 | 233.59 | 53.47% | 187.5 | 756 | 25% | 125.5 | -142.91 | 1073.64 | 438.2 | 112.7% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2240. - PCS Precast Structures | 148.1 | 93.33 | -54.77 | 158.7% | 116.784 | 129.76 | 90% | 83.997 | -64.103 | 164.5556 | 238.1 | -55.12% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2140. - SVR Services | 202.96 | 87.5 | -115.46 | 232% | 41.25 | 75 | 55% | 48.125 | -154.835 | 369.0182 | 88 | 99.43% |  | 2026-03-31
2407. - So SLC Lift Station | 150.1230. - T Transporting | 415.63 | 460 | 44.37 | 90.35% | 140 | 460 | 70% | 322 | -93.63 | 593.7571 | 458.9 | 100.2% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2450. - Unknown Phase | 63.53 | 393.26 | 329.73 | 16.15% | 3 | 198.21 | 100% | 393.26 | 329.73 | 63.53 | 63.53 | 183.8% |  | 2026-03-31
2407. - So SLC Lift Station | 200.5400. - HAT Hatch/Skylights | 31.42 | 6 | -25.42 | 523.7% | 11.76 | 12 | 98% | 5.88 | -25.54 | 32.0612 | 69.42 | -957% |  | 2026-03-31
2407. - So SLC Lift Station | 500.3000. - CNC Concrete Work | 4 | 0 | -4 |  | 0 | 2085.51 | 95% | 0 | -4 | 4.2105 | 4 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 300.7100. - IMP Interior Mech/Piping | 0 | 203.33 | 203.33 | 0% | 225 | 310 | 75% | 152.4975 | 152.4975 | 0 | 0 | 200% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2080. - EXS Excavate Structure | 171.43 | 136 | -35.43 | 126.1% | 1038 | 1227 | 100% | 136 | -35.43 | 171.43 | 171.43 | 73.95% |  | 2026-03-31
2407. - So SLC Lift Station | 500.7700. - SEQ Specialized Equipment | 60.53 | 86 | 25.47 | 70.38% | 105.78 | 129 | 100% | 86 | 25.47 | 60.53 | 60.53 | 129.6% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1108. - TF Setup Staging Area Laydown Yard | 0 | 18 | 18 | 0% | 16.2 | 18 | 90% | 16.2 | 16.2 | 0 | 0 | 200% |  | 2026-03-31
2407. - So SLC Lift Station | 400.6500. - P Painting | 0 | 33.3 | 33.3 | 0% | 422.475 | 39.9 | 25% | 8.325 | 8.325 | 0 | 0 | 200% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2030. - Unknown Phase | 313.1 | 421.56 | 108.46 | 74.27% | 321.42 | 321.42 | 100% | 421.56 | 108.46 | 313.1 | 338.1 | 119.8% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2085. - BFST Backfill Structure | 561.55 | 3 | -558.55 | 18718% | 264.306 | 6 | 97% | 2.91 | -558.64 | 578.917 | 761.55 | -25185% |  | 2026-03-31
2407. - So SLC Lift Station | 200.5000. - MET Metals | 46.94 | 56 | 9.06 | 83.82% | 33.3 | 29 | 73.3% | 41.0491 | -5.8909 | 64.0366 | 95.82 | 28.89% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1200. - HOOK Hook Truck Dumpster Transporting | 58.1 | 35 | -23.1 | 166% | 29.05 | 35 | 83% | 29.05 | -29.05 | 70 | 86.57 | -47.34% |  | 2026-03-31
2407. - So SLC Lift Station | 200.7900. - ELC Electrical | 452.3 | 75 | -377.3 | 603.1% | 80 | 100 | 80% | 60 | -392.3 | 565.375 | 433.78 | -378.4% |  | 2026-03-31
2407. - So SLC Lift Station | 800.1940. - PL Punch List Work | 4 | 150 | 146 | 2.667% | 0 | 225 | 0% | 150 | 146 | 150 | 150.83 | 99.45% |  | 2026-03-31
2407. - So SLC Lift Station | 400.3000. - CNC Concrete Work | 0 | 200 | 200 | 0% | 4856.36 | 4856.36 | 95.25% | 190.5068 | 190.5068 | 0 | 0 | 200% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1702. - FS People Superintendent | 427.11 | 675 | 247.89 | 63.28% | 0.75 | 675 | 75% | 506.25 | 79.14 | 569.48 | 540.86 | 119.9% |  | 2026-03-31
2407. - So SLC Lift Station | 400.7100. - IMP Interior Mech/Piping | 592.32 | 990.83 | 398.51 | 59.78% | 557.375 | 1592.5 | 35% | 346.7907 | -245.5293 | 1692.3419 | 577.05 | 141.8% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1501. - SM Safety Meetings | 12.5 | 0 | -12.5 |  | 3.75 | 15 | 75% | 0 | -12.5 | 16.6667 | 132.5 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2220. - ADS Pipe | 481.04 | 483.36 | 2.32 | 99.52% | 207.144 | 230.16 | 90% | 435.024 | -46.016 | 534.4889 | 581.04 | 79.79% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2081. - SHOR Shoring | 206.37 | 0 | -206.37 |  | 0 | 0 | 0% | 0 | -206.37 | 206.37 | 206.37 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2120. - DIP Ductile Iron Pipe | 794.7 | 1577.1 | 782.4 | 50.39% | 500.8 | 626 | 80% | 1261.68 | 466.98 | 993.375 | 758.87 | 151.9% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2130. - PVC Pipe | 42.35 | 258 | 215.65 | 16.41% | 117 | 130 | 90% | 232.2 | 189.85 | 47.0556 | 256.16 | 100.7% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1704. - FS Quality Control/Assurance | 10 | 129 | 119 | 7.752% | 0.4 | 129 | 40% | 51.6 | 41.6 | 25 | 100 | 122.5% |  | 2026-03-31
2407. - So SLC Lift Station | 400.6300. - DAW Doors & Windows | 15 | 29 | 14 | 51.72% | 0 | 87 | 0% | 29 | 14 | 29 | 20 | 131% |  | 2026-03-31
2407. - So SLC Lift Station | 200.6500. - Unknown Phase | 0 | 60 | 60 | 0% | 0 | 60 | 0% | 60 | 60 | 60 | 0 | 200% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1510. - S Surveying | 214.86 | 360 | 145.14 | 59.68% | 150 | 220 | 75% | 270 | 55.14 | 286.48 | 348.28 | 103.3% |  | 2026-03-31
2407. - So SLC Lift Station | 800.1930. - MC Misc Cleanup | 22.37 | 100 | 77.63 | 22.37% | 30 | 300 | 10% | 10 | -12.37 | 223.7 | 100 | 100% |  | 2026-03-31
2407. - So SLC Lift Station | 200.3000. - Unknown Phase | 21.24 | 89 | 67.76 | 23.87% | 10.6 | 215 | 5% | 4.45 | -16.79 | 424.8 | 21.24 | 176.1% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2060. - Unknown Phase | 11.98 | 18 | 6.02 | 66.56% | 24 | 24 | 100% | 18 | 6.02 | 11.98 | 15.88 | 111.8% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2120. - DIP Ductile Iron Pipe | 45.18 | 378.9 | 333.72 | 11.92% | 201.48 | 235 | 92% | 348.588 | 303.408 | 49.1087 | 370 | 102.3% |  | 2026-03-31
2407. - So SLC Lift Station | 160.5000. - Unknown Phase | 164.43 | 0 | -164.43 |  | 0 | 0 | 30% | 0 | -164.43 | 548.1 | 155.88 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 180.2081. - SHOR Shoring | 0 | 0 | 0 |  | 0 | 6 | 100% | 0 | 0 | 0 | 0 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 500.7100. - IMP Interior Mech/Piping | 40.66 | 95 | 54.34 | 42.8% | 49.875 | 142.5 | 35% | 33.25 | -7.41 | 116.1714 | 95 | 100% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1033.64 | 836 | -197.64 | 123.6% | 0.75 | 836 | 75% | 627 | -406.64 | 1378.1867 | 1319.25 | 42.19% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2080. - EXS Excavate Structure | 74.94 | 1109.38 | 1034.44 | 6.755% | 132.704 | 165.88 | 79.7% | 884.1785 | 809.2385 | 94.0273 | 25 | 197.7% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1700. - FS Project Manager | 1761.5 | 955 | -806.5 | 184.5% | 0.75 | 955 | 75% | 716.25 | -1045.25 | 2348.6667 | 2055.5 | -15.24% |  | 2026-03-31
2407. - So SLC Lift Station | 700.3000. - CNC Concrete Work | 25 | 41.9 | 16.9 | 59.67% | 0 | 99.38 | 7.414% | 3.1066 | -21.8934 | 337.1838 | 100 | -38.66% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2600. - DW Dewatering | 1086.68 | 50 | -1036.68 | 2173% | 45 | 50 | 90% | 45 | -1041.68 | 1207.4222 | 1081.5 | -1963% |  | 2026-03-31
2217. - Bluffdale Day Ranch Park | 100.1703. - FS Job Site Superintendent | 477.19 | 0 | -477.19 |  | 0 | 0 | 0% | 0 | -477.19 | 477.19 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2930. - AP Asphalt Prep (DO NOT USE) | 1138.79 | 223.11 | -915.68 | 510.4% | 80 | 291 | 50% | 111.555 | -1027.235 | 2277.58 | 202.76 | 109.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 800.1940. - PL Punch List Work | 186.95 | 342.5 | 155.55 | 54.58% | 0 | 185 | 0% | 342.5 | 155.55 | 342.5 | 312.5 | 108.8% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 3684.18 | 1573.01 | -2111.17 | 234.2% | 600.8 | 938 | 100% | 1573.01 | -2111.17 | 3684.18 | 2310.45 | 53.12% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 800.1930. - MC Misc Cleanup | 170.94 | 385 | 214.06 | 44.4% | 0 | 510 | 0% | 385 | 214.06 | 385 | 300 | 122.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.3000. - CNC Concrete Work | 101.76 | 130 | 28.24 | 78.28% | 0 | 260 | 0% | 130 | 28.24 | 130 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2900. - ASPH Asphalt | 176.68 | 6.28 | -170.4 | 2813% | 0 | 6 | 0% | 6.28 | -170.4 | 176.68 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2610. - PT Pressure Test/Chlorinating | 0 | 19.25 | 19.25 | 0% | 0 | 22 | 0% | 19.25 | 19.25 | 19.25 | 17.5 | 109.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.7100. - IMP Interior Mech/Piping | 137.15 | 10 | -127.15 | 1372% | 0 | 20 | 0% | 10 | -127.15 | 137.15 | 10 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.6900. - EF Roofing | 399.52 | 285.89 | -113.63 | 139.7% | 0 | 540.28 | 0% | 285.89 | -113.63 | 399.52 | 280.75 | 101.8% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.3000. - CNC Concrete Work | 3459.24 | 437.94 | -3021.3 | 789.9% | 0 | 880.11 | 0% | 437.94 | -3021.3 | 3459.24 | 326.33 | 125.5% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2010. - RG Grading (DO NOT USE) | 0 | 174.94 | 174.94 | 0% | 0 | 163 | 0% | 174.94 | 174.94 | 174.94 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2050. - RW Retaining Walls | 485.17 | 268 | -217.17 | 181% | 212 | 268 | 40% | 107.2 | -377.97 | 1212.925 | 265 | 101.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2080. - EXS Excavate Structure | 1250.52 | 413.75 | -836.77 | 302.2% | 90.6 | 463 | 10.58% | 43.7918 | -1206.7282 | 11815.0675 | 403.75 | 102.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2030. - Unknown Phase | 34.88 | 83.88 | 49 | 41.58% | 25 | 55 | 39.68% | 33.2857 | -1.5943 | 87.8976 | 38.25 | 154.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 150.2760. - Unknown Phase | 207.97 | 87.58 | -120.39 | 237.5% | 23.2 | 87.5 | 134.1% | 117.4302 | -90.5398 | 155.105 | 30.66 | 165% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 150.2750. - Unknown Phase | 2558.15 | 421.95 | -2136.2 | 606.3% | 184.45 | 428.26 | 70% | 295.365 | -2262.785 | 3654.5 | 1582.71 | -175.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 150.1230. - T Transporting | 1004.34 | 345 | -659.34 | 291.1% | 60 | 345 | 10% | 34.5 | -969.84 | 10043.4 | 315.84 | 108.5% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2300. - Unknown Phase | 11485.18 | 1009.74 | -10475.44 | 1137% | 627.3 | 1152 | 32.1% | 324.0777 | -11161.1023 | 35784.767 | 908.33 | 110% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1700. - FS Project Manager | 2213.92 | 350 | -1863.92 | 632.5% | 54 | 350 | 16.67% | 58.3333 | -2155.5867 | 13283.52 | 270 | 122.9% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9010. - Re-Work Pipe | 6 | 0.2 | -5.8 | 3000% | 0 | 1 | 0% | 0.2 | -5.8 | 6 | 0.2 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9005. - Re-Work Surveying | 97 | 0 | -97 |  | 0 | 0 | 0% | 0 | -97 | 97 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.1600. - TC Traffic Control | 194.59 | 1100 | 905.41 | 17.69% | 90 | 300 | 7.563% | 83.1933 | -111.3967 | 2572.9122 | 1100 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2010. - RG Grading (DO NOT USE) | 7099.79 | 3255.59 | -3844.2 | 218.1% | 2487.6 | 2832 | 42.16% | 1372.4124 | -5727.3776 | 16841.88 | 3581.19 | 90% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.3000. - CNC Concrete Work | 36 | 460 | 424 | 7.826% | 0 | 640 | 0% | 460 | 424 | 460 | 460 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 93.34 | 0 | -93.34 |  | 0 | 0 | 0% | 0 | -93.34 | 93.34 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9055. - Re-Work Finishes | 5.15 | 0.1 | -5.05 | 5150% | 0 | 1 | 0% | 0.1 | -5.05 | 5.15 | 0.1 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1702. - FS People Superintendent | 412.36 | 0 | -412.36 |  | 0 | 0 | 0% | 0 | -412.36 | 412.36 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.7600. - MEQ Mechanical Equipment | 2107.63 | 1770 | -337.63 | 119.1% | 0 | 1770 | 0% | 1770 | -337.63 | 2107.63 | 1770 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.7100. - IMP Interior Mech/Piping | 9.82 | 50 | 40.18 | 19.64% | 0 | 60 | 0% | 50 | 40.18 | 50 | 50 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.2040. - LR Landscaping/Restoration | 1465.14 | 0 | -1465.14 |  | 0 | 0 | 0% | 0 | -1465.14 | 1465.14 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.3500. - Unknown Phase | 0 | 42 | 42 | 0% | 0 | 126 | 0% | 42 | 42 | 42 | 42 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.2080. - EXS Excavate Structure | 58.1 | 70 | 11.9 | 83% | 42 | 60 | 32.31% | 22.6154 | -35.4846 | 179.8333 | 70 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.5100. - W Welding | 233.63 | 141 | -92.63 | 165.7% | 0 | 118 | 0% | 141 | -92.63 | 233.63 | 116 | 117.7% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9015. - Re-Work Concrete | 382.89 | 0.2 | -382.69 | 191445% | 0 | 1 | 0% | 0.2 | -382.69 | 382.89 | 0.2 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.5400. - HAT Hatch/Skylights | 54.63 | 32 | -22.63 | 170.7% | 0 | 24 | 0% | 32 | -22.63 | 54.63 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.6500. - Unknown Phase | 703.97 | 73 | -630.97 | 964.3% | 0 | 146 | 0% | 73 | -630.97 | 703.97 | 70 | 104.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2040. - LR Landscaping/Restoration | 346.89 | 0 | -346.89 |  | 0 | 0 | 0% | 0 | -346.89 | 346.89 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.5110. - Fab Shop Pipe Fabrication | 253.86 | 0 | -253.86 |  | 0 | 0 | 0% | 0 | -253.86 | 253.86 | 56.06 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 47.5 | 0 | -47.5 |  | 0 | 0 | 0% | 0 | -47.5 | 47.5 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 260.3000. - CNC Concrete Work | 48.55 | 160 | 111.45 | 30.34% | 0 | 350 | 0% | 160 | 111.45 | 160 | 160 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2500. - MH Manholes (DO NOT USE) | 0 | 20 | 20 | 0% | 0 | 30 | 0% | 20 | 20 | 20 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2800. - Unknown Phase | 761.72 | 533.44 | -228.28 | 142.8% | 0 | 538.19 | 0% | 533.44 | -228.28 | 761.72 | 510 | 104.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.5210. - Fab Shop Structural Steel Fabrication | 159.17 | 87.5 | -71.67 | 181.9% | 0 | 150 | 0% | 87.5 | -71.67 | 159.17 | 87.5 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2020. - Unknown Phase | 3936.94 | 522 | -3414.94 | 754.2% | 198 | 198 | 27.5% | 143.55 | -3793.39 | 14316.1455 | 522 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2080. - EXS Excavate Structure | 36.72 | 90 | 53.28 | 40.8% | 0 | 90 | 0% | 90 | 53.28 | 90 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 478.22 | 511.98 | 33.76 | 93.41% | 281.4 | 475 | 28.56% | 146.2206 | -331.9994 | 1674.4498 | 507.1 | 101% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 159.96 | 156.25 | -3.71 | 102.4% | 0 | 105 | 0% | 156.25 | -3.71 | 159.96 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2800. - BFST Backfill (DO NOT USE) | 443.48 | 17.5 | -425.98 | 2534% | 0 | 15 | 0% | 17.5 | -425.98 | 443.48 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2030. - D Demolition | 6.04 | 4 | -2.04 | 151% | 0 | 6 | 0% | 4 | -2.04 | 6.04 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2940. - CP Concrete Prep (DO NOT USE) | 525.37 | 25 | -500.37 | 2101% | 0 | 30 | 0% | 25 | -500.37 | 525.37 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2910. - MP Milling/Pulverize | 0 | 9.4 | 9.4 | 0% | 0 | 12 | 0% | 9.4 | 9.4 | 9.4 | 9.4 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1510. - S Surveying | 2709.5 | 1020 | -1689.5 | 265.6% | 180.8 | 500 | 13.33% | 136 | -2573.5 | 20321.25 | 904 | 111.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.1600. - TC Traffic Control | 65.44 | 330 | 264.56 | 19.83% | 0 | 90 | 0% | 330 | 264.56 | 330 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 350.1650. - SB Signage | 99.85 | 40 | -59.85 | 249.6% | 0 | 60 | 0% | 40 | -59.85 | 99.85 | 40 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2070. - RGC Rough Grade Cut | 456.64 | 55 | -401.64 | 830.3% | 18 | 65 | 30% | 16.5 | -440.14 | 1522.1333 | 356.25 | -447.7% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1300. - Unknown Phase | 80.12 | 0 | -80.12 |  | 0 | 0 | 0% | 0 | -80.12 | 80.12 | 5 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 270.3000. - CNC Concrete Work | 24 | 44 | 20 | 54.55% | 0 | 110 | 0% | 44 | 20 | 44 | 44 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.5310. - Fab Shop Misc Metals Fabrication | 153.96 | 0 | -153.96 |  | 0 | 0 | 0% | 0 | -153.96 | 153.96 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.2010. - RG Grading (DO NOT USE) | 12984.39 | 967.46 | -12016.93 | 1342% | 436 | 1090 | 21.2% | 205.062 | -12779.328 | 61258.9225 | 967.46 | 100% |  | 2023-05-31
2512. - South SLC Davis Tank Lid Replacement | 100.1702. - FS People Superintendent | 61.83 | 136.82 | 74.99 | 45.19% | 96.474 | 136.82 | 70% | 95.774 | 33.944 | 88.3286 | 130.99 | 104.3% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 800.1930. - MC Misc Cleanup | 5.41 | 40 | 34.59 | 13.53% | 1.2 | 120 | 0.75% | 0.3 | -5.11 | 721.3333 | 40 | 100% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1200. - HOOK Hook Truck Dumpster Transporting | 33.93 | 15 | -18.93 | 226.2% | 9.75 | 15 | 65% | 9.75 | -24.18 | 52.2 | 43.5 | -90% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 231.5100. - W Welding | 31.85 | 0 | -31.85 |  | 0 | 0 | 0% | 0 | -31.85 | 31.85 | 31.85 | 0% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1704. - FS Quality Control/Assurance | 108.5 | 252.76 | 144.26 | 42.93% | 177.632 | 252.76 | 70% | 176.932 | 68.432 | 155 | 100 | 160.4% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 900.9010. - Re-Work Pipe | 34 | 0.4 | -33.6 | 8500% | 0 | 0.6 | 0% | 0.4 | -33.6 | 34 | 34 | -8300% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1700. - FS Project Manager | 117.5 | 168.33 | 50.83 | 69.8% | 115.731 | 168.33 | 70% | 117.831 | 0.331 | 167.8571 | 162.5 | 103.5% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 112.82 | 146.12 | 33.3 | 77.21% | 102.984 | 146.12 | 70% | 102.284 | -10.536 | 161.1714 | 143.18 | 102% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 210.5100. - W Welding | 14.53 | 30 | 15.47 | 48.43% | 15 | 15 | 100% | 30 | 15.47 | 14.53 | 14.53 | 151.6% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 240.7100. - IMP Interior Mech/Piping | 2.16 | 3 | 0.84 | 72% | 0 | 9 | 0% | 3 | 0.84 | 3 | 2.16 | 128% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1703. - FS Job Site Superintendent | 611.45 | 214.72 | -396.73 | 284.8% | 145.404 | 214.72 | 70% | 150.304 | -461.146 | 873.5 | 587.73 | -73.72% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 200.7400. - HVAC HVAC | 24.65 | 8 | -16.65 | 308.1% | 12 | 24 | 50% | 4 | -20.65 | 49.3 | 24.65 | -108.1% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 150.1230. - T Transporting | 130.03 | 105 | -25.03 | 123.8% | 66.5 | 105 | 70% | 73.5 | -56.53 | 185.7571 | 160.25 | 47.38% |  | 2026-03-13
2513. - CUWCD Summit Creek Irrigation HDPE | 200.1800. - PH Potholing | 8 | 30 | 22 | 26.67% | 45 | 45 | 100% | 30 | 22 | 8 | 8 | 173.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1200. - HOOK Hook Truck Dumpster Transporting | 4.95 | 5 | 0.05 | 99% | 5 | 5 | 100% | 5 | 0.05 | 4.95 | 4.95 | 101% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1702. - FS People Superintendent | 118.42 | 100.81 | -17.61 | 117.5% | 95.769 | 100.81 | 47.5% | 47.8845 | -70.5355 | 249.3066 | 130.42 | 70.63% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1704. - FS Quality Control/Assurance | 39 | 20.08 | -18.92 | 194.2% | 20.08 | 20.08 | 50% | 10.04 | -28.96 | 78 | 47 | -34.06% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 230.2170. - HDPE Fusion Pipe <15' Depth | 50 | 20 | -30 | 250% | 15 | 15 | 42.86% | 8.5714 | -41.4286 | 116.6667 | 50 | -50% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 240.2080. - EXS Excavate Structure | 295.6 | 41.28 | -254.32 | 716.1% | 63.02 | 55.04 | 67.75% | 27.9667 | -267.6333 | 436.3172 | 293.6 | -511.2% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1700. - FS Project Manager | 84.23 | 171.04 | 86.81 | 49.25% | 162.488 | 171.04 | 48.08% | 82.244 | -1.986 | 175.1702 | 95.23 | 144.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 200.2170. - HDPE Fusion Pipe <15' Depth | 329.95 | 863.5 | 533.55 | 38.21% | 392.5 | 392.5 | 31.25% | 269.8438 | -60.1063 | 1055.84 | 329.95 | 161.8% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 0 | 161.72 | 161.72 | 0% | 153.634 | 161.72 | 47.5% | 76.817 | 76.817 | 0 | 25 | 184.5% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 270.2170. - HDPE Fusion Pipe <15' Depth | 0 | 16 | 16 | 0% | 0 | 12 | 0% | 16 | 16 | 16 | 50 | -112.5% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.5000. - MET Metals | 9 | 17.2 | 8.2 | 52.33% | 25.8 | 25.8 | 60% | 10.32 | 1.32 | 15 | 9 | 147.7% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 800.1930. - MC Misc Cleanup | 139 | 40 | -99 | 347.5% | 24 | 60 | 40% | 16 | -123 | 347.5 | 69.5 | 26.25% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1703. - FS Job Site Superintendent | 142.07 | 198.63 | 56.56 | 71.52% | 178.767 | 198.63 | 51.25% | 101.798 | -40.272 | 277.2094 | 182.07 | 108.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.3000. - CNC Concrete Work | 172.52 | 41.18 | -131.34 | 418.9% | 202.61 | 202.61 | 83.11% | 34.224 | -138.296 | 207.5843 | 202.52 | -291.8% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.2080. - EXS Excavate Structure | 23 | 44 | 21 | 52.27% | 41 | 41 | 48.24% | 21.2235 | -1.7765 | 47.6829 | 28 | 136.4% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 220.2170. - HDPE Fusion Pipe <15' Depth | 451.59 | 751.93 | 300.34 | 60.06% | 341.79 | 341.79 | 93.13% | 700.235 | 248.645 | 484.9287 | 434.13 | 142.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 200.2610. - PT Pressure Test/Chlorinating | 149.41 | 20 | -129.41 | 747.1% | 54 | 30 | 140% | 28 | -121.41 | 106.7214 | 149.41 | -547.1% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 270.2240. - PCS Precast Structures | 4.27 | 75 | 70.73 | 5.693% | 40 | 40 | 34.78% | 26.087 | 21.817 | 12.2762 | 4.27 | 194.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 200.2030. - Unknown Phase | 138.88 | 88 | -50.88 | 157.8% | 66 | 66 | 42.86% | 37.7143 | -101.1657 | 324.0533 | 138.88 | 42.18% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 160.5000. - Unknown Phase | 37.33 | 0 | -37.33 |  | 0 | 0 | 49.96% | 0 | -37.33 | 74.7211 | 37.33 | 0% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 150.2750. - Unknown Phase | 154.9 | 296.18 | 141.28 | 52.3% | 150.09 | 150.09 | 33.63% | 99.6116 | -55.2884 | 460.5718 | 146.26 | 150.6% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 150.2760. - Unknown Phase | 2 | 28 | 26 | 7.143% | 14 | 14 | 33.33% | 9.3333 | 7.3333 | 6 | 10.64 | 162% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1510. - S Surveying | 354.98 | 195 | -159.98 | 182% | 65 | 65 | 100% | 195 | -159.98 | 354.98 | 341.98 | 24.63% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 290.2170. - HDPE Fusion Pipe <15' Depth | 195.3 | 48.02 | -147.28 | 406.7% | 46.02 | 46.02 | 48.94% | 23.4994 | -171.8006 | 399.0876 | 195.3 | -206.7% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 150.1230. - T Transporting | 163.94 | 40 | -123.94 | 409.8% | 40 | 40 | 68.75% | 27.5 | -136.44 | 238.4582 | 192.65 | -281.6% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 210.2170. - HDPE Fusion Pipe <15' Depth | 939.58 | 301.32 | -638.26 | 311.8% | 225.99 | 225.99 | 43.14% | 129.9983 | -809.5817 | 2177.8306 | 939.58 | -111.8% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.2600. - DW Dewatering | 1086.07 | 1030 | -56.07 | 105.4% | 130 | 75 | 100% | 1030 | -56.07 | 1086.07 | 1083.07 | 94.85% |  | 2026-03-31
2403. - Cedar Hills Harvey Well Pump House Upgrades | 800.1930. - MC Misc Cleanup | 46.59 | 60 | 13.41 | 77.65% | 54 | 60 | 100% | 60 | 13.41 | 46.59 | 60 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 150.1230. - T Transporting | 16.96 | 50 | 33.04 | 33.92% | 50 | 50 | 100% | 50 | 33.04 | 16.96 | 50 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 300.7900. - ELC Electrical | 10.23 | 20 | 9.77 | 51.15% | 30 | 30 | 100% | 20 | 9.77 | 10.23 | 20 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.6000. - IF Interior Finishes | 265.28 | 50 | -215.28 | 530.6% | 50 | 50 | 100% | 50 | -215.28 | 265.28 | 50 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.5400. - HAT Hatch/Skylights | 104.9 | 20 | -84.9 | 524.5% | 0 | 30 | 0% | 20 | -84.9 | 104.9 | 20 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9015. - Re-Work Concrete | 6 | 0.2 | -5.8 | 3000% | 0.4 | 0.4 | 100% | 0.2 | -5.8 | 6 | 0.2 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 800.1940. - PL Punch List Work | 0 | 30 | 30 | 0% | 81 | 90 | 100% | 30 | 30 | 0 | 30 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 728.44 | 150 | -578.44 | 485.6% | 150 | 150 | 100% | 150 | -578.44 | 728.44 | 150 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.2080. - EXS Excavate Structure | 126.43 | 150 | 23.57 | 84.29% | 150 | 150 | 100% | 150 | 23.57 | 126.43 | 150 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.2030. - Unknown Phase | 198.83 | 205 | 6.17 | 96.99% | 195 | 195 | 100% | 205 | 6.17 | 198.83 | 205 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 150.2750. - Unknown Phase | 15.32 | 1.06 | -14.26 | 1445% | 1.06 | 1.06 | 100% | 1.06 | -14.26 | 15.32 | 1.06 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.3100. - CNC Rebar | 26.23 | 10 | -16.23 | 262.3% | 15 | 15 | 100% | 10 | -16.23 | 26.23 | 10 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1700. - FS Project Manager | 314.5 | 118 | -196.5 | 266.5% | 0 | 118 | 0% | 118 | -196.5 | 314.5 | 118 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9010. - Re-Work Pipe | 23.36 | 0.2 | -23.16 | 11680% | 0.4 | 0.4 | 100% | 0.2 | -23.16 | 23.36 | 0.2 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.3000. - Unknown Phase | 49.01 | 27 | -22.01 | 181.5% | 66 | 56 | 100% | 27 | -22.01 | 49.01 | 27 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 300.3000. - CNC Concrete Work | 69.42 | 40 | -29.42 | 173.6% | 100 | 100 | 100% | 40 | -29.42 | 69.42 | 40 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1703. - FS Job Site Superintendent | 416.07 | 200 | -216.07 | 208% | 180 | 200 | 100% | 200 | -216.07 | 416.07 | 200 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 150.2760. - Unknown Phase | 4 | 21 | 17 | 19.05% | 21 | 21 | 100% | 21 | 17 | 4 | 21 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1500. - VIS Meetings (Vision, Safety, Training) | 0 | 0 | 0 |  | 10 | 10 | 100% | 0 | 0 | 0 | 0 | 0% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1702. - FS People Superintendent | 107.7 | 100 | -7.7 | 107.7% | 100 | 100 | 100% | 100 | -7.7 | 107.7 | 100 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.6300. - DAW Doors & Windows | 23.43 | 10 | -13.43 | 234.3% | 30 | 30 | 100% | 10 | -13.43 | 23.43 | 10 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1200. - HOOK Hook Truck Dumpster Transporting | 4.25 | 35 | 30.75 | 12.14% | 17.5 | 17.5 | 100% | 35 | 30.75 | 4.25 | 35 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9100. - Job Related Equipment Repairs | 74.1 | 1 | -73.1 | 7410% | 1 | 1 | 100% | 1 | -73.1 | 74.1 | 1 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.7400. - HVAC HVAC | 10.23 | 100 | 89.77 | 10.23% | 150 | 150 | 100% | 100 | 89.77 | 10.23 | 100 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.7100. - IMP Interior Mech/Piping | 127.41 | 100.33 | -27.08 | 127% | 175 | 181 | 100% | 100.33 | -27.08 | 127.41 | 100.33 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9055. - Re-Work Finishes | 0 | 1 | 1 | 0% | 3 | 3 | 100% | 1 | 1 | 0 | 1 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.6800. - CLK Caulking | 214.5 | 70 | -144.5 | 306.4% | 30 | 70 | 100% | 70 | -144.5 | 214.5 | 70 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.2060. - Unknown Phase | 2.67 | 20 | 17.33 | 13.35% | 30 | 30 | 100% | 20 | 17.33 | 2.67 | 20 | 100% |  | 2025-03-25
2321. - CUWCD Santaquin Reach | 375.2750. - H Hauling | 149.93 | 323.84 | 173.91 | 46.3% | 322.59 | 323.26 | 100% | 323.84 | 173.91 | 149.93 | 149.93 | 153.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2940. - CP Concrete Prep (DO NOT USE) | 34.44 | 32.5 | -1.94 | 106% | 21 | 30 | 70% | 22.75 | -11.69 | 49.2 | 34.44 | 94.03% |  | 2026-05-01
2307. - JVWCD 2022-2023 Vault Improvements | 300.5320. - FAB Shop Misc Metals Coatings (DO NOT USE) | 11.6 | 11 | -0.6 | 105.5% | 0 | 22 | 0% | 11 | -0.6 | 11.6 | 11 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 399.88 | 112.5 | -287.38 | 355.4% | 0 | 155 | 0.3738% | 0.42056 | -399.4594 | 106967.9 | 112.5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2030. - D Demolition | 217.8 | 60 | -157.8 | 363% | 0 | 60 | 0% | 60 | -157.8 | 217.8 | 60 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1230. - T Transporting | 51.29 | 30 | -21.29 | 171% | 0 | 30 | 0% | 30 | -21.29 | 51.29 | 30 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.2760. - HO Haul Off | 9.13 | 10 | 0.87 | 91.3% | 0 | 10 | 0% | 10 | 0.87 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9055. - Re-Work Finishes | 18.06 | 0.1 | -17.96 | 18060% | 0 | 0.2 | 0% | 0.1 | -17.96 | 18.06 | 0.1 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2750. - H Hauling | 16 | 12 | -4 | 133.3% | 1 | 12 | 4.167% | 0.5 | -15.5 | 384 | 12 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.1230. - T Transporting | 3 | 10 | 7 | 30% | 0 | 10 | 0% | 10 | 7 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9020. - Re-Work Fab | 5.25 | 0.4 | -4.85 | 1312% | 0 | 1 | 0% | 0.4 | -4.85 | 5.25 | 0.4 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1940. - PL Punch List Work | 77.8 | 25 | -52.8 | 311.2% | 0 | 10 | 0% | 25 | -52.8 | 77.8 | 25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5000. - MET Metals | 37.86 | 140 | 102.14 | 27.04% | 0 | 70 | 3.226% | 4.5161 | -33.3439 | 1173.66 | 100 | 128.6% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2750. - H Hauling | 19.11 | 3.87 | -15.24 | 493.8% | 2 | 3.87 | 38.76% | 1.5 | -17.61 | 49.3038 | 3.87 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2760. - HO Haul Off | 148.04 | 16 | -132.04 | 925.2% | 0 | 16 | 0% | 16 | -132.04 | 148.04 | 16 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2300. 2 - WPL Water Pipe Laying (DO NOT USE) | 10.25 | 11 | 0.75 | 93.18% | 0 | 16.5 | 0% | 11 | 0.75 | 11 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2930. - AP Asphalt Prep (DO NOT USE) | 42.21 | 11.25 | -30.96 | 375.2% | 1 | 10 | 9.412% | 1.0588 | -41.1512 | 448.4812 | 11.25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2030. - D Demolition | 31 | 30 | -1 | 103.3% | 0 | 40 | 0% | 30 | -1 | 31 | 30 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.1930. - MC Misc Cleanup | 68.98 | 30 | -38.98 | 229.9% | 0 | 40 | 0% | 30 | -38.98 | 68.98 | 30 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1940. - PL Punch List Work | 65.41 | 25 | -40.41 | 261.6% | 0 | 10 | 0% | 25 | -40.41 | 65.41 | 25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.2300. 4 - WPL Water Pipe Laying (DO NOT USE) | 0 | 10.68 | 10.68 | 0% | 0 | 4.5 | 0% | 10.68 | 10.68 | 10.68 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1510. - S Surveying | 53.08 | 20 | -33.08 | 265.4% | 0 | 10 | 0% | 20 | -33.08 | 53.08 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9100. - Job Related Equipment Repairs | 0 | 1 | 1 | 0% | 0 | 1 | 0% | 1 | 1 | 1 | 1 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2300. 1 - WPL Water Pipe Laying (DO NOT USE) | 10 | 4 | -6 | 250% | 0 | 2 | 0% | 4 | -6 | 10 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.3000. - CNC Concrete Work | 11 | 34.5 | 23.5 | 31.88% | 0 | 66 | 0% | 34.5 | 23.5 | 34.5 | 34.5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.1940. - PL Punch List Work | 23.2 | 75 | 51.8 | 30.93% | 0 | 30 | 0% | 75 | 51.8 | 75 | 75 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.5320. - FAB Shop Misc Metals Coatings (DO NOT USE) | 0 | 5 | 5 | 0% | 0 | 10 | 0% | 5 | 5 | 5 | 5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2030. - D Demolition | 5.97 | 17.5 | 11.53 | 34.11% | 0 | 15 | 0% | 17.5 | 11.53 | 17.5 | 17.5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1702. - FS People Superintendent | 163.29 | 0 | -163.29 |  | 0 | 0 | 0% | 0 | -163.29 | 163.29 | 0 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.2760. - HO Haul Off | 9 | 5 | -4 | 180% | 0 | 5 | 0% | 5 | -4 | 9 | 5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 123.5 | 90 | -33.5 | 137.2% | 2 | 170 | 1.154% | 1.0385 | -122.4615 | 10703.3333 | 90 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2510. - CB Catch Basins DO NOT USE) | 8 | 20 | 12 | 40% | 0 | 20 | 0% | 20 | 12 | 20 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2930. - AP Asphalt Prep (DO NOT USE) | 34 | 11.25 | -22.75 | 302.2% | 0 | 10 | 0% | 11.25 | -22.75 | 34 | 11.25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9010. - Re-Work Pipe | 12 | 0.2 | -11.8 | 6000% | 0 | 0.4 | 0% | 0.2 | -11.8 | 12 | 0.2 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.1230. - T Transporting | 109.06 | 20 | -89.06 | 545.3% | 0 | 20 | 0% | 20 | -89.06 | 109.06 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.2930. - AP Asphalt Prep (DO NOT USE) | 0 | 43.5 | 43.5 | 0% | 2 | 51 | 5.291% | 2.3016 | 2.3016 | 0 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2750. - H Hauling | 4.52 | 11.79 | 7.27 | 38.34% | 0 | 11.79 | 0% | 11.79 | 7.27 | 11.79 | 11.79 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 0 | 20 | 20 | 0% | 0 | 10 | 0% | 20 | 20 | 20 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1600. - TC Traffic Control | 40.78 | 520 | 479.22 | 7.842% | 0 | 120 | 0% | 520 | 479.22 | 520 | 520 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.3000. - Unknown Phase | 86.04 | 31.25 | -54.79 | 275.3% | 1 | 55 | 3.478% | 1.087 | -84.953 | 2473.65 | 31.25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.1230. - T Transporting | 88.39 | 20 | -68.39 | 442% | 0 | 20 | 0% | 20 | -68.39 | 88.39 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 10.27 | 50 | 39.73 | 20.54% | 0 | 25 | 0% | 50 | 39.73 | 50 | 50 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1930. - MC Misc Cleanup | 39.42 | 20.04 | -19.38 | 196.7% | 0 | 27.02 | 0% | 20.04 | -19.38 | 39.42 | 15 | 125.1% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.1600. - TC Traffic Control | 24.59 | 390 | 365.41 | 6.305% | 0 | 90 | 0.2083% | 0.8125 | -23.7775 | 11803.2 | 390 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 27.5 | 0 | -27.5 |  | 0 | 0 | 0% | 0 | -27.5 | 27.5 | 0 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5100. - W Welding | 235.81 | 40 | -195.81 | 589.5% | 0 | 20 | 0% | 40 | -195.81 | 235.81 | 40 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1700. - FS Project Manager | 37 | 0 | -37 |  | 0 | 0 | 0% | 0 | -37 | 37 | 0 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 230.71 | 275 | 44.29 | 83.89% | 2 | 280 | 0.5405% | 1.4865 | -229.2235 | 42681.35 | 275 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5110. - FAB Shop Pipe Fabrication (DO NOT USE) | 140.96 | 120 | -20.96 | 117.5% | 0 | 60 | 0% | 120 | -20.96 | 140.96 | 120 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.1940. - PL Punch List Work | 4 | 12.5 | 8.5 | 32% | 0 | 5 | 0% | 12.5 | 8.5 | 12.5 | 12.5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1930. - MC Misc Cleanup | 5.62 | 15 | 9.38 | 37.47% | 0 | 20 | 0% | 15 | 9.38 | 15 | 15 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1230. - T Transporting | 94.26 | 34 | -60.26 | 277.2% | 12 | 34 | 30% | 10.2 | -84.06 | 314.2 | 20 | 141.2% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1600. - TC Traffic Control | 122.41 | 812 | 689.59 | 15.08% | 1 | 228 | 0.03076% | 0.24973 | -122.1603 | 398016.115 | 260 | 168% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2760. - HO Haul Off | 40.42 | 10 | -30.42 | 404.2% | 0 | 10 | 0% | 10 | -30.42 | 40.42 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2930. - AP Asphalt Prep (DO NOT USE) | 10 | 67.5 | 57.5 | 14.81% | 0 | 60 | 0% | 67.5 | 57.5 | 67.5 | 67.5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2760. - HO Haul Off | 79.14 | 22 | -57.14 | 359.7% | 0 | 22 | 0% | 22 | -57.14 | 79.14 | 14 | 136.4% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.2300. - WPL Water Pipe Laying (DO NOT USE) | 25.68 | 120 | 94.32 | 21.4% | 2 | 180 | 1.333% | 1.6 | -24.08 | 1926 | 120 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 62.94 | 100 | 37.06 | 62.94% | 0 | 50 | 0.6667% | 0.66667 | -62.2733 | 9441 | 100 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.7100. - Unknown Phase | 23.62 | 20 | -3.62 | 118.1% | 0 | 20 | 0% | 20 | -3.62 | 23.62 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2300. - Unknown Phase | 236.98 | 830.25 | 593.27 | 28.54% | 0 | 331 | 0.2377% | 1.9738 | -235.0062 | 99679.7125 | 631.25 | 124% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2300. - WPL Water Pipe Laying (DO NOT USE) | 92.55 | 255 | 162.45 | 36.29% | 1 | 75 | 0.303% | 0.77273 | -91.7773 | 30541.5 | 255 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2760. - HO Haul Off | 24.41 | 10 | -14.41 | 244.1% | 0 | 10 | 0% | 10 | -14.41 | 24.41 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1703. - FS Job Site Superintendent | 435.15 | 0 | -435.15 |  | 0 | 0 | 0% | 0 | -435.15 | 435.15 | 97.78 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.1600. - TC Traffic Control | 8.58 | 650 | 641.42 | 1.32% | 0 | 150 | 0% | 650 | 641.42 | 650 | 650 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.3000. - CNC Concrete Work | 8.16 | 10 | 1.84 | 81.6% | 1 | 20 | 43.33% | 4.3333 | -3.8267 | 18.8308 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5120. - FAB Shop Pipe Linings & Coatings (DO NOT USE) | 0 | 60.18 | 60.18 | 0% | 0 | 114 | 0% | 60.18 | 60.18 | 60.18 | 50 | 116.9% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.1930. - MC Misc Cleanup | 3.08 | 15 | 11.92 | 20.53% | 0 | 20 | 0% | 15 | 11.92 | 15 | 15 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.6500. - P Painting | 214.71 | 20 | -194.71 | 1074% | 0 | 40 | 0% | 20 | -194.71 | 214.71 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2930. - AP Asphalt Prep (DO NOT USE) | 143.49 | 11.25 | -132.24 | 1275% | 0 | 15 | 0% | 11.25 | -132.24 | 143.49 | 11.25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.1600. - TC Traffic Control | 4 | 390 | 386 | 1.026% | 0 | 90 | 0% | 390 | 386 | 390 | 390 | 100% |  | 2024-07-16
2315. - VanCon SLC Flowfill Project | 200.2710. - FWF Flowable Fill | 14096.63 | 2383.34 | -11713.29 | 591.5% | 0 | 1466.67 | 0.02597% | 0.61905 | -14096.011 | 54272166.4663 | 14004.88 | -387.6%
2315. - VanCon SLC Flowfill Project | 300.2760. - HO Haul Off | 94.53 | 2 | -92.53 | 4726% | 0 | 2 | 0% | 2 | -92.53 | 94.53 | 54.53 | -2526%
2315. - VanCon SLC Flowfill Project | 300.1230. - T Transporting | 58 | 50 | -8 | 116% | 0 | 50 | 0% | 50 | -8 | 58 | 98 | 4%
2315. - VanCon SLC Flowfill Project | 300.2710. - FWF Flowable Fill | 247.24 | 160 | -87.24 | 154.5% | 0 | 250 | 0% | 160 | -87.24 | 247.24 | 247.24 | 45.48%
2315. - VanCon SLC Flowfill Project | 200.2750. - H Hauling | 2010.41 | 632.5 | -1377.91 | 317.9% | 0 | 632.5 | 0% | 632.5 | -1377.91 | 2010.41 | 2034.39 | -121.6%
2315. - VanCon SLC Flowfill Project | 150.2710. - FWF Flowable Fill | -84.61 | 160 | 244.61 | -52.88% | 0 | 250 | 0% | 160 | 244.61 | 160 | -34.13 | 221.3%
2315. - VanCon SLC Flowfill Project | 300.2000. - SWC Site Work Complete (DO NOT USE) | 21 | 15 | -6 | 140% | 0 | 10 | 0% | 15 | -6 | 21 | 28.95 | 7%
2315. - VanCon SLC Flowfill Project | 150.1230. - T Transporting | 117.4 | 50 | -67.4 | 234.8% | 0 | 50 | 0% | 50 | -67.4 | 117.4 | 73.65 | 52.7%
2315. - VanCon SLC Flowfill Project | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 53.34 | 35 | -18.34 | 152.4% | 0 | 30 | 0% | 35 | -18.34 | 53.34 | 45.67 | 69.51%
2315. - VanCon SLC Flowfill Project | 150.2750. - Unknown Phase | 895.58 | 105.6 | -789.98 | 848.1% | 0 | 105.6 | 88.3% | 93.25 | -802.33 | 1014.1903 | 896.52 | -649%
2129. - JVWCD 3600 W 10200 S Pump Station | 250.6500. - P Painting | 283.95 | 0 | -283.95 |  | 0 | 0 | 0% | 0 | -283.95 | 283.95 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.3000.10 - CNC Concrete Work | 68.3 | 78 | 9.7 | 87.56% | 0 | 1 | 0% | 78 | 9.7 | 78 | 0 | 200% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 276.2 | 0 | -276.2 |  | 0 | 0 | 0% | 0 | -276.2 | 276.2 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9100. - Job Related Equipment Repairs | 81.65 | 1 | -80.65 | 8165% | 0 | 1 | 0% | 1 | -80.65 | 81.65 | 1 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2070. - RGC Rough Grade Cut | 643.69 | 30 | -613.69 | 2146% | 1.5 | 30 | 2.5% | 0.75 | -642.94 | 25747.6 | 30 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9010. - Re-Work Pipe | 21.66 | 0.2 | -21.46 | 10830% | 0 | 0.6 | 0% | 0.2 | -21.46 | 21.66 | 0.2 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1700. - FS Project Manager | 203 | 0 | -203 |  | 0 | 0 | 0% | 0 | -203 | 203 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1703. - FS Job Site Superintendent | 368.03 | 0 | -368.03 |  | 0 | 0 | 0% | 0 | -368.03 | 368.03 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1510. - S Surveying | 849.11 | 400 | -449.11 | 212.3% | 0 | 400 | 3.875% | 15.5 | -833.61 | 21912.5161 | 400 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 800.1940 - Unknown Phase | 3.05 | 0 | -3.05 |  | 0 | 0 | 0% | 0 | -3.05 | 3.05 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.2080. - EXS Excavate Structure | 383.78 | 533.34 | 149.56 | 71.96% | 0 | 562.1 | 0% | 533.34 | 149.56 | 533.34 | 533.34 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.5000. - MET Metals | 197.98 | 186.66 | -11.32 | 106.1% | 0 | 232 | 0% | 186.66 | -11.32 | 197.98 | 186.66 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.3000. - Unknown Phase | 3671.04 | 173.5 | -3497.54 | 2116% | 0 | 410 | 0% | 173.5 | -3497.54 | 3671.04 | 170 | 102% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 180.5000. - MET Metals | 1088.78 | 0 | -1088.78 |  | 0 | 0 | 0% | 0 | -1088.78 | 1088.78 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 180.7400. - HVAC HVAC | 183.9 | 0 | -183.9 |  | 0 | 0 | 0% | 0 | -183.9 | 183.9 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2010. - RG Grading (DO NOT USE) | 33.95 | 499 | 465.05 | 6.804% | 0 | 578 | 0% | 499 | 465.05 | 499 | 499 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1702. - FS People Superintendent | 155.76 | 0 | -155.76 |  | 0 | 0 | 0% | 0 | -155.76 | 155.76 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7100. - IMP Interior Mech/Piping | 1510.54 | 654.66 | -855.88 | 230.7% | 0 | 1087 | 0% | 654.66 | -855.88 | 1510.54 | 654.66 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7600. - MEQ Mechanical Equipment | 139.94 | 74 | -65.94 | 189.1% | 0 | 111 | 0% | 74 | -65.94 | 139.94 | 74 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7300. - PLUM Plumbing | 151.97 | 420 | 268.03 | 36.18% | 0 | 810 | 0% | 420 | 268.03 | 420 | 420 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.5000. - MET Metals | 98.95 | 1243.49 | 1144.54 | 7.957% | 0 | 1166.38 | 0% | 1243.49 | 1144.54 | 1243.49 | 1243.49 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.5100. - W Welding | 534.12 | 166 | -368.12 | 321.8% | 0 | 83 | 0% | 166 | -368.12 | 534.12 | 166 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 6709.17 | 3405 | -3304.17 | 197% | 0 | 2720 | 0% | 3405 | -3304.17 | 6709.17 | 3405 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9020. - Re-Work Fab | 33.92 | 0.4 | -33.52 | 8480% | 0 | 0.2 | 0% | 0.4 | -33.52 | 33.92 | 0.4 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 800.1930. - MC Misc Cleanup | 67.75 | 250 | 182.25 | 27.1% | 0 | 200 | 0% | 250 | 182.25 | 250 | 250 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.6200. - IN Insulation | 133.16 | 40 | -93.16 | 332.9% | 0 | 80 | 0% | 40 | -93.16 | 133.16 | 40 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2000. - Unknown Phase | 2717.67 | 87 | -2630.67 | 3124% | 0 | 102 | 0% | 87 | -2630.67 | 2717.67 | 87 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.5000. - MET Metals | 232 | 200.5 | -31.5 | 115.7% | 0 | 1 | 0% | 200.5 | -31.5 | 232 | 0 | 200% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1704. - FS Quality Control/Assurance | 20.51 | 0 | -20.51 |  | 0 | 0 | 0% | 0 | -20.51 | 20.51 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 700.2610. - PT Pressure Test/Chlorinating | 95.48 | 175 | 79.52 | 54.56% | 0 | 200 | 0% | 175 | 79.52 | 175 | 175 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 800.1940. - PL Punch List Work | 514.08 | 100 | -414.08 | 514.1% | 0 | 300 | 10% | 10 | -504.08 | 5140.8 | 100 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2040. - LR Landscaping/Restoration | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.6000. - IF Interior Finishes | 2520.55 | 3 | -2517.55 | 84018% | 0 | 9 | 0% | 3 | -2517.55 | 2520.55 | 3 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 150.2750. - Unknown Phase | 246.07 | 195.68 | -50.39 | 125.8% | 0 | 195.68 | 0% | 195.68 | -50.39 | 246.07 | 195.68 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9012. - Re-Work Mechanical | 62.38 | 0.2 | -62.18 | 31190% | 0 | 0.4 | 0% | 0.2 | -62.18 | 62.38 | 0.2 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.2800. - BFST Backfill (DO NOT USE) | 1126.07 | 350 | -776.07 | 321.7% | 0 | 300 | 0% | 350 | -776.07 | 1126.07 | 350 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2030. - Unknown Phase | 97.14 | 250 | 152.86 | 38.86% | 0 | 247 | 0% | 250 | 152.86 | 250 | 250 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.1600. - TC Traffic Control | 21.04 | 330 | 308.96 | 6.376% | 0 | 30 | 0% | 330 | 308.96 | 330 | 330 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 150.2760. - Unknown Phase | 1236.68 | 1246 | 9.32 | 99.25% | 0 | 1244 | 0% | 1246 | 9.32 | 1246 | 1244 | 100.2% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 180.2900.40 - ASPH Asphalt | 25.04 | 6.19 | -18.85 | 404.5% | 0 | 1 | 0% | 6.19 | -18.85 | 25.04 | 0 | 200% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.2300. - WPL Water Pipe Laying (DO NOT USE) | 12.99 | 100 | 87.01 | 12.99% | 0 | 100 | 0% | 100 | 87.01 | 100 | 100 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 185.7100. - IMP Interior Mech/Piping | 193.7 | 0 | -193.7 |  | 0 | 0 | 0% | 0 | -193.7 | 193.7 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 201.5000. - MET Metals | 3435.62 | 0 | -3435.62 |  | 0 | 0 | 0% | 0 | -3435.62 | 3435.62 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.2050. - RW Retaining Walls | 1 | 30 | 29 | 3.333% | 0 | 30 | 0% | 30 | 29 | 30 | 30 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7900. - ELC Electrical | 290.55 | 197.8 | -92.75 | 146.9% | 0 | 270 | 0% | 197.8 | -92.75 | 290.55 | 185 | 106.5% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 150.1230. - T Transporting | 677.71 | 400 | -277.71 | 169.4% | 0 | 400 | 0% | 400 | -277.71 | 677.71 | 400 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.2110. - SS Sewer Services (DO NOT USE) | 290.2 | 168 | -122.2 | 172.7% | 0 | 92 | 0% | 168 | -122.2 | 290.2 | 168 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 162.5000. - MET Metals | 80.26 | 0 | -80.26 |  | 0 | 0 | 0% | 0 | -80.26 | 80.26 | 169.63 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9015. - Re-Work Concrete | 176.86 | 0.2 | -176.66 | 88430% | 0 | 0.4 | 0% | 0.2 | -176.66 | 176.86 | 0.2 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.3000. - CNC Concrete Work | 5812.11 | 1602.73 | -4209.38 | 362.6% | 0 | 4006.71 | 0% | 1602.73 | -4209.38 | 5812.11 | 1602.73 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 170.2300. - WPL Water Pipe Laying (DO NOT USE) | 1695.1 | 0 | -1695.1 |  | 0 | 0 | 0% | 0 | -1695.1 | 1695.1 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.6500. - P Painting | 1534.74 | 260 | -1274.74 | 590.3% | 0 | 780 | 0% | 260 | -1274.74 | 1534.74 | 260 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 350.3000. - CNC Concrete Work | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-12-31
2519. - Corix IEC Site Utilities | 100.1510. - S Surveying | 58.4 | 250 | 191.6 | 23.36% | 55 | 100 | 55% | 137.5 | 79.1 | 106.1818 | 304.4 | 78.24% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 400.7100. - IMP Interior Mech/Piping | 62.37 | 20 | -42.37 | 311.9% | 18 | 60 | 30% | 6 | -56.37 | 207.9 | 20 | 100% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1702. - FS People Superintendent | 56.5 | 74 | 17.5 | 76.35% | 0.55 | 74 | 55% | 40.7 | -15.8 | 102.7273 | 65 | 112.2% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 200.2075. - FG Finish Grade | 127 | 155 | 28 | 81.94% | 60 | 200 | 30% | 46.5 | -80.5 | 423.3333 | 184.4 | 81.03% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1704. - FS Quality Control/Assurance | 1 | 29 | 28 | 3.448% | 0.55 | 29 | 55% | 15.95 | 14.95 | 1.8182 | 10 | 165.5% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 200.2240. - PCS Precast Structures | 605.84 | 81.55 | -524.29 | 742.9% | 37 | 92.5 | 40% | 32.62 | -573.22 | 1514.6 | 735.35 | -701.7% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 800.1940. - PL Punch List Work | 6.82 | 30 | 23.18 | 22.73% | 24 | 40 | 60% | 18 | 11.18 | 11.3667 | 30 | 100% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2075. - FG Finish Grade | 49.89 | 192.46 | 142.57 | 25.92% | 19.632 | 196.32 | 10% | 19.246 | -30.644 | 498.9 | 200 | 96.08% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2080. - EXS Excavate Structure | 103.8 | 152 | 48.2 | 68.29% | 80 | 160 | 50% | 76 | -27.8 | 207.6 | 253.8 | 33.03% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.3000. - CNC Concrete Work | 522.98 | 177.2 | -345.78 | 295.1% | 928.2 | 928.2 | 100% | 177.2 | -345.78 | 522.98 | 472.13 | -66.44% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2085. - BFST Backfill Structure | 117.43 | 102.5 | -14.93 | 114.6% | 62.5 | 125 | 50% | 51.25 | -66.18 | 234.86 | 107.99 | 94.64% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.3100. - CNC Rebar | 48.66 | 24 | -24.66 | 202.8% | 86.4 | 144 | 60% | 14.4 | -34.26 | 81.1 | 148.66 | -419.4% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 48.76 | 219 | 170.24 | 22.26% | 83.05 | 219 | 55% | 120.45 | 71.69 | 88.6545 | 198.76 | 109.2% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1700. - FS Project Manager | 58.5 | 138 | 79.5 | 42.39% | 28.05 | 138 | 55% | 75.9 | 17.4 | 106.3636 | 132.5 | 104% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 500.2075. - FG Finish Grade | 15.06 | 25.8 | 10.74 | 58.37% | 1.2 | 12 | 10% | 2.58 | -12.48 | 150.6 | 50 | 6.202% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 150.1230. - T Transporting | 14 | 50 | 36 | 28% | 22.5 | 50 | 45% | 22.5 | 8.5 | 31.1111 | 50 | 100% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1703. - FS Job Site Superintendent | 132.31 | 116 | -16.31 | 114.1% | 0.55 | 116 | 55% | 63.8 | -68.51 | 240.5636 | 166.66 | 56.33% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2600. - DW Dewatering | 0 | 123 | 123 | 0% | 180 | 180 | 100% | 123 | 123 | 0 | 0 | 200% |  | 2026-04-01
2504. - Marathon - 1900 N Sewer | 200.2075. - FG Finish Grade | 194.89 | 422.5 | 227.61 | 46.13% | 280 | 280 | 100% | 422.5 | 227.61 | 194.89 | 194.89 | 153.9% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1230. - T Transporting | 187.02 | 40 | -147.02 | 467.6% | 40 | 40 | 100% | 40 | -147.02 | 187.02 | 187.02 | -267.6% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1702. - FS People Superintendent | 101.11 | 37.14 | -63.97 | 272.2% | 137.14 | 137.14 | 100% | 37.14 | -63.97 | 101.11 | 101.11 | -72.24% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 6 | 47.23 | 41.23 | 12.7% | 147.23 | 147.23 | 100% | 47.23 | 41.23 | 6 | 6 | 187.3% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1700. - FS Project Manager | 112.48 | 50.8 | -61.68 | 221.4% | 50.8 | 50.8 | 100% | 50.8 | -61.68 | 112.48 | 112.48 | -21.42% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 250.2600. - DW Dewatering | 43.66 | 112.5 | 68.84 | 38.81% | 0 | 150 | 0% | 112.5 | 68.84 | 112.5 | 42.66 | 162.1% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.1600. - TC Traffic Control | 23.49 | 70 | 46.51 | 33.56% | 130 | 130 | 100% | 70 | 46.51 | 23.49 | 24.49 | 165% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1707. - S Survey | 206.56 | 0 | -206.56 |  | 0 | 0 | 0% | 0 | -206.56 | 206.56 | 206.56 | 0% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2071. - RGF Rough Grade Fill | 979.96 | 70 | -909.96 | 1400% | 80 | 80 | 100% | 70 | -909.96 | 979.96 | 979.96 | -1200% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1703. - FS Job Site Superintendent | 230.69 | 75.28 | -155.41 | 306.4% | 75.28 | 75.28 | 100% | 75.28 | -155.41 | 230.69 | 230.69 | -106.4% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2240. - PCS Precast Structures | 343.99 | 75.31 | -268.68 | 456.8% | 92.5 | 92.5 | 100% | 75.31 | -268.68 | 343.99 | 346.99 | -260.7% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 250.1600. - TC Traffic Control | 28.5 | 0 | -28.5 |  | 0 | 0 | 0% | 0 | -28.5 | 28.5 | 28.5 | 0% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2130. - PVC Pipe | 1149.35 | 805.28 | -344.07 | 142.7% | 397.75 | 397.75 | 100% | 805.28 | -344.07 | 1149.35 | 1149.35 | 57.27% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 150.2750. - Unknown Phase | 366.1 | 38 | -328.1 | 963.4% | 38 | 38 | 100% | 38 | -328.1 | 366.1 | 363.1 | -755.5% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2030. - Unknown Phase | 178.6 | 200 | 21.4 | 89.3% | 0 | 150 | 0% | 200 | 21.4 | 200 | 178.6 | 110.7% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 150.2760. - Unknown Phase | 162.25 | 152.35 | -9.9 | 106.5% | 152.35 | 152.35 | 100% | 152.35 | -9.9 | 162.25 | 162.25 | 93.5% |  | 2025-07-11
2602. - JVWCD Rosecrest WSP Pipeline | 100.1515. - S Drone/Lidar Requirements | 96.48 | 650 | 553.52 | 14.84% | 0 | 650 | 0% | 650 | 553.52 | 650 | 650 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 16.5 | 1421.78 | 1405.28 | 1.161% | 0 | 1421.78 | 0% | 1421.78 | 1405.28 | 1421.78 | 1421.78 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 900.9100. - Job Related Equipment Repairs | 6 | 1 | -5 | 600% | 0 | 1 | 0% | 1 | -5 | 6 | 1 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 150.2750. - Unknown Phase | 11.16 | 415.78 | 404.62 | 2.684% | 0 | 259.86 | 0% | 415.78 | 404.62 | 415.78 | 415.78 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1700. - FS Project Manager | 28.25 | 1568.06 | 1539.81 | 1.802% | 0 | 1568.06 | 0% | 1568.06 | 1539.81 | 1568.06 | 1568.06 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1711. - FS Pre-Construction Video | 4.5 | 40 | 35.5 | 11.25% | 0 | 40 | 0% | 40 | 35.5 | 40 | 40 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1108. - TF Setup Staging Area Laydown Yard | 32.72 | 5.6 | -27.12 | 584.3% | 0 | 4 | 0% | 5.6 | -27.12 | 32.72 | 5.6 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1702. - FS People Superintendent | 0 | 1312.89 | 1312.89 | 0% | 0 | 1312.89 | 0% | 1312.89 | 1312.89 | 1312.89 | 1312.89 | 100% |  | 2028-05-15
2518. - Mt Pleasant Lagoon Improvement | 100.1703. - FS Job Site Superintendent | 11 | 228.02 | 217.02 | 4.824% | 0 | 228.02 | 0% | 228.02 | 217.02 | 228.02 | 228.02 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 150.1230. - T Transporting | 19.32 | 75 | 55.68 | 25.76% | 0 | 75 | 0% | 75 | 55.68 | 75 | 75 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1700. - FS Project Manager | 47.5 | 181.06 | 133.56 | 26.23% | 0 | 181.06 | 0% | 181.06 | 133.56 | 181.06 | 181.06 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 156.25 | 164.82 | 8.57 | 94.8% | 0 | 164.82 | 0% | 164.82 | 8.57 | 164.82 | 164.82 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 200.2030. - Unknown Phase | 52.75 | 3.1 | -49.65 | 1702% | 0 | 3 | 0% | 3.1 | -49.65 | 52.75 | 3.1 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1702. - FS People Superintendent | 42 | 151.89 | 109.89 | 27.65% | 0 | 151.89 | 0% | 151.89 | 109.89 | 151.89 | 151.89 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1200. - HOOK Hook Truck Dumpster Transporting | 0.35 | 15 | 14.65 | 2.333% | 0 | 15 | 0% | 15 | 14.65 | 15 | 15 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 500.2030. - D Demolition | 0 | 15.3 | 15.3 | 0% | 0 | 15 | 0% | 15.3 | 15.3 | 15.3 | 15.3 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1201. - HOOK Hook Truck Conex, Skid Transporting | 0.2 | 5 | 4.8 | 4% | 0 | 5 | 0% | 5 | 4.8 | 5 | 5 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1510. - S Surveying | 69 | 125 | 56 | 55.2% | 0 | 50 | 0% | 125 | 56 | 125 | 125 | 100% |  | 2026-11-30
2516. - Ephraim Lower Penstock Replacement | 150.2760. - Unknown Phase | 18.7 | 9.57 | -9.13 | 195.4% | 0 | 9.57 | 0% | 9.57 | -9.13 | 18.7 | 46 | -280.7% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2130. - PVC Pipe | 224.98 | 305.2 | 80.22 | 73.72% | 217.39 | 210.8 | 54.43% | 166.1219 | -58.8581 | 413.3344 | 244.98 | 119.7% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2240. - PCS Precast Structures | 276.5 | 362.47 | 85.97 | 76.28% | 0.9 | 122.72 | 45% | 163.1115 | -113.3885 | 614.4444 | 277.17 | 123.5% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2140. - SVR Services | 269.1 | 133.5 | -135.6 | 201.6% | 1 | 50.32 | 50% | 66.75 | -202.35 | 538.2 | 269.1 | -1.573% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2030. - Unknown Phase | 0 | 68.8 | 68.8 | 0% | 38.7 | 63 | 14.73% | 10.1334 | 10.1334 | 0 | 50 | 127.3% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.5100. - W Welding | 760.43 | 4659.57 | 3899.14 | 16.32% | 640.8 | 2136 | 5.552% | 258.6945 | -501.7355 | 13696.7588 | 2160.43 | 153.6% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1702. - FS People Superintendent | 144.3 | 248.93 | 104.63 | 57.97% | 74.379 | 247.93 | 15% | 37.3395 | -106.9605 | 962 | 274.8 | 89.61% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2160. - WSP Welded Steel Pipe <15' Depth | 8844.88 | 4299.9 | -4544.98 | 205.7% | 864.021 | 2880.07 | 11.06% | 475.5546 | -8369.3254 | 79974.1958 | 9490.43 | -20.71% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 900.9100. - Job Related Equipment Repairs | 0 | 2 | 2 | 0% | 0 | 1 | 0% | 2 | 2 | 2 | 0 | 200% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.5400. - HAT Hatch/Skylights | 100 | 15 | -85 | 666.7% | 18 | 36 | 46.15% | 6.9231 | -93.0769 | 216.6667 | 15 | 100% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 300.5000. - MET Metals | 295.79 | 55.2 | -240.59 | 535.9% | 0 | 0 | 0% | 55.2 | -240.59 | 295.79 | 295.79 | -335.9% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.1515. - S Drone/Lidar Requirements | 790.23 | 550 | -240.23 | 143.7% | 225 | 450 | 2.284% | 12.5635 | -777.6665 | 34594.5133 | 990.63 | 19.89% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2120. - DIP Ductile Iron Pipe | 541.32 | 280.47 | -260.85 | 193% | 80 | 202.14 | 50% | 140.235 | -401.085 | 1082.64 | 543.32 | 6.282% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2085. - BFST Backfill Structure | 964.03 | 3743.62 | 2779.59 | 25.75% | 501.93 | 1667.55 | 0.04287% | 1.6048 | -962.4252 | 2248824.5161 | 601.73 | 183.9% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.1800. - PH Potholing | 378.17 | 288 | -90.17 | 131.3% | 240 | 320 | 50% | 144 | -234.17 | 756.34 | 378.17 | 68.69% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 800.1930. - MC Misc Cleanup | 154.65 | 200 | 45.35 | 77.33% | 225 | 300 | 75% | 150 | -4.65 | 206.2 | 200 | 100% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 161.5100. - W Welding | 243.38 | 440 | 196.62 | 55.31% | 220 | 44 | 43.64% | 192 | -51.38 | 557.7458 | 336.51 | 123.5% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1703. - FS Job Site Superintendent | 446.72 | 373.53 | -73.19 | 119.6% | 111.759 | 372.53 | 15% | 56.0295 | -390.6905 | 2978.1333 | 626.39 | 32.31% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2610. - PT Pressure Test/Chlorinating | 0 | 96.72 | 96.72 | 0% | 0 | 124.2 | 0% | 96.72 | 96.72 | 96.72 | 0 | 200% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2020. - Unknown Phase | 132.13 | 320 | 187.87 | 41.29% | 250 | 250 | 99.6% | 318.7251 | 186.5951 | 132.6585 | 182.13 | 143.1% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.1600. - TC Traffic Control | 50.5 | 0 | -50.5 |  | 0 | 0 | 0% | 0 | -50.5 | 50.5 | 70.5 | 0% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1704. - FS Quality Control/Assurance | 81 | 97.06 | 16.06 | 83.45% | 38.424 | 96.06 | 20% | 19.412 | -61.588 | 405 | 151 | 44.43% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 150.1230. - T Transporting | 404.25 | 200 | -204.25 | 202.1% | 100 | 200 | 50% | 100 | -304.25 | 808.5 | 552.78 | -76.39% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1700. - FS Project Manager | 228.73 | 296.67 | 67.94 | 77.1% | 87.201 | 295.67 | 15% | 44.5005 | -184.2295 | 1524.8667 | 281.23 | 105.2% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 225.09 | 270.1 | 45.01 | 83.34% | 80.73 | 269.1 | 15% | 40.515 | -184.575 | 1500.6 | 380.34 | 59.19% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.3000. - Unknown Phase | 97.39 | 40.9 | -56.49 | 238.1% | 124.75 | 124.75 | 97.65% | 39.9395 | -57.4505 | 99.732 | 129.7 | -117.1% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 150.2750. - Unknown Phase | 674.36 | 686.68 | 12.32 | 98.21% | 171.67 | 343.34 | 6.739% | 46.2766 | -628.0834 | 10006.5486 | 1953.33 | -84.46% |  | 2026-10-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.3000. - Unknown Phase | 51.2 | 10 | -41.2 | 512% | 0 | 1 | 0% | 10 | -41.2 | 51.2 | 20 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.5000. - MET Metals | 142.64 | 10 | -132.64 | 1426% | 0 | 30 | 0% | 10 | -132.64 | 142.64 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 2.5 | 0 | -2.5 |  | 0 | 0 | 0% | 0 | -2.5 | 2.5 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.5100. - W Welding | 12.92 | 20 | 7.08 | 64.6% | 0 | 10 | 0% | 20 | 7.08 | 20 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 150.1230. - T Transporting | 252.72 | 90 | -162.72 | 280.8% | 0 | 90 | 0% | 90 | -162.72 | 252.72 | 60 | 133.3% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1700. - FS Project Manager | 42 | 250 | 208 | 16.8% | 0 | 200 | 0% | 250 | 208 | 250 | 125 | 150% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.2030. - Unknown Phase | 139.44 | 160 | 20.56 | 87.15% | 0 | 395 | 0% | 160 | 20.56 | 160 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.6500. - P Painting | 99.16 | 398 | 298.84 | 24.91% | 0 | 1200 | 0% | 398 | 298.84 | 398 | 180 | 154.8% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 400.5000. - MET Metals | 26.04 | 0 | -26.04 |  | 0 | 0 | 0% | 0 | -26.04 | 26.04 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1703. - FS Job Site Superintendent | 281.66 | 0 | -281.66 |  | 0 | 0 | 0% | 0 | -281.66 | 281.66 | 74.44 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 160.6500. - P Painting | 240.36 | -30 | -270.36 |  | 1 | -60 | 150% | -45 | -285.36 | 160.24 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1930. - MC Misc Cleanup | 26.28 | 40 | 13.72 | 65.7% | 0 | 60 | 0% | 40 | 13.72 | 40 | 20 | 150% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.3000. - CNC Concrete Work | 516.8 | 50 | -466.8 | 1034% | 0 | 1 | 0% | 50 | -466.8 | 516.8 | 10 | 180% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1510. - S Surveying | 52 | 90 | 38 | 57.78% | 0 | 45 | 0% | 90 | 38 | 90 | 60 | 133.3% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.5100. - W Welding | 1436.09 | 20 | -1416.09 | 7180% | 0 | 10 | 0% | 20 | -1416.09 | 1436.09 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 160.5000. - Unknown Phase | 2813.43 | 412 | -2401.43 | 682.9% | 0 | 0 | 0% | 412 | -2401.43 | 2813.43 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1940. - PL Punch List Work | 366.66 | 40 | -326.66 | 916.6% | 0 | 60 | 0% | 40 | -326.66 | 366.66 | 20 | 150% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.7100. - IMP Interior Mech/Piping | 510.95 | 817.5 | 306.55 | 62.5% | 0 | 1 | 0% | 817.5 | 306.55 | 817.5 | 455 | 144.3% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.5000. - MET Metals | 0 | 10 | 10 | 0% | 0 | 30 | 0% | 10 | 10 | 10 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.2030. - D Demolition | 0 | 350 | 350 | 0% | 0 | 645 | 0% | 350 | 350 | 350 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 900.9012. - Re-Work Mechanical | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 210.6500. - P Painting | 501.27 | 0 | -501.27 |  | 0 | 0 | 0% | 0 | -501.27 | 501.27 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.7100. - IMP Interior Mech/Piping | 143.04 | 1067.5 | 924.46 | 13.4% | 0 | 1 | 0% | 1067.5 | 924.46 | 1067.5 | 900 | 115.7% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.6500. - Unknown Phase | 1422.15 | 50 | -1372.15 | 2844% | 0 | 1200 | 0% | 50 | -1372.15 | 1422.15 | 180 | -160% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1702. - FS People Superintendent | 101.92 | 0 | -101.92 |  | 0 | 0 | 0% | 0 | -101.92 | 101.92 | 0 | 0% |  | 2023-12-31
2606. - SLCo FAC126702 SMH HVAC Replacement | 100.1706. - FS Executive | 1 | 1 | 0 | 100% | 0 | 1 | 0% | 1 | 0 | 1 | 1 | 100% |  | 2026-02-16
2606. - SLCo FAC126702 SMH HVAC Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 29.33 | 46.81 | 17.48 | 62.66% | 0 | 46.81 | 0% | 46.81 | 17.48 | 46.81 | 46.81 | 100% |  | 2026-02-16
2606. - SLCo FAC126702 SMH HVAC Replacement | 100.1700. - FS Project Manager | 7 | 51.52 | 44.52 | 13.59% | 0 | 51.52 | 0% | 51.52 | 44.52 | 51.52 | 51.52 | 100% |  | 2026-02-16
2517. - CUWCD Ashley Valley BWRB Rehab | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 11.75 | 87.54 | 75.79 | 13.42% | 0 | 87.54 | 0% | 87.54 | 75.79 | 87.54 | 51.75 | 140.9% |  | 2027-04-01
2517. - CUWCD Ashley Valley BWRB Rehab | 100.1700. - FS Project Manager | 74.5 | 106.11 | 31.61 | 70.21% | 0 | 106.11 | 0% | 106.11 | 31.61 | 106.11 | 146.5 | 61.94% |  | 2027-04-01
2603. - Highland City Mitchell Hollow Trail | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 59.5 | 169.5 | 110 | 35.1% | 16.95 | 169.5 | 10% | 16.95 | -42.55 | 595 | 169.5 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 200.1600. - TC Traffic Control | 7 | 50 | 43 | 14% | 0 | 50 | 0% | 50 | 43 | 50 | 50 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1703. - FS Job Site Superintendent | 10.53 | 235.25 | 224.72 | 4.476% | 23.525 | 235.25 | 10% | 23.525 | 12.995 | 105.3 | 235.25 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1700. - FS Project Manager | 39.5 | 186.85 | 147.35 | 21.14% | 18.685 | 186.85 | 10% | 18.685 | -20.815 | 395 | 186.85 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 800.1940. - PL Punch List Work | 40.5 | 60 | 19.5 | 67.5% | 0 | 90 | 0% | 60 | 19.5 | 60 | 60 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1510. - S Surveying | 122 | 600 | 478 | 20.33% | 20 | 200 | 10% | 60 | -62 | 1220 | 600 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1702. - FS People Superintendent | 15 | 156.59 | 141.59 | 9.579% | 15.659 | 156.59 | 10% | 15.659 | 0.659 | 150 | 54 | 165.5% |  | 2026-12-16
2604. - Murray 900 East Storm Drain Phase 2 | 100.1702. - FS People Superintendent | 17.5 | 242.82 | 225.32 | 7.207% | 0 | 242.82 | 0% | 242.82 | 225.32 | 242.82 | 242.82 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 200.1600. - TC Traffic Control | 77 | 4044 | 3967 | 1.904% | 0 | 1 | 0% | 4044 | 3967 | 4044 | 4044 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 100.1700. - FS Project Manager | 71 | 289.85 | 218.85 | 24.5% | 0 | 289.85 | 0% | 289.85 | 218.85 | 289.85 | 289.85 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 16.28 | 262.89 | 246.61 | 6.193% | 0 | 262.89 | 0% | 262.89 | 246.61 | 262.89 | 262.89 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 200.2210. - RCP Reinforced Concrete Pipe | 121.52 | 2919.9 | 2798.38 | 4.162% | 0 | 2388 | 0% | 2919.9 | 2798.38 | 2919.9 | 2919.9 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 150.2750. - Unknown Phase | 0 | 2124.7 | 2124.7 | 0% | 0 | 4162 | 0% | 2124.7 | 2124.7 | 2124.7 | 2124.7 | 100% |  | 2026-12-31
2608. - Springville City WRF Headworks | 100.1700. - FS Project Manager | 43 | 162.93 | 119.93 | 26.39% | 0 | 162.93 | 0% | 162.93 | 119.93 | 162.93 | 224 | 62.52% |  | 2026-08-31
2605. - Highland City Well #1&#5 Chlorine | 100.1500. - VIS Meetings (Vision, Safety, Training) | 0 | 0 | 0 |  | 0.1 | 1 | 10% | 0 | 0 | 0 | 0 | 0% |  | 2026-05-15
2605. - Highland City Well #1&#5 Chlorine | 100.1703. - FS Job Site Superintendent | 4.5 | 60.03 | 55.53 | 7.496% | 6.003 | 60.03 | 10% | 6.003 | 1.503 | 45 | 84 | 60.07% |  | 2026-05-15
2605. - Highland City Well #1&#5 Chlorine | 100.1700. - FS Project Manager | 44 | 47.83 | 3.83 | 91.99% | 4.783 | 47.83 | 10% | 4.783 | -39.217 | 440 | 68 | 57.83% |  | 2026-05-15
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-11-06
2317. - CUWCD CWP Wellhouse 17 | 300.7300. - PLUM Plumbing | 63.31 | 125 | 61.69 | 50.65% | 170 | 150 | 100% | 125 | 61.69 | 63.31 | 63.31 | 149.4% |  | 2025-12-30
2607. - CUWCD Cathodic & Pump Improvements | 100.1703. - FS Job Site Superintendent | 6 | 177.84 | 171.84 | 3.374% | 0 | 177.84 | 0% | 177.84 | 171.84 | 177.84 | 177.84 | 100%
2607. - CUWCD Cathodic & Pump Improvements | 100.1700. - FS Project Manager | 132 | 128.21 | -3.79 | 103% | 10.598 | 141.31 | 7.738% | 9.9207 | -122.0793 | 1705.9046 | 128.21 | 100%
2219. - GHID 20D Kent Booster Station | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
|  | 925693.98 | 578654.96 | -347039.02 |  | 397813.553 | 512331.709 |  | 436902.2846 | -488791.6954 | 61478714.0547 | 797869.8 |  | 0