## Job Scheduling
Priority | Job | Start | Proj End | Milestone | Reason | Priority Department(s) | Liquidated Damage | Chad Wants
1 | 2508. Turner Dam & Joint Diversion Rehab | 2025-06-23 |  | 2026-04-24 06:00 | Finish up | [object Object],[object Object]
2 | 2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 2025-08-01 | 46022 | 2026-05-01 06:00 | Get through the intersections | [object Object],[object Object]
2 | 2519. Corix IEC Site Utilities | 2025-12-03 | 46113 | 2026-04-30 06:00 | Pave in June, Need 90's Fabricated | [object Object],[object Object],[object Object]
3 | 2503. HVSSD Headworks Upgrade | 2025-04-15 | 45945 |  | Punchlist Phase - Railing | [object Object]
4 | 2507. SLC Industrial Lift Station | 2025-07-01 |  | 2026-05-01 06:00 | Electrical, Mechanical punchlist | [object Object]
5 | 2321. CUWCD Santaquin Reach | 2023-12-01 | 46143 | 2026-05-20 06:00 | Pipe backfill, Pave | [object Object],[object Object],[object Object]
6 | 2511. GHID 25H East Rec. & Decker N. Improvements | 2025-09-30 | 46022 | 2026-04-30 06:00 | Finish Door by April 30 | [object Object]
7 | 2408. Santaquin City WRF Phase 3 Upgrades | 2024-09-30 | 46265 | 2026-05-29 06:00 | piping, concrete, Bypass by end of May | [object Object]
8 | 2407. So SLC Lift Station | 2024-09-30 | 46112 | 2026-05-29 06:00 | Startup pumps | [object Object],[object Object]
8 | 2605. Highland City Well #1&#5 Chlorine | 2026-02-06 | 46157 | 2026-04-27 06:00 | Finish by end of May | [object Object],[object Object],[object Object]
9 | 2316. CUWCD CWP Wellhouse 7 | 2023-06-30 | 46022 | 2026-04-30 06:00 | Punchlist | [object Object]
9 | 2510. Draper Pump Station #3 Improvements | 2025-09-01 | 46096 | 2026-05-29 06:00 | Set pumps, Vaults, Cathodics, Pulsco | [object Object],[object Object]
9 | 2512. South SLC Davis Tank Lid Replacement | 2025-10-01 | 46094 | 2026-05-15 06:00 | Finish outside coating
9 | 2516. Ephraim Lower Penstock Replacement | 2025-10-31 | 46326 | 2026-05-29 06:00 | Finish up and pack out | [object Object]
10 | 2611. CDSD Trickling Filter Replacement | 2026-03-31 | 46296 | 2026-05-29 06:00 | Replace Drive Unit & Arms | [object Object]
10 | 2650. Fab Shop Jobs 2026 Projects
11 | 2316. CUWCD CWP Wellhouse 17 | 2023-06-30 | 46021 | 2026-04-30 06:00 | punchlist | [object Object]
12 | 2316. CUWCD CWP Wellhouse 16 | 2023-06-30 | 46022 | 2025-05-16 06:00 | March 1 Well on! | [object Object],[object Object],[object Object] | 5000
12 | 2409. JVWCD 2024 Vault Improvement Project | 2024-11-22 | 46113 | 2026-04-30 06:00 | painting, punchlist, SUBS, QC | [object Object]
12 | 2411. CWSID Dewatering Bldg HVACV Project | 2025-01-01 | 46234 |  | HVAC SUB
12 | 2603. Highland City Mitchell Hollow Trail | 2026-02-01 | 46372 |  | Start 4/27 | [object Object]
13 | 2513. CUWCD Summit Creek Irrigation HDPE | 2025-10-01 | 46112 | 2026-10-30 06:00 | punchlist, Collars in Fall, DMJ
13 | 2518. Mt Pleasant Lagoon Improvement | 2025-11-30 | 46356 | 2026-05-29 06:00 | Demo, Fnd, concrete,
14 | 2604. Murray 900 East Storm Drain Phase 2 | 2026-02-02 | 46387 |  | Start May 18, | [object Object],[object Object]
16 | 2350. Fab Shop Jobs 2023 Projects
16 | 2602. JVWCD Rosecrest WSP Pipeline | 2026-02-09 | 46888 |  | Start June | [object Object],[object Object],[object Object],[object Object]
17 | 2231. UDOT Bangerter Hwy Aqueduct Protection | 2022-11-01 | 46142 | 2027-01-29 07:00 | Nov, Jan, | [object Object]
17 | 2410. Wellington Waterline Coal Creek PRV | 2025-01-01 | 45807 |  | PRV lid install in May
17 | 2506. UDOT Big Cottonwood Creek Culvert Preservation | 2025-05-05 | 45961 | 2025-10-16 | Contract deadline | [object Object]
17 | 2607. CUWCD Cathodic & Pump Improvements |  |  |  | June 1 Start on Deep Wells, & Anodes | [object Object]
17 | 2608. Springville City WRF Headworks | 2026-03-09 | 46265 |  | Start Electrical Building, | [object Object],[object Object]
18 | 2505. JVWCD JVWTP Chemical Bldg Upgrade | 2025-05-19 | 46052 |  | punchlist - ATC
18 | 2517. CUWCD Ashley Valley BWRB Rehab | 2025-11-01 | 46478
18 | 2550. Fab Shop Jobs 2025 Projects | 2025-01-01 | 46022
19 | 2312. SLC SW1 Sewer Forcemains & Influent Pipe |  | 45657 |  | Re work 84" Hobas | [object Object],[object Object],[object Object]
19 | 2515. UWCD Steinaker Service Canal Gate Rahab | 2025-10-07 | 46127
19 | 2609. JVWCD JA-1 Internal Buttstraps | 2026-03-23 | 46122
20 | 2325. Santaquin Flowfill/CLSM Project | 2023-12-01 | 46143
20 | 2450. Fab Shop Jobs 2024 Projects | 2024-01-01
20 | 2570. Jon Stubbs Hauling
20 | 2601. 2026 Misc. Jobs | 2026-01-01 | 46387 |  | Fall Sed basin work
20 | 2606. SLCo FAC126702 SMH HVAC Replacement | 2026-02-16 | 46069
20 | 14924. Elberta Pit Job
20 | 14924. Elberta test sub jobs