## Productivity Summary
Job | Phase | Actual Hours | Est Hours | Variance | Percent Used | Units Complete | Actual Units | % Complete | Calculated Budget Hrs | Calculated Budget Hrs-Actual | Calculated Projected Hours | Projected Hours | Efficiency Rate |  | End Date
2321. - CUWCD Santaquin Reach | 600.2930. - AP Asphalt Prep (DO NOT USE) | 35.91 | 48 | 12.09 | 74.81% | 0 | 48 | 0% | 48 | 12.09 | 48 | 85.91 | 21.02% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 1125.23 | 809.5 | -315.73 | 139% | 514 | 713.5 | 70.38% | 569.7147 | -555.5153 | 1598.8242 | 1125.23 | 61% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7800. - PRK Park Equipment | 21.87 | 79.52 | 57.65 | 27.5% | 63.616 | 79.52 | 80% | 63.616 | 41.746 | 27.3375 | 21.87 | 172.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2080. - EXS Excavate Structure | 1096.25 | 319 | -777.25 | 343.7% | 180 | 319 | 100% | 319 | -777.25 | 1096.25 | 1096.25 | -143.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2800. - BFST Backfill (DO NOT USE) | 311.59 | 64 | -247.59 | 486.9% | 49 | 64 | 100% | 64 | -247.59 | 311.59 | 311.59 | -286.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2710. - FWF Flowable Fill | 61.05 | 125 | 63.95 | 48.84% | 95 | 125 | 100% | 125 | 63.95 | 61.05 | 61.05 | 151.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.3000. - CNC Concrete Work | 2342.7 | 2364.5 | 21.8 | 99.08% | 1890 | 2364.5 | 80% | 1891.6 | -451.1 | 2928.375 | 2462.7 | 95.85% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 12929.58 | 4532.89 | -8396.69 | 285.2% | 3595.89 | 5422.89 | 100% | 4532.89 | -8396.69 | 12929.58 | 12929.58 | -85.24% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1600. - TC Traffic Control | 171.94 | 65 | -106.94 | 264.5% | 60 | 65 | 100% | 65 | -106.94 | 171.94 | 171.94 | -64.52% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 305.5000. - MET Metals | 57.65 | 28 | -29.65 | 205.9% | 28 | 28 | 44.44% | 12.4444 | -45.2056 | 129.7125 | 71.65 | -55.89% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2760. - HO Haul Off | 52.08 | 113.51 | 61.43 | 45.88% | 117.8 | 113.51 | 100% | 113.51 | 61.43 | 52.08 | 52.08 | 154.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2080. - EXS Excavate Structure | 1146.96 | 404.49 | -742.47 | 283.6% | 782.022 | 404.49 | 60% | 242.694 | -904.266 | 1911.6 | 1146.96 | -83.56% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2760. - HO Haul Off | 186.17 | 95.36 | -90.81 | 195.2% | 95.36 | 95.36 | 100% | 95.36 | -90.81 | 186.17 | 186.17 | 4.771% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.5000. - MET Metals | 46.67 | 79 | 32.33 | 59.08% | 79 | 79 | 97.41% | 76.9527 | 30.2827 | 47.9116 | 24.72 | 168.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.5000. - MET Metals | 10.53 | 103 | 92.47 | 10.22% | 103 | 103 | 97.52% | 100.4502 | 89.9202 | 10.7973 | 60.53 | 141.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2080. - EXS Excavate Structure | 422.53 | 485 | 62.47 | 87.12% | 435 | 485 | 100% | 485 | 62.47 | 422.53 | 422.53 | 112.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2300. - WPL Water Pipe Laying (DO NOT USE) | 70.73 | 209.56 | 138.83 | 33.75% | 209.56 | 209.56 | 100% | 209.56 | 138.83 | 70.73 | 70.73 | 166.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1940. - PL Punch List Work | 41.86 | 180 | 138.14 | 23.26% | 0 | 180 | 0% | 180 | 138.14 | 180 | 182.96 | 98.36% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 235.2300. - WPL Water Pipe Laying (DO NOT USE) | 250.67 | 205.38 | -45.29 | 122.1% | 205.38 | 205.38 | 100% | 205.38 | -45.29 | 250.67 | 250.67 | 77.95% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2300. - WPL Water Pipe Laying (DO NOT USE) | 105.2 | 363.9 | 258.7 | 28.91% | 219.51 | 363.9 | 90% | 327.51 | 222.31 | 116.8889 | 105.2 | 171.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2080. - EXS Excavate Structure | 963.28 | 457.5 | -505.78 | 210.6% | 465.75 | 457.5 | 100% | 457.5 | -505.78 | 963.28 | 963.28 | -10.55% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.5110. - FAB Shop Pipe Fabrication (DO NOT USE) | 329.95 | 77 | -252.95 | 428.5% | 1 | 77 | 100% | 77 | -252.95 | 329.95 | 329.95 | -228.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.3000. - CNC Concrete Work | 28.32 | 840 | 811.68 | 3.371% | 318.8 | 840 | 100% | 840 | 811.68 | 28.32 | 148.32 | 182.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2710. - FWF Flowable Fill | 13.27 | 64 | 50.73 | 20.73% | 16.5 | 64 | 100% | 64 | 50.73 | 13.27 | 13.27 | 179.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2610. - PT Pressure Test/Chlorinating | 212.51 | 0 | -212.51 |  | 0 | 0 | 0% | 0 | -212.51 | 212.51 | 212.51 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2050. - RW Retaining Walls | 10.25 | 126.66 | 116.41 | 8.093% | 0 | 126.66 | 0% | 126.66 | 116.41 | 126.66 | 135.25 | 93.22% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.7100. - IMP Interior Mech/Piping | 377.38 | 30 | -347.38 | 1258% | 25 | 30 | 100% | 30 | -347.38 | 377.38 | 377.38 | -1058% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 6961.59 | 3884.88 | -3076.71 | 179.2% | 90 | 3884.88 | 87.5% | 3399.27 | -3562.32 | 7956.1029 | 7251.18 | 13.35% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2090. - MTL Materials | 29.35 | 144.12 | 114.77 | 20.36% | 144.12 | 144.12 | 75.95% | 109.4554 | 80.1054 | 38.6452 | 77.35 | 146.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2760. - HO Haul Off | 137.24 | 2855.51 | 2718.27 | 4.806% | 2855.51 | 2855.51 | 100% | 2855.51 | 2718.27 | 137.24 | 137.24 | 195.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 96 | 174.8 | 78.8 | 54.92% | 174.8 | 174.8 | 28.66% | 50.1025 | -45.8975 | 334.9291 | 96 | 145.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.7900. - ELC Electrical | 12 | 215.48 | 203.48 | 5.569% | 198.48 | 215.48 | 100% | 215.48 | 203.48 | 12 | 12 | 194.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 210.2300. - WPL Water Pipe Laying (DO NOT USE) | 6976.85 | 1514.64 | -5462.21 | 460.6% | 2787.44 | 1514.64 | 100% | 1514.6403 | -5462.2097 | 6976.8484 | 6976.85 | -260.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2300. - WPL Water Pipe Laying (DO NOT USE) | 1174.3 | 756 | -418.3 | 155.3% | 756 | 756 | 100% | 756 | -418.3 | 1174.3 | 1174.3 | 44.67% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2750. - H Hauling | 182.19 | 1185.24 | 1003.05 | 15.37% | 1185.24 | 1185.24 | 100% | 1185.24 | 1003.05 | 182.19 | 182.19 | 184.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1710. - FS Starup/Commissioning | 5.07 | 60 | 54.93 | 8.45% | 0 | 60 | 0% | 60 | 54.93 | 60 | 105.07 | 24.88% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2800. - Unknown Phase | 237.33 | 38.49 | -198.84 | 616.6% | 162.711 | 38.49 | 90% | 34.641 | -202.689 | 263.7 | 237.33 | -416.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 240.2750. - H Hauling | 26.07 | 50 | 23.93 | 52.14% | 50 | 50 | 100% | 50 | 23.93 | 26.07 | 26.07 | 147.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 800.1940. - PL Punch List Work | 4 | 300 | 296 | 1.333% | 0 | 300 | 0% | 300 | 296 | 300 | 304 | 98.67% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7900. - ELC Electrical | 82.38 | 76 | -6.38 | 108.4% | 46 | 76 | 100% | 76 | -6.38 | 82.38 | 82.38 | 91.61% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2300. - WPL Water Pipe Laying (DO NOT USE) | 904.47 | 543.83 | -360.64 | 166.3% | 543.83 | 543.83 | 31.57% | 171.6987 | -732.7713 | 2864.7731 | 904.47 | 33.69% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1200. - HOOK Hook Truck Dumpster Transporting | 6.47 | 30 | 23.53 | 21.57% | 28.5 | 30 | 95% | 28.5 | 22.03 | 6.8105 | 6.47 | 178.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 161.3000. - CNC Concrete Work | 8.55 | 50 | 41.45 | 17.1% | 50 | 50 | 86.21% | 43.1034 | 34.5534 | 9.918 | 8.55 | 182.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.2750. - H Hauling | 20.45 | 3.41 | -17.04 | 599.7% | 3.41 | 3.41 | 100% | 3.41 | -17.04 | 20.45 | 20.45 | -399.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.6500. - Unknown Phase | 32.03 | 0 | -32.03 |  | -32.03 | 420 | -5.898% | 0 | -32.03 | -543.0457 | 32.03 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2610. - PT Pressure Test/Chlorinating | 2 | 20 | 18 | 10% | 20 | 20 | 100% | 20 | 18 | 2 | 2 | 190% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 35.54 | 0 | -35.54 |  | 0 | 0 | 0% | 0 | -35.54 | 35.54 | 35.54 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1930. - MC Misc Cleanup | 21.16 | 120 | 98.84 | 17.63% | 90 | 120 | 62.5% | 75 | 53.84 | 33.856 | 121.16 | 99.03% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1501. - SM Safety Meetings | 267.53 | 0 | -267.53 |  | 0 | 0 | 0% | 0 | -267.53 | 267.53 | 317.53 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.5400. - HAT Hatch/Skylights | 2 | 56 | 54 | 3.571% | 0 | 56 | 0% | 56 | 54 | 56 | 52 | 107.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2080. - EXS Excavate Structure | 366.29 | 340 | -26.29 | 107.7% | 198 | 340 | 100% | 340 | -26.29 | 366.29 | 366.29 | 92.27% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7900. - ELC Electrical | 297.5 | 427 | 129.5 | 69.67% | 257 | 427 | 100% | 427 | 129.5 | 297.5 | 278.85 | 134.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1510. - S Surveying | 100.83 | 90 | -10.83 | 112% | 39 | 90 | 65% | 58.5 | -42.33 | 155.1231 | 100.83 | 87.97% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.6200. - IN Insulation | 179.37 | 120 | -59.37 | 149.5% | 120 | 120 | 98.75% | 118.5 | -60.87 | 181.6405 | 134.34 | 88.05% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.7500. - PUMP Pumps/Motors | 58.34 | 45 | -13.34 | 129.6% | -10 | 45 | -33.33% | 45 | -13.34 | -175.02 | 98.34 | -18.53% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2300. - WPL Water Pipe Laying (DO NOT USE) | 8535.86 | 2445.34 | -6090.52 | 349.1% | 2395.34 | 2445.34 | 100% | 2445.34 | -6090.52 | 8535.86 | 8535.86 | -149.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.1510. - S Surveying | 122.78 | 50 | -72.78 | 245.6% | 40 | 50 | 36.67% | 18.3333 | -104.4467 | 334.8545 | 171.28 | -142.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2800. - BFST Backfill (DO NOT USE) | 280.64 | 210 | -70.64 | 133.6% | 210 | 210 | 100% | 210 | -70.64 | 280.64 | 280.64 | 66.36% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 180.2060. - FE Fencing | 6 | 8.53 | 2.53 | 70.34% | 5.851 | 8.53 | 84.83% | 7.2362 | 1.2362 | 7.0728 | 6 | 129.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.3000. - CNC Concrete Work | 1047.23 | 1410 | 362.77 | 74.27% | 1340 | 1410 | 100% | 1410 | 362.77 | 1047.23 | 1167.23 | 117.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.5000. - MET Metals | 74.68 | 147 | 72.32 | 50.8% | 139.65 | 147 | 95% | 139.65 | 64.97 | 78.6105 | 74.68 | 149.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.6500. - P Painting | 3 | 0 | -3 |  | 30 | 60 | 38.75% | 0 | -3 | 7.7419 | 3 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.1930. - MC Misc Cleanup | 57.9 | 80 | 22.1 | 72.38% | 16 | 80 | 10% | 8 | -49.9 | 579 | 107.9 | 65.12% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 116.36 | 92 | -24.36 | 126.5% | 72 | 92 | 75% | 69 | -47.36 | 155.1467 | 116.36 | 73.52% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2310. - WS Water Services (DO NOT USE) | 251.14 | 267 | 15.86 | 94.06% | 267 | 267 | 100% | 267 | 15.86 | 251.14 | 251.14 | 105.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2300. - WPL Water Pipe Laying (DO NOT USE) | 92.88 | 220.77 | 127.89 | 42.07% | 199.27 | 220.77 | 99.78% | 220.2795 | 127.3995 | 93.0868 | 92.88 | 157.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 86.57 | 311 | 224.43 | 27.84% | 100 | 100 | 100% | 311 | 224.43 | 86.57 | 86.57 | 172.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 850.7100. - IMP Interior Mech/Piping | 102.17 | 0 | -102.17 |  | 0 | 0 | 0% | 0 | -102.17 | 102.17 | 102.7 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2020. - CG Clearing/Grubbing | 84.83 | 20 | -64.83 | 424.2% | 20 | 20 | 100% | 20 | -64.83 | 84.83 | 84.83 | -224.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2080. - EXS Excavate Structure | 301.18 | 75 | -226.18 | 401.6% | 75 | 75 | 100% | 75 | -226.18 | 301.18 | 301.18 | -201.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.7800. - PRK Park Equipment | 46.83 | 70 | 23.17 | 66.9% | 70 | 70 | 100% | 70 | 23.17 | 46.83 | 46.83 | 133.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2800. - BFST Backfill (DO NOT USE) | 523.61 | 135 | -388.61 | 387.9% | 135 | 135 | 100% | 135 | -388.61 | 523.61 | 523.61 | -187.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.2080. - EXS Excavate Structure | 10.02 | 45 | 34.98 | 22.27% | 0 | 45 | 0% | 45 | 34.98 | 45 | 10.02 | 177.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2060. - FE Fencing | 30.69 | 18 | -12.69 | 170.5% | 18 | 18 | 100% | 18 | -12.69 | 30.69 | 30.69 | 29.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.7100. - IMP Interior Mech/Piping | 248.64 | 269 | 20.36 | 92.43% | 269 | 269 | 76.12% | 204.7595 | -43.8805 | 326.6474 | 306.64 | 86.01% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2750. - Unknown Phase | 4.22 | 2 | -2.22 | 211% | 0 | 2 | 0% | 2 | -2.22 | 4.22 | 4.22 | -11% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 800.1930. - MC Misc Cleanup | 438.61 | 300 | -138.61 | 146.2% | 270 | 300 | 90% | 270 | -168.61 | 487.3444 | 638.91 | -12.97% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7800. - PRK Park Equipment | 10.98 | 72 | 61.02 | 15.25% | 72 | 72 | 100% | 72 | 61.02 | 10.98 | 10.98 | 184.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 61.63 | 501.34 | 439.71 | 12.29% | 501.34 | 501.34 | 100% | 501.34 | 439.71 | 61.63 | 61.63 | 187.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1930. - MC Misc Cleanup | 22.05 | 60 | 37.95 | 36.75% | 54 | 60 | 70% | 42 | 19.95 | 31.5 | 62.05 | 96.58% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1610. - TC Concrete & Water Barrier | 10 | 110.67 | 100.67 | 9.036% | 110.67 | 110.67 | 100% | 110.67 | 100.67 | 10 | 10 | 191% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2750. - H Hauling | 122.34 | 135.16 | 12.82 | 90.51% | 103.8 | 134.8 | 85% | 114.886 | -7.454 | 143.9294 | 122.34 | 109.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2060. - FE Fencing | 2 | 30 | 28 | 6.667% | 30 | 30 | 80% | 24 | 22 | 2.5 | 2 | 193.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 1061.65 | 832.52 | -229.13 | 127.5% | 872.52 | 832.52 | 100% | 832.52 | -229.13 | 1061.65 | 1141.65 | 62.87% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1704. - FS Quality Control/Assurance | 2333.65 | 681.21 | -1652.44 | 342.6% | 90 | 681.21 | 87.5% | 596.0588 | -1737.5912 | 2667.0286 | 2366.65 | -147.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.5100. - W Welding | 551.58 | 61 | -490.58 | 904.2% | 61 | 61 | 100% | 61 | -490.58 | 551.58 | 551.58 | -704.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 290.7800. - PRK Park Equipment | 1462.33 | 1202.4 | -259.93 | 121.6% | 1312.16 | 1202.4 | 97.63% | 1173.8465 | -288.4835 | 1497.9008 | 1492.33 | 75.89% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2750. - H Hauling | 121.54 | 103.29 | -18.25 | 117.7% | 105.29 | 103.29 | 100% | 103.29 | -18.25 | 121.54 | 121.54 | 82.33% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2750. - H Hauling | 263.78 | 99.84 | -163.94 | 264.2% | 81.81 | 98.41 | 100% | 99.84 | -163.94 | 263.78 | 263.78 | -64.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2710. - FWF Flowable Fill | 52.03 | 419.04 | 367.01 | 12.42% | 419.04 | 419.04 | 100% | 419.04 | 367.01 | 52.03 | 52.03 | 187.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2750. - H Hauling | 288.54 | 1197.64 | 909.1 | 24.09% | 1197.64 | 1197.64 | 100% | 1197.64 | 909.1 | 288.54 | 288.54 | 175.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1930. - MC Misc Cleanup | 101.06 | 60 | -41.06 | 168.4% | 0 | 60 | 0% | 60 | -41.06 | 101.06 | 101.06 | 31.57% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2060. - FE Fencing | 48.5 | 15 | -33.5 | 323.3% | 15 | 15 | 92% | 13.8 | -34.7 | 52.7174 | 48.5 | -123.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2080. - EXS Excavate Structure | 253.27 | 90 | -163.27 | 281.4% | 90 | 90 | 100% | 90 | -163.27 | 253.27 | 253.27 | -81.41% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2710. - FWF Flowable Fill | 20.55 | 40 | 19.45 | 51.38% | 40 | 40 | 100% | 40 | 19.45 | 20.55 | 20.55 | 148.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2050. - RW Retaining Walls | 343.34 | 80 | -263.34 | 429.2% | 118.33 | 80 | 100% | 80 | -263.34 | 343.34 | 343.34 | -229.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.5000. - MET Metals | 68.44 | 43 | -25.44 | 159.2% | 43 | 43 | 97.5% | 41.925 | -26.515 | 70.1949 | 68.44 | 40.84% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 270.2760. - HO Haul Off | 67.13 | 65 | -2.13 | 103.3% | 37.05 | 65 | 60% | 39 | -28.13 | 111.8833 | 67.13 | 96.72% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2940. - CP Concrete Prep (DO NOT USE) | 344.02 | 790.02 | 446 | 43.55% | 840.02 | 790.02 | 100% | 790.02 | 446 | 344.02 | 344.02 | 156.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1940. - PL Punch List Work | 60.17 | 90 | 29.83 | 66.86% | 0 | 90 | 0% | 90 | 29.83 | 90 | 150.17 | 33.14% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 27.75 | 380 | 352.25 | 7.303% | 45.225 | 380 | 90% | 342 | 314.25 | 30.8333 | 27.75 | 192.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1930. - MC Misc Cleanup | 78.68 | 80 | 1.32 | 98.35% | 60 | 80 | 62.5% | 50 | -28.68 | 125.888 | 103.68 | 70.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.7100. - IMP Interior Mech/Piping | 198.09 | 131.5 | -66.59 | 150.6% | 119.592 | 131.5 | 59.93% | 78.8022 | -119.2878 | 330.5597 | 226.41 | 27.83% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1930. - MC Misc Cleanup | 327.51 | 120 | -207.51 | 272.9% | 60 | 100 | 30% | 36 | -291.51 | 1091.7 | 378.19 | -115.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2750. - H Hauling | 44.85 | 61.79 | 16.94 | 72.58% | 50.46 | 61.79 | 100% | 61.79 | 16.94 | 44.85 | 44.85 | 127.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.2080. - EXS Excavate Structure | 371.96 | 320 | -51.96 | 116.2% | 320 | 320 | 99.87% | 319.5753 | -52.3847 | 372.4543 | 371.96 | 83.76% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2800. - BFST Backfill (DO NOT USE) | 520.02 | 153.99 | -366.03 | 337.7% | 153.99 | 153.99 | 82.79% | 127.4821 | -392.5379 | 628.1499 | 520.02 | -137.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 380.2610. - PT Pressure Test/Chlorinating | 502.73 | 310 | -192.73 | 162.2% | 315.5 | 310 | 99.56% | 308.6295 | -194.1005 | 504.9624 | 502.73 | 37.83% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1930. - MC Misc Cleanup | 29.67 | 80 | 50.33 | 37.09% | 40 | 80 | 50% | 40 | 10.33 | 59.34 | 109.67 | 62.91% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 280.2300. - WPL Water Pipe Laying (DO NOT USE) | 34.23 | 40 | 5.77 | 85.58% | 45 | 40 | 100% | 40 | 5.77 | 34.23 | 34.23 | 114.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2750. - H Hauling | 93.41 | 458.86 | 365.45 | 20.36% | 422.69 | 458.86 | 36.04% | 165.3937 | 71.9837 | 259.152 | 93.41 | 179.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.6200. - IN Insulation | 150.48 | 150 | -0.48 | 100.3% | 41.4 | 150 | 22.02% | 33.0319 | -117.4481 | 683.3391 | 448.07 | -98.71% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2940. - CP Concrete Prep (DO NOT USE) | 15.6 | 20.8 | 5.2 | 75% | 20.8 | 20.8 | 100% | 20.8 | 5.2 | 15.6 | 15.6 | 125% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2750. - H Hauling | 122.12 | 228.87 | 106.75 | 53.36% | 284.784 | 228.87 | 93.59% | 214.2071 | 92.0871 | 130.4794 | 122.12 | 146.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2940. - CP Concrete Prep (DO NOT USE) | 3.4 | 15 | 11.6 | 22.67% | 0 | 15 | 0% | 15 | 11.6 | 15 | 3.4 | 177.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.3000. - CNC Concrete Work | 421.34 | 180 | -241.34 | 234.1% | 135 | 180 | 100% | 180 | -241.34 | 421.34 | 421.34 | -34.08% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2800. - BFST Backfill (DO NOT USE) | 160.86 | 303 | 142.14 | 53.09% | 151.5 | 303 | 21.43% | 64.9286 | -95.9314 | 750.68 | 427.25 | 58.99% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 395.5100. - W Welding | 4701.18 | 3797 | -904.18 | 123.8% | 3717.8 | 3787 | 98.78% | 3750.7328 | -950.4472 | 4759.1714 | 4701.18 | 76.19% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2800. - BFST Backfill (DO NOT USE) | 256.17 | 633.46 | 377.29 | 40.44% | 631.67 | 633.46 | 71.32% | 451.7593 | 195.5893 | 359.2034 | 256.17 | 159.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1510. - S Surveying | 215.02 | 115 | -100.02 | 187% | 95 | 115 | 98.33% | 113.0833 | -101.9367 | 218.6644 | 215.02 | 13.03% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 356.64 | 546.19 | 189.55 | 65.3% | 273.1 | 546.19 | 100% | 546.19 | 189.55 | 356.64 | 356.64 | 134.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.5000. - MET Metals | 399.05 | 557.5 | 158.45 | 71.58% | 55.288 | 557.5 | 7.51% | 41.869 | -357.181 | 5313.4812 | 587.91 | 94.55% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 390.2300. - WPL Water Pipe Laying (DO NOT USE) | 5215.38 | 3512.71 | -1702.67 | 148.5% | 3134.53 | 3512.71 | 99.77% | 3504.689 | -1710.691 | 5227.3162 | 5213.88 | 51.57% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9010. - Re-Work Pipe | 128.38 | 0.4 | -127.98 | 32095% | 0.4 | 0.4 | 100% | 0.4 | -127.98 | 128.38 | 128.38 | -31895% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1705. - FS Estimator/Change Orders/Scheduling | 16.88 | 10 | -6.88 | 168.8% | 10 | 10 | 100% | 10 | -6.88 | 16.88 | 16.88 | 31.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1230. - T Transporting | 102.86 | 120 | 17.14 | 85.72% | 114 | 120 | 95% | 114 | 11.14 | 108.2737 | 102.86 | 114.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 240.2760. - HO Haul Off | 481.14 | 625.5 | 144.36 | 76.92% | 625.5 | 625.5 | 100% | 625.5 | 144.36 | 481.14 | 481.14 | 123.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1200. - HOOK Hook Truck Dumpster Transporting | 3 | 10 | 7 | 30% | 7.5 | 10 | 100% | 10 | 7 | 3 | 3 | 170% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1230. - T Transporting | 12 | 40 | 28 | 30% | 40 | 40 | 125% | 50 | 38 | 9.6 | 12 | 170% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2020. - Unknown Phase | 1003.32 | 1704.6 | 701.28 | 58.86% | 1704.6 | 1704.6 | 100% | 1704.6 | 701.28 | 1003.32 | 1003.32 | 141.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.5100. - W Welding | 111.3 | 17.5 | -93.8 | 636% | 17.5 | 17.5 | 100% | 17.5 | -93.8 | 111.3 | 111.3 | -436% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2300. - WPL Water Pipe Laying (DO NOT USE) | 18808.9 | 6207.75 | -12601.15 | 303% | 5978.25 | 6207.75 | 100% | 6207.75 | -12601.15 | 18808.9 | 18808.9 | -103% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.6200. - IN Insulation | 73.89 | 60 | -13.89 | 123.2% | 171.9 | 60 | 90% | 54 | -19.89 | 82.1 | 73.89 | 76.85% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2020. - CG Clearing/Grubbing | 69.76 | 4 | -65.76 | 1744% | 4 | 4 | 100% | 4 | -65.76 | 69.76 | 69.76 | -1544% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2020. - CG Clearing/Grubbing | 10.58 | 6 | -4.58 | 176.3% | 6 | 6 | 100% | 6 | -4.58 | 10.58 | 10.58 | 23.67% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7100. - IMP Interior Mech/Piping | 205.66 | 224.34 | 18.68 | 91.67% | 201.906 | 224.34 | 69.07% | 154.9423 | -50.7177 | 297.7738 | 264.69 | 82.01% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2800. - BFST Backfill (DO NOT USE) | 99.53 | 1653.73 | 1554.2 | 6.019% | 1623.357 | 1653.73 | 90% | 1488.357 | 1388.827 | 110.5889 | 99.53 | 194% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.7900. - ELC Electrical | 199.25 | 253.33 | 54.08 | 78.65% | 173.33 | 253.33 | 57.57% | 145.8445 | -53.4055 | 346.0946 | 199.25 | 121.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2300. - WPL Water Pipe Laying (DO NOT USE) | 61.92 | 113.06 | 51.14 | 54.77% | 113.06 | 113.06 | 100% | 113.06 | 51.14 | 61.92 | 61.92 | 145.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2080. - EXS Excavate Structure | 734.05 | 558 | -176.05 | 131.6% | 558 | 558 | 100% | 558 | -176.05 | 734.05 | 735.55 | 68.18% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.6500. - P Painting | 5 | 0 | -5 |  | 0 | 150 | 0% | 0 | -5 | 5 | 5 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 270.2750. - H Hauling | 9.55 | 32.96 | 23.41 | 28.97% | 18.786 | 32.96 | 60% | 19.776 | 10.226 | 15.9167 | 9.55 | 171% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 240.2300. - WPL Water Pipe Laying (DO NOT USE) | 6937.48 | 1784 | -5153.48 | 388.9% | 1590.75 | 1784 | 100% | 1784 | -5153.48 | 6937.48 | 6937.48 | -188.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 340.2300. - WPL Water Pipe Laying (DO NOT USE) | 516.5 | 540.98 | 24.48 | 95.47% | 529.083 | 540.98 | 98.17% | 531.0648 | 14.5648 | 526.1432 | 516.5 | 104.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1700. - FS Project Manager | 26.25 | 20 | -6.25 | 131.2% | 0 | 20 | 0% | 20 | -6.25 | 26.25 | 66.25 | -131.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.7100. - IMP Interior Mech/Piping | 466.37 | 171 | -295.37 | 272.7% | 171 | 171 | 65.53% | 112.0634 | -354.3066 | 711.6444 | 479.38 | -80.34% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.6200. - IN Insulation | 13.13 | 30 | 16.87 | 43.77% | 0 | 30 | 0% | 30 | 16.87 | 30 | 29 | 103.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.3000. - CNC Concrete Work | 862.79 | 937.75 | 74.96 | 92.01% | 918.995 | 937.75 | 98% | 918.995 | 56.205 | 880.398 | 982.79 | 95.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1230. - T Transporting | 67.07 | 90 | 22.93 | 74.52% | 90 | 90 | 100% | 90 | 22.93 | 67.07 | 67.07 | 125.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.1510. - S Surveying | 36.08 | 88 | 51.92 | 41% | 88 | 88 | 100% | 88 | 51.92 | 36.08 | 36.08 | 159% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1703. - FS Job Site Superintendent | 7886.62 | 6138.16 | -1748.46 | 128.5% | 90 | 6138.16 | 87.5% | 5370.89 | -2515.73 | 9013.28 | 8121.62 | 67.69% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 330.1600. - TC Traffic Control | 3328.01 | 800 | -2528.01 | 416% | 860 | 800 | 99.07% | 792.5373 | -2535.4727 | 3359.3471 | 3326.83 | -215.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2070. - RGC Rough Grade Cut | 13.32 | 12 | -1.32 | 111% | 6 | 12 | 50% | 6 | -7.32 | 26.64 | 13.32 | 89% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1940. - PL Punch List Work | 10.17 | 90 | 79.83 | 11.3% | 0 | 90 | 0% | 90 | 79.83 | 90 | 90.17 | 99.81% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.5100. - W Welding | 260.84 | 65 | -195.84 | 401.3% | 65 | 65 | 40% | 26 | -234.84 | 652.1 | 310.84 | -278.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1230. - T Transporting | 52.81 | 50 | -2.81 | 105.6% | 50 | 50 | 100% | 50 | -2.81 | 52.81 | 52.81 | 94.38% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.1230. - T Transporting | 2592.83 | 867 | -1725.83 | 299.1% | 972 | 862 | 87.8% | 761.208 | -1831.622 | 2953.179 | 2671.79 | -108.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.5000. - MET Metals | 757.9 | 404.4 | -353.5 | 187.4% | 371.4 | 389.4 | 54.88% | 221.9226 | -535.9774 | 1381.0883 | 787.9 | 5.168% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9005. - Re-Work Surveying | 6.5 | 1 | -5.5 | 650% | 1 | 1 | 100% | 1 | -5.5 | 6.5 | 6.5 | -450% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 235.2080. - EXS Excavate Structure | 374.39 | 360 | -14.39 | 104% | 360 | 360 | 100% | 360 | -14.39 | 374.39 | 374.39 | 96% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.7800. - PRK Park Equipment | 344.01 | 36.66 | -307.35 | 938.4% | 36.66 | 36.66 | 100% | 36.66 | -307.35 | 344.01 | 344.01 | -738.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 181.3100. - CNC Rebar | 264.02 | 0 | -264.02 |  | 0 | 0 | 0% | 0 | -264.02 | 264.02 | 264.02 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.3000. - CNC Concrete Work | 2405.42 | 1879.27 | -526.15 | 128% | 1503.416 | 1879.27 | 57.58% | 1082.0065 | -1323.4135 | 4177.8248 | 2359.03 | 74.47% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2760. - HO Haul Off | 21.87 | 152.5 | 130.63 | 14.34% | 22.875 | 152.5 | 99.98% | 152.4667 | 130.5967 | 21.8748 | 21.87 | 185.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 263.03 | 201 | -62.03 | 130.9% | 110 | 201 | 100% | 201 | -62.03 | 263.03 | 263.03 | 69.14% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1510. - S Surveying | 22.46 | 110 | 87.54 | 20.42% | 75 | 110 | 100% | 110 | 87.54 | 22.46 | 22.46 | 179.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.6500. - P Painting | 20.03 | 0 | -20.03 |  | 32.03 | 60 | 0% | 0 | -20.03 | 20.03 | 20.03 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1930. - MC Misc Cleanup | 29.47 | 40 | 10.53 | 73.67% | 36 | 40 | 90% | 36 | 6.53 | 32.7444 | 39.47 | 101.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1710. - FS Starup/Commissioning | 1.29 | 40 | 38.71 | 3.225% | 0 | 40 | 0% | 40 | 38.71 | 40 | 41.29 | 96.78% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1200. - HOOK Hook Truck Dumpster Transporting | 3.7 | 20 | 16.3 | 18.5% | 13 | 20 | 65% | 13 | 9.3 | 5.6923 | 3.7 | 181.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1600. - TC Traffic Control | 448.62 | 400 | -48.62 | 112.2% | 400 | 400 | 100% | 400 | -48.62 | 448.62 | 448.62 | 87.84% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.5100. - W Welding | 133.24 | 152.8 | 19.56 | 87.2% | 80 | 80 | 100% | 152.8 | 19.56 | 133.24 | 133.24 | 112.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.5100. - W Welding | 109.5 | 30.17 | -79.33 | 362.9% | 16.67 | 30.17 | 100% | 30.17 | -79.33 | 109.5 | 109.5 | -162.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1700. - FS Project Manager | 3893.08 | 4180.8 | 287.72 | 93.12% | 144 | 4180.8 | 87.23% | 3646.8037 | -246.2763 | 4463.1381 | 4142.58 | 100.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.2750. - H Hauling | 53.27 | 1.14 | -52.13 | 4673% | 0 | 1.14 | 0% | 1.14 | -52.13 | 53.27 | 53.27 | -4473% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2040. - LR Landscaping/Restoration | 48.69 | 2865.59 | 2816.9 | 1.699% | 2349.19 | 2865.59 | 100% | 2865.59 | 2816.9 | 48.69 | 48.69 | 198.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2750. - H Hauling | 149.07 | 196.95 | 47.88 | 75.69% | 95.725 | 191.45 | 37.5% | 73.856 | -75.214 | 397.5214 | 206.96 | 94.92% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7100. - IMP Interior Mech/Piping | 458.04 | 410.33 | -47.71 | 111.6% | 410.33 | 410.33 | 73.62% | 302.0831 | -155.9569 | 622.1716 | 642.03 | 43.53% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.6300. - DAW Doors & Windows | 64.97 | 90 | 25.03 | 72.19% | 63 | 90 | 52.5% | 47.25 | -17.72 | 123.7524 | 114.97 | 72.26% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2410. - IS Irrigation Services (DO NOT USE) | 117.52 | 658.84 | 541.32 | 17.84% | 658.84 | 658.84 | 100% | 658.84 | 541.32 | 117.52 | 117.52 | 182.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.7900. - ELC Electrical | 93.34 | 200.28 | 106.94 | 46.6% | 42.002 | 200.28 | 20% | 40.056 | -53.284 | 466.7 | 93.34 | 153.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2750. - H Hauling | 155.51 | 804.73 | 649.22 | 19.32% | 797.73 | 804.73 | 100% | 804.73 | 649.22 | 155.51 | 155.51 | 180.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2800. - BFST Backfill (DO NOT USE) | 407.9 | 388.41 | -19.49 | 105% | 214.956 | 388.41 | 90% | 349.569 | -58.331 | 453.2222 | 407.9 | 94.98% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 295.7900. - ELC Electrical | 699.42 | 1931.34 | 1231.92 | 36.21% | 1913.21 | 1931.34 | 100% | 1931.34 | 1231.92 | 699.42 | 699.42 | 163.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2760. - HO Haul Off | 531.4 | 1645 | 1113.6 | 32.3% | 1645 | 1645 | 100% | 1645 | 1113.6 | 531.4 | 531.4 | 167.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 285.2760. - HO Haul Off | 41.77 | 98.5 | 56.73 | 42.41% | 98.5 | 98.5 | 100% | 98.5 | 56.73 | 41.77 | 41.77 | 157.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2050. - RW Retaining Walls | 88.86 | 63.92 | -24.94 | 139% | 31.96 | 63.92 | 68% | 43.4634 | -45.3966 | 130.683 | 88.86 | 60.98% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 210.2750. - H Hauling | 156.16 | 271.82 | 115.66 | 57.45% | 135.91 | 271.82 | 100% | 271.82 | 115.66 | 156.16 | 156.16 | 142.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.5000. - MET Metals | 35.31 | 75 | 39.69 | 47.08% | 121.25 | 75 | 83.45% | 62.5862 | 27.2762 | 42.3136 | 57.71 | 123.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.5100. - W Welding | 7.27 | 20 | 12.73 | 36.35% | 20 | 20 | 100% | 20 | 12.73 | 7.27 | 7.27 | 163.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.2800. - BFST Backfill (DO NOT USE) | 60.78 | 15.99 | -44.79 | 380.1% | 0 | 15.99 | 0% | 15.99 | -44.79 | 60.78 | 60.78 | -180.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2700. - SG Sand & Gravel | 11.37 | -10 | -21.37 |  | 1 | -10 | 100% | -10 | -21.37 | 11.37 | 11.37 | 313.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.3000. - CNC Concrete Work | 492.05 | 50 | -442.05 | 984.1% | 18 | 50 | 56.52% | 28.2609 | -463.7891 | 870.55 | 492.05 | -784.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2750. - H Hauling | 1033.17 | 1431.99 | 398.82 | 72.15% | 1412.49 | 1431.99 | 100% | 1431.99 | 398.82 | 1033.17 | 1033.17 | 127.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9015. - Re-Work Concrete | 46.49 | 0.4 | -46.09 | 11622% | 0.4 | 0.4 | 100% | 0.4 | -46.09 | 46.49 | 46.49 | -11422% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.2080. - EXS Excavate Structure | 365.63 | 360 | -5.63 | 101.6% | 360 | 360 | 100% | 360 | -5.63 | 365.63 | 365.63 | 98.44% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1500. - VIS Meetings (Vision, Safety, Training) | 144.8 | 0 | -144.8 |  | 0 | 0 | 0% | 0 | -144.8 | 144.8 | 144.8 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 37.02 | 90 | 52.98 | 41.13% | 90 | 90 | 100% | 90 | 52.98 | 37.02 | 37.02 | 158.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.7900. - ELC Electrical | 63.15 | 0 | -63.15 |  | 0 | 0 | 0% | 0 | -63.15 | 63.15 | 63.15 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2910. - MP Milling/Pulverize | 34.48 | 235.79 | 201.31 | 14.62% | 235.79 | 235.79 | 100% | 235.79 | 201.31 | 34.48 | 34.48 | 185.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 345.2300. - WPL Water Pipe Laying (DO NOT USE) | 1778.9 | 1050 | -728.9 | 169.4% | 1050 | 1050 | 100% | 1050 | -728.9 | 1778.9 | 1778.9 | 30.58% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7500. - PUMP Pumps/Motors | 69.46 | 45 | -24.46 | 154.4% | 45 | 45 | 91.67% | 41.25 | -28.21 | 75.7745 | 69.46 | 45.64% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 385.2300. - WPL Water Pipe Laying (DO NOT USE) | 1202.26 | 2968.34 | 1766.08 | 40.5% | 2846.51 | 2968.34 | 99.97% | 2967.4589 | 1765.1989 | 1202.617 | 1202.26 | 159.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 97.08 | 172 | 74.92 | 56.44% | 172 | 172 | 100% | 172 | 74.92 | 97.08 | 97.08 | 143.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2140. - SVR Services | 269.15 | 171 | -98.15 | 157.4% | 1 | 171 | 100% | 171 | -98.15 | 269.15 | 269.15 | 42.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2020. - CG Clearing/Grubbing | 62.16 | 60 | -2.16 | 103.6% | 30 | 60 | 100% | 60 | -2.16 | 62.16 | 62.16 | 96.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.6200. - IN Insulation | 396.74 | 84.48 | -312.26 | 469.6% | 84.48 | 84.48 | 100% | 84.48 | -312.26 | 396.74 | 368.74 | -236.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1510. - S Surveying | 127.84 | 50 | -77.84 | 255.7% | 50 | 50 | 100% | 50 | -77.84 | 127.84 | 127.84 | -55.68% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.7900. - ELC Electrical | 10.77 | 114 | 103.23 | 9.447% | 108 | 114 | 100% | 114 | 103.23 | 10.77 | 10.77 | 190.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2110. - SS Sewer Services (DO NOT USE) | 249.08 | 580.67 | 331.59 | 42.9% | 580.67 | 580.67 | 100% | 580.67 | 331.59 | 249.08 | 249.08 | 157.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7500. - PUMP Pumps/Motors | 25.56 | 45 | 19.44 | 56.8% | 45 | 45 | 97.5% | 43.875 | 18.315 | 26.2154 | 25.56 | 143.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.2930. - AP Asphalt Prep (DO NOT USE) | 339.38 | 88.88 | -250.5 | 381.8% | 88.88 | 88.88 | 100% | 88.88 | -250.5 | 339.38 | 339.38 | -181.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 85.56 | 83 | -2.56 | 103.1% | 0 | 83 | 0% | 83 | -2.56 | 85.56 | 85.56 | 96.92% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 750.2300. - WPL Water Pipe Laying (DO NOT USE) | 375.48 | 455.4 | 79.92 | 82.45% | 0 | 0 | 0% | 455.4 | 79.92 | 455.4 | 375.48 | 117.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1940. - PL Punch List Work | 6.44 | 90 | 83.56 | 7.156% | 0 | 90 | 0% | 90 | 83.56 | 90 | 96.44 | 92.84% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2080. - EXS Excavate Structure | 578.56 | 114.3 | -464.26 | 506.2% | 114.3 | 114.3 | 100% | 114.3 | -464.26 | 578.56 | 578.56 | -306.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.3000. - CNC Concrete Work | 1183.16 | 1830 | 646.84 | 64.65% | 1824 | 1830 | 100% | 1830 | 646.84 | 1183.16 | 1183.16 | 135.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2080. - EXS Excavate Structure | 1330.33 | 231.67 | -1098.66 | 574.2% | 231.67 | 231.67 | 100% | 231.67 | -1098.66 | 1330.33 | 1330.33 | -374.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.5000. - MET Metals | 175.26 | 42.02 | -133.24 | 417.1% | 22 | 42.02 | 86.22% | 36.2315 | -139.0285 | 203.2601 | 180.26 | -229% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.3000. - CNC Concrete Work | 1568.17 | 1909.25 | 341.08 | 82.14% | 1894.25 | 1909.25 | 100% | 1909.25 | 341.08 | 1568.17 | 1568.17 | 117.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9012. - Re-Work Mechanical | 20.83 | 0.4 | -20.43 | 5208% | 0.4 | 0.4 | 100% | 0.4 | -20.43 | 20.83 | 20.83 | -5008% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1230. - T Transporting | 100.69 | 62 | -38.69 | 162.4% | 60 | 62 | 100% | 62 | -38.69 | 100.69 | 100.69 | 37.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.7500. - PUMP Pumps/Motors | 36.66 | 45 | 8.34 | 81.47% | 45 | 45 | 100% | 45 | 8.34 | 36.66 | 36.66 | 118.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.2800. - BFST Backfill (DO NOT USE) | 291.91 | 263.67 | -28.24 | 110.7% | 263.67 | 263.67 | 84.92% | 223.9039 | -68.0061 | 343.7543 | 291.91 | 89.29% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 285.2300. - WPL Water Pipe Laying (DO NOT USE) | 522.87 | 387.38 | -135.49 | 135% | 238.866 | 387.38 | 60% | 232.428 | -290.442 | 871.45 | 522.87 | 65.02% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2760. - HO Haul Off | 40.27 | 0 | -40.27 |  | 0 | 0 | 0% | 0 | -40.27 | 40.27 | 40.27 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 180.2040. - LR Landscaping/Restoration | 10.83 | 20 | 9.17 | 54.15% | 1 | 20 | 66.67% | 13.3333 | 2.5033 | 16.245 | 10.83 | 145.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2710. - FWF Flowable Fill | 11.35 | 295.88 | 284.53 | 3.836% | 295.88 | 295.88 | 100% | 295.88 | 284.53 | 11.35 | 11.35 | 196.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.5100. - W Welding | 160.21 | 55 | -105.21 | 291.3% | 40 | 55 | 86.67% | 47.6667 | -112.5433 | 184.8577 | 160.21 | -91.29% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 210.2760. - HO Haul Off | 411.1 | 777 | 365.9 | 52.91% | 671.6 | 777 | 100% | 777 | 365.9 | 411.1 | 411.1 | 147.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 235.2800. - BFST Backfill (DO NOT USE) | 75.86 | 402 | 326.14 | 18.87% | 360 | 402 | 100% | 402 | 326.14 | 75.86 | 75.86 | 181.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.6200. - IN Insulation | 92.56 | 111 | 18.44 | 83.39% | 99.9 | 111 | 90% | 99.9 | 7.34 | 102.8444 | 80.26 | 127.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2030. - D Demolition | 28.08 | 39 | 10.92 | 72% | 39 | 39 | 100% | 39 | 10.92 | 28.08 | 28.08 | 128% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2080. - EXS Excavate Structure | 64.54 | 26 | -38.54 | 248.2% | 26 | 26 | 100% | 26 | -38.54 | 64.54 | 64.54 | -48.23% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 1014.7 | 1124.71 | 110.01 | 90.22% | 1035.71 | 1124.71 | 99.93% | 1123.8796 | 109.1796 | 1015.4497 | 1014.7 | 109.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 305.2800. - BFST Backfill (DO NOT USE) | 37.8 | 15.99 | -21.81 | 236.4% | 0 | 15.99 | 0% | 15.99 | -21.81 | 37.8 | 37.8 | -36.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.2800. - BFST Backfill (DO NOT USE) | 233.23 | 180 | -53.23 | 129.6% | 180 | 180 | 100% | 180 | -53.23 | 233.23 | 233.23 | 70.43% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2070. - RGC Rough Grade Cut | 3994.2 | 1067.7 | -2926.5 | 374.1% | 1460.3 | 1067 | 96.46% | 1029.9119 | -2964.2881 | 4140.7495 | 4018.2 | -176.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1510. - S Surveying | 75.66 | 50 | -25.66 | 151.3% | 50 | 50 | 100% | 50 | -25.66 | 75.66 | 75.66 | 48.68% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 175.2300. - WPL Water Pipe Laying (DO NOT USE) | 125.03 | 0 | -125.03 |  | 1 | 0 | 66.67% | 0 | -125.03 | 187.545 | 125.03 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.1940. - PL Punch List Work | 36.63 | 150 | 113.37 | 24.42% | 0 | 150 | 0% | 150 | 113.37 | 150 | 157.25 | 95.17% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.2760. - HO Haul Off | 18.24 | 67.33 | 49.09 | 27.09% | 67.33 | 67.33 | 100% | 67.33 | 49.09 | 18.24 | 18.24 | 172.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.7500. - PUMP Pumps/Motors | 15.59 | 45 | 29.41 | 34.64% | 36 | 45 | 61.25% | 27.5625 | 11.9725 | 25.4531 | 15.59 | 165.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7100. - IMP Interior Mech/Piping | 820.85 | 361.86 | -458.99 | 226.8% | 343.767 | 361.86 | 73.08% | 264.4521 | -556.3979 | 1123.2009 | 861.04 | -37.95% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.5000. - MET Metals | 33.57 | 132 | 98.43 | 25.43% | 0 | 132 | 0% | 132 | 98.43 | 132 | 163.57 | 76.08% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2800. - BFST Backfill (DO NOT USE) | 476.68 | 486.22 | 9.54 | 98.04% | 486.22 | 486.22 | 100% | 486.22 | 9.54 | 476.68 | 476.68 | 102% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.7100. - IMP Interior Mech/Piping | 140.48 | 120 | -20.48 | 117.1% | 64.8 | 120 | 60% | 72 | -68.48 | 234.1333 | 140.48 | 82.93% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.6500. - P Painting | 2.2 | 0 | -2.2 |  | 0 | 1077 | 0% | 0 | -2.2 | 2.2 | 2.2 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.7900. - ELC Electrical | 62.83 | 188 | 125.17 | 33.42% | 80 | 188 | 99.27% | 186.6227 | 123.7927 | 63.2937 | 62.83 | 166.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 117.69 | 117.69 | 0% | 117.69 | 117.69 | 100% | 117.69 | 117.69 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2300. - WPL Water Pipe Laying (DO NOT USE) | 824.01 | 416.3 | -407.71 | 197.9% | 416.3 | 416.3 | 100% | 416.3 | -407.71 | 824.01 | 824.01 | 2.063% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2300. - WPL Water Pipe Laying (DO NOT USE) | 72.65 | 62 | -10.65 | 117.2% | 62 | 62 | 100% | 62 | -10.65 | 72.65 | 72.65 | 82.82% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.2800. - BFST Backfill (DO NOT USE) | 98.3 | 360 | 261.7 | 27.31% | 360 | 360 | 100% | 360 | 261.7 | 98.3 | 98.3 | 172.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2610. - PT Pressure Test/Chlorinating | 2.78 | 10 | 7.22 | 27.8% | 0 | 10 | 0% | 10 | 7.22 | 10 | 2.78 | 172.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.5100. - W Welding | 351.62 | 120 | -231.62 | 293% | 120 | 120 | 100% | 120 | -231.62 | 351.62 | 351.62 | -93.02% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2060. - Unknown Phase | 137.11 | 652.6 | 515.49 | 21.01% | 652.6 | 652.6 | 100% | 652.6 | 515.49 | 137.11 | 137.11 | 179% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2610. - PT Pressure Test/Chlorinating | 206.67 | 40 | -166.67 | 516.7% | 40 | 40 | 100% | 40 | -166.67 | 206.67 | 206.67 | -316.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.6000. - IF Interior Finishes | 10.23 | 6 | -4.23 | 170.5% | 6 | 6 | 75% | 4.5 | -5.73 | 13.64 | 10.23 | 29.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2800. - BFST Backfill (DO NOT USE) | 222.12 | 271.72 | 49.6 | 81.75% | 247.18 | 271.82 | 100% | 271.72 | 49.6 | 222.12 | 222.12 | 118.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.7100. - IMP Interior Mech/Piping | 152.22 | 150 | -2.22 | 101.5% | 84.375 | 150 | 67.31% | 100.9615 | -51.2585 | 226.1554 | 192.07 | 71.95% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.6200. - IN Insulation | 19.45 | 0.12 | -19.33 | 16208% | 1 | 0.12 | 50% | 0.06 | -19.39 | 38.9 | 19.45 | -16008% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 363.53 | 1076 | 712.47 | 33.79% | 900 | 1076 | 100% | 1075.9634 | 712.4334 | 363.5424 | 363.53 | 166.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2760. - HO Haul Off | 49.11 | 777.33 | 728.22 | 6.318% | 583.677 | 798.04 | 90% | 699.597 | 650.487 | 54.5667 | 49.11 | 193.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 88.86 | 105.12 | 16.26 | 84.53% | 105.12 | 105.12 | 100% | 105.12 | 16.26 | 88.86 | 88.86 | 115.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 220.2710. - FWF Flowable Fill | 7.62 | 408.88 | 401.26 | 1.864% | 408.88 | 408.88 | 100% | 408.88 | 401.26 | 7.62 | 7.62 | 198.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2750. - H Hauling | 122.18 | 95.4 | -26.78 | 128.1% | 14.31 | 95.4 | 100% | 95.4 | -26.78 | 122.18 | 122.18 | 71.93% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.1510. - S Surveying | 35.11 | 30 | -5.11 | 117% | 30 | 30 | 100% | 30 | -5.11 | 35.11 | 35.11 | 82.97% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1930. - MC Misc Cleanup | 69.48 | 60 | -9.48 | 115.8% | 30 | 60 | 37.5% | 22.5 | -46.98 | 185.28 | 69.48 | 84.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.1700. - FS Project Manager | 9.72 | 40 | 30.28 | 24.3% | 0 | 40 | 0% | 40 | 30.28 | 40 | 39.72 | 100.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.7100. - IMP Interior Mech/Piping | 246.78 | 1028 | 781.22 | 24.01% | 326.2 | 1028 | 21.63% | 222.3467 | -24.4333 | 1140.9651 | 867.52 | 115.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2750. - H Hauling | 169.99 | 141.27 | -28.72 | 120.3% | 132.27 | 135.27 | 80% | 113.016 | -56.974 | 212.4875 | 169.99 | 79.67% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.2750. - H Hauling | 318.1 | 500.61 | 182.51 | 63.54% | 477.86 | 500.61 | 100% | 500.61 | 182.51 | 318.1 | 318.1 | 136.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1510. - S Surveying | 86.77 | 75 | -11.77 | 115.7% | 75 | 75 | 86.67% | 65 | -21.77 | 100.1192 | 86.77 | 84.31% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.6200. - IN Insulation | 134.76 | 102.27 | -32.49 | 131.8% | 161.7 | 102.27 | 99.42% | 101.6744 | -33.0856 | 135.5495 | 120.99 | 81.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2750. - H Hauling | 38.92 | 0.09 | -38.83 | 43244% | 0.09 | 0.09 | 100% | 0.09 | -38.83 | 38.92 | 38.92 | -43044% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.6200. - IN Insulation | 340.3 | 84.48 | -255.82 | 402.8% | 84.48 | 84.48 | 100% | 84.48 | -255.82 | 340.3 | 350.3 | -214.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.5100. - W Welding | 24.9 | 7.5 | -17.4 | 332% | 7.5 | 7.5 | 100% | 7.5 | -17.4 | 24.9 | 24.9 | -132% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2080. - EXS Excavate Structure | 799.08 | 180 | -619.08 | 443.9% | 180 | 180 | 19.57% | 35.2174 | -763.8626 | 4084.1867 | 799.08 | -243.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 245.2800. - BFST Backfill (DO NOT USE) | 100.75 | 360 | 259.25 | 27.99% | 360 | 360 | 100% | 360 | 259.25 | 100.75 | 100.75 | 172% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1200. - HOOK Hook Truck Dumpster Transporting | 281.68 | 60 | -221.68 | 469.5% | 57 | 60 | 92.5% | 55.5 | -226.18 | 304.5189 | 301.5 | -302.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.7900. - ELC Electrical | 61.7 | 90 | 28.3 | 68.56% | 90 | 90 | 100% | 90 | 28.3 | 61.7 | 61.7 | 131.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 285.2750. - H Hauling | 18.21 | 92.18 | 73.97 | 19.75% | 13.83 | 92.18 | 100% | 92.18 | 73.97 | 18.21 | 18.21 | 180.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.6500. - P Painting | 10.02 | 0 | -10.02 |  | 0 | 225 | 0% | 0 | -10.02 | 10.02 | 10.02 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.7800. - PRK Park Equipment | 25.12 | 42.5 | 17.38 | 59.11% | 42.5 | 42.5 | 56.67% | 24.0833 | -1.0367 | 44.3294 | 49.12 | 84.42% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1702. - FS People Superintendent | 7689.9 | 2901.22 | -4788.68 | 265.1% | 225 | 2901.22 | 87.5% | 2538.5675 | -5151.3325 | 8788.4571 | 7780.52 | -68.18% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1100. - TF Temporary Office Trailer, Conex, Dumpsters, Skids | 170.77 | 0 | -170.77 |  | 0 | 0 | 0% | 0 | -170.77 | 170.77 | 200.77 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.7100. - IMP Interior Mech/Piping | 445.74 | 357 | -88.74 | 124.9% | 306.9 | 357 | 59.8% | 213.4905 | -232.2495 | 745.3691 | 633.37 | 22.59% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2710. - FWF Flowable Fill | 3 | 68.92 | 65.92 | 4.353% | 6.204 | 68.92 | 60% | 41.352 | 38.352 | 5 | 3 | 195.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.5000. - MET Metals | 125.13 | 171 | 45.87 | 73.18% | 228.51 | 171 | 90% | 153.9 | 28.77 | 139.0333 | 125.13 | 126.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.6500. - P Painting | 4 | 0 | -4 |  | 17.25 | 345 | 100% | 0 | -4 | 4 | 4 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.6500. - P Painting | 3 | 0 | -3 |  | 0 | 90 | 0% | 0 | -3 | 3 | 3 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 230.2760. - HO Haul Off | 1307.21 | 1657 | 349.79 | 78.89% | 1657 | 1657 | 100% | 1657 | 349.79 | 1307.21 | 1307.21 | 121.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1940. - PL Punch List Work | 5.08 | 200 | 194.92 | 2.54% | 0 | 200 | 0% | 200 | 194.92 | 200 | 155.08 | 122.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.2750. - H Hauling | 21.1 | 0.68 | -20.42 | 3103% | 0.68 | 0.68 | 100% | 0.68 | -20.42 | 21.1 | 21.1 | -2903% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2060. - FE Fencing | 29.45 | 24 | -5.45 | 122.7% | 24 | 24 | 100% | 24 | -5.45 | 29.45 | 29.45 | 77.29% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 360.5100. - W Welding | 53.43 | 0 | -53.43 |  | 0 | 0 | 0% | 0 | -53.43 | 53.43 | 53.43 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 255.3000. - CNC Concrete Work | 5 | 84 | 79 | 5.952% | 33.6 | 84 | 40% | 33.6 | 28.6 | 12.5 | 5 | 194% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.6000. - IF Interior Finishes | 15.25 | 6 | -9.25 | 254.2% | 5.7 | 6 | 93.75% | 5.625 | -9.625 | 16.2667 | 35.25 | -387.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.7900. - ELC Electrical | 5 | 122.67 | 117.67 | 4.076% | 89.802 | 122.67 | 60% | 73.602 | 68.602 | 8.3333 | 5 | 195.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2030. - Unknown Phase | 305.51 | 1583.47 | 1277.96 | 19.29% | 1583.47 | 1583.47 | 100% | 1583.47 | 1277.96 | 305.51 | 305.51 | 180.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.2800. - BFST Backfill (DO NOT USE) | 32.39 | 60 | 27.61 | 53.98% | 31.5 | 60 | 50% | 30 | -2.39 | 64.78 | 32.39 | 146% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.7500. - PUMP Pumps/Motors | 4.6 | 45 | 40.4 | 10.22% | 45 | 45 | 90% | 40.5 | 35.9 | 5.1111 | 4.6 | 189.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2760. - Unknown Phase | 10.75 | 10 | -0.75 | 107.5% | 1 | 10 | 100% | 10 | -0.75 | 10.75 | 10.75 | 92.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 310.7100. - IMP Interior Mech/Piping | 9.82 | 30 | 20.18 | 32.73% | 0 | 30 | 0% | 30 | 20.18 | 30 | 9.82 | 167.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.6200. - IN Insulation | 135.48 | 210 | 74.52 | 64.51% | 189 | 210 | 67.5% | 141.75 | 6.27 | 200.7111 | 180.48 | 114.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 250.2300. - WPL Water Pipe Laying (DO NOT USE) | 2275.03 | 855.14 | -1419.89 | 266% | 1855.14 | 855.14 | 100% | 855.14 | -1419.89 | 2275.03 | 2275.03 | -66.04% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1650. - SB Signage | 19.5 | 20 | 0.5 | 97.5% | 20 | 20 | 100% | 20 | 0.5 | 19.5 | 19.5 | 102.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.3000. - CNC Concrete Work | 1782.25 | 1325.87 | -456.38 | 134.4% | 1282.87 | 1325.87 | 100% | 1325.87 | -456.38 | 1782.25 | 1902.25 | 56.53% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2760. - HO Haul Off | 143.6 | 158.94 | 15.34 | 90.35% | 158.94 | 158.94 | 100% | 158.94 | 15.34 | 143.6 | 143.6 | 109.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2080. - EXS Excavate Structure | 100.76 | 117.26 | 16.5 | 85.93% | 117.26 | 117.26 | 100% | 117.26 | 16.5 | 100.76 | 100.76 | 114.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2800. - BFST Backfill (DO NOT USE) | 236.35 | 120 | -116.35 | 197% | 120 | 120 | 100% | 120 | -116.35 | 236.35 | 236.35 | 3.042% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9055. - Re-Work Finishes | 24.77 | 3 | -21.77 | 825.7% | 3 | 3 | 100% | 3 | -21.77 | 24.77 | 24.77 | -625.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.7800. - PRK Park Equipment | 64.41 | 47.5 | -16.91 | 135.6% | 47.5 | 47.5 | 100% | 47.5 | -16.91 | 64.41 | 64.41 | 64.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.1230. - T Transporting | 82.46 | 100 | 17.54 | 82.46% | 64 | 100 | 80% | 80 | -2.46 | 103.075 | 82.46 | 117.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 450.3000. - CNC Concrete Work | 1063.67 | 1317.13 | 253.46 | 80.76% | 1317.13 | 1317.13 | 100% | 1317.13 | 253.46 | 1063.67 | 1183.67 | 110.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 180.91 | 342 | 161.09 | 52.9% | 0 | 0 | 0% | 342 | 161.09 | 342 | 180.91 | 147.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2030. - D Demolition | 10.35 | 66.81 | 56.46 | 15.49% | 66.81 | 66.81 | 100% | 66.81 | 56.46 | 10.35 | 10.35 | 184.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2760. - HO Haul Off | 0 | 32.15 | 32.15 | 0% | 1.61 | 32.15 | 100% | 32.15 | 32.15 | 0 | 0 | 200% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2930. - AP Asphalt Prep (DO NOT USE) | 409.39 | 321.46 | -87.93 | 127.4% | 181.916 | 321.46 | 87.5% | 281.2792 | -128.1108 | 467.8715 | 409.39 | 72.65% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.7100. - IMP Interior Mech/Piping | 425.18 | 13.5 | -411.68 | 3149% | 13.5 | 13.5 | 81.25% | 10.9688 | -414.2113 | 523.2985 | 441.92 | -3073% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.1230. - T Transporting | 154.55 | 90 | -64.55 | 171.7% | 63 | 90 | 40% | 36 | -118.55 | 386.375 | 185.86 | -6.511% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 150.2070. - RGC Rough Grade Cut | 61.99 | 1099 | 1037.01 | 5.641% | 869.56 | 1099 | 88.02% | 967.3193 | 905.3293 | 70.4287 | 61.99 | 194.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 315.2800. - BFST Backfill (DO NOT USE) | 128.45 | 45 | -83.45 | 285.4% | 33.75 | 45 | 100% | 45 | -83.45 | 128.45 | 128.45 | -85.44% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 200.5100. - W Welding | 4 | 30 | 26 | 13.33% | 0.8 | 30 | 88.89% | 26.6667 | 22.6667 | 4.5 | 4 | 186.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 160.5000. - Unknown Phase | 38.83 | 197 | 158.17 | 19.71% | -27.43 | 197 | 123.9% | 244.1367 | 205.3067 | 31.3329 | 38.83 | 180.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.2760. - HO Haul Off | 5.32 | 28.57 | 23.25 | 18.62% | 28.57 | 28.57 | 100% | 28.57 | 23.25 | 5.32 | 5.32 | 181.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.3000. - CNC Concrete Work | 807.63 | 1041.99 | 234.36 | 77.51% | 1038 | 1041.99 | 94.12% | 980.7465 | 173.1165 | 858.0631 | 927.63 | 111% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2760. - HO Haul Off | 61.01 | 28.79 | -32.22 | 211.9% | 26.79 | 28.79 | 100% | 28.79 | -32.22 | 61.01 | 61.01 | -11.91% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 550.2070. - RGC Rough Grade Cut | 145.32 | 48 | -97.32 | 302.8% | 48 | 48 | 100% | 48 | -97.32 | 145.32 | 145.32 | -102.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 270.2300. - WPL Water Pipe Laying (DO NOT USE) | 348.27 | 345.26 | -3.01 | 100.9% | 211.074 | 345.26 | 60% | 207.156 | -141.114 | 580.45 | 348.27 | 99.13% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1230. - T Transporting | 166.05 | 122 | -44.05 | 136.1% | 98 | 122 | 89% | 108.58 | -57.47 | 186.573 | 166.05 | 63.89% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 700.1940. - PL Punch List Work | 5.95 | 180 | 174.05 | 3.306% | 0 | 180 | 0% | 180 | 174.05 | 180 | 185.95 | 96.69% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.7900. - ELC Electrical | 42.33 | 170.28 | 127.95 | 24.86% | 119.97 | 140.28 | 100% | 170.28 | 127.95 | 42.33 | 42.33 | 175.1% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.3000. - CNC Concrete Work | 134.58 | 350 | 215.42 | 38.45% | 353.5 | 350 | 100% | 350 | 215.42 | 134.58 | 134.58 | 161.5% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.6300. - DAW Doors & Windows | 21.85 | 60 | 38.15 | 36.42% | 60 | 60 | 93.75% | 56.25 | 34.4 | 23.3067 | 21.85 | 163.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 900.9100. - Job Related Equipment Repairs | 38.06 | 1 | -37.06 | 3806% | 1 | 1 | 66.67% | 0.66667 | -37.3933 | 57.09 | 38.06 | -3606% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.1230. - T Transporting | 146.52 | 50 | -96.52 | 293% | 50 | 50 | 90% | 45 | -101.52 | 162.8 | 146.52 | -93.04% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1515. - S Drone/Lidar Requirements | 216.32 | 11 | -205.32 | 1967% | 10.45 | 11 | 86.6% | 9.526 | -206.794 | 249.7921 | 231.32 | -1903% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.3000. - CNC Concrete Work | 13685.77 | 8105.6 | -5580.17 | 168.8% | 7799.86 | 8105.6 | 87.81% | 7117.1989 | -6568.5711 | 15586.3814 | 13530.89 | 33.07% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.2020. - CG Clearing/Grubbing | 57.92 | 17.72 | -40.2 | 326.9% | 8.86 | 17.72 | 100% | 17.72 | -40.2 | 57.92 | 57.92 | -126.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.1940. - PL Punch List Work | 24.6 | 150 | 125.4 | 16.4% | 0 | 150 | 0% | 150 | 125.4 | 150 | 174.6 | 83.6% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.6500. - P Painting | 12.67 | 0 | -12.67 |  | 75 | 75 | 100% | 0 | -12.67 | 12.67 | 12.67 | 0% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 600.2760. - HO Haul Off | 388.36 | 257.08 | -131.28 | 151.1% | 257.08 | 257.08 | 62.5% | 160.675 | -227.685 | 621.376 | 388.36 | 48.93% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 300.5000. - MET Metals | 88.03 | 114 | 25.97 | 77.22% | 57.42 | 114 | 60% | 68.4 | -19.63 | 146.7167 | 100.35 | 112% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 400.2760. - HO Haul Off | 231.76 | 74.29 | -157.47 | 312% | 74.29 | 74.29 | 90% | 66.861 | -164.899 | 257.5111 | 231.76 | -112% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 215.2300. - WPL Water Pipe Laying (DO NOT USE) | 433.22 | 270 | -163.22 | 160.5% | 270 | 270 | 100% | 270 | -163.22 | 433.22 | 433.22 | 39.55% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 350.5100. - W Welding | 54.99 | 50 | -4.99 | 110% | 32.5 | 50 | 100% | 50 | -4.99 | 54.99 | 104.99 | -9.98% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 320.2300. - WPL Water Pipe Laying (DO NOT USE) | 38 | 210 | 172 | 18.1% | 210 | 210 | 100% | 210 | 172 | 38 | 38 | 181.9% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.7800. - PRK Park Equipment | 17.73 | 81.2 | 63.47 | 21.83% | 77.14 | 81.2 | 100% | 81.2 | 63.47 | 17.73 | 17.73 | 178.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 375.1200. - HOOK Hook Truck Dumpster Transporting | 3.92 | 20 | 16.08 | 19.6% | 19 | 20 | 100% | 20 | 16.08 | 3.92 | 3.92 | 180.4% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 500.7800. - PRK Park Equipment | 12.77 | 142 | 129.23 | 8.993% | 142 | 142 | 100% | 142 | 129.23 | 12.77 | 12.77 | 191% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 225.2760. - HO Haul Off | 2058.74 | 2149 | 90.26 | 95.8% | 2149 | 2149 | 100% | 2149 | 90.26 | 2058.74 | 2058.74 | 104.2% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 100.1510. - S Surveying | 5007.78 | 2301 | -2706.78 | 217.6% | 2137.5 | 2301 | 95% | 2185.95 | -2821.83 | 5271.3474 | 5092.08 | -21.3% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 260.3000. - CNC Concrete Work | 11.33 | 378 | 366.67 | 2.997% | 381.78 | 378 | 67.48% | 255.0688 | 243.7388 | 16.7905 | 11.33 | 197% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 962.88 | 906.06 | -56.82 | 106.3% | 906.06 | 906.06 | 100.8% | 913.5415 | -49.3385 | 954.9944 | 962.88 | 93.73% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 275.2300. - WPL Water Pipe Laying (DO NOT USE) | 1269.56 | 724.9 | -544.66 | 175.1% | 671.39 | 675.9 | 81.29% | 589.2747 | -680.2853 | 1561.7573 | 1269.56 | 24.86% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 325.2930. - AP Asphalt Prep (DO NOT USE) | 1986.39 | 274.73 | -1711.66 | 723% | 1108.764 | 334.73 | 66.68% | 183.1866 | -1803.2034 | 2979.0446 | 2106.39 | -566.7% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 205.2605. - BYP Bypass Pumping | 20.15 | 120 | 99.85 | 16.79% | 120 | 120 | 100% | 120 | 99.85 | 20.15 | 20.15 | 183.2% |  | 2026-05-01
2507. - SLC Industrial Lift Station | 150.2750. - Unknown Phase | 72.19 | 37.38 | -34.81 | 193.1% | 63.804 | 37.35 | 100% | 37.3816 | -34.8084 | 72.1869 | 72.19 | 6.875%
2507. - SLC Industrial Lift Station | 800.1930. - MC Misc Cleanup | 108.54 | 120 | 11.46 | 90.45% | 60 | 120 | 50% | 60 | -48.54 | 217.08 | 120.47 | 99.61%
2507. - SLC Industrial Lift Station | 100.1703. - FS Job Site Superintendent | 351.97 | 138.75 | -213.22 | 253.7% | 116.55 | 138.75 | 84% | 116.55 | -235.42 | 419.0119 | 333.57 | -40.41%
2507. - SLC Industrial Lift Station | 200.2085. - BFST Backfill Structure | 34.81 | 36 | 1.19 | 96.69% | 0 | 36 | 0% | 36 | 1.19 | 36 | 34.81 | 103.3%
2507. - SLC Industrial Lift Station | 150.2760. - Unknown Phase | 19.77 | 6.66 | -13.11 | 296.8% | 3.33 | 6.66 | 100% | 6.66 | -13.11 | 19.77 | 19.77 | -96.85%
2507. - SLC Industrial Lift Station | 200.2600. - DW Dewatering | 7.62 | 124.96 | 117.34 | 6.098% | 0 | 124.96 | 0% | 124.96 | 117.34 | 124.96 | 7.62 | 193.9%
2507. - SLC Industrial Lift Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 388.26 | 101.36 | -286.9 | 383.1% | 80.655 | 101.36 | 82% | 83.115 | -305.145 | 473.489 | 403.26 | -197.8%
2507. - SLC Industrial Lift Station | 100.1700. - FS Project Manager | 243 | 155.5 | -87.5 | 156.3% | 90.61 | 155.5 | 82% | 127.51 | -115.49 | 296.3415 | 246 | 41.8%
2507. - SLC Industrial Lift Station | 200.3000. - Unknown Phase | 167.01 | 451.2 | 284.19 | 37.01% | 0 | 451.2 | 0% | 451.2 | 284.19 | 451.2 | 167.01 | 163%
2507. - SLC Industrial Lift Station | 200.2140. - SVR Services | 6.32 | 40 | 33.68 | 15.8% | 30 | 40 | 100% | 40 | 33.68 | 6.32 | 6.32 | 184.2%
2507. - SLC Industrial Lift Station | 150.1230. - T Transporting | 41.73 | 101 | 59.27 | 41.32% | 98.98 | 101 | 98% | 98.98 | 57.25 | 42.5816 | 41.73 | 158.7%
2507. - SLC Industrial Lift Station | 200.2605. - BYP Bypass Pumping | 65.14 | 50 | -15.14 | 130.3% | 25 | 50 | 100% | 50 | -15.14 | 65.14 | 65.14 | 69.72%
2507. - SLC Industrial Lift Station | 200.2030. - Unknown Phase | 24.64 | 134.16 | 109.52 | 18.37% | 0 | 134.16 | 0% | 134.16 | 109.52 | 134.16 | 24.64 | 181.6%
2507. - SLC Industrial Lift Station | 200.5400. - HAT Hatch/Skylights | 1 | 15 | 14 | 6.667% | 15 | 15 | 100% | 15 | 14 | 1 | 1 | 193.3%
2507. - SLC Industrial Lift Station | 200.1600. - TC Traffic Control | 31.33 | 142 | 110.67 | 22.06% | 142 | 142 | 100% | 142 | 110.67 | 31.33 | 31.33 | 177.9%
2507. - SLC Industrial Lift Station | 900.9012. - Re-Work Mechanical | 6.85 | 0.6 | -6.25 | 1142% | 0 | 0.6 | 0% | 0.6 | -6.25 | 6.85 | 6.85 | -941.7%
2507. - SLC Industrial Lift Station | 200.2610. - PT Pressure Test/Chlorinating | 28.63 | 60 | 31.37 | 47.72% | 0 | 60 | 0% | 60 | 31.37 | 60 | 28.63 | 152.3%
2507. - SLC Industrial Lift Station | 200.2170. - HDPE Fusion Pipe <15' Depth | 389.76 | 471.74 | 81.98 | 82.62% | 372 | 471.74 | 100% | 471.74 | 81.98 | 389.76 | 389.76 | 117.4%
2507. - SLC Industrial Lift Station | 900.9015. - Re-Work Concrete | 39.97 | 0.6 | -39.37 | 6662% | 0 | 0.6 | 0% | 0.6 | -39.37 | 39.97 | 39.97 | -6462%
2507. - SLC Industrial Lift Station | 200.7900. - ELC Electrical | 11.55 | 20 | 8.45 | 57.75% | 0 | 20 | 0% | 20 | 8.45 | 20 | 11.55 | 142.2%
2507. - SLC Industrial Lift Station | 200.2240. - PCS Precast Structures | 95.34 | 28 | -67.34 | 340.5% | 0 | 28 | 0% | 28 | -67.34 | 95.34 | 95.34 | -140.5%
2507. - SLC Industrial Lift Station | 180.1600. - TC Traffic Control | 2.5 | 0 | -2.5 |  | 0 | 0 | 0% | 0 | -2.5 | 2.5 | 2.5 | 0%
2507. - SLC Industrial Lift Station | 150.1200. - HOOK Hook Truck Dumpster Transporting | 10 | 7.5 | -2.5 | 133.3% | 7.35 | 7.5 | 98% | 7.35 | -2.65 | 10.2041 | 10 | 66.67%
2507. - SLC Industrial Lift Station | 200.7100. - IMP Interior Mech/Piping | 161.62 | 259.89 | 98.27 | 62.19% | 258 | 259.89 | 100% | 259.89 | 98.27 | 161.62 | 161.62 | 137.8%
2507. - SLC Industrial Lift Station | 200.7500. - PUMP Pumps/Motors | 20.55 | 78 | 57.45 | 26.35% | 78 | 78 | 100% | 78 | 57.45 | 20.55 | 20.55 | 173.7%
2507. - SLC Industrial Lift Station | 100.1706. - FS Executive | 1 | 1 | 0 | 100% | 1 | 1 | 100% | 1 | 0 | 1 | 1 | 100%
2507. - SLC Industrial Lift Station | 100.1510. - S Surveying | 30.36 | 40 | 9.64 | 75.9% | 30 | 40 | 100% | 40 | 9.64 | 30.36 | 30.36 | 124.1%
2507. - SLC Industrial Lift Station | 200.2075. - FG Finish Grade | 100.54 | 45.25 | -55.29 | 222.2% | 56.439 | 45.25 | 95% | 42.9873 | -57.5527 | 105.832 | 100.54 | -22.19%
2507. - SLC Industrial Lift Station | 200.1800. - PH Potholing | 50.57 | 150 | 99.43 | 33.71% | 150 | 150 | 100% | 150 | 99.43 | 50.57 | 50.57 | 166.3%
2507. - SLC Industrial Lift Station | 100.1704. - FS Quality Control/Assurance | 16.5 | 36.15 | 19.65 | 45.64% | 0 | 36.15 | 0% | 36.15 | 19.65 | 36.15 | 16.5 | 154.4%
2507. - SLC Industrial Lift Station | 900.9100. - Job Related Equipment Repairs | 12.65 | 1 | -11.65 | 1265% | 0 | 1 | 0% | 1 | -11.65 | 12.65 | 3 | -100%
2507. - SLC Industrial Lift Station | 200.5000. - MET Metals | 5.93 | 85.5 | 79.57 | 6.936% | 85.5 | 85.5 | 100% | 85.5 | 79.57 | 5.93 | 5.93 | 193.1%
2507. - SLC Industrial Lift Station | 100.1702. - FS People Superintendent | 28.5 | 92.17 | 63.67 | 30.92% | 46.085 | 92.17 | 99.99% | 92.16 | 63.66 | 28.5031 | 28.5 | 169.1%
2507. - SLC Industrial Lift Station | 150.1201. - HOOK Hook Truck Conex, Skid Transporting | 6 | 7.5 | 1.5 | 80% | 7.35 | 7.5 | 98% | 7.35 | 1.35 | 6.1224 | 6 | 120%
2507. - SLC Industrial Lift Station | 800.1940. - PL Punch List Work | 53.78 | 135 | 81.22 | 39.84% | 128.25 | 135 | 95% | 128.25 | 74.47 | 56.6105 | 133.78 | 100.9%
2219. - GHID 20D Kent Booster Station | 220.2080. - EXS Excavate Structure | 217.54 | 320 | 102.46 | 67.98% | 0 | 320 | 0% | 320 | 102.46 | 320 | 217.54 | 132% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.2080. - EXS Excavate Structure | 5.77 | 0 | -5.77 |  | 0 | 0 | 0% | 0 | -5.77 | 5.77 | 5.77 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9100. - Job Related Equipment Repairs | 15.7 | 2 | -13.7 | 785% | 1 | 1 | 50% | 1 | -14.7 | 31.4 | 15.7 | -585% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7600. - MEQ Mechanical Equipment | 553.63 | 3 | -550.63 | 18454% | 3 | 3 | 75% | 2.25 | -551.38 | 738.1733 | 553.63 | -18254% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.5000. - MET Metals | 104.81 | 1 | -103.81 | 10481% | 1 | 1 | 33.33% | 0.33333 | -104.4767 | 314.43 | 104.81 | -10281% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.2300. - WPL Water Pipe Laying (DO NOT USE) | 534.61 | 139 | -395.61 | 384.6% | 139 | 139 | 48.94% | 68.0317 | -466.5783 | 1092.2967 | 534.61 | -184.6% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.7100. - IMP Interior Mech/Piping | 572.44 | 0 | -572.44 |  | 0 | 0 | 0% | 0 | -572.44 | 572.44 | 572.44 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.6500. - P Painting | 2 | 90 | 88 | 2.222% | 90 | 90 | 75% | 67.5 | 65.5 | 2.6667 | 2 | 197.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 700.2300. - WPL Water Pipe Laying (DO NOT USE) | 437.62 | 600 | 162.38 | 72.94% | 600 | 600 | 60% | 360 | -77.62 | 729.3667 | 437.62 | 127.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.5100. - W Welding | 18.33 | 42 | 23.67 | 43.64% | 0 | 4 | 0% | 42 | 23.67 | 42 | 18.33 | 156.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.2600. - DW Dewatering | 2 | 30 | 28 | 6.667% | 0 | 30 | 0% | 30 | 28 | 30 | 2 | 193.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.3000. - CNC Concrete Work | 535.69 | 3 | -532.69 | 17856% | 6 | 3 | 75% | 2.25 | -533.44 | 714.2533 | 535.69 | -17656% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2800. - BFST Backfill (DO NOT USE) | 179.81 | 240 | 60.19 | 74.92% | 240 | 240 | 46.15% | 110.7692 | -69.0408 | 389.5883 | 179.81 | 125.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9010. - Re-Work Pipe | 852.38 | 0.8 | -851.58 | 106547% | 0.4 | 0.4 | 66.67% | 0.53333 | -851.8467 | 1278.57 | 852.38 | -106347% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1700. - FS Project Manager | 1082.52 | 1 | -1081.52 | 108252% | 0 | 0 | 0% | 1 | -1081.52 | 1082.52 | 1078.52 | -107652% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7500. - PUMP Pumps/Motors | 36.4 | 180 | 143.6 | 20.22% | 0 | 180 | 0% | 180 | 143.6 | 180 | 36.4 | 179.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 602.11 | 350 | -252.11 | 172% | 350 | 350 | 40.7% | 142.4419 | -459.6681 | 1479.4703 | 602.11 | 27.97% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2600. - DW Dewatering | 126.41 | 15 | -111.41 | 842.7% | 0 | 15 | 0% | 15 | -111.41 | 126.41 | 126.41 | -642.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 210.7600. - MEQ Mechanical Equipment | 953.59 | 400 | -553.59 | 238.4% | 380 | 400 | 58.02% | 232.0611 | -721.5289 | 1643.688 | 953.59 | -38.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.2300. - WPL Water Pipe Laying (DO NOT USE) | 457.58 | 260 | -197.58 | 176% | 230 | 230 | 71.88% | 186.875 | -270.705 | 636.633 | 457.58 | 24.01% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.5000. - MET Metals | 169.39 | 115 | -54.39 | 147.3% | 115 | 115 | 62.84% | 72.2678 | -97.1222 | 269.551 | 169.39 | 52.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.3000. - CNC Concrete Work | 389.63 | 181.08 | -208.55 | 215.2% | 151.08 | 151.08 | 70.47% | 127.6065 | -262.0235 | 552.9043 | 389.63 | -15.17% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6000. - IF Interior Finishes | 320.83 | 45 | -275.83 | 713% | 42.75 | 45 | 71.25% | 32.0625 | -288.7675 | 450.2877 | 320.83 | -513% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2070. - RGC Rough Grade Cut | 60 | 90 | 30 | 66.67% | 90 | 90 | 51.67% | 46.5 | -13.5 | 116.129 | 60 | 133.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.2800. - BFST Backfill (DO NOT USE) | 91.35 | 150 | 58.65 | 60.9% | 150 | 150 | 46.15% | 69.2308 | -22.1192 | 197.925 | 91.35 | 139.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2010. - RG Grading (DO NOT USE) | 10.15 | 51 | 40.85 | 19.9% | 0 | 51 | 0% | 51 | 40.85 | 51 | 10.15 | 180.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 180.2040. - LR Landscaping/Restoration | 531.49 | 236.19 | -295.3 | 225% | 0 | 1 | 0% | 236.19 | -295.3 | 531.49 | 531.49 | -25.03% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1510. - S Surveying | 1186.06 | 1000 | -186.06 | 118.6% | 1000 | 1000 | 50% | 500 | -686.06 | 2372.12 | 1186.06 | 81.39% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.6500. - P Painting | 125.77 | 158 | 32.23 | 79.6% | 150 | 150 | 75% | 118.5 | -7.27 | 167.6933 | 125.77 | 120.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6500. - Unknown Phase | 1193.28 | 1095.54 | -97.74 | 108.9% | 1094 | 1095.54 | 79.8% | 874.1946 | -319.0854 | 1495.4176 | 1193.28 | 91.08% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.6500. - P Painting | 26.98 | 150 | 123.02 | 17.99% | 150 | 150 | 75% | 112.5 | 85.52 | 35.9733 | 26.98 | 182% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 370.5100. - W Welding | 141.15 | 50 | -91.15 | 282.3% | 0 | 50 | 0% | 50 | -91.15 | 141.15 | 141.15 | -82.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.7100. - IMP Interior Mech/Piping | 272.05 | 105 | -167.05 | 259.1% | 105 | 105 | 67.74% | 71.129 | -200.921 | 401.5976 | 272.05 | -59.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 8.22 | -15 | -23.22 |  | 0 | -15 | 7.273% | -1.0909 | -9.3109 | 113.025 | 8.22 | 254.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.5000. - MET Metals | 8.82 | 6 | -2.82 | 147% | 6 | 6 | 75% | 4.5 | -4.32 | 11.76 | 8.82 | 53% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.5000. - MET Metals | 49.24 | 231 | 181.76 | 21.32% | 231 | 231 | 56.16% | 129.7248 | 80.4848 | 87.6813 | 49.24 | 178.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1504.74 | 1 | -1503.74 | 150474% | 0 | 0 | 0% | 1 | -1503.74 | 1504.74 | 1504.74 | -150274% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.7100. - IMP Interior Mech/Piping | 73.25 | 307.22 | 233.97 | 23.84% | 234 | 234 | 74.52% | 228.9474 | 155.6974 | 98.2927 | 73.25 | 176.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.1930. - MC Misc Cleanup | 1126.58 | 400 | -726.58 | 281.6% | 380 | 400 | 42.22% | 168.8889 | -957.6911 | 2668.2158 | 1126.58 | -81.64% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.5000. - MET Metals | 1 | 0 | -1 |  | 0 | 0 | 0% | 0 | -1 | 1 | 1 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 550.3000. - CNC Concrete Work | 1334.89 | 64 | -1270.89 | 2086% | 20 | 20 | 66.67% | 42.6667 | -1292.2233 | 2002.335 | 1334.89 | -1886% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.2080. - EXS Excavate Structure | 29.53 | 140 | 110.47 | 21.09% | 140 | 140 | 49.56% | 69.3805 | 39.8505 | 59.5873 | 29.53 | 178.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.6500. - P Painting | 108.86 | 300 | 191.14 | 36.29% | 300 | 300 | 75% | 225 | 116.14 | 145.1467 | 108.86 | 163.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 892.8 | 3693 | 2800.2 | 24.18% | 3678 | 3678 | 27.34% | 1009.5023 | 116.7023 | 3266.075 | 892.8 | 175.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7900. - ELC Electrical | 321.41 | 530 | 208.59 | 60.64% | 490 | 490 | 56.32% | 298.5057 | -22.9043 | 570.6667 | 321.41 | 139.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 350.5100. - W Welding | 389.68 | 160 | -229.68 | 243.6% | 40 | 40 | 33.33% | 53.3333 | -336.3467 | 1169.04 | 389.68 | -43.55% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.5100. - W Welding | 395.69 | 329 | -66.69 | 120.3% | 329 | 329 | 33.33% | 109.6667 | -286.0233 | 1187.07 | 395.69 | 79.73% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.3000. - CNC Concrete Work | 14 | 33 | 19 | 42.42% | 33 | 33 | 68.75% | 22.6875 | 8.6875 | 20.3636 | 14 | 157.6% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.5000. - MET Metals | 6 | 2 | -4 | 300% | 32 | 32 | 88.89% | 1.7778 | -4.2222 | 6.75 | 6 | -100% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1702. - FS People Superintendent | 1210.15 | 1 | -1209.15 | 121015% | 0 | 0 | 0% | 1 | -1209.15 | 1210.15 | 1210.15 | -120815% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2080. - EXS Excavate Structure | 283.25 | 165 | -118.25 | 171.7% | 0 | 165 | 0% | 165 | -118.25 | 283.25 | 283.25 | 28.33% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9020. - Re-Work Fab | 40.59 | 0.2 | -40.39 | 20295% | 0.2 | 0.2 | 33.33% | 0.066667 | -40.5233 | 121.77 | 40.59 | -20095% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.1700. - FS Project Manager | 20.53 | 70 | 49.47 | 29.33% | 66.5 | 70 | 47.5% | 33.25 | 12.72 | 43.2211 | 20.53 | 170.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.3000. - Unknown Phase | 3783.35 | 2016.54 | -1766.81 | 187.6% | 2291 | 2016.54 | 71.15% | 1434.7494 | -2348.6006 | 5317.4976 | 3783.35 | 12.38% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1704. - FS Quality Control/Assurance | 12 | 1 | -11 | 1200% | 0 | 0 | 0% | 1 | -11 | 12 | 12 | -1000% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 340.3000. - CNC Concrete Work | 6.5 | 66 | 59.5 | 9.848% | 66 | 66 | 67.35% | 44.449 | 37.949 | 9.6515 | 6.5 | 190.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.3000. - CNC Concrete Work | 142.96 | 70.52 | -72.44 | 202.7% | 70.52 | 70.52 | 71.3% | 50.2787 | -92.6813 | 200.513 | 142.96 | -2.723% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2800. - Unknown Phase | 1179.81 | 150 | -1029.81 | 786.5% | 150 | 150 | 46.15% | 69.2308 | -1110.5792 | 2556.255 | 1179.81 | -586.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.2610. - PT Pressure Test/Chlorinating | 982.54 | 600 | -382.54 | 163.8% | 600 | 600 | 53.33% | 320 | -662.54 | 1842.2625 | 982.54 | 36.24% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.2800. - BFST Backfill (DO NOT USE) | 295.2 | 150 | -145.2 | 196.8% | 0 | 150 | 0% | 150 | -145.2 | 295.2 | 295.2 | 3.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.5000. - MET Metals | 708.11 | 983.5 | 275.39 | 72% | 894.9 | 894.9 | 54.07% | 531.7389 | -176.3711 | 1309.7147 | 708.11 | 128% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.6200. - IN Insulation | 32.9 | 210 | 177.1 | 15.67% | 210 | 210 | 75% | 157.5 | 124.6 | 43.8667 | 32.9 | 184.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.2080. - EXS Excavate Structure | 11.83 | 25 | 13.17 | 47.32% | 25 | 25 | 44.44% | 11.1111 | -0.71889 | 26.6175 | 11.83 | 152.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.2300. - WPL Water Pipe Laying (DO NOT USE) | 5177.36 | 365.7 | -4811.66 | 1416% | 354 | 354 | 41.4% | 151.4126 | -5025.9474 | 12504.6407 | 5177.36 | -1216% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 383.91 | 30 | -353.91 | 1280% | 30 | 30 | 54.55% | 16.3636 | -367.5464 | 703.835 | 383.91 | -1080% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.2300. - WPL Water Pipe Laying (DO NOT USE) | 38.78 | 135.36 | 96.58 | 28.65% | 0 | 135.36 | 0% | 135.36 | 96.58 | 135.36 | 38.78 | 171.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 800.1940. - PL Punch List Work | 1804.72 | 600 | -1204.72 | 300.8% | 540 | 600 | 67.5% | 405 | -1399.72 | 2673.6593 | 1801.72 | -100.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.5100. - W Welding | 34.2 | 15 | -19.2 | 228% | 15 | 15 | 25% | 3.75 | -30.45 | 136.8 | 34.2 | -28% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 161.39 | 72.96 | -88.43 | 221.2% | 0 | 72.96 | 0% | 72.96 | -88.43 | 161.39 | 161.39 | -21.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 330.2300. - WPL Water Pipe Laying (DO NOT USE) | 1255.6 | 355 | -900.6 | 353.7% | 0 | 355 | 0% | 355 | -900.6 | 1255.6 | 1255.6 | -153.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 370.7100. - IMP Interior Mech/Piping | 169.42 | 60 | -109.42 | 282.4% | 0 | 60 | 0% | 60 | -109.42 | 169.42 | 169.42 | -82.37% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.7100. - IMP Interior Mech/Piping | 137.92 | 36 | -101.92 | 383.1% | 0 | 6 | 0% | 36 | -101.92 | 137.92 | 137.92 | -183.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.5000. - MET Metals | 55.49 | 202 | 146.51 | 27.47% | 202 | 202 | 70.63% | 142.6713 | 87.1813 | 78.565 | 55.49 | 172.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.7100. - IMP Interior Mech/Piping | 186.3 | 15 | -171.3 | 1242% | 15 | 15 | 75% | 11.25 | -175.05 | 248.4 | 186.3 | -1042% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9015. - Re-Work Concrete | 24.38 | 0.8 | -23.58 | 3048% | 0.4 | 0.4 | 66.67% | 0.53333 | -23.8467 | 36.57 | 24.38 | -2848% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2080. - EXS Excavate Structure | 826.4 | 303 | -523.4 | 272.7% | 0 | 303 | 0% | 303 | -523.4 | 826.4 | 826.4 | -72.74% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2300. - Unknown Phase | 666.19 | 671.64 | 5.45 | 99.19% | 601.64 | 611.64 | 47.15% | 316.669 | -349.521 | 1412.9575 | 666.19 | 100.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.3000. - CNC Concrete Work | 4.5 | 30 | 25.5 | 15% | 30 | 30 | 75% | 22.5 | 18 | 6 | 4.5 | 185% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2020. - CG Clearing/Grubbing | 43.4 | 20 | -23.4 | 217% | 0 | 20 | 0% | 20 | -23.4 | 43.4 | 43.4 | -17% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.5000. - MET Metals | 374.68 | 246 | -128.68 | 152.3% | 141 | 141 | 52.81% | 129.9101 | -244.7699 | 709.5004 | 374.68 | 47.69% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9012. - Re-Work Mechanical | 176.24 | 0.8 | -175.44 | 22030% | 0.4 | 0.4 | 66.67% | 0.53333 | -175.7067 | 264.36 | 176.24 | -21830% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 1228.8 | 891.35 | -337.45 | 137.9% | 887.5 | 891.35 | 45.02% | 401.3133 | -827.4867 | 2729.2663 | 1228.8 | 62.14% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 110.31 | 210 | 99.69 | 52.53% | 0 | 210 | 0% | 210 | 99.69 | 210 | 110.31 | 147.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.3000. - CNC Concrete Work | 1148.27 | 621.2 | -527.07 | 184.8% | 621.2 | 621.2 | 69.52% | 431.8369 | -716.4331 | 1651.7934 | 1148.27 | 15.15% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5110. - Fab Shop Pipe Fabrication | 3930.59 | 2283 | -1647.59 | 172.2% | 2283 | 2283 | 50.31% | 1148.5 | -2782.09 | 7813.2668 | 3930.59 | 27.83% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.2800. - BFST Backfill (DO NOT USE) | 130.8 | 120 | -10.8 | 109% | 120 | 120 | 46.15% | 55.3846 | -75.4154 | 283.4 | 130.8 | 91% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.3000. - CNC Concrete Work | 1150.12 | 858 | -292.12 | 134% | 858 | 858 | 70.68% | 606.3954 | -543.7246 | 1627.326 | 1150.12 | 65.95% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 412.14 | 300 | -112.14 | 137.4% | 300 | 300 | 50% | 150 | -262.14 | 824.28 | 412.14 | 62.62% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.2750. - Unknown Phase | 880.44 | 1169.11 | 288.67 | 75.31% | 1111.98 | 1114.31 | 49.55% | 579.2981 | -301.1419 | 1776.8592 | 880.44 | 124.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.2600. - DW Dewatering | 5.08 | 30 | 24.92 | 16.93% | 0 | 30 | 0% | 30 | 24.92 | 30 | 5.08 | 183.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.2010. - RG Grading (DO NOT USE) | 130.34 | 16 | -114.34 | 814.6% | 16 | 16 | 47.06% | 7.5294 | -122.8106 | 276.9725 | 130.34 | -614.6% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.7100. - IMP Interior Mech/Piping | 33.52 | 225 | 191.48 | 14.9% | 75 | 75 | 71.43% | 160.7143 | 127.1943 | 46.928 | 33.52 | 185.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2080. - EXS Excavate Structure | 12 | 25 | 13 | 48% | 0 | 25 | 0% | 25 | 13 | 25 | 12 | 152% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.7100. - IMP Interior Mech/Piping | 441.59 | 249.72 | -191.87 | 176.8% | 234 | 234 | 66.1% | 165.0692 | -276.5208 | 668.0464 | 441.59 | 23.17% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 370.2300. - WPL Water Pipe Laying (DO NOT USE) | 1491.34 | 690 | -801.34 | 216.1% | 0 | 690 | 0% | 690 | -801.34 | 1491.34 | 1491.34 | -16.14% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.3000. - CNC Concrete Work | 15.1 | 110 | 94.9 | 13.73% | 110 | 110 | 73.33% | 80.6667 | 65.5667 | 20.5909 | 15.1 | 186.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.2800. - BFST Backfill (DO NOT USE) | 10.82 | 15 | 4.18 | 72.13% | 15 | 15 | 46.15% | 6.9231 | -3.8969 | 23.4433 | 10.82 | 127.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 900.9055. - Re-Work Finishes | 26 | 3.2 | -22.8 | 812.5% | 0.2 | 0.2 | 66.67% | 2.1333 | -23.8667 | 39 | 26 | -612.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.6500. - P Painting | 10.74 | 120 | 109.26 | 8.95% | 120 | 120 | 75% | 90 | 79.26 | 14.32 | 10.74 | 191.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 230.7100. - IMP Interior Mech/Piping | 175.75 | 219 | 43.25 | 80.25% | 219 | 219 | 67.38% | 147.5723 | -28.1777 | 260.8162 | 175.75 | 119.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.2010. - RG Grading (DO NOT USE) | 329.68 | 25.5 | -304.18 | 1293% | 25.5 | 25.5 | 53.97% | 13.7619 | -315.9181 | 610.8776 | 329.68 | -1093% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1600. - TC Traffic Control | 1194.71 | 300 | -894.71 | 398.2% | 240 | 240 | 4.348% | 13.0435 | -1181.6665 | 27478.33 | 1194.71 | -198.2% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.2760. - Unknown Phase | 1162.98 | 2327.18 | 1164.2 | 49.97% | 2334 | 2316 | 50% | 1163.59 | 0.61 | 2325.96 | 1162.98 | 150% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 300.2030. - D Demolition | 10.2 | 15 | 4.8 | 68% | 15 | 15 | 50% | 7.5 | -2.7 | 20.4 | 10.2 | 132% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 380.2030. - D Demolition | 9.75 | 6 | -3.75 | 162.5% | 6 | 6 | 50% | 3 | -6.75 | 19.5 | 9.75 | 37.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.7100. - IMP Interior Mech/Piping | 2536.49 | 1456.54 | -1079.95 | 174.1% | 1339.5 | 1411.54 | 65.66% | 956.3899 | -1580.1001 | 3862.9635 | 2536.49 | 25.86% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2800. - BFST Backfill (DO NOT USE) | 16.42 | 30 | 13.58 | 54.73% | 30 | 30 | 46.15% | 13.8462 | -2.5738 | 35.5767 | 16.42 | 145.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 150.1230. - T Transporting | 749.86 | 600 | -149.86 | 125% | 600 | 600 | 50% | 300 | -449.86 | 1499.72 | 744.88 | 75.85% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 360.2300. - WPL Water Pipe Laying (DO NOT USE) | 861.51 | 751.75 | -109.76 | 114.6% | 751.75 | 751.75 | 42.72% | 321.1849 | -540.3251 | 2016.409 | 861.51 | 85.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.3000. - CNC Concrete Work | 1787.59 | 627.28 | -1160.31 | 285% | 627.28 | 627.28 | 70.8% | 444.1136 | -1343.4764 | 2524.8483 | 1787.59 | -84.97% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5120. - Fab Shop Pipe Linings & Coatings | 4296.17 | 1733 | -2563.17 | 247.9% | 1733 | 1733 | 50% | 866.5 | -3429.67 | 8592.34 | 4296.17 | -47.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2800. - BFST Backfill (DO NOT USE) | 55.83 | 90 | 34.17 | 62.03% | 90 | 90 | 46.15% | 41.5385 | -14.2915 | 120.965 | 55.83 | 138% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.2500. - MH Manholes (DO NOT USE) | 14.73 | 0 | -14.73 |  | 0 | 0 | 0% | 0 | -14.73 | 14.73 | 14.73 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.5100. - W Welding | 211.17 | 25 | -186.17 | 844.7% | 25 | 25 | 33.33% | 8.3333 | -202.8367 | 633.51 | 211.17 | -644.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2300. - WPL Water Pipe Laying (DO NOT USE) | 121.69 | 20 | -101.69 | 608.5% | 0 | 20 | 0% | 20 | -101.69 | 121.69 | 121.69 | -408.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.7600. - MEQ Mechanical Equipment | 452.46 | 204 | -248.46 | 221.8% | 204 | 204 | 75% | 153 | -299.46 | 603.28 | 452.46 | -21.79% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.7100. - IMP Interior Mech/Piping | 849.23 | 224 | -625.23 | 379.1% | 221 | 221 | 65.38% | 146.4615 | -702.7685 | 1298.8224 | 849.23 | -179.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 340.2300. - WPL Water Pipe Laying (DO NOT USE) | 873.52 | 812.05 | -61.47 | 107.6% | 849.25 | 849.25 | 45.29% | 367.8045 | -505.7155 | 1928.584 | 873.52 | 92.43% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 220.5100. - W Welding | 24.33 | 10 | -14.33 | 243.3% | 10 | 10 | 33.33% | 3.3333 | -20.9967 | 72.99 | 24.33 | -43.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.5000. - MET Metals | 103.49 | 116 | 12.51 | 89.22% | 86 | 86 | 55.13% | 63.9487 | -39.5413 | 187.726 | 103.49 | 110.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 500.2030. - D Demolition | 604.55 | 792 | 187.45 | 76.33% | 792 | 792 | 43.36% | 343.4222 | -261.1278 | 1394.2129 | 604.55 | 123.7% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.1650. - SB Signage | 40.6 | 100 | 59.4 | 40.6% | 100 | 100 | 66.67% | 66.6667 | 26.0667 | 60.9 | 40.6 | 159.4% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 550.2930. - AP Asphalt Prep (DO NOT USE) | 921.86 | 505.59 | -416.27 | 182.3% | 489 | 489 | -6.225% | 505.59 | -416.27 | -14809.7964 | 921.86 | 17.67% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1703. - FS Job Site Superintendent | 4007.04 | 1 | -4006.04 | 400704% | 0 | 0 | 0% | 1 | -4006.04 | 4007.04 | 4007.04 | -400504% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6300. - DAW Doors & Windows | 709.26 | 60 | -649.26 | 1182% | 60 | 60 | 66.67% | 40 | -669.26 | 1063.89 | 709.26 | -982.1% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 320.3000. - CNC Concrete Work | 50.94 | 8 | -42.94 | 636.8% | 8 | 8 | 66.67% | 5.3333 | -45.6067 | 76.41 | 50.94 | -436.8% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.2080. - EXS Excavate Structure | 204.73 | 125 | -79.73 | 163.8% | 125 | 125 | 49.5% | 61.8812 | -142.8488 | 413.5546 | 204.73 | 36.22% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 340.7100. - IMP Interior Mech/Piping | 91.23 | 45 | -46.23 | 202.7% | 45 | 45 | 64.29% | 28.9286 | -62.3014 | 141.9133 | 91.23 | -2.733% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 270.2030. - D Demolition | 5.87 | 15 | 9.13 | 39.13% | 0 | 15 | 0% | 15 | 9.13 | 15 | 5.87 | 160.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 200.6200. - IN Insulation | 221.06 | 146.25 | -74.81 | 151.2% | 146.25 | 146.25 | 75% | 109.6875 | -111.3725 | 294.7467 | 221.06 | 48.85% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.2010. - RG Grading (DO NOT USE) | 27.17 | 4 | -23.17 | 679.2% | 4 | 4 | 47.06% | 1.8824 | -25.2876 | 57.7362 | 27.17 | -479.3% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 250.2800. - BFST Backfill (DO NOT USE) | 126.59 | 60 | -66.59 | 211% | 60 | 60 | 46.15% | 27.6923 | -98.8977 | 274.2783 | 126.59 | -10.98% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.0000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 170.2300. - WPL Water Pipe Laying (DO NOT USE) | 5.58 | -6 | -11.58 |  | 0 | -6 | 0% | -6 | -11.58 | 5.58 | 5.58 | 293% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.7100. - IMP Interior Mech/Piping | 116.98 | 63 | -53.98 | 185.7% | 63 | 63 | 64.95% | 40.9175 | -76.0625 | 180.1121 | 116.98 | 14.32% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 240.6500. - P Painting | 5.47 | 60 | 54.53 | 9.117% | 0 | 60 | 0% | 60 | 54.53 | 60 | 5.47 | 190.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5310. - Fab Shop Misc Metals Fabrication | 629.4 | 498 | -131.4 | 126.4% | 484 | 484 | 50.52% | 251.5723 | -377.8277 | 1245.9288 | 629.4 | 73.61% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 280.6500. - P Painting | 94.81 | 60 | -34.81 | 158% | 60 | 60 | 75% | 45 | -49.81 | 126.4133 | 94.81 | 41.98% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 160.5320. - Fab Shop Misc Metals Coatings | 85.06 | 137 | 51.94 | 62.09% | 103 | 103 | 50% | 68.5 | -16.56 | 170.12 | 85.06 | 137.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 260.3000. - CNC Concrete Work | 157.79 | 24 | -133.79 | 657.5% | 24 | 24 | 66.67% | 16 | -141.79 | 236.685 | 157.79 | -457.5% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 100.1705. - FS Estimator/Change Orders/Scheduling | 189.92 | 1 | -188.92 | 18992% | 0 | 0 | 0% | 1 | -188.92 | 189.92 | 189.92 | -18792% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 330.5100. - W Welding | 14.54 | 22 | 7.46 | 66.09% | 2 | 2 | 33.33% | 7.3333 | -7.2067 | 43.62 | 14.54 | 133.9% |  | 2024-03-15
2219. - GHID 20D Kent Booster Station | 550.2010. - RG Grading (DO NOT USE) | 52.85 | 51 | -1.85 | 103.6% | 51 | 51 | 53.97% | 27.5238 | -25.3262 | 97.9279 | 52.85 | 96.37% |  | 2024-03-15
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1510. - S Surveying | 1 | 20 | 19 | 5% | 1 | 20 | 5% | 1 | 0 | 20 | 20 | 100% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1702. - FS People Superintendent | 16 | 44.68 | 28.68 | 35.81% | 2.234 | 44.68 | 5% | 2.234 | -13.766 | 320 | 46 | 97.05% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1703. - FS Job Site Superintendent | 16 | 67 | 51 | 23.88% | 3.35 | 67 | 5% | 3.35 | -12.65 | 320 | 166 | -47.76% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1700. - FS Project Manager | 60.5 | 53.47 | -7.03 | 113.1% | 2.674 | 53.47 | 5.001% | 2.674 | -57.826 | 1209.7737 | 136 | -54.35% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 136.65 | 47.66 | -88.99 | 286.7% | 2.383 | 47.66 | 8.659% | 4.127 | -132.523 | 1578.0982 | 135.15 | -83.57% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 200.1600. - TC Traffic Control | 0.75 | 10 | 9.25 | 7.5% | 0.1 | 10 | 1% | 0.1 | -0.65 | 75 | 10 | 100% |  | 2025-10-31
2506. - UDOT Big Cottonwood Creek Culvert Preservation | 100.1706. - FS Executive | 1 | 1 | 0 | 100% | 0.05 | 1 | 5% | 0.05 | -0.95 | 20 | 1 | 100% |  | 2025-10-31
2125. - Price WWTP Nutrient Upgrades | 650.7100. - IMP Interior Mech/Piping | 1991.15 | 1440 | -551.15 | 138.3% | 0 | 1440 | 0% | 1440 | -551.15 | 1991.15 | 1395 | 103.1%
2125. - Price WWTP Nutrient Upgrades | 600.6500. - P Painting | 0 | 100 | 100 | 0% | 0 | 100 | 0% | 100 | 100 | 100 | 100 | 100%
2125. - Price WWTP Nutrient Upgrades | 600.3000. - CNC Concrete Work | 64.1 | 30 | -34.1 | 213.7% | 0 | 30 | 0% | 30 | -34.1 | 64.1 | 30 | 100%
2125. - Price WWTP Nutrient Upgrades | 500.7600. - MEQ Mechanical Equipment | 618.79 | 80 | -538.79 | 773.5% | 0 | 80 | 0% | 80 | -538.79 | 618.79 | 80 | 100%
2125. - Price WWTP Nutrient Upgrades | 200.3000. - Unknown Phase | 493.64 | 252 | -241.64 | 195.9% | 0 | 252 | 0% | 252 | -241.64 | 493.64 | 208 | 117.5%
2125. - Price WWTP Nutrient Upgrades | 600.5000. - MET Metals | 87.27 | 56 | -31.27 | 155.8% | 0 | 56 | 0% | 56 | -31.27 | 87.27 | 46 | 117.9%
2125. - Price WWTP Nutrient Upgrades | 750.7600. - MEQ Mechanical Equipment | 219.31 | 100 | -119.31 | 219.3% | 0 | 100 | 0% | 100 | -119.31 | 219.31 | 100 | 100%
2125. - Price WWTP Nutrient Upgrades | 800.1930. - MC Misc Cleanup | 475.64 | 100 | -375.64 | 475.6% | 0 | 100 | 0% | 100 | -375.64 | 475.64 | 100 | 100%
2125. - Price WWTP Nutrient Upgrades | 300.7100. - IMP Interior Mech/Piping | 1409.7 | 500 | -909.7 | 281.9% | 0 | 500 | 0% | 500 | -909.7 | 1409.7 | 480 | 104%
2125. - Price WWTP Nutrient Upgrades | 200.2030. - Unknown Phase | 1290.42 | 978.02 | -312.4 | 131.9% | 0 | 966.02 | 0% | 978.02 | -312.4 | 1290.42 | 951.02 | 102.8%
2125. - Price WWTP Nutrient Upgrades | 900.9012. - Re-Work Mechanical | 25.12 | 0.8 | -24.32 | 3140% | 0 | 0.4 | 0% | 0.8 | -24.32 | 25.12 | 0.4 | 150%
2125. - Price WWTP Nutrient Upgrades | 650.7500. - PUMP Pumps/Motors | 122.18 | 150 | 27.82 | 81.45% | 0 | 150 | 0% | 150 | 27.82 | 150 | 150 | 100%
2125. - Price WWTP Nutrient Upgrades | 160.7100. - IMP Interior Mech/Piping | 103.77 | 360 | 256.23 | 28.82% | 0 | 360 | 0% | 360 | 256.23 | 360 | 360 | 100%
2125. - Price WWTP Nutrient Upgrades | 650.5000. - MET Metals | 331.88 | 122 | -209.88 | 272% | 0 | 122 | 0% | 122 | -209.88 | 331.88 | 122 | 100%
2125. - Price WWTP Nutrient Upgrades | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 5.5 | 0 | -5.5 |  | 0 | 0 | 0% | 0 | -5.5 | 5.5 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 900.9015. - Re-Work Concrete | 0 | 0.8 | 0.8 | 0% | 0 | 0.4 | 0% | 0.8 | 0.8 | 0.8 | 0.4 | 150%
2125. - Price WWTP Nutrient Upgrades | 510.7600. - MEQ Mechanical Equipment | 658.19 | 120 | -538.19 | 548.5% | 0 | 120 | 0% | 120 | -538.19 | 658.19 | 120 | 100%
2125. - Price WWTP Nutrient Upgrades | 150.1230. - T Transporting | 51.96 | 205 | 153.04 | 25.35% | 0 | 205 | 0% | 205 | 153.04 | 205 | 200 | 102.4%
2125. - Price WWTP Nutrient Upgrades | 650.6500. - P Painting | 635.12 | 520 | -115.12 | 122.1% | 0 | 520 | 0% | 520 | -115.12 | 635.12 | 500 | 103.8%
2125. - Price WWTP Nutrient Upgrades | 160.5000. - Unknown Phase | 26.03 | 15 | -11.03 | 173.5% | 0 | 15 | 0% | 15 | -11.03 | 26.03 | 0 | 200%
2125. - Price WWTP Nutrient Upgrades | 100.1510. - S Surveying | 6.5 | 20 | 13.5 | 32.5% | 0 | 20 | 0% | 20 | 13.5 | 20 | 20 | 100%
2125. - Price WWTP Nutrient Upgrades | 900.9055. - Re-Work Finishes | 4 | 0.4 | -3.6 | 1000% | 0 | 0.2 | 0% | 0.4 | -3.6 | 4 | 0.2 | 150%
2125. - Price WWTP Nutrient Upgrades | 600.7600. - MEQ Mechanical Equipment | 284.08 | 72 | -212.08 | 394.6% | 0 | 72 | 40.89% | 29.44 | -254.64 | 694.7609 | 72 | 100%
2125. - Price WWTP Nutrient Upgrades | 210.7100. - IMP Interior Mech/Piping | 30.25 | 30 | -0.25 | 100.8% | 0 | 30 | 0% | 30 | -0.25 | 30.25 | 30 | 100%
2125. - Price WWTP Nutrient Upgrades | 100.1702. - FS People Superintendent | 20.52 | 0 | -20.52 |  | 0 | 0 | 0% | 0 | -20.52 | 20.52 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 100.1704. - FS Quality Control/Assurance | 3.5 | 0 | -3.5 |  | 0 | 0 | 0% | 0 | -3.5 | 3.5 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 700.5100. - W Welding | 186.58 | 40 | -146.58 | 466.5% | 0 | 40 | 0% | 40 | -146.58 | 186.58 | 40 | 100%
2125. - Price WWTP Nutrient Upgrades | 200.7100. - IMP Interior Mech/Piping | 132.42 | 30 | -102.42 | 441.4% | 0 | 30 | 0% | 30 | -102.42 | 132.42 | 30 | 100%
2125. - Price WWTP Nutrient Upgrades | 750.5100. - W Welding | 137.87 | 50 | -87.87 | 275.7% | 0 | 50 | 0% | 50 | -87.87 | 137.87 | 50 | 100%
2125. - Price WWTP Nutrient Upgrades | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2125. - Price WWTP Nutrient Upgrades | 700.7600. - MEQ Mechanical Equipment | 28.08 | 222 | 193.92 | 12.65% | 0 | 222 | 0% | 222 | 193.92 | 222 | 222 | 100%
2125. - Price WWTP Nutrient Upgrades | 800.1940. - PL Punch List Work | 877.43 | 100 | -777.43 | 877.4% | 0 | 100 | 0% | 100 | -777.43 | 877.43 | 100 | 100%
2125. - Price WWTP Nutrient Upgrades | 210.3000. - CNC Concrete Work | 1518.87 | 1332.5 | -186.37 | 114% | 0 | 1332.5 | 0% | 1332.5 | -186.37 | 1518.87 | 0 | 200%
2125. - Price WWTP Nutrient Upgrades | 700.5000. - MET Metals | 18.83 | 4 | -14.83 | 470.7% | 0 | 4 | 0% | 4 | -14.83 | 18.83 | 4 | 100%
2125. - Price WWTP Nutrient Upgrades | 200.5000. - MET Metals | 129.48 | 55 | -74.48 | 235.4% | 0 | 55 | 0% | 55 | -74.48 | 129.48 | 50 | 109.1%
2125. - Price WWTP Nutrient Upgrades | 400.3000. - CNC Concrete Work | 508.14 | 251.5 | -256.64 | 202% | 0 | 242.5 | 0% | 251.5 | -256.64 | 508.14 | 111.5 | 155.7%
2125. - Price WWTP Nutrient Upgrades | 700.6500. - P Painting | 4.33 | 110 | 105.67 | 3.936% | 0 | 110 | 0% | 110 | 105.67 | 110 | 80 | 127.3%
2226. - Tooele Berra Wellhouse | 160.5320. - Fab Shop Misc Metals Coatings | 138.54 | 40 | -98.54 | 346.3% | 0 | 40 | 0% | 40 | -98.54 | 138.54 | 40 | 100%
2226. - Tooele Berra Wellhouse | 500.3000. - CNC Concrete Work | 18.15 | 108 | 89.85 | 16.81% | 0 | 108 | 0% | 108 | 89.85 | 108 | 108 | 100%
2226. - Tooele Berra Wellhouse | 300.7100. - IMP Interior Mech/Piping | 1223.69 | 420.75 | -802.94 | 290.8% | 0 | 420.75 | 0% | 420.75 | -802.94 | 1223.69 | 420.75 | 100%
2226. - Tooele Berra Wellhouse | 300.7500. - PUMP Pumps/Motors | 10.58 | 150 | 139.42 | 7.053% | 0 | 150 | 0% | 150 | 139.42 | 150 | 150 | 100%
2226. - Tooele Berra Wellhouse | 900.9015. - Re-Work Concrete | 6 | 0.4 | -5.6 | 1500% | 0 | 0.4 | 0% | 0.4 | -5.6 | 6 | 0.4 | 100%
2226. - Tooele Berra Wellhouse | 300.5000. - MET Metals | 36.9 | 149.5 | 112.6 | 24.68% | 0 | 149.5 | 0% | 149.5 | 112.6 | 149.5 | 149.5 | 100%
2226. - Tooele Berra Wellhouse | 300.7400. - HVAC HVAC | 3.5 | 30 | 26.5 | 11.67% | 0 | 30 | 0% | 30 | 26.5 | 30 | 30 | 100%
2226. - Tooele Berra Wellhouse | 160.5110. - Fab Shop Pipe Fabrication | 952.93 | 364 | -588.93 | 261.8% | 0 | 364 | 0% | 364 | -588.93 | 952.93 | 364 | 100%
2226. - Tooele Berra Wellhouse | 400.7900. - ELC Electrical | 30.83 | 60 | 29.17 | 51.38% | 0 | 60 | 0% | 60 | 29.17 | 60 | 60 | 100%
2226. - Tooele Berra Wellhouse | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2226. - Tooele Berra Wellhouse | 200.2710. - FWF Flowable Fill | 18.18 | 80 | 61.82 | 22.73% | 0 | 80 | 0% | 80 | 61.82 | 80 | 80 | 100%
2226. - Tooele Berra Wellhouse | 160.5310. - Fab Shop Misc Metals Fabrication | 198.1 | 52 | -146.1 | 381% | 0 | 52 | 0% | 52 | -146.1 | 198.1 | 52 | 100%
2226. - Tooele Berra Wellhouse | 300.7600. - MEQ Mechanical Equipment | 11.17 | 3 | -8.17 | 372.3% | 0 | 3 | 0% | 3 | -8.17 | 11.17 | 3 | 100%
2226. - Tooele Berra Wellhouse | 300.6100. - F Framing | 18.07 | 15 | -3.07 | 120.5% | 0 | 15 | 0% | 15 | -3.07 | 18.07 | 15 | 100%
2226. - Tooele Berra Wellhouse | 300.2800. - BFST Backfill (DO NOT USE) | 975.91 | 60 | -915.91 | 1627% | 0 | 60 | 0% | 60 | -915.91 | 975.91 | 60 | 100%
2226. - Tooele Berra Wellhouse | 100.1702. - FS People Superintendent | 205.29 | 0 | -205.29 |  | 0 | 0 | 0% | 0 | -205.29 | 205.29 | 0 | 0%
2226. - Tooele Berra Wellhouse | 900.9020. - Re-Work Fab | 30.45 | 0.2 | -30.25 | 15225% | 0 | 0.2 | 0% | 0.2 | -30.25 | 30.45 | 0.2 | 100%
2226. - Tooele Berra Wellhouse | 100.1510. - S Surveying | 291.76 | 80 | -211.76 | 364.7% | 0 | 80 | 0% | 80 | -211.76 | 291.76 | 80 | 100%
2226. - Tooele Berra Wellhouse | 300.2010. - RG Grading (DO NOT USE) | 122.14 | 98.5 | -23.64 | 124% | 0 | 98.5 | 0% | 98.5 | -23.64 | 122.14 | 98.5 | 100%
2226. - Tooele Berra Wellhouse | 250.2300. - WPL Water Pipe Laying (DO NOT USE) | 717.72 | 1198 | 480.28 | 59.91% | 0 | 1182.25 | 0% | 1198 | 480.28 | 1198 | 1182.25 | 101.3%
2226. - Tooele Berra Wellhouse | 250.5100. - W Welding | 169.68 | 10 | -159.68 | 1697% | 0 | 10 | 0% | 10 | -159.68 | 169.68 | 10 | 100%
2226. - Tooele Berra Wellhouse | 400.7100. - IMP Interior Mech/Piping | 155.13 | 106 | -49.13 | 146.3% | 0 | 106 | 0% | 106 | -49.13 | 155.13 | 106 | 100%
2226. - Tooele Berra Wellhouse | 300.6300. - DAW Doors & Windows | 162.31 | 180 | 17.69 | 90.17% | 0 | 180 | 0% | 180 | 17.69 | 180 | 180 | 100%
2226. - Tooele Berra Wellhouse | 300.3000. - CNC Concrete Work | 1158.58 | 621.5 | -537.08 | 186.4% | 0 | 621.5 | 0% | 621.5 | -537.08 | 1158.58 | 621.5 | 100%
2226. - Tooele Berra Wellhouse | 700.2610. - PT Pressure Test/Chlorinating | 503.65 | 40 | -463.65 | 1259% | 0 | 40 | 0% | 40 | -463.65 | 503.65 | 40 | 100%
2226. - Tooele Berra Wellhouse | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 11 | 0 | -11 |  | 0 | 0 | 0% | 0 | -11 | 11 | 0 | 0%
2226. - Tooele Berra Wellhouse | 300.2080. - EXS Excavate Structure | 126.99 | 111 | -15.99 | 114.4% | 0 | 111 | 0% | 111 | -15.99 | 126.99 | 111 | 100%
2226. - Tooele Berra Wellhouse | 185.7900. - ELC Electrical | 15.43 | 0 | -15.43 |  | 0 | 0 | 0% | 0 | -15.43 | 15.43 | 0 | 0%
2226. - Tooele Berra Wellhouse | 500.2010. - RG Grading (DO NOT USE) | 472.53 | 217 | -255.53 | 217.8% | 0 | 217 | 0% | 217 | -255.53 | 472.53 | 217 | 100%
2226. - Tooele Berra Wellhouse | 160.5015. - Fab Shop Transport | 10.73 | 20 | 9.27 | 53.65% | 0 | 20 | 0% | 20 | 9.27 | 20 | 20 | 100%
2226. - Tooele Berra Wellhouse | 800.1700. - FS Project Manager | 53.35 | 140 | 86.65 | 38.11% | 0 | 140 | 0% | 140 | 86.65 | 140 | 140 | 100%
2226. - Tooele Berra Wellhouse | 100.1700. - FS Project Manager | 225.38 | 0 | -225.38 |  | 0 | 0 | 0% | 0 | -225.38 | 225.38 | 0 | 0%
2226. - Tooele Berra Wellhouse | 200.3000. - Unknown Phase | 93.15 | 20 | -73.15 | 465.8% | 0 | 20 | 0% | 20 | -73.15 | 93.15 | 20 | 100%
2226. - Tooele Berra Wellhouse | 200.2300. - Unknown Phase | 1781.45 | 96 | -1685.45 | 1856% | 0 | 96 | 0% | 96 | -1685.45 | 1781.45 | 96 | 100%
2226. - Tooele Berra Wellhouse | 100.1703. - FS Job Site Superintendent | 569.59 | 0 | -569.59 |  | 0 | 0 | 0% | 0 | -569.59 | 569.59 | 0 | 0%
2226. - Tooele Berra Wellhouse | 150.2750. - Unknown Phase | 127.46 | 66.01 | -61.45 | 193.1% | 0 | 66.01 | 0% | 66.01 | -61.45 | 127.46 | 66.01 | 100%
2226. - Tooele Berra Wellhouse | 150.2760. - Unknown Phase | 28.53 | 105 | 76.47 | 27.17% | 0 | 105 | 0% | 105 | 76.47 | 105 | 105 | 100%
2226. - Tooele Berra Wellhouse | 800.1940. - PL Punch List Work | 200.4 | 200 | -0.4 | 100.2% | 0 | 200 | 0% | 200 | -0.4 | 200.4 | 200 | 100%
2226. - Tooele Berra Wellhouse | 150.1230. - T Transporting | 141.38 | 200 | 58.62 | 70.69% | 0 | 200 | 0% | 200 | 58.62 | 200 | 200 | 100%
2226. - Tooele Berra Wellhouse | 160.5120. - Fab Shop Pipe Linings & Coatings | 1204.12 | 380 | -824.12 | 316.9% | 0 | 380 | 0% | 380 | -824.12 | 1204.12 | 380 | 100%
2226. - Tooele Berra Wellhouse | 900.9005. - Re-Work Surveying | 5.5 | 0 | -5.5 |  | 0 | 0 | 0% | 0 | -5.5 | 5.5 | 0 | 0%
2226. - Tooele Berra Wellhouse | 300.6500. - P Painting | 909.71 | 400 | -509.71 | 227.4% | 0 | 400 | 0% | 400 | -509.71 | 909.71 | 400 | 100%
2226. - Tooele Berra Wellhouse | 250.2710. - FWF Flowable Fill | 4.38 | 40 | 35.62 | 10.95% | 0 | 40 | 0% | 40 | 35.62 | 40 | 40 | 100%
2226. - Tooele Berra Wellhouse | 250.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 26.69 | 40 | 13.31 | 66.72% | 0 | 40 | 0% | 40 | 13.31 | 40 | 40 | 100%
2226. - Tooele Berra Wellhouse | 200.1000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2226. - Tooele Berra Wellhouse | 300.6900. - EF Roofing | 27.62 | 30 | 2.38 | 92.07% | 0 | 30 | 0% | 30 | 2.38 | 30 | 30 | 100%
2317. - CUWCD CWP Wellhouse 17 | 200.2800. - Unknown Phase | 216.64 | 165 | -51.64 | 131.3% | 33 | 165 | 9.167% | 15.125 | -201.515 | 2363.3455 | 216.64 | 68.7% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 400.3000. - CNC Concrete Work | 406.49 | 530.47 | 123.98 | 76.63% | 483.2 | 530.2 | 100% | 530.47 | 123.98 | 406.49 | 406.49 | 123.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9100. - Job Related Equipment Repairs | 4 | 1 | -3 | 400% | 1 | 1 | 100% | 1 | -3 | 4 | 4 | -200% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5320. - Fab Shop Misc Metals Coatings | 20.4 | 480 | 459.6 | 4.25% | 1 | 480 | 100% | 480 | 459.6 | 20.4 | 20.4 | 195.8% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2710. - FWF Flowable Fill | 32.98 | 3.56 | -29.42 | 926.4% | 0.712 | 3.56 | 13.33% | 0.47467 | -32.5053 | 247.35 | 32.98 | -726.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 378.44 | 37.5 | -340.94 | 1009% | 37.5 | 37.5 | 100% | 37.5 | -340.94 | 378.44 | 378.44 | -809.2% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9055. - Re-Work Finishes | 8.47 | 0.2 | -8.27 | 4235% | 0 | 0.2 | 0% | 0.2 | -8.27 | 8.47 | 8.47 | -4035% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5310. - Fab Shop Misc Metals Fabrication | 33.18 | 253.5 | 220.32 | 13.09% | 1 | 253.5 | 100% | 253.5 | 220.32 | 33.18 | 33.18 | 186.9% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.7600. - MEQ Mechanical Equipment | 36.96 | 110 | 73.04 | 33.6% | 110 | 110 | 100% | 110 | 73.04 | 36.96 | 36.96 | 166.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.6300. - DAW Doors & Windows | 74.02 | 60 | -14.02 | 123.4% | 60 | 60 | 100% | 60 | -14.02 | 74.02 | 74.02 | 76.63% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 58.4 | 135 | 76.6 | 43.26% | 135 | 135 | 100% | 135 | 76.6 | 58.4 | 58.4 | 156.7% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2070. - RGC Rough Grade Cut | 1 | 106 | 105 | 0.9434% | 106 | 106 | 100% | 106 | 105 | 1 | 1 | 199.1% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.2800. - BFST Backfill (DO NOT USE) | 263.92 | 150 | -113.92 | 175.9% | 150 | 150 | 100% | 150 | -113.92 | 263.92 | 263.92 | 24.05% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9020. - Re-Work Fab | 81.55 | 0.2 | -81.35 | 40775% | 0 | 0.2 | 0% | 0.2 | -81.35 | 81.55 | 81.55 | -40575% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1650. - SB Signage | 2.5 | 15 | 12.5 | 16.67% | 15 | 15 | 100% | 15 | 12.5 | 2.5 | 2.5 | 183.3% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1702. - FS People Superintendent | 499.65 | 291.32 | -208.33 | 171.5% | 117.6 | 291.32 | 98% | 285.4936 | -214.1564 | 509.8469 | 509.65 | 25.05% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.7900. - ELC Electrical | 220.57 | 144.75 | -75.82 | 152.4% | 144.75 | 144.75 | 100% | 144.75 | -75.82 | 220.57 | 220.57 | 47.62% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 800.1940. - PL Punch List Work | 58.13 | 200 | 141.87 | 29.07% | 130 | 200 | 65% | 130 | 71.87 | 89.4308 | 81.27 | 159.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 545.67 | 233.72 | -311.95 | 233.5% | 199.72 | 233.72 | 100% | 233.72 | -311.95 | 545.67 | 545.67 | -33.47% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 800.1700. - FS Project Manager | 41.75 | 400 | 358.25 | 10.44% | 400 | 400 | 100% | 400 | 358.25 | 41.75 | 41.75 | 189.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.2080. - EXS Excavate Structure | 66.28 | 400 | 333.72 | 16.57% | 400 | 400 | 100% | 400 | 333.72 | 66.28 | 66.28 | 183.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.5000. - MET Metals | 127.89 | 40 | -87.89 | 319.7% | 40 | 40 | 240.7% | 96.2963 | -31.5937 | 53.1235 | 127.89 | -119.7% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1704. - FS Quality Control/Assurance | 455.24 | 58.23 | -397.01 | 781.8% | 100 | 58.23 | 100% | 58.23 | -397.01 | 455.24 | 465.24 | -599% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.7100. - IMP Interior Mech/Piping | 436 | 100 | -336 | 436% | 100 | 100 | 100% | 100 | -336 | 436 | 436 | -236% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.1650. - SB Signage | 11.25 | 10 | -1.25 | 112.5% | 10 | 10 | 100% | 10 | -1.25 | 11.25 | 1 | 190% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.6100. - F Framing | 35 | 20 | -15 | 175% | 20 | 20 | 100% | 20 | -15 | 35 | 35 | 25% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1510. - S Surveying | 219.2 | 106 | -113.2 | 206.8% | 252.45 | 106 | 100% | 106 | -113.2 | 219.2 | 219.2 | -6.792% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9015. - Re-Work Concrete | 2 | 0.4 | -1.6 | 500% | 0 | 0.4 | 0% | 0.4 | -1.6 | 2 | 2 | -300% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 523.84 | 372.02 | -151.82 | 140.8% | 78.4 | 372.018 | 98% | 364.5796 | -159.2604 | 534.5306 | 529.34 | 57.71% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1700. - FS Project Manager | 777.25 | 400.64 | -376.61 | 194% | 181.055 | 400.64 | 98% | 392.6272 | -384.6228 | 793.1122 | 780.25 | 5.249% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.3000. - CNC Concrete Work | 1021.07 | 930 | -91.07 | 109.8% | 930 | 930 | 100% | 930 | -91.07 | 1021.07 | 1021.07 | 90.21% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 100.1703. - FS Job Site Superintendent | 1080.51 | 596.54 | -483.97 | 181.1% | 519.4 | 596.54 | 98% | 584.6092 | -495.9008 | 1102.5612 | 1080.61 | 18.85% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5110. - Fab Shop Pipe Fabrication | 294.83 | 0 | -294.83 |  | 0 | 0 | 0% | 0 | -294.83 | 294.83 | 294.83 | 0% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 400.2010. - RG Grading (DO NOT USE) | 224.91 | 270.03 | 45.12 | 83.29% | 267.6 | 270.6 | 100% | 270.03 | 45.12 | 224.91 | 224.91 | 116.7% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9012. - Re-Work Mechanical | 71.13 | 0.4 | -70.73 | 17782% | 0 | 0.4 | 0% | 0.4 | -70.73 | 71.13 | 70.33 | -17382% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.5100. - W Welding | 191.8 | 80 | -111.8 | 239.8% | 60 | 80 | 100% | 80 | -111.8 | 191.8 | 191.8 | -39.75% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2040. - LR Landscaping/Restoration | 10.53 | 44.62 | 34.09 | 23.6% | 50 | 44.62 | 100% | 44.62 | 34.09 | 10.53 | 10.53 | 176.4% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2610. - PT Pressure Test/Chlorinating | 239.87 | 140 | -99.87 | 171.3% | 140 | 140 | 100% | 140 | -99.87 | 239.87 | 239.87 | 28.66% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 800.1930. - MC Misc Cleanup | 12.23 | 100 | 87.77 | 12.23% | 60 | 100 | 60% | 60 | 47.77 | 20.3833 | 32.23 | 167.8% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.3000. - Unknown Phase | 822.68 | 513 | -309.68 | 160.4% | 513 | 513 | 100% | 513 | -309.68 | 822.68 | 822.68 | 39.63% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.7100. - IMP Interior Mech/Piping | 701.38 | 489 | -212.38 | 143.4% | 470.25 | 489 | 95% | 464.55 | -236.83 | 738.2947 | 701.38 | 56.57% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9010. - Re-Work Pipe | 45.59 | 0.4 | -45.19 | 11398% | 0 | 0.4 | 0% | 0.4 | -45.19 | 45.59 | 45.59 | -11198% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.6200. - IN Insulation | 104.41 | 16 | -88.41 | 652.6% | 39.6 | 16 | 99% | 15.84 | -88.57 | 105.4646 | 104.41 | -452.6% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 300.6400. - DRY Drywall & Metal Studs | 94.14 | 68 | -26.14 | 138.4% | 68 | 68 | 100% | 68 | -26.14 | 94.14 | 94.14 | 61.56% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.1230. - T Transporting | 108.24 | 152 | 43.76 | 71.21% | 152 | 152 | 100% | 152 | 43.76 | 108.24 | 118.24 | 122.2% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 400.2000. - SWC Site Work Complete (DO NOT USE) | 360.86 | 84.77 | -276.09 | 425.7% | 25 | 84.77 | 100% | 84.77 | -276.09 | 360.86 | 360.86 | -225.7% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 160.5120. - Fab Shop Pipe Linings & Coatings | 559.2 | 0 | -559.2 |  | 0 | 0 | 0% | 0 | -559.2 | 559.2 | 559.2 | 0% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2030. - Unknown Phase | 4.5 | 15 | 10.5 | 30% | 15 | 15 | 100% | 15 | 10.5 | 4.5 | 15 | 100% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 900.9005. - Re-Work Surveying | 1 | 1 | 0 | 100% | 0 | 1 | 0% | 1 | 0 | 1 | 1 | 100% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.2760. - Unknown Phase | 197.74 | 387.72 | 189.98 | 51% | 387 | 388 | 100% | 387.72 | 189.98 | 197.74 | 197.74 | 149% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.2750. - Unknown Phase | 149.48 | 267.33 | 117.85 | 55.92% | 258.06 | 267.59 | 94.38% | 252.3091 | 102.8291 | 158.3791 | 149.48 | 144.1% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 150.2710. - FWF Flowable Fill | 83.41 | 0.28 | -83.13 | 29789% | 1 | 1.12 | 100% | 0.28 | -83.13 | 83.41 | 83.41 | -29589% |  | 2025-12-30
2317. - CUWCD CWP Wellhouse 17 | 200.2300. - Unknown Phase | 533.42 | 438.37 | -95.05 | 121.7% | 319.65 | 438.25 | 100% | 438.37 | -95.05 | 533.42 | 533.42 | 78.32% |  | 2025-12-30
2232. - Syracuse Secondary Reservoir | 400.2410. - IS Irrigation Services (DO NOT USE) | 139.76 | 210 | 70.24 | 66.55% | 840 | 210 | 218.2% | 458.1818 | 318.4218 | 64.0567 | 210 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.7900. - ELC Electrical | 64.55 | 204 | 139.45 | 31.64% | 306 | 204 | 64.29% | 131.1429 | 66.5929 | 100.4111 | 204 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.6300. - DAW Doors & Windows | 2 | 40 | 38 | 5% | 80 | 40 | 133.3% | 53.3333 | 51.3333 | 1.5 | 40 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2030. - D Demolition | 94.42 | 39.24 | -55.18 | 240.6% | 78.48 | 39.24 | 80.97% | 31.7742 | -62.6458 | 116.6053 | 39.24 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 310.2030. - D Demolition | 43.92 | 100 | 56.08 | 43.92% | 300 | 100 | 122.4% | 122.449 | 78.529 | 35.868 | 100 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 360.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 13.17 | 75 | 61.83 | 17.56% | 75 | 75 | 40.54% | 30.4046 | 17.2346 | 32.4869 | 75 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5320. - Fab Shop Misc Metals Coatings | 26.93 | 24 | -2.93 | 112.2% | 24 | 24 | 50% | 12 | -14.93 | 53.86 | 24 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.2080. - EXS Excavate Structure | 311.96 | 140 | -171.96 | 222.8% | 140 | 140 | 19.38% | 27.128 | -284.832 | 1609.9364 | 140 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 330.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 1138.68 | 682 | -456.68 | 167% | 1364 | 682 | 69.2% | 471.9651 | -666.7149 | 1645.4176 | 682 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.6200. - IN Insulation | 1 | 4 | 3 | 25% | 8 | 4 | 133.3% | 5.3333 | 4.3333 | 0.75 | 4 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2080. - EXS Excavate Structure | 3544.12 | 850.88 | -2693.24 | 416.5% | 838.88 | 850.88 | 42% | 357.3935 | -3186.7265 | 8437.8176 | 838.88 | 101.4% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.7500. - PUMP Pumps/Motors | 29.45 | 120 | 90.55 | 24.54% | 144 | 120 | 80% | 96 | 66.55 | 36.8125 | 120 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9040. - Re-Work Drivers | 4 | 0.1 | -3.9 | 4000% | 0 | 0.1 | 0% | 0.1 | -3.9 | 4 | 0.1 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.7100. - IMP Interior Mech/Piping | 273.88 | 90 | -183.88 | 304.3% | 225 | 90 | 150% | 135 | -138.88 | 182.5867 | 90 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 260.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 21.21 | 132 | 110.79 | 16.07% | 0 | 132 | 0% | 132 | 110.79 | 132 | 132 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.7100. - IMP Interior Mech/Piping | 55.5 | 120 | 64.5 | 46.25% | 120 | 120 | 60% | 72 | 16.5 | 92.5 | 120 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 310.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 3343.25 | 789.33 | -2553.92 | 423.6% | 2283.99 | 789.33 | 110.5% | 872.2769 | -2470.9731 | 3025.3325 | 761.33 | 103.5% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9015. - Re-Work Concrete | 108.81 | 0.4 | -108.41 | 27202% | 0 | 0.4 | 0% | 0.4 | -108.41 | 108.81 | 0.4 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 400.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 222.23 | 113 | -109.23 | 196.7% | 452 | 113 | 133.3% | 150.6622 | -71.5678 | 166.6774 | 113 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5110. - Fab Shop Pipe Fabrication | 802.36 | 150 | -652.36 | 534.9% | 195 | 150 | 65% | 97.5 | -704.86 | 1234.4 | 150 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2500. - MH Manholes (DO NOT USE) | 152.49 | 160 | 7.51 | 95.31% | 192 | 160 | 83.48% | 133.5652 | -18.9248 | 182.6703 | 160 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9012. - Re-Work Mechanical | 30.8 | 0.4 | -30.4 | 7700% | 1.96 | 0.4 | 2827% | 11.3067 | -19.4933 | 1.0896 | 0.4 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.7100. - IMP Interior Mech/Piping | 1338.22 | 559.01 | -779.21 | 239.4% | 950.317 | 559.01 | 91.23% | 509.9758 | -828.2442 | 1466.8899 | 559.01 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 240.2010. - RG Grading (DO NOT USE) | 42.44 | 36.57 | -5.87 | 116.1% | 73.14 | 36.57 | 99.99% | 36.565 | -5.875 | 42.4458 | 36.57 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2800. - Unknown Phase | 926.21 | 150 | -776.21 | 617.5% | 165 | 150 | 50.77% | 76.1538 | -850.0562 | 1824.353 | 150 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2070. - RGC Rough Grade Cut | 57.62 | 30 | -27.62 | 192.1% | 48 | 94.23 | 80% | 24 | -33.62 | 72.025 | 30 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 260.5100. - W Welding | 1.58 | 20 | 18.42 | 7.9% | 40 | 20 | 66.67% | 13.3333 | 11.7533 | 2.37 | 20 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1510. - S Surveying | 1001.26 | 800 | -201.26 | 125.2% | 1320 | 800 | 82.5% | 660 | -341.26 | 1213.6485 | 800 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1702. - FS People Superintendent | 598.62 | 0 | -598.62 |  | 0 | 0 | 0% | 0 | -598.62 | 598.62 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 380.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 118.83 | 36 | -82.83 | 330.1% | 108 | 36 | 100% | 36 | -82.83 | 118.83 | 36 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 4 | 214 | 210 | 1.869% | 165 | 214 | 61.11% | 130.7778 | 126.7778 | 6.5455 | 150 | 129.9% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.5100. - W Welding | 165.68 | 20 | -145.68 | 828.4% | 30 | 20 | 50% | 10 | -155.68 | 331.36 | 20 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.2760. - Unknown Phase | 3139.37 | 4589.17 | 1449.8 | 68.41% | 15569.178 | 4589.17 | 191.3% | 8778.8525 | 5639.4825 | 1641.1146 | 4579.17 | 100.2% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 350.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 145.05 | 15 | -130.05 | 967% | 16.5 | 15 | 36.67% | 5.4999 | -139.5501 | 395.5997 | 15 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 270.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 418.61 | 95 | -323.61 | 440.6% | 133 | 95 | 53.2% | 50.54 | -368.07 | 786.8609 | 95 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.5000. - MET Metals | 10.35 | 18 | 7.65 | 57.5% | 25.2 | 18 | 93.33% | 16.8 | 6.45 | 11.0893 | 18 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9100. - Job Related Equipment Repairs | 150.63 | 1 | -149.63 | 15063% | 0 | 1 | 0% | 1 | -149.63 | 150.63 | 1 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.3010. - WP Winter Protection | 314.93 | 0 | -314.93 |  | 0 | 0 | 0% | 0 | -314.93 | 314.93 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2020. - CG Clearing/Grubbing | 24.23 | 27.6 | 3.37 | 87.79% | 35.88 | 27.6 | 52% | 14.352 | -9.878 | 46.5962 | 27.6 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 400.2310. - WS Water Services (DO NOT USE) | 279.94 | 150 | -129.94 | 186.6% | 600 | 150 | 218.2% | 327.2727 | 47.3327 | 128.3058 | 150 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 600.2000. - SWC Site Work Complete (DO NOT USE) | 789 | 411.09 | -377.91 | 191.9% | 1644.36 | 411.09 | 204.9% | 842.2692 | 53.2692 | 385.0907 | 411.09 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5310. - Fab Shop Misc Metals Fabrication | 382.41 | 135 | -247.41 | 283.3% | 135 | 135 | 51.85% | 70 | -312.41 | 737.505 | 135 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.1520. - TEST Testing 3rd Party Soils/Concrete/Welding/Special | 7.97 | 100 | 92.03 | 7.97% | 380 | 100 | 190% | 190 | 182.03 | 4.1947 | 100 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9055. - Re-Work Finishes | 7.85 | 0.2 | -7.65 | 3925% | 0 | 0.2 | 0% | 0.2 | -7.65 | 7.85 | 0.2 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.3000. - CNC Concrete Work | 53.73 | 30 | -23.73 | 179.1% | 30 | 30 | 75% | 22.5 | -31.23 | 71.64 | 30 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.6100. - F Framing | 41.39 | 0 | -41.39 |  | 0 | 0 | 0% | 0 | -41.39 | 41.39 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1374.05 | 0 | -1374.05 |  | 0 | 0 | 0% | 0 | -1374.05 | 1374.05 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 629.04 | 634 | 4.96 | 99.22% | 634 | 634 | 43.87% | 278.1615 | -350.8785 | 1433.7402 | 634 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 240.3000. - CNC Concrete Work | 148.06 | 97.11 | -50.95 | 152.5% | 97.11 | 97.11 | 75% | 72.8325 | -75.2275 | 197.4133 | 97.11 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2020. - Unknown Phase | 320.28 | 80 | -240.28 | 400.3% | 80 | 80 | 47.06% | 37.6471 | -282.6329 | 680.595 | 80 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 716.51 | 60 | -656.51 | 1194% | 60 | 60 | 54.55% | 32.7273 | -683.7827 | 1313.6017 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 181.41 | 150 | -31.41 | 120.9% | 285 | 150 | 95% | 142.5 | -38.91 | 190.9579 | 150 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.2800. - BFST Backfill (DO NOT USE) | 50.92 | 30 | -20.92 | 169.7% | 45 | 30 | 69.23% | 20.7692 | -30.1508 | 73.5511 | 30 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.2800. - BFST Backfill (DO NOT USE) | 973.33 | 120 | -853.33 | 811.1% | 132 | 120 | 50.77% | 60.9231 | -912.4069 | 1917.1652 | 120 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1700. - FS Project Manager | 611.78 | 2 | -609.78 | 30589% | 0 | 2 | 0% | 2 | -609.78 | 611.78 | 0 | 200% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.2750. - Unknown Phase | 3573.35 | 1681.93 | -1891.42 | 212.5% | 3190.689 | 1681.96 | 96.02% | 1614.994 | -1958.356 | 3721.4531 | 1679.28 | 100.2% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 700.2610. - PT Pressure Test/Chlorinating | 240.44 | 444 | 203.56 | 54.15% | 2220 | 444 | 290.2% | 1288.4706 | 1048.0306 | 82.8543 | 444 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 800.1930. - MC Misc Cleanup | 405.4 | 200 | -205.4 | 202.7% | 950 | 200 | 211.1% | 422.2222 | 16.8222 | 192.0316 | 200 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1000. - GR General Requirements | 0 | 1 | 1 | 0% | 3 | 1 | 0% | 1 | 1 | 1 | 0 | 200% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 370.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 29.65 | 131 | 101.35 | 22.63% | 131 | 131 | 37.11% | 48.6146 | 18.9646 | 79.8968 | 131 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1704. - FS Quality Control/Assurance | 7.5 | 0 | -7.5 |  | 0 | 0 | 0% | 0 | -7.5 | 7.5 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 150.1230. - T Transporting | 755.1 | 500 | -255.1 | 151% | 950 | 500 | 95% | 475 | -280.1 | 794.8421 | 500 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 700.3000. - CNC Concrete Work | 121.7 | 18 | -103.7 | 676.1% | 54 | 18 | 225% | 40.5 | -81.2 | 54.0889 | 18 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2010. - RG Grading (DO NOT USE) | 580.89 | 1740 | 1159.11 | 33.38% | 1740 | 1740 | 52.45% | 912.6149 | 331.7249 | 1107.5302 | 1740 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 240.2800. - BFST Backfill (DO NOT USE) | 521.75 | 60 | -461.75 | 869.6% | 120 | 60 | 100% | 60 | -461.75 | 521.75 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 250.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 19.75 | 117 | 97.25 | 16.88% | 117 | 117 | 40.34% | 47.2034 | 27.4534 | 48.953 | 117 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 600.3000. - CNC Concrete Work | 1403.98 | 1068.59 | -335.39 | 131.4% | 5342.95 | 1068.59 | 324.9% | 3472.0825 | 2068.1025 | 432.0977 | 1068.59 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 180.6100. - F Framing | 159.16 | 0 | -159.16 |  | 0 | 0 | 0% | 0 | -159.16 | 159.16 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 220.7600. - MEQ Mechanical Equipment | 99.98 | 90 | -9.98 | 111.1% | 180 | 90 | 133.3% | 120 | 20.02 | 74.985 | 90 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 280.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 79.37 | 39 | -40.37 | 203.5% | 46.8 | 39 | 39.96% | 15.5853 | -63.7847 | 198.6116 | 39 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 800.1700. - FS Project Manager | 5 | 50 | 45 | 10% | 242.5 | 50 | 242.5% | 121.25 | 116.25 | 2.0619 | 50 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 320.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 2553.49 | 836.5 | -1716.99 | 305.3% | 1505.7 | 836.5 | 64.24% | 537.3623 | -2016.1277 | 3974.9616 | 836.5 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.3000. - CNC Concrete Work | 97.81 | 66 | -31.81 | 148.2% | 198 | 66 | 200% | 132 | 34.19 | 48.905 | 66 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.2800. - BFST Backfill (DO NOT USE) | 94.19 | 60 | -34.19 | 157% | 120 | 60 | 92.31% | 55.3846 | -38.8054 | 102.0392 | 60 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 340.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 50.4 | 26.68 | -23.72 | 188.9% | 42.688 | 26.68 | 53.35% | 14.2329 | -36.1671 | 94.4764 | 26.68 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.2600. - DW Dewatering | 7485.85 | 1854 | -5631.85 | 403.8% | 2966.4 | 1854 | 33.47% | 620.5653 | -6865.2847 | 22364.7148 | 1854 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 210.2500. - MH Manholes (DO NOT USE) | 95.22 | 40 | -55.22 | 238.1% | 80 | 40 | 139.1% | 55.6522 | -39.5678 | 68.4394 | 40 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5120. - Fab Shop Pipe Linings & Coatings | 580.01 | 110 | -470.01 | 527.3% | 143 | 110 | 106.4% | 117.05 | -462.96 | 545.0756 | 110 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 230.2080. - EXS Excavate Structure | 2 | 40 | 38 | 5% | 40 | 40 | 49.23% | 19.6923 | 17.6923 | 4.0625 | 40 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.3000. - Unknown Phase | 5 | 0 | -5 |  | 12407.3 | 0 | 71.84% | 0 | -5 | 6.9603 | 12407.3 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2600. - DW Dewatering | 582.46 | 315.26 | -267.2 | 184.8% | 945.78 | 315.26 | 85.71% | 270.2204 | -312.2396 | 679.5428 | 315.26 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 10.28 | 40 | 29.72 | 25.7% | 160 | 40 | 133.3% | 53.3333 | 43.0533 | 7.71 | 40 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 200.1600. - TC Traffic Control | 830.11 | 465 | -365.11 | 178.5% | 990 | 465 | 41.25% | 191.8125 | -638.2975 | 2012.3879 | 450 | 103.2% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 100.1703. - FS Job Site Superintendent | 1884.85 | 0 | -1884.85 |  | 0 | 0 | 0% | 0 | -1884.85 | 1884.85 | 0 | 0% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 160.5015. - Fab Shop Transport | 30.67 | 20 | -10.67 | 153.4% | 50 | 20 | 125% | 25 | -5.67 | 24.536 | 20 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 300.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 4205.43 | 2187.72 | -2017.71 | 192.2% | 3281.58 | 2187.72 | 66.43% | 1453.3485 | -2752.0815 | 6330.4179 | 2187.72 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 600.2930. - AP Asphalt Prep (DO NOT USE) | 1423.06 | 107.64 | -1315.42 | 1322% | 430.56 | 107.64 | 200% | 215.28 | -1207.78 | 711.53 | 107.64 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 390.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 23.2 | 30 | 6.8 | 77.33% | 90 | 30 | 100% | 30 | 6.8 | 23.2 | 30 | 100% |  | 2024-04-01
2232. - Syracuse Secondary Reservoir | 900.9010. - Re-Work Pipe | 851.39 | 0.4 | -850.99 | 212848% | 1.94 | 0.4 | 323.3% | 1.2933 | -850.0967 | 263.3165 | 0.4 | 100% |  | 2024-04-01
2406. - DR Horton Viridian Wellhouse | 100.1704. - FS Quality Control/Assurance | 24.5 | 36.98 | 12.48 | 66.25% | 0 | 36.98 | 0% | 36.98 | 12.48 | 36.98 | 24.5 | 133.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 160.5000. - Unknown Phase | 8.53 | 150 | 141.47 | 5.687% | 1 | 150 | 100% | 150 | 141.47 | 8.53 | 8.53 | 194.3% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2075. - FG Finish Grade | 70.18 | 82.04 | 11.86 | 85.54% | 61.19 | 82.04 | 100% | 82.04 | 11.86 | 70.18 | 70.18 | 114.5% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1510. - S Surveying | 9.47 | 10 | 0.53 | 94.7% | 0 | 10 | 0% | 10 | 0.53 | 10 | 9.47 | 105.3% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2240. - PCS Precast Structures | 51.12 | 40 | -11.12 | 127.8% | 0 | 40 | 0% | 40 | -11.12 | 51.12 | 51.12 | 72.2% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.7100. - IMP Interior Mech/Piping | 542.54 | 598.5 | 55.96 | 90.65% | 589.5 | 598.5 | 100% | 598.5 | 55.96 | 542.54 | 542.54 | 109.4% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2120. - DIP Ductile Iron Pipe | 509.17 | 237.74 | -271.43 | 214.2% | 0 | 237.74 | 0% | 237.74 | -271.43 | 509.17 | 509.17 | -14.17% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.4000. - MAS Masonry | 27.48 | 40.95 | 13.47 | 67.11% | 0 | 186.95 | 0% | 40.95 | 13.47 | 40.95 | 27.48 | 132.9% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2085. - BFST Backfill Structure | 46.41 | 92.7 | 46.29 | 50.06% | 0 | 92.7 | 0% | 92.7 | 46.29 | 92.7 | 46.41 | 149.9% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1200. - HOOK Hook Truck Dumpster Transporting | 21.27 | 30 | 8.73 | 70.9% | 47 | 30 | 100% | 30 | 8.73 | 21.27 | 21.27 | 129.1% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 800.1940. - PL Punch List Work | 132.25 | 135 | 2.75 | 97.96% | 38 | 135 | 100% | 135 | 2.75 | 132.25 | 132.25 | 102% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 84.3 | 55 | -29.3 | 153.3% | 0 | 55 | 0% | 55 | -29.3 | 84.3 | 84.3 | 46.73% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6800. - CLK Caulking | 104.36 | 80 | -24.36 | 130.4% | 80 | 80 | 100% | 80 | -24.36 | 104.36 | 104.36 | 69.55% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.7900. - ELC Electrical | 51.53 | 118.6 | 67.07 | 43.45% | 1 | 118 | 100% | 118.6 | 67.07 | 51.53 | 51.53 | 156.6% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.5000. - MET Metals | 175.7 | 107.84 | -67.86 | 162.9% | 107.84 | 107.84 | 100% | 107.84 | -67.86 | 175.7 | 175.7 | 37.07% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 161.2090. - MTL Materials | 2.75 | 33 | 30.25 | 8.333% | 1 | 33 | 100% | 33 | 30.25 | 2.75 | 2.75 | 191.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1702. - FS People Superintendent | 185.82 | 186.95 | 1.13 | 99.4% | 1 | 186.95 | 100% | 186.95 | 1.13 | 185.82 | 185.82 | 100.6% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 150.1230. - T Transporting | 33.9 | 100 | 66.1 | 33.9% | 100 | 100 | 100% | 100 | 66.1 | 33.9 | 33.9 | 166.1% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 900.9015. - Re-Work Concrete | 84.22 | 0.4 | -83.82 | 21055% | 0.4 | 0.4 | 100% | 0.4 | -83.82 | 84.22 | 84.22 | -20855% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.3000. - Unknown Phase | 1200.06 | 777.91 | -422.15 | 154.3% | 768.91 | 777.91 | 100% | 777.91 | -422.15 | 1200.06 | 1200.06 | 45.73% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 900.9012. - Re-Work Mechanical | 10 | 0.6 | -9.4 | 1667% | 0.6 | 0.6 | 100% | 0.6 | -9.4 | 10 | 10 | -1467% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 263.92 | 239.1 | -24.82 | 110.4% | 0.95 | 239.1 | 95% | 227.145 | -36.775 | 277.8105 | 263.92 | 89.62% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 150.2750. - Unknown Phase | 65.63 | 190.88 | 125.25 | 34.38% | 167.55 | 190.88 | 100% | 190.88 | 125.25 | 65.63 | 65.63 | 165.6% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 150.2760. - Unknown Phase | 2.13 | 53.08 | 50.95 | 4.013% | 53.08 | 53.08 | 100% | 53.08 | 50.95 | 2.13 | 2.13 | 196% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6000. - IF Interior Finishes | 54.3 | 1.5 | -52.8 | 3620% | 1.5 | 1.5 | 100% | 1.5 | -52.8 | 54.3 | 54.3 | -3420% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6300. - DAW Doors & Windows | 32.3 | 150 | 117.7 | 21.53% | 150 | 150 | 100% | 150 | 117.7 | 32.3 | 32.3 | 178.5% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1703. - FS Job Site Superintendent | 1008.25 | 384.2 | -624.05 | 262.4% | 0.95 | 384.2 | 105.6% | 405.5444 | -602.7056 | 955.1842 | 1008.25 | -62.43% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1700. - FS Project Manager | 738 | 264.59 | -473.41 | 278.9% | 0.95 | 264.59 | 95% | 251.3605 | -486.6395 | 776.8421 | 738 | -78.92% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 900.9010. - Re-Work Pipe | 42.55 | 0.6 | -41.95 | 7092% | 0.6 | 0.6 | 100% | 0.6 | -41.95 | 42.55 | 42.55 | -6892% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2150. - PSR Pipe w/ Slide Rail | 5 | 42 | 37 | 11.9% | 0 | 42 | 0% | 42 | 37 | 42 | 5 | 188.1% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.6200. - IN Insulation | 63.24 | 12 | -51.24 | 527% | 0 | 12 | 0% | 12 | -51.24 | 63.24 | 63.24 | -327% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2140. - SVR Services | 12.67 | 21 | 8.33 | 60.33% | 0 | 21 | 0% | 21 | 8.33 | 21 | 12.67 | 139.7% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 100.1201. - HOOK Hook Truck Conex, Skid Transporting | 2 | 5 | 3 | 40% | 5 | 5 | 100% | 5 | 3 | 2 | 2 | 160% |  | 2025-05-31
2406. - DR Horton Viridian Wellhouse | 200.2080. - EXS Excavate Structure | 24.67 | 37.73 | 13.06 | 65.39% | 0 | 37.73 | 0% | 37.73 | 13.06 | 37.73 | 24.67 | 134.6% |  | 2025-05-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.2080. - EXS Excavate Structure | 180.71 | 40 | -140.71 | 451.8% | 40 | 40 | 100% | 40 | -140.71 | 180.71 | 180.71 | -251.8% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.2085. - BFST Backfill Structure | 334.07 | 40 | -294.07 | 835.2% | 40 | 40 | 100% | 40 | -294.07 | 334.07 | 334.07 | -635.2% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 800.1940. - PL Punch List Work | 14.67 | 840 | 825.33 | 1.746% | 0 | 840 | 0% | 840 | 825.33 | 840 | 840 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.3000. - CNC Concrete Work | 544.14 | 388.56 | -155.58 | 140% | 310.848 | 388.56 | 80% | 310.848 | -233.292 | 680.175 | 544.14 | 59.96% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2120. - DIP Ductile Iron Pipe | 316.56 | 511.55 | 194.99 | 61.88% | 434.817 | 511.55 | 85% | 434.8173 | 118.2573 | 372.4237 | 511.55 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 550.3000. - CNC Concrete Work | 1231.75 | 897.35 | -334.4 | 137.3% | 673.013 | 897.35 | 75% | 673.0133 | -558.7367 | 1642.3313 | 1129.81 | 74.09% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1200. - HOOK Hook Truck Dumpster Transporting | 28.37 | 56.25 | 27.88 | 50.44% | 0 | 56.25 | 0% | 56.25 | 27.88 | 56.25 | 30.85 | 145.2% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.7900. - ELC Electrical | 234.25 | 180 | -54.25 | 130.1% | 81 | 180 | 45% | 81.0002 | -153.2498 | 520.5542 | 273.17 | 48.24% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.2120. - DIP Ductile Iron Pipe | 89.1 | 30 | -59.1 | 297% | 18 | 30 | 61.25% | 18.375 | -70.725 | 145.4694 | 89.1 | -97% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.7100. - IMP Interior Mech/Piping | 5.37 | 60 | 54.63 | 8.95% | 60 | 60 | 100% | 60 | 54.63 | 5.37 | 5.37 | 191.1% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.6300. - DAW Doors & Windows | 13.92 | 105 | 91.08 | 13.26% | 0 | 105 | 0% | 105 | 91.08 | 105 | 105 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 550.2085. - BFST Backfill Structure | 260.57 | 160 | -100.57 | 162.9% | 120 | 160 | 75% | 120 | -140.57 | 347.4267 | 160 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2065. - SFC SWPPP | 0.5 | 26 | 25.5 | 1.923% | 13 | 26 | 50% | 13 | 12.5 | 1 | 26 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 700.7100. - IMP Interior Mech/Piping | 159.23 | 124 | -35.23 | 128.4% | 0 | 124 | 0% | 124 | -35.23 | 159.23 | 100 | 119.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.7100. - IMP Interior Mech/Piping | 4 | 57 | 53 | 7.018% | 0 | 57 | 0% | 57 | 53 | 57 | 57 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.2080. - EXS Excavate Structure | 118.15 | 120 | 1.85 | 98.46% | 108 | 120 | 90% | 108 | -10.15 | 131.2778 | 120 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1702. - FS People Superintendent | 633.77 | 1001 | 367.23 | 63.31% | 500 | 1001 | 50% | 500.5 | -133.27 | 1267.54 | 997.52 | 100.3% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1510. - S Surveying | 350.44 | 250 | -100.44 | 140.2% | 200 | 250 | 80% | 200 | -150.44 | 438.05 | 383.11 | 46.76% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.7100. - IMP Interior Mech/Piping | 11.31 | 80 | 68.69 | 14.14% | 40 | 80 | 50% | 40 | 28.69 | 22.62 | 80 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 800.1930. - MC Misc Cleanup | 9.73 | 412.5 | 402.77 | 2.359% | 0 | 412.5 | 0% | 412.5 | 402.77 | 412.5 | 412.5 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.6100. - F Framing | 187.81 | 60 | -127.81 | 313% | 0 | 60 | 0% | 60 | -127.81 | 187.81 | 84.24 | 59.6% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.3000. - CNC Concrete Work | 1523.74 | 2353.6 | 829.86 | 64.74% | 2353.6 | 2353.6 | 100% | 2353.6 | 829.86 | 1523.74 | 1523.74 | 135.3% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.1800. - PH Potholing | 11 | 9 | -2 | 122.2% | 8.1 | 9 | 90% | 8.1 | -2.9 | 12.2222 | 11 | 77.78% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1704. - FS Quality Control/Assurance | 242.5 | 501 | 258.5 | 48.4% | 250 | 501 | 50% | 250.5 | 8 | 485 | 500 | 100.2% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.2130. - PVC Pipe | 96.62 | 400.69 | 304.07 | 24.11% | 400.69 | 400.69 | 100% | 400.69 | 304.07 | 96.62 | 96.62 | 175.9% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.2080. - EXS Excavate Structure | 1084.23 | 300 | -784.23 | 361.4% | 300 | 300 | 100% | 300 | -784.23 | 1084.23 | 1084.23 | -161.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.7600. - MEQ Mechanical Equipment | 108.81 | 30 | -78.81 | 362.7% | 30 | 30 | 100% | 30 | -78.81 | 108.81 | 108.81 | -162.7% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 550.2080. - EXS Excavate Structure | 75.63 | 80 | 4.37 | 94.54% | 80 | 80 | 100% | 80 | 4.37 | 75.63 | 75.63 | 105.5% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1700. - FS Project Manager | 948.58 | 2251 | 1302.42 | 42.14% | 0 | 2251 | 0% | 2251 | 1302.42 | 2251 | 1170.33 | 148% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 260.2210. - RCP Reinforced Concrete Pipe | 73.82 | 0 | -73.82 |  | 0 | 0 | 0% | 0 | -73.82 | 73.82 | 39.32 | 0% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 541.78 | 501 | -40.78 | 108.1% | 250 | 501 | 50% | 250.5 | -291.28 | 1083.56 | 589.59 | 82.32% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 300.6500. - P Painting | 2.5 | 0 | -2.5 |  | 0 | 0 | 0% | 0 | -2.5 | 2.5 | 2.5 | 0% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 150.2750. - Unknown Phase | 346.44 | 348.7 | 2.26 | 99.35% | 174.35 | 348.7 | 50% | 174.35 | -172.09 | 692.88 | 341.55 | 102.1% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 100.1703. - FS Job Site Superintendent | 1902.8 | 3001 | 1098.2 | 63.41% | 1500 | 3001 | 50% | 1500.5 | -402.3 | 3805.6 | 3000 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 600.3000. - CNC Concrete Work | 570.14 | 140 | -430.14 | 407.2% | 140 | 140 | 100% | 140 | -430.14 | 570.14 | 570.14 | -207.2% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.3000. - CNC Concrete Work | 955.84 | 754.76 | -201.08 | 126.6% | 641.546 | 754.76 | 85% | 641.546 | -314.294 | 1124.5176 | 754.76 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 150.1230. - T Transporting | 156.06 | 170 | 13.94 | 91.8% | 75 | 170 | 50% | 85 | -71.06 | 312.12 | 143.98 | 115.3% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2150. - PSR Pipe w/ Slide Rail | 212.74 | 280 | 67.26 | 75.98% | 280 | 280 | 100% | 280 | 67.26 | 212.74 | 238.93 | 114.7% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.6300. - DAW Doors & Windows | 52.66 | 60 | 7.34 | 87.77% | 57 | 60 | 95% | 57 | 4.34 | 55.4316 | 66.66 | 88.9% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 200.2065. - SFC SWPPP | 275.87 | 51 | -224.87 | 540.9% | 25.5 | 51 | 50% | 25.5 | -250.37 | 551.74 | 308.25 | -404.4% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.7900. - ELC Electrical | 33.18 | 0 | -33.18 |  | 0 | 0 | 0% | 0 | -33.18 | 33.18 | 33.18 | 0% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.7600. - MEQ Mechanical Equipment | 12.08 | 20 | 7.92 | 60.4% | 20 | 20 | 100% | 20 | 7.92 | 12.08 | 12.08 | 139.6% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 500.2085. - BFST Backfill Structure | 786.72 | 625 | -161.72 | 125.9% | 593.75 | 625 | 95% | 593.75 | -192.97 | 828.1263 | 809.52 | 70.48% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.5000. - MET Metals | 64.55 | 291 | 226.45 | 22.18% | 72.75 | 291 | 25% | 72.75 | 8.2 | 258.2 | 291 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.2130. - PVC Pipe | 348.24 | 458.08 | 109.84 | 76.02% | 137.424 | 458.08 | 30% | 137.424 | -210.816 | 1160.8 | 458.08 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 150.2760. - Unknown Phase | 72.6 | 565.5 | 492.9 | 12.84% | 113.1 | 565.5 | 20% | 113.1 | 40.5 | 363 | 432.6 | 123.5% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2210. - RCP Reinforced Concrete Pipe | 618.41 | 417.95 | -200.46 | 148% | 334.36 | 417.95 | 80% | 334.36 | -284.05 | 773.0125 | 545.61 | 69.46% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 400.2085. - BFST Backfill Structure | 188.15 | 100 | -88.15 | 188.2% | 100 | 100 | 100% | 100 | -88.15 | 188.15 | 227.22 | -27.22% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 250.2130. - PVC Pipe | 160.64 | 171.5 | 10.86 | 93.67% | 145.775 | 171.5 | 85% | 145.775 | -14.865 | 188.9882 | 171.5 | 100% |  | 2026-08-31
2408. - Santaquin City WRF Phase 3 Upgrades | 220.6100. - F Framing | 19.56 | 5.12 | -14.44 | 382% | 5.12 | 5.12 | 100% | 5.12 | -14.44 | 19.56 | 19.56 | -182% |  | 2026-08-31
2508. - Turner Dam & Joint Diversion Rehab | 500.3000. - CNC Concrete Work | 987.26 | 60 | -927.26 | 1645% | 51 | 60 | 85% | 51 | -936.26 | 1161.4824 | 977.01 | -1428%
2508. - Turner Dam & Joint Diversion Rehab | 500.2030. - D Demolition | 27.85 | 92 | 64.15 | 30.27% | 73.6 | 92 | 80% | 73.6 | 45.75 | 34.8125 | 27.85 | 169.7%
2508. - Turner Dam & Joint Diversion Rehab | 250.7600. - MEQ Mechanical Equipment | 112.18 | 1290 | 1177.82 | 8.696% | 645 | 1290 | 50% | 645 | 532.82 | 224.36 | 1354.21 | 95.02%
2508. - Turner Dam & Joint Diversion Rehab | 600.2070. - RGC Rough Grade Cut | 5.5 | 110 | 104.5 | 5% | 27.5 | 110 | 0% | 110 | 104.5 | 110 | 5.5 | 195%
2508. - Turner Dam & Joint Diversion Rehab | 400.2600. - DW Dewatering | 3.77 | 90 | 86.23 | 4.189% | 90 | 90 | 100% | 90 | 86.23 | 3.77 | 41.35 | 154.1%
2508. - Turner Dam & Joint Diversion Rehab | 600.2075. - FG Finish Grade | 1014.8 | 51.56 | -963.24 | 1968% | 0 | 51.56 | 0% | 51.56 | -963.24 | 1014.8 | 764.35 | -1282%
2508. - Turner Dam & Joint Diversion Rehab | 600.1940. - PL Punch List Work | 84.62 | 80 | -4.62 | 105.8% | 0 | 80 | 0% | 80 | -4.62 | 84.62 | 0 | 200%
2508. - Turner Dam & Joint Diversion Rehab | 260.2080. - EXS Excavate Structure | 64.93 | 90 | 25.07 | 72.14% | 0 | 90 | 0% | 90 | 25.07 | 90 | 64.93 | 127.9%
2508. - Turner Dam & Joint Diversion Rehab | 300.2030. - D Demolition | 4.7 | 60 | 55.3 | 7.833% | 60 | 60 | 100% | 60 | 55.3 | 4.7 | 4.7 | 192.2%
2508. - Turner Dam & Joint Diversion Rehab | 600.5000. - MET Metals | 19.6 | 15 | -4.6 | 130.7% | 0 | 15 | 0% | 15 | -4.6 | 19.6 | 50 | -133.3%
2508. - Turner Dam & Joint Diversion Rehab | 150.2760. - Unknown Phase | 118.08 | 109.72 | -8.36 | 107.6% | 104.234 | 109.72 | 95% | 104.234 | -13.846 | 124.2947 | 124.08 | 86.91%
2508. - Turner Dam & Joint Diversion Rehab | 350.2075. - FG Finish Grade | 353.93 | 315.56 | -38.37 | 112.2% | 315.56 | 315.56 | 100% | 315.56 | -38.37 | 353.93 | 364.26 | 84.57%
2508. - Turner Dam & Joint Diversion Rehab | 900.9100. - Job Related Equipment Repairs | 5.57 | 1 | -4.57 | 557% | 0.4 | 1 | 40% | 0.4 | -5.17 | 13.925 | 5.57 | -357%
2508. - Turner Dam & Joint Diversion Rehab | 100.1706. - FS Executive | 3.5 | 1 | -2.5 | 350% | 0.35 | 1 | 35% | 0.35 | -3.15 | 10 | 3.5 | -150%
2508. - Turner Dam & Joint Diversion Rehab | 300.7600. - MEQ Mechanical Equipment | 37.88 | 90 | 52.12 | 42.09% | 67.5 | 90 | 75% | 67.5 | 29.62 | 50.5067 | 37.88 | 157.9%
2508. - Turner Dam & Joint Diversion Rehab | 600.2600. - DW Dewatering | 53.75 | 58 | 4.25 | 92.67% | 0 | 58 | 0% | 58 | 4.25 | 58 | 52.32 | 109.8%
2508. - Turner Dam & Joint Diversion Rehab | 350.2240. - PCS Precast Structures | 104.74 | 110 | 5.26 | 95.22% | 110 | 110 | 100% | 110 | 5.26 | 104.74 | 104.74 | 104.8%
2508. - Turner Dam & Joint Diversion Rehab | 100.1200. - HOOK Hook Truck Dumpster Transporting | 23.08 | 15 | -8.08 | 153.9% | 7.5 | 15 | 75% | 11.25 | -11.83 | 30.7733 | 22.58 | 49.47%
2508. - Turner Dam & Joint Diversion Rehab | 500.3010. - WP Winter Protection | 20.92 | 18 | -2.92 | 116.2% | 9 | 18 | 50% | 9 | -11.92 | 41.84 | 20.92 | 83.78%
2508. - Turner Dam & Joint Diversion Rehab | 350.2050. - RW Retaining Walls | 98.69 | 23.36 | -75.33 | 422.5% | 23.36 | 23.36 | 100% | 23.36 | -75.33 | 98.69 | 98.69 | -222.5%
2508. - Turner Dam & Joint Diversion Rehab | 600.2140. - SVR Services | 10.07 | 46 | 35.93 | 21.89% | 0 | 46 | 0% | 46 | 35.93 | 46 | 10.07 | 178.1%
2508. - Turner Dam & Joint Diversion Rehab | 350.3000. - CNC Concrete Work | 416.66 | 189.8 | -226.86 | 219.5% | 189.8 | 189.8 | 100% | 189.8 | -226.86 | 416.66 | 422.66 | -22.69%
2508. - Turner Dam & Joint Diversion Rehab | 300.5000. - MET Metals | 133.17 | 50.4 | -82.77 | 264.2% | 1.008 | 50.4 | 23.47% | 11.8292 | -121.3408 | 567.391 | 103.48 | -5.317%
2508. - Turner Dam & Joint Diversion Rehab | 100.1702. - FS People Superintendent | 328.41 | 160.77 | -167.64 | 204.3% | 112.539 | 160.77 | 70% | 112.539 | -215.871 | 469.1571 | 420.91 | -61.81%
2508. - Turner Dam & Joint Diversion Rehab | 100.1510. - S Surveying | 96.35 | 20 | -76.35 | 481.8% | 19 | 20 | 95% | 19 | -77.35 | 101.4211 | 93.05 | -265.2%
2508. - Turner Dam & Joint Diversion Rehab | 400.7600. - MEQ Mechanical Equipment | 73.23 | 240 | 166.77 | 30.51% | 204 | 240 | 85% | 204 | 130.77 | 86.1529 | 73.23 | 169.5%
2508. - Turner Dam & Joint Diversion Rehab | 300.3000. - CNC Concrete Work | 27.75 | 223.04 | 195.29 | 12.44% | 223.04 | 223.04 | 100% | 223.04 | 195.29 | 27.75 | 27.75 | 187.6%
2508. - Turner Dam & Joint Diversion Rehab | 400.5000. - MET Metals | 24.48 | 22.5 | -1.98 | 108.8% | 22.5 | 22.5 | 100% | 22.5 | -1.98 | 24.48 | 27.48 | 77.87%
2508. - Turner Dam & Joint Diversion Rehab | 665.5000. - MET Metals | 3.25 | 4 | 0.75 | 81.25% | 0 | 4 | 0% | 4 | 0.75 | 4 | 10 | -50%
2508. - Turner Dam & Joint Diversion Rehab | 420.7600. - MEQ Mechanical Equipment | 533.11 | 115.92 | -417.19 | 459.9% | 0 | 116 | 0% | 115.92 | -417.19 | 533.11 | 549.11 | -273.7%
2508. - Turner Dam & Joint Diversion Rehab | 100.1704. - FS Quality Control/Assurance | 7 | 60.68 | 53.68 | 11.54% | 21.238 | 60.68 | 35% | 21.238 | 14.238 | 20 | 10 | 183.5%
2508. - Turner Dam & Joint Diversion Rehab | 250.2030. - D Demolition | 19.95 | 21 | 1.05 | 95% | 18.9 | 21 | 90% | 18.9 | -1.05 | 22.1667 | 19.95 | 105%
2508. - Turner Dam & Joint Diversion Rehab | 350.2020. - CG Clearing/Grubbing | 160.53 | 10 | -150.53 | 1605% | 10 | 10 | 100% | 10 | -150.53 | 160.53 | 160.53 | -1405%
2508. - Turner Dam & Joint Diversion Rehab | 600.1930. - MC Misc Cleanup | 47.46 | 80 | 32.54 | 59.33% | 32 | 80 | 0% | 80 | 32.54 | 80 | 29.48 | 163.2%
2508. - Turner Dam & Joint Diversion Rehab | 600.2595. - CD Coffer Dams | 3 | 60 | 57 | 5% | 0 | 60 | 0% | 60 | 57 | 60 | 3 | 195%
2508. - Turner Dam & Joint Diversion Rehab | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 446.84 | 196.29 | -250.55 | 227.6% | 137.403 | 196.29 | 70% | 137.403 | -309.437 | 638.3429 | 452.89 | -30.72%
2508. - Turner Dam & Joint Diversion Rehab | 100.1700. - FS Project Manager | 426.5 | 191.9 | -234.6 | 222.3% | 134.33 | 191.9 | 70% | 134.33 | -292.17 | 609.2857 | 462 | -40.75%
2508. - Turner Dam & Joint Diversion Rehab | 100.1703. - FS Job Site Superintendent | 365.31 | 236.62 | -128.69 | 154.4% | 164.395 | 236.85 | 70% | 165.634 | -199.676 | 521.8714 | 407.21 | 27.91%
2508. - Turner Dam & Joint Diversion Rehab | 420.5000. - MET Metals | 261.97 | 0 | -261.97 |  | 0 | 0 | 0% | 0 | -261.97 | 261.97 | 271.03 | 0%
2508. - Turner Dam & Joint Diversion Rehab | 350.2210. - RCP Reinforced Concrete Pipe | 3 | 12.5 | 9.5 | 24% | 12.5 | 12.5 | 100% | 12.5 | 9.5 | 3 | 3 | 176%
2508. - Turner Dam & Joint Diversion Rehab | 450.5000. - MET Metals | 30.27 | 64 | 33.73 | 47.3% | 64 | 64 | 0% | 64 | 33.73 | 64 | 30.27 | 152.7%
2508. - Turner Dam & Joint Diversion Rehab | 350.2085. - BFST Backfill Structure | 244.07 | 81 | -163.07 | 301.3% | 81 | 81 | 100% | 81 | -163.07 | 244.07 | 244.07 | -101.3%
2508. - Turner Dam & Joint Diversion Rehab | 250.3000. - CNC Concrete Work | 332.85 | 45 | -287.85 | 739.7% | 40.5 | 45 | 90% | 40.5 | -292.35 | 369.8333 | 346.28 | -569.5%
2508. - Turner Dam & Joint Diversion Rehab | 350.7600. - MEQ Mechanical Equipment | 4 | 50 | 46 | 8% | 0.5 | 50 | 1% | 0.5 | -3.5 | 400 | 4 | 192%
2508. - Turner Dam & Joint Diversion Rehab | 150.2750. - Unknown Phase | 261.16 | 149.86 | -111.3 | 174.3% | 142.367 | 149.86 | 95% | 142.367 | -118.793 | 274.9053 | 273.66 | 17.39%
2508. - Turner Dam & Joint Diversion Rehab | 350.2070. - RGC Rough Grade Cut | 41.38 | 64.8 | 23.42 | 63.86% | 64.8 | 64.8 | 100% | 64.8 | 23.42 | 41.38 | 47.38 | 126.9%
2508. - Turner Dam & Joint Diversion Rehab | 620.2075. - FG Finish Grade | 9.2 | 268.41 | 259.21 | 3.428% | 0 | 268.41 | 0% | 268.41 | 259.21 | 268.41 | 9.2 | 196.6%
2508. - Turner Dam & Joint Diversion Rehab | 300.2085. - BFST Backfill Structure | 42.2 | 9 | -33.2 | 468.9% | 9 | 9 | 100% | 9 | -33.2 | 42.2 | 42.2 | -268.9%
2508. - Turner Dam & Joint Diversion Rehab | 600.2750. - H Hauling | 118.64 | 119.86 | 1.22 | 98.98% | 0 | 119.86 | 0% | 119.86 | 1.22 | 119.86 | 129.3 | 92.12%
2508. - Turner Dam & Joint Diversion Rehab | 250.2595. - CD Coffer Dams | 32.75 | 100 | 67.25 | 32.75% | 60 | 100 | 60% | 60 | 27.25 | 54.5833 | 100.17 | 99.83%
2508. - Turner Dam & Joint Diversion Rehab | 150.1230. - T Transporting | 277.14 | 175 | -102.14 | 158.4% | 60 | 175 | 80% | 140 | -137.14 | 346.425 | 275.84 | 42.38%
2508. - Turner Dam & Joint Diversion Rehab | 600.3000. - CNC Concrete Work | 365.1 | 639.09 | 273.99 | 57.13% | 0 | 639.09 | 0% | 639.09 | 273.99 | 639.09 | 100 | 184.4%
2508. - Turner Dam & Joint Diversion Rehab | 250.5000. - MET Metals | 1 | 88 | 87 | 1.136% | 0.88 | 88 | 1% | 0.88 | -0.12 | 100 | 88 | 100%
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1704. - FS Quality Control/Assurance | 135 | 147.24 | 12.24 | 91.69% | 87.744 | 146.24 | 57.5% | 84.663 | -50.337 | 234.7826 | 185 | 74.35% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 205.2170. - HDPE Fusion Pipe <15' Depth | 2670.04 | 2407.99 | -262.05 | 110.9% | 402.6 | 746 | 55% | 1324.3945 | -1345.6455 | 4854.6182 | 4386.52 | 17.83% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 527.34 | 454.26 | -73.08 | 116.1% | 271.956 | 453.26 | 60% | 272.556 | -254.784 | 878.9 | 812.34 | 21.17% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1700. - FS Project Manager | 268 | 484.4 | 216.4 | 55.33% | 290.04 | 483.4 | 60% | 290.64 | 22.64 | 446.6667 | 461.5 | 104.7% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 300.5100. - W Welding | 307.93 | 0 | -307.93 |  | 0 | 0 | 0% | 0 | -307.93 | 307.93 | 307.93 | 0% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 150.2750. - Unknown Phase | 526.55 | 1099.29 | 572.74 | 47.9% | 605 | 15250 | 55% | 604.6095 | 78.0595 | 957.3636 | 1054.67 | 104.1% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1703. - FS Job Site Superintendent | 560.89 | 571.11 | 10.22 | 98.21% | 342.066 | 570.11 | 60% | 342.666 | -218.224 | 934.8167 | 706.78 | 76.24% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2170. - HDPE Fusion Pipe <15' Depth | 4667.14 | 4886.59 | 219.45 | 95.51% | 4009.5 | 7290 | 55% | 2687.6245 | -1979.5155 | 8485.7091 | 5677.86 | 83.81% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1510. - S Surveying | 352.6 | 106.5 | -246.1 | 331.1% | 55 | 100 | 55% | 58.575 | -294.025 | 641.0909 | 470.72 | -242% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 150.1230. - T Transporting | 75.76 | 152 | 76.24 | 49.84% | 82.5 | 150 | 55% | 83.6 | 7.84 | 137.7455 | 143.26 | 105.8% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2075. - FG Finish Grade | 12.35 | 63 | 50.65 | 19.6% | 0 | 7200 | 0% | 63 | 50.65 | 63 | 62.35 | 101% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1201. - HOOK Hook Truck Conex, Skid Transporting | 1.25 | 10 | 8.75 | 12.5% | 4 | 10 | 40% | 4 | 2.75 | 3.125 | 11.25 | 87.5% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1600. - TC Traffic Control | 9.75 | 140 | 130.25 | 6.964% | 84 | 140 | 60% | 84 | 74.25 | 16.25 | 59.75 | 157.3% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 350.2170. - HDPE Fusion Pipe <15' Depth | 772.87 | 0 | -772.87 |  | 0 | 0 | 0% | 0 | -772.87 | 772.87 | 702.8 | 0% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1200. - HOOK Hook Truck Dumpster Transporting | 14 | 20 | 6 | 70% | 10 | 20 | 50% | 10 | -4 | 28 | 59.5 | -97.5% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 160.5000. - Unknown Phase | 21.1 | 0 | -21.1 |  | -21.1 | 0 | 0% | 0 | -21.1 | 21.1 | 21.1 | 0% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 215.2170. - HDPE Fusion Pipe <15' Depth | 40.3 | 1056 | 1015.7 | 3.816% | 6.6 | 22 | 30% | 316.8 | 276.5 | 134.3333 | 540.3 | 148.8% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 210.2170. - HDPE Fusion Pipe <15' Depth | 113.54 | 382.68 | 269.14 | 29.67% | 5.4 | 18 | 45% | 172.206 | 58.666 | 252.3111 | 314.25 | 117.9% |  | 2025-12-31
2509. - Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1702. - FS People Superintendent | 363.37 | 378.66 | 15.29 | 95.96% | 226.596 | 377.66 | 60% | 227.196 | -136.174 | 605.6167 | 408.45 | 92.13% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2080. - EXS Excavate Structure | 183.38 | 298.18 | 114.8 | 61.5% | 150 | 297 | 100% | 298.18 | 114.8 | 183.38 | 183.38 | 138.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.3000. - Unknown Phase | 1031.7 | 573 | -458.7 | 180.1% | 432.8 | 573 | 100% | 573 | -458.7 | 1031.7 | 1031.7 | 19.95% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.2010. - RG Grading (DO NOT USE) | 33.59 | 160 | 126.41 | 20.99% | 160 | 160 | 100% | 160 | 126.41 | 33.59 | 33.59 | 179% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 510.2040. - LR Landscaping/Restoration | 308.07 | 230 | -78.07 | 133.9% | 230 | 230 | 100% | 230 | -78.07 | 308.07 | 308.07 | 66.06% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 150.2750. - Unknown Phase | 665.03 | 940.86 | 275.83 | 70.68% | 916.24 | 940.66 | 100% | 940.86 | 275.83 | 665.03 | 665.03 | 129.3% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 400.2010. - RG Grading (DO NOT USE) | 91.32 | 308.47 | 217.15 | 29.6% | 277.623 | 308.47 | 100% | 308.4733 | 217.1533 | 91.319 | 91.32 | 170.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2610. - PT Pressure Test/Chlorinating | 255.69 | 160 | -95.69 | 159.8% | 160 | 160 | 100% | 160 | -95.69 | 255.69 | 255.69 | 40.19% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7300. - PLUM Plumbing | 623.26 | 150 | -473.26 | 415.5% | 90 | 150 | 100% | 150 | -473.26 | 623.26 | 623.26 | -215.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9010. - Re-Work Pipe | 14.5 | 0.4 | -14.1 | 3625% | 0.4 | 0.4 | 100% | 0.4 | -14.1 | 14.5 | 14.5 | -3425% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1703. - FS Job Site Superintendent | 2143.89 | 1049.46 | -1094.43 | 204.3% | 1048.071 | 1049.464 | 98% | 1028.471 | -1115.419 | 2187.6424 | 2151.89 | -5.047% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5120. - Fab Shop Pipe Linings & Coatings | 2203.25 | 440 | -1763.25 | 500.7% | 0 | 440 | 0% | 440 | -1763.25 | 2203.25 | 2203.25 | -300.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9005. - Re-Work Surveying | 4.15 | 1 | -3.15 | 415% | 1 | 1 | 100% | 1 | -3.15 | 4.15 | 4.15 | -215% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9011. - Unknown Phase | 50.45 | 0 | -50.45 |  | 0 | 0 | 0% | 0 | -50.45 | 50.45 | 50.45 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 150.1230. - T Transporting | 173.57 | 261.5 | 87.93 | 66.37% | 247 | 261.5 | 95% | 248.425 | 74.855 | 182.7053 | 173.57 | 133.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 5649.9 | 930.2 | -4719.7 | 607.4% | 930.2 | 930.2 | 100% | 930.2 | -4719.7 | 5649.9 | 5649.9 | -407.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.6200. - IN Insulation | 356.41 | 48.28 | -308.13 | 738.2% | 16 | 48 | 100% | 48.28 | -308.13 | 356.41 | 356.41 | -538.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 310.7900. - ELC Electrical | 15.75 | 0 | -15.75 |  | 0 | 0 | 0% | 0 | -15.75 | 15.75 | 15.75 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.5100. - W Welding | 573.05 | 395 | -178.05 | 145.1% | 121.5 | 395 | 100% | 395 | -178.05 | 573.05 | 573.05 | 54.92% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 510.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 525.21 | 225 | -300.21 | 233.4% | 225 | 225 | 100% | 225 | -300.21 | 525.21 | 525.21 | -33.43% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 310.3000. - CNC Concrete Work | 333.78 | 0 | -333.78 |  | 0 | 0 | 0% | 0 | -333.78 | 333.78 | 333.78 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2040. - LR Landscaping/Restoration | 112.55 | 80.8 | -31.75 | 139.3% | 1 | 80.8 | 100% | 80.8 | -31.75 | 112.55 | 112.55 | 60.71% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9012. - Re-Work Mechanical | 55.92 | 0.4 | -55.52 | 13980% | 0.4 | 0.4 | 100% | 0.4 | -55.52 | 55.92 | 55.92 | -13780% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1500. - VIS Meetings (Vision, Safety, Training) | 40.9 | 0 | -40.9 |  | 0 | 0 | 0% | 0 | -40.9 | 40.9 | 40.9 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7900. - ELC Electrical | 513.17 | 90 | -423.17 | 570.2% | 75 | 90 | 100% | 90 | -423.17 | 513.17 | 513.17 | -370.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5110. - Fab Shop Pipe Fabrication | 1221.42 | 308 | -913.42 | 396.6% | 0 | 308 | 0% | 308 | -913.42 | 1221.42 | 1221.42 | -196.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.3000. - CNC Concrete Work | 1177.85 | 1569.62 | 391.77 | 75.04% | 1255.696 | 1569.62 | 100% | 1569.615 | 391.765 | 1177.8538 | 1177.85 | 125% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7100. - IMP Interior Mech/Piping | 1873.41 | 576 | -1297.41 | 325.2% | 570 | 576 | 100% | 576 | -1297.41 | 1873.41 | 1873.41 | -125.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 150.2760. - Unknown Phase | 70.8 | 839.49 | 768.69 | 8.434% | 843.14 | 838.14 | 100% | 839.49 | 768.69 | 70.8 | 70.8 | 191.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.6400. - DRY Drywall & Metal Studs | 627.94 | 68 | -559.94 | 923.4% | 64.6 | 68 | 100% | 68 | -559.94 | 627.94 | 627.94 | -723.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 400.2000. - SWC Site Work Complete (DO NOT USE) | 683.33 | 221.16 | -462.17 | 309% | 176.928 | 221.16 | 100% | 221.1575 | -462.1725 | 683.3377 | 683.33 | -109% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.7600. - MEQ Mechanical Equipment | 127.73 | 350 | 222.27 | 36.49% | 99 | 350 | 100% | 350 | 222.27 | 127.73 | 127.73 | 163.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2300. - Unknown Phase | 583.11 | 783.03 | 199.92 | 74.47% | 614.9 | 783.04 | 100% | 783.03 | 199.92 | 583.11 | 583.11 | 125.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.7100. - IMP Interior Mech/Piping | 312.92 | 109 | -203.92 | 287.1% | 70 | 109 | 100% | 109 | -203.92 | 312.92 | 312.92 | -87.08% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.1650. - SB Signage | 147.58 | 15 | -132.58 | 983.9% | 15 | 15 | 100% | 15 | -132.58 | 147.58 | 147.58 | -783.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 600.2030. - D Demolition | 233.05 | 219 | -14.05 | 106.4% | 0 | 219 | 0% | 219 | -14.05 | 233.05 | 233.05 | 93.58% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9055. - Re-Work Finishes | 9.88 | 0.2 | -9.68 | 4940% | 0.2 | 0.2 | 100% | 0.2 | -9.68 | 9.88 | 9.88 | -4740% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.7100. - IMP Interior Mech/Piping | 88.48 | 258.63 | 170.15 | 34.21% | 168.142 | 258.63 | 65% | 168.1095 | 79.6295 | 136.1231 | 236.78 | 108.4% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9020. - Re-Work Fab | 14.05 | 0.2 | -13.85 | 7025% | 0.2 | 0.2 | 100% | 0.2 | -13.85 | 14.05 | 14.05 | -6825% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.5000. - MET Metals | 187 | 52 | -135 | 359.6% | 8 | 52 | 100% | 52 | -135 | 187 | 187 | -159.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.6100. - F Framing | 10.13 | 30 | 19.87 | 33.77% | 30 | 30 | 100% | 30 | 19.87 | 10.13 | 10.13 | 166.2% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 760.93 | 264.39 | -496.54 | 287.8% | 237.951 | 264.39 | 100% | 264.3911 | -496.5389 | 760.9268 | 760.93 | -87.81% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2800. - Unknown Phase | 526.13 | 165 | -361.13 | 318.9% | 165 | 165 | 100% | 165 | -361.13 | 526.13 | 526.13 | -118.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.2800. - BFST Backfill (DO NOT USE) | 813.93 | 150 | -663.93 | 542.6% | 0 | 150 | 0% | 150 | -663.93 | 813.93 | 813.93 | -342.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1702. - FS People Superintendent | 1337.74 | 512.76 | -824.98 | 260.9% | 522.105 | 512.755 | 98% | 502.505 | -835.235 | 1365.0403 | 1346.61 | -62.62% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5310. - Fab Shop Misc Metals Fabrication | 261.39 | 300.5 | 39.11 | 86.99% | 0 | 300.5 | 0% | 300.5 | 39.11 | 300.5 | 261.39 | 113% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2710. - FWF Flowable Fill | 36.44 | 8.08 | -28.36 | 451% | 3.56 | 7.68 | 100% | 8.08 | -28.36 | 36.44 | 36.44 | -251% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1510. - S Surveying | 622.21 | 175 | -447.21 | 355.5% | 150 | 175 | 100% | 175 | -447.21 | 622.21 | 622.21 | -155.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 160.5320. - Fab Shop Misc Metals Coatings | 20.9 | 491 | 470.1 | 4.257% | 0 | 491 | 0% | 491 | 470.1 | 491 | 20.9 | 195.7% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.5000. - MET Metals | 284.03 | 76.92 | -207.11 | 369.3% | 75 | 76.92 | 100% | 76.92 | -207.11 | 284.03 | 284.03 | -169.3% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 550.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 265.62 | 0 | -265.62 |  | 0 | 0 | 0% | 0 | -265.62 | 265.62 | 265.62 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 400.3000. - CNC Concrete Work | 988.19 | 869.56 | -118.63 | 113.6% | 778.6 | 869.56 | 100% | 869.56 | -118.63 | 988.19 | 988.19 | 86.36% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 210.2300. - WPL Water Pipe Laying (DO NOT USE) | 96.09 | 100 | 3.91 | 96.09% | 100 | 100 | 100% | 100 | 3.91 | 96.09 | 96.09 | 103.9% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1704. - FS Quality Control/Assurance | 1955.48 | 104.63 | -1850.85 | 1869% | 104.633 | 104.633 | 100% | 104.63 | -1850.85 | 1955.48 | 1965.48 | -1679% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.3000. - CNC Concrete Work | 1268.29 | 287.93 | -980.36 | 440.5% | 1 | 287 | 100% | 287.93 | -980.36 | 1268.29 | 1268.29 | -240.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.6300. - DAW Doors & Windows | 424.18 | 90 | -334.18 | 471.3% | 85.5 | 90 | 100% | 90 | -334.18 | 424.18 | 424.18 | -271.3% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 900.9100. - Job Related Equipment Repairs | 93.78 | 1 | -92.78 | 9378% | 0 | 1 | 0% | 1 | -92.78 | 93.78 | 93.78 | -9178% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.1650. - SB Signage | 9.52 | 10 | 0.48 | 95.2% | 8 | 10 | 100% | 10 | 0.48 | 9.52 | 9.52 | 104.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2500. - MH Manholes (DO NOT USE) | 13.33 | 96 | 82.67 | 13.89% | 1 | 96 | 100% | 96 | 82.67 | 13.33 | 13.33 | 186.1% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 800.1940. - PL Punch List Work | 749.14 | 222.5 | -526.64 | 336.7% | 198 | 222 | 99% | 220.275 | -528.865 | 756.7071 | 747.89 | -136.1% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1101. - TF Temporary Office Trailer VanCon | 2 | 0 | -2 |  | 0 | 0 | 0% | 0 | -2 | 2 | 2 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 67.99 | 165 | 97.01 | 41.21% | 165 | 165 | 100% | 165 | 97.01 | 67.99 | 67.99 | 158.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 600.6000. - IF Interior Finishes | 46.23 | 90 | 43.77 | 51.37% | 31 | 90 | 100% | 90 | 43.77 | 46.23 | 46.23 | 148.6% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 510.2300. - WPL Water Pipe Laying (DO NOT USE) | 61.47 | 0 | -61.47 |  | 0 | 0 | 0% | 0 | -61.47 | 61.47 | 61.47 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.7900. - ELC Electrical | 353.5 | 661.25 | 307.75 | 53.46% | 661.25 | 661.25 | 100% | 661.25 | 307.75 | 353.5 | 353.5 | 146.5% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 200.2600. - DW Dewatering | 115.78 | 32 | -83.78 | 361.8% | 1 | 32 | 66.67% | 21.3333 | -94.4467 | 173.67 | 115.78 | -161.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 800.1700. - FS Project Manager | 116.84 | 400 | 283.16 | 29.21% | 380 | 400 | 100% | 400 | 283.16 | 116.84 | 116.84 | 170.8% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 500.2000. - SWC Site Work Complete (DO NOT USE) | 129.77 | 0 | -129.77 |  | 0 | 0 | 0% | 0 | -129.77 | 129.77 | 129.77 | 0% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1700. - FS Project Manager | 1947.29 | 704.98 | -1242.31 | 276.2% | 710.48 | 704.98 | 98% | 690.88 | -1256.41 | 1987.0317 | 1960.29 | -78.06% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 300.2080. - EXS Excavate Structure | 24.82 | 250 | 225.18 | 9.928% | 0 | 250 | 0% | 250 | 225.18 | 250 | 24.82 | 190.1% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 800.1930. - MC Misc Cleanup | 418.55 | 230 | -188.55 | 182% | 198 | 230 | 99% | 227.7 | -190.85 | 422.7778 | 417.65 | 18.41% |  | 2025-12-31
2316. - CUWCD CWP Wellhouse 16 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 2227.32 | 654.65 | -1572.67 | 340.2% | 651.357 | 654.654 | 98% | 641.557 | -1585.763 | 2272.7755 | 2240.82 | -142.3% |  | 2025-12-31
2402. - SLC Little Dell Dam Outlet Works | 100.1703. - FS Job Site Superintendent | 78.76 | 50 | -28.76 | 157.5% | 50 | 50 | 100% | 50 | -28.76 | 78.76 | 78.76 | 42.48% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 100.1700. - FS Project Manager | 139.75 | 25 | -114.75 | 559% | 25 | 25 | 100% | 25 | -114.75 | 139.75 | 139.75 | -359% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 33.5 | 25 | -8.5 | 134% | 25 | 25 | 100% | 25 | -8.5 | 33.5 | 33.5 | 66% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 900.9100. - Job Related Equipment Repairs | 5 | 1 | -4 | 500% | 1 | 1 | 100% | 1 | -4 | 5 | 5 | -300% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 100.1702. - FS People Superintendent | 6.5 | 20 | 13.5 | 32.5% | 20 | 20 | 100% | 20 | 13.5 | 6.5 | 6.5 | 167.5% |  | 2024-10-31
2402. - SLC Little Dell Dam Outlet Works | 200.7600. - MEQ Mechanical Equipment | 131.7 | 90 | -41.7 | 146.3% | 90 | 90 | 100% | 90 | -41.7 | 131.7 | 131.7 | 53.67% |  | 2024-10-31
2231. - UDOT Bangerter Hwy Aqueduct Protection | 110.1600. - TC Traffic Control | 9.75 | 225 | 215.25 | 4.333% | 0 | 225 | 0% | 225 | 215.25 | 225 | 224.75 | 100.1% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 100.1700. - FS Project Manager | 148.84 | 20 | -128.84 | 744.2% | 0 | 20 | 0% | 20 | -128.84 | 148.84 | 148.84 | -544.2% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 150.2750. - Unknown Phase | 21.75 | 10 | -11.75 | 217.5% | 0 | 10 | 0% | 10 | -11.75 | 21.75 | 31.75 | -117.5% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 200.2000. - Unknown Phase | 47.38 | 30 | -17.38 | 157.9% | 0 | 30 | 0% | 30 | -17.38 | 47.38 | 47.38 | 42.07% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 300.3000. - CNC Concrete Work | 5 | 875 | 870 | 0.5714% | 0 | 875 | 0% | 875 | 870 | 875 | 875 | 100% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 150.1230. - T Transporting | 43.18 | 100 | 56.82 | 43.18% | 0 | 100 | 0% | 100 | 56.82 | 100 | 93.18 | 106.8% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 900.9600. - Reallocate EQ/FOO costs to actual | 2.5 | 0 | -2.5 |  | 0 | 0 | 0% | 0 | -2.5 | 2.5 | 2.5 | 0% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 100.1600. - TC Traffic Control | 85.34 | 150 | 64.66 | 56.89% | 0 | 150 | 0% | 150 | 64.66 | 150 | 85.34 | 143.1% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 200.2030. - Unknown Phase | 4.5 | 30 | 25.5 | 15% | 0 | 30 | 0% | 30 | 25.5 | 30 | 4.5 | 185% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 300.7100. - IMP Interior Mech/Piping | 34.77 | 2482.51 | 2447.74 | 1.401% | 0 | 2482.51 | 0% | 2482.51 | 2447.74 | 2482.51 | 2484.77 | 99.91% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 200.7100. - IMP Interior Mech/Piping | 333.06 | 210 | -123.06 | 158.6% | 0 | 210 | 0% | 210 | -123.06 | 333.06 | 333.06 | 41.4% |  | 2026-04-30
2231. - UDOT Bangerter Hwy Aqueduct Protection | 900.9100. - Job Related Equipment Repairs | 8.83 | 1 | -7.83 | 883% | 0 | 1 | 0% | 1 | -7.83 | 8.83 | 8.83 | -683% |  | 2026-04-30
2515. - UWCD Steinaker Service Canal Gate Rahab | 150.1230. - T Transporting | 37.2 | 40 | 2.8 | 93% | 20 | 40 | 50% | 20 | -17.2 | 74.4 | 37.2 | 107% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1700. - FS Project Manager | 35.5 | 12.83 | -22.67 | 276.7% | 6.415 | 12.83 | 50% | 6.415 | -29.085 | 71 | 35.5 | -76.7% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 9.17 | 11.77 | 2.6 | 77.91% | 0 | 11.77 | 0% | 11.77 | 2.6 | 11.77 | 9.17 | 122.1% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1703. - FS Job Site Superintendent | 102.83 | 15.92 | -86.91 | 645.9% | 7.96 | 15.92 | 50% | 7.96 | -94.87 | 205.66 | 102.83 | -445.9% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 300.7600. - MEQ Mechanical Equipment | 186.21 | 60 | -126.21 | 310.3% | 0 | 60 | 0% | 60 | -126.21 | 186.21 | 186.21 | -110.3% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 200.7600. - MEQ Mechanical Equipment | 24.6 | 30 | 5.4 | 82% | 30 | 30 | 100% | 30 | 5.4 | 24.6 | 24.6 | 118% |  | 2026-04-15
2515. - UWCD Steinaker Service Canal Gate Rahab | 100.1702. - FS People Superintendent | 5 | 10.92 | 5.92 | 45.79% | 0 | 10.92 | 0% | 10.92 | 5.92 | 10.92 | 5 | 154.2% |  | 2026-04-15
2318. - CUWCD CWP Wellhouse 7 | 200.2080. - EXS Excavate Structure | 160.18 | 150 | -10.18 | 106.8% | 0 | 150 | 0% | 150 | -10.18 | 160.18 | 160.18 | 93.21% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 150.2750. - Unknown Phase | 351.1 | 500.21 | 149.11 | 70.19% | 489.54 | 500.21 | 99.9% | 499.6996 | 148.5996 | 351.4586 | 351.1 | 129.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 400.2010. - RG Grading (DO NOT USE) | 616.04 | 263.5 | -352.54 | 233.8% | 263.5 | 263.5 | 100% | 263.5 | -352.54 | 616.04 | 616.04 | -33.79% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2300. - Unknown Phase | 407.16 | 302.44 | -104.72 | 134.6% | 302.44 | 302.44 | 100% | 302.44 | -104.72 | 407.16 | 407.16 | 65.37% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1703. - FS Job Site Superintendent | 1160.46 | 622.24 | -538.22 | 186.5% | 421.4 | 622.239 | 98% | 609.7952 | -550.6648 | 1184.1429 | 1163.91 | 12.95% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2040. - LR Landscaping/Restoration | 88.01 | 44.92 | -43.09 | 195.9% | 40 | 44.92 | 100% | 44.92 | -43.09 | 88.01 | 88.01 | 4.074% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7300. - PLUM Plumbing | 154.69 | 150 | -4.69 | 103.1% | 150 | 150 | 100% | 150 | -4.69 | 154.69 | 154.69 | 96.87% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5120. - Fab Shop Pipe Linings & Coatings | 568.14 | 0 | -568.14 |  | 0 | 0 | 0% | 0 | -568.14 | 568.14 | 568.14 | 0% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9005. - Re-Work Surveying | 2 | 1 | -1 | 200% | 0 | 1 | 0% | 1 | -1 | 2 | 2 | 0% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.7100. - IMP Interior Mech/Piping | 348.29 | 200 | -148.29 | 174.1% | 196 | 200 | 98% | 196 | -152.29 | 355.398 | 348.29 | 25.86% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.6300. - DAW Doors & Windows | 51.08 | 60 | 8.92 | 85.13% | 60 | 60 | 100% | 60 | 8.92 | 51.08 | 51.08 | 114.9% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2610. - PT Pressure Test/Chlorinating | 83.17 | 140 | 56.83 | 59.41% | 140 | 140 | 100% | 140 | 56.83 | 83.17 | 83.17 | 140.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.6200. - IN Insulation | 96.25 | 16 | -80.25 | 601.6% | 15.84 | 16 | 99% | 15.84 | -80.41 | 97.2222 | 96.25 | -401.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.3000. - CNC Concrete Work | 795.68 | 930 | 134.32 | 85.56% | 930 | 930 | 100% | 930 | 134.32 | 795.68 | 795.68 | 114.4% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7500. - PUMP Pumps/Motors | 20.48 | 40 | 19.52 | 51.2% | 40 | 40 | 100% | 40 | 19.52 | 20.48 | 20.48 | 148.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7100. - IMP Interior Mech/Piping | 643.39 | 414 | -229.39 | 155.4% | 399 | 414 | 95% | 393.3 | -250.09 | 677.2526 | 643.39 | 44.59% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9012. - Re-Work Mechanical | 50.15 | 0.4 | -49.75 | 12538% | 0 | 0.4 | 0% | 0.4 | -49.75 | 50.15 | 50.15 | -12338% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.3000. - Unknown Phase | 638.24 | 561 | -77.24 | 113.8% | 32500 | 561 | 91.42% | 512.8762 | -125.3638 | 698.1269 | 638.24 | 86.23% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.5100. - W Welding | 58.06 | 40 | -18.06 | 145.2% | 40 | 40 | 100% | 40 | -18.06 | 58.06 | 58.06 | 54.85% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5110. - Fab Shop Pipe Fabrication | 458.48 | 0 | -458.48 |  | 0 | 0 | 0% | 0 | -458.48 | 458.48 | 458.48 | 0% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.1600. - TC Traffic Control | 36.56 | 20 | -16.56 | 182.8% | 0 | 20 | 100% | 20 | -16.56 | 36.56 | 36.56 | 17.2% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 150.2760. - Unknown Phase | 136.93 | 609.14 | 472.21 | 22.48% | 578.683 | 609.14 | 95% | 578.683 | 441.753 | 144.1368 | 136.93 | 177.5% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2710. - FWF Flowable Fill | 41.35 | 3.56 | -37.79 | 1162% | 200 | 3.56 | 100% | 3.56 | -37.79 | 41.35 | 41.35 | -961.5% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 150.1230. - T Transporting | 81.58 | 152 | 70.42 | 53.67% | 144.4 | 152 | 95% | 144.4 | 62.82 | 85.8737 | 91.58 | 139.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 400.2000. - SWC Site Work Complete (DO NOT USE) | 441.48 | 195.29 | -246.19 | 226.1% | 195.29 | 195.29 | 100% | 195.29 | -246.19 | 441.48 | 441.48 | -26.06% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2030. - Unknown Phase | 4.5 | 15 | 10.5 | 30% | 15 | 15 | 100% | 15 | 10.5 | 4.5 | 4.5 | 170% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.7600. - MEQ Mechanical Equipment | 3.5 | 110 | 106.5 | 3.182% | 110 | 110 | 100% | 110 | 106.5 | 3.5 | 3.5 | 196.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.6400. - DRY Drywall & Metal Studs | 59.86 | 68 | 8.14 | 88.03% | 68 | 68 | 100% | 68 | 8.14 | 59.86 | 59.86 | 112% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9055. - Re-Work Finishes | 7.52 | 0.2 | -7.32 | 3760% | 0 | 0.2 | 0% | 0.2 | -7.32 | 7.52 | 7.52 | -3560% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 2.03 | 26.25 | 24.22 | 7.733% | 0 | 26.25 | 0% | 26.25 | 24.22 | 26.25 | 2.03 | 192.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.2800. - BFST Backfill (DO NOT USE) | 233.09 | 150 | -83.09 | 155.4% | 150 | 150 | 100% | 150 | -83.09 | 233.09 | 233.09 | 44.61% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5310. - Fab Shop Misc Metals Fabrication | 101.03 | 238.5 | 137.47 | 42.36% | 1 | 238.5 | 100% | 238.5 | 137.47 | 101.03 | 101.03 | 157.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 800.1940. - PL Punch List Work | 89.64 | 200 | 110.36 | 44.82% | 130 | 200 | 65% | 130 | 40.36 | 137.9077 | 108.79 | 145.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 50.28 | 87 | 36.72 | 57.79% | 87 | 87 | 100% | 87 | 36.72 | 50.28 | 50.28 | 142.2% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 400.3000. - CNC Concrete Work | 102.43 | 683.2 | 580.77 | 14.99% | 668.2 | 683.2 | 100% | 683.2 | 580.77 | 102.43 | 102.43 | 185% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9020. - Re-Work Fab | 28.6 | 0.2 | -28.4 | 14300% | 0 | 0.2 | 0% | 0.2 | -28.4 | 28.6 | 28.6 | -14100% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.5000. - MET Metals | 3 | 35 | 32 | 8.571% | 2000 | 35 | 100% | 35 | 32 | 3 | 3 | 191.4% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.6100. - F Framing | 48.83 | 20 | -28.83 | 244.2% | 20 | 20 | 100% | 20 | -28.83 | 48.83 | 48.83 | -44.15% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.7900. - ELC Electrical | 226.1 | 103.14 | -122.96 | 219.2% | 103.14 | 103.14 | 100% | 103.14 | -122.96 | 226.1 | 226.1 | -19.22% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 160.5320. - Fab Shop Misc Metals Coatings | 13.83 | 460 | 446.17 | 3.007% | 1 | 460 | 100% | 460 | 446.17 | 13.83 | 13.83 | 197% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 800.1930. - MC Misc Cleanup | 18.38 | 100 | 81.62 | 18.38% | 65 | 100 | 65% | 65 | 46.62 | 28.2769 | 34.38 | 165.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1650. - SB Signage | 2.5 | 15 | 12.5 | 16.67% | 15 | 15 | 100% | 15 | 12.5 | 2.5 | 2.5 | 183.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1702. - FS People Superintendent | 504.77 | 303.31 | -201.46 | 166.4% | 98 | 303.314 | 98% | 297.2438 | -207.5262 | 515.0714 | 510.27 | 31.77% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 500.2030. - D Demolition | 6.43 | 52 | 45.57 | 12.37% | 0 | 52 | 0% | 52 | 45.57 | 52 | 6.43 | 187.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 500.7900. - ELC Electrical | 159.33 | 253.99 | 94.66 | 62.73% | 0 | 253.99 | 51.66% | 131.2164 | -28.1136 | 308.4083 | 159.33 | 137.3% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1704. - FS Quality Control/Assurance | 485.25 | 60.8 | -424.45 | 798.1% | 320 | 60.798 | 100% | 60.8 | -424.45 | 485.25 | 495.25 | -614.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1510. - S Surveying | 246.56 | 100 | -146.56 | 246.6% | 100 | 100 | 100% | 100 | -146.56 | 246.56 | 246.56 | -46.56% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.5000. - MET Metals | 62.52 | 75 | 12.48 | 83.36% | 75 | 75 | 100% | 75 | 12.48 | 62.52 | 62.52 | 116.6% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 900.9100. - Job Related Equipment Repairs | 34.76 | 1 | -33.76 | 3476% | 0 | 1 | 0% | 1 | -33.76 | 34.76 | 34.76 | -3276% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 800.1700. - FS Project Manager | 40.94 | 400 | 359.06 | 10.23% | 400 | 400 | 100% | 400 | 359.06 | 40.94 | 40.94 | 189.8% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 300.2080. - EXS Excavate Structure | 474.47 | 250 | -224.47 | 189.8% | 250 | 250 | 100% | 250 | -224.47 | 474.47 | 474.47 | 10.21% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 702.26 | 295.8 | -406.46 | 237.4% | 279.8 | 295.8 | 100% | 295.8 | -406.46 | 702.26 | 702.26 | -37.41% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 499.03 | 387.63 | -111.4 | 128.7% | 686 | 387.634 | 98% | 379.8774 | -119.1526 | 509.2143 | 505.53 | 69.58% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 200.2800. - Unknown Phase | 355.72 | 165 | -190.72 | 215.6% | 9000 | 165 | 100% | 165 | -190.72 | 355.72 | 355.72 | -15.59% |  | 2025-12-31
2318. - CUWCD CWP Wellhouse 7 | 100.1700. - FS Project Manager | 670 | 417.54 | -252.46 | 160.5% | 292.04 | 417.537 | 98% | 409.1892 | -260.8108 | 683.6735 | 673 | 38.82% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.2030. - Unknown Phase | 20.64 | 10 | -10.64 | 206.4% | 10 | 10 | 100% | 10 | -10.64 | 20.64 | 20.64 | -6.4% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.7100. - IMP Interior Mech/Piping | 27.26 | 60 | 32.74 | 45.43% | 60 | 60 | 100% | 60 | 32.74 | 27.26 | 27.26 | 154.6% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.5100. - W Welding | 4 | 23 | 19 | 17.39% | 23 | 23 | 100% | 23 | 19 | 4 | 4 | 182.6% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 200.6500. - Unknown Phase | 5.5 | 60 | 54.5 | 9.167% | 60 | 60 | 100% | 60 | 54.5 | 5.5 | 5.5 | 190.8% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 800.1940. - PL Punch List Work | 32.57 | 15 | -17.57 | 217.1% | 15 | 15 | 100% | 15 | -17.57 | 32.57 | 32.57 | -17.13% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 22.25 | 4.45 | -17.8 | 500% | 0.445 | 4.45 | 10% | 0.445 | -21.805 | 222.5 | 22.25 | -300% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1700. - FS Project Manager | 10.5 | 4.79 | -5.71 | 219.2% | 0.479 | 4.79 | 10% | 0.479 | -10.021 | 105 | 10.5 | -19.21% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 100.1703. - FS Job Site Superintendent | 10.28 | 5.78 | -4.5 | 177.9% | 0.578 | 5.78 | 10% | 0.578 | -9.702 | 102.8 | 10.28 | 22.15% |  | 2025-12-31
2514. - CUWCD Stillwater Dam Pipework | 800.1930. - MC Misc Cleanup | 4.38 | 15 | 10.62 | 29.2% | 15 | 15 | 100% | 15 | 10.62 | 4.38 | 4.38 | 170.8% |  | 2025-12-31
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 150.1230. - T Transporting | 131.73 | 130 | -1.73 | 101.3% | 130 | 130 | 50% | 65 | -66.73 | 263.46 | 130 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.5100. - W Welding | 406.86 | 110 | -296.86 | 369.9% | 60 | 110 | 33.33% | 36.6667 | -370.1933 | 1220.58 | 60 | 145.5% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.3000. - CNC Concrete Work | 962.53 | 240 | -722.53 | 401.1% | 180 | 240 | 75% | 180 | -782.53 | 1283.3733 | 180 | 125% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 250.7100. - IMP Interior Mech/Piping | 12 | 540 | 528 | 2.222% | 540 | 540 | 61.36% | 331.3636 | 319.3636 | 19.5556 | 540 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 350.6200. - IN Insulation | 9 | 90 | 81 | 10% | 90 | 90 | 75% | 67.5 | 58.5 | 12 | 90 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 19.92 | 30 | 10.08 | 66.4% | 30 | 30 | 38.46% | 11.5385 | -8.3815 | 51.792 | 30 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 70.28 | 0 | -70.28 |  | 0 | 0 | 0% | 0 | -70.28 | 70.28 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1700. - FS Project Manager | 17.5 | 0 | -17.5 |  | 0 | 0 | 0% | 0 | -17.5 | 17.5 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 150.2750. - Unknown Phase | 26.24 | 10 | -16.24 | 262.4% | 10 | 10 | 50% | 5 | -21.24 | 52.48 | 10 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 200.3000. - Unknown Phase | 1677.59 | 1880 | 202.41 | 89.23% | 2200 | 1880 | 49.66% | 933.5909 | -743.9991 | 3378.2133 | 2200 | 82.98% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 350.5000. - MET Metals | 7.92 | 30 | 22.08 | 26.4% | 30 | 30 | 46.88% | 14.0625 | 6.1425 | 16.896 | 30 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1703. - FS Job Site Superintendent | 561.9 | 0 | -561.9 |  | 0 | 0 | 0% | 0 | -561.9 | 561.9 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.5000. - MET Metals | 64.22 | 90 | 25.78 | 71.36% | 90 | 90 | 46.88% | 42.1875 | -22.0325 | 137.0027 | 90 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 160.1230. - T Transporting | 47.63 | 50 | 2.37 | 95.26% | 0 | 50 | 0% | 50 | 2.37 | 50 | 0 | 200% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 160.5310. - Fab Shop Misc Metals Fabrication | 697.44 | 173 | -524.44 | 403.1% | 0 | 173 | 0% | 173 | -524.44 | 697.44 | 0 | 200% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 165.7100. - IMP Interior Mech/Piping | 160 | 133 | -27 | 120.3% | 0 | 133 | 0% | 133 | -27 | 160 | 0 | 200% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 160.5320. - Fab Shop Misc Metals Coatings | 47.43 | 156 | 108.57 | 30.4% | 0 | 156 | 0% | 156 | 108.57 | 156 | 0 | 200% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 200.7100. - IMP Interior Mech/Piping | 177.1 | 1263.3 | 1086.2 | 14.02% | 1410 | 1263.3 | 61.2% | 773.1766 | 596.0766 | 289.3652 | 1410 | 88.39% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 900.9100. - Job Related Equipment Repairs | 2 | 1 | -1 | 200% | 1 | 1 | 50% | 0.5 | -1.5 | 4 | 1 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 12 | 180 | 168 | 6.667% | 180 | 180 | 38.46% | 69.2308 | 57.2308 | 31.2 | 180 | 100% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1702. - FS People Superintendent | 138.6 | 0 | -138.6 |  | 0 | 0 | 0% | 0 | -138.6 | 138.6 | 0 | 0% |  | 2023-11-06
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 300.2080. - EXS Excavate Structure | 9.5 | 180 | 170.5 | 5.278% | 180 | 180 | 38.46% | 69.2308 | 59.7308 | 24.7 | 180 | 100% |  | 2023-11-06
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 903.36 | 1253 | 349.64 | 72.1% | 1253 | 1253 | 33.66% | 421.7053 | -481.6547 | 2684.1255 | 1253 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2800. - BFST Backfill (DO NOT USE) | 240.94 | 30 | -210.94 | 803.1% | 30 | 30 | 50% | 15 | -225.94 | 481.88 | 30 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 393.11 | 234 | -159.11 | 168% | 234 | 234 | 60% | 140.4 | -252.71 | 655.1833 | 234 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.6500. - P Painting | 221.2 | 240 | 18.8 | 92.17% | 240 | 240 | 66.67% | 160 | -61.2 | 331.8 | 240 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9020. - Re-Work Fab | 40.09 | 0.2 | -39.89 | 20045% | 0.2 | 0.2 | 33.33% | 0.066667 | -40.0233 | 120.27 | 0.2 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2600. - DW Dewatering | 14.5 | 500 | 485.5 | 2.9% | 500 | 500 | 47.06% | 235.2941 | 220.7941 | 30.8125 | 500 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.7100. - IMP Interior Mech/Piping | 1152.45 | 210 | -942.45 | 548.8% | 210 | 210 | 60% | 126 | -1026.45 | 1920.75 | 210 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2750. - H Hauling | 2 | 7.28 | 5.28 | 27.47% | 7.28 | 7.28 | 50% | 3.64 | 1.64 | 4 | 7.28 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 410.2000. - SWC Site Work Complete (DO NOT USE) | 53.06 | 30 | -23.06 | 176.9% | 30 | 30 | 52.17% | 15.6522 | -37.4078 | 101.6983 | 30 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 600.5000. - MET Metals | 9.5 | 12 | 2.5 | 79.17% | 12 | 12 | 54.55% | 6.5455 | -2.9545 | 17.4167 | 12 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.5100. - W Welding | 1738.76 | 1030 | -708.76 | 168.8% | 1030 | 1030 | 32.89% | 338.7664 | -1399.9936 | 5286.6006 | 1030 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2750. - H Hauling | 81.11 | 79.37 | -1.74 | 102.2% | 79.37 | 79.37 | 50% | 39.685 | -41.425 | 162.22 | 79.37 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.5000. - MET Metals | 226.9 | 364 | 137.1 | 62.34% | 266 | 266 | 63.18% | 229.9857 | 3.0857 | 359.1162 | 266 | 126.9% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2080. - EXS Excavate Structure | 26.98 | 140 | 113.02 | 19.27% | 140 | 140 | 29.66% | 41.5254 | 14.5454 | 90.9611 | 140 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2750. - H Hauling | 6 | 974.53 | 968.53 | 0.6157% | 974.53 | 974.53 | 50% | 487.265 | 481.265 | 12 | 974.53 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.7100. - IMP Interior Mech/Piping | 1040.9 | 255 | -785.9 | 408.2% | 255 | 255 | 60% | 153 | -887.9 | 1734.8333 | 255 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.5100. - W Welding | 174.22 | 210 | 35.78 | 82.96% | 210 | 210 | 32.12% | 67.457 | -106.763 | 542.3635 | 210 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 310.2300. - WPL Water Pipe Laying (DO NOT USE) | 37.22 | 475 | 437.78 | 7.836% | 475 | 475 | 54.29% | 257.8571 | 220.6371 | 68.5632 | 475 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2030. - D Demolition | 99.86 | 125 | 25.14 | 79.89% | 125 | 125 | 51.02% | 63.7755 | -36.0845 | 195.7256 | 125 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.7900. - ELC Electrical | 17.07 | 20 | 2.93 | 85.35% | 20 | 20 | 44.44% | 8.8889 | -8.1811 | 38.4075 | 20 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2800. - BFST Backfill (DO NOT USE) | 559 | 300 | -259 | 186.3% | 300 | 300 | 48% | 144 | -415 | 1164.5833 | 300 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2030. - D Demolition | 361 | 380 | 19 | 95% | 380 | 380 | 39.5% | 150.104 | -210.896 | 913.9 | 380 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 320.2300. - WPL Water Pipe Laying (DO NOT USE) | 25 | 140 | 115 | 17.86% | 140 | 140 | 46.67% | 65.3333 | 40.3333 | 53.5714 | 140 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1510. - S Surveying | 781.83 | 500 | -281.83 | 156.4% | 500 | 500 | 33.33% | 166.6667 | -615.1633 | 2345.49 | 500 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2760. - HO Haul Off | 28.95 | 173 | 144.05 | 16.73% | 173 | 173 | 50% | 86.5 | 57.55 | 57.9 | 173 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.7900. - ELC Electrical | 1.5 | 20 | 18.5 | 7.5% | 20 | 20 | 44.44% | 8.8889 | 7.3889 | 3.375 | 20 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2800. - BFST Backfill (DO NOT USE) | 190.33 | 375 | 184.67 | 50.75% | 375 | 375 | 42.86% | 160.7143 | -29.6157 | 444.1033 | 375 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2800. - BFST Backfill (DO NOT USE) | 355.85 | 210 | -145.85 | 169.5% | 210 | 210 | 47.19% | 99.1011 | -256.7489 | 754.0631 | 210 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 160.5010. - Fab Shop Steel Materials | 927.64 | 0 | -927.64 |  | 0 | 0 | 466.7% | 0 | -927.64 | 198.78 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9100. - Job Related Equipment Repairs | 1.25 | 5 | 3.75 | 25% | 1 | 1 | 50% | 2.5 | 1.25 | 2.5 | 1 | 180% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.5000. - MET Metals | 6.7 | 75 | 68.3 | 8.933% | 75 | 75 | 60% | 45 | 38.3 | 11.1667 | 75 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.3000. - CNC Concrete Work | 1091.83 | 1090 | -1.83 | 100.2% | 1080 | 1080 | 67.92% | 740.3774 | -351.4526 | 1607.4164 | 1080 | 100.9% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2080. - EXS Excavate Structure | 16.37 | 10 | -6.37 | 163.7% | 10 | 10 | 50% | 5 | -11.37 | 32.74 | 10 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 250.2080. - EXS Excavate Structure | 349.79 | 600 | 250.21 | 58.3% | 600 | 600 | 17.65% | 105.8824 | -243.9076 | 1982.1433 | 600 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1702. - FS People Superintendent | 662.98 | 4 | -658.98 | 16574% | -13.63 | 0 | 0% | 4 | -658.98 | 662.98 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2030. - D Demolition | 10.03 | 40 | 29.97 | 25.07% | 30 | 30 | 50% | 20 | 9.97 | 20.06 | 30 | 125% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 37.5 | 40 | 2.5 | 93.75% | 40 | 40 | 33.33% | 13.3333 | -24.1667 | 112.5 | 40 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.3000. - CNC Concrete Work | 533.01 | 140 | -393.01 | 380.7% | 140 | 140 | 73.68% | 103.1579 | -429.8521 | 723.3707 | 140 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 410.2300. - WPL Water Pipe Laying (DO NOT USE) | 55.7 | 225 | 169.3 | 24.76% | 225 | 225 | 60% | 135 | 79.3 | 92.8333 | 225 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 180.1600. - TC Traffic Control | 381.35 | 0 | -381.35 |  | 0 | 0 | 0% | 0 | -381.35 | 381.35 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2760. - HO Haul Off | 50.53 | 110.67 | 60.14 | 45.66% | 110.67 | 110.67 | 50% | 55.335 | 4.805 | 101.06 | 110.67 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9010. - Re-Work Pipe | 170.75 | 2 | -168.75 | 8538% | 0.4 | 0.4 | 66.67% | 1.3333 | -169.4167 | 256.125 | 0.4 | 180% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.7100. - IMP Interior Mech/Piping | 137.48 | 20 | -117.48 | 687.4% | 20 | 20 | 66.67% | 13.3333 | -124.1467 | 206.22 | 20 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 210.2010. - RG Grading (DO NOT USE) | 486.05 | 515.86 | 29.81 | 94.22% | 0 | 0 | 0% | 515.86 | 29.81 | 515.86 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 800.1930. - MC Misc Cleanup | 283.22 | 450 | 166.78 | 62.94% | 450 | 450 | 54.55% | 245.4545 | -37.7655 | 519.2367 | 450 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2080. - EXS Excavate Structure | 209.43 | 295 | 85.57 | 70.99% | 295 | 295 | 22.15% | 65.3341 | -144.0959 | 945.6297 | 295 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2080. - EXS Excavate Structure | 156.84 | 190 | 33.16 | 82.55% | 175 | 175 | 19.42% | 36.9034 | -119.9366 | 807.5019 | 175 | 107.9% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.3000. - Unknown Phase | 281.94 | 496 | 214.06 | 56.84% | 440 | 440 | 66.67% | 330.6667 | 48.7267 | 422.91 | 440 | 111.3% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2000. - Unknown Phase | 11.8 | 250 | 238.2 | 4.72% | 250 | 250 | 50% | 125 | 113.2 | 23.6 | 250 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2610. - PT Pressure Test/Chlorinating | 393.64 | 20 | -373.64 | 1968% | 20 | 20 | 40% | 8 | -385.64 | 984.1 | 20 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2000. - SWC Site Work Complete (DO NOT USE) | 2 | 15 | 13 | 13.33% | 15 | 15 | 52.17% | 7.8261 | 5.8261 | 3.8333 | 15 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 210.2300. - WPL Water Pipe Laying (DO NOT USE) | 789.21 | 540 | -249.21 | 146.2% | 540 | 540 | 60% | 324 | -465.21 | 1315.35 | 540 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.1230. - T Transporting | 567.03 | 520 | -47.03 | 109% | 900 | 500 | 90% | 468 | -99.03 | 630.0333 | 500 | 103.8% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 900.9005. - Re-Work Surveying | 7 | 5 | -2 | 140% | 1 | 1 | 33.33% | 1.6667 | -5.3333 | 21 | 1 | 180% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 160.5120. - Fab Shop Pipe Linings & Coatings | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1700. - FS Project Manager | 515.73 | 18 | -497.73 | 2865% | -12.75 | 0 | 0% | 18 | -497.73 | 515.73 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 651.96 | 1202 | 550.04 | 54.24% | 1202 | 1202 | 34.02% | 408.8875 | -243.0725 | 1916.5563 | 1202 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.5100. - W Welding | 266.62 | 140 | -126.62 | 190.4% | 140 | 140 | 31.46% | 44.0449 | -222.5751 | 847.4707 | 140 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 800.1940. - PL Punch List Work | 728.15 | 310 | -418.15 | 234.9% | 290.72 | 300 | 60.48% | 187.488 | -540.662 | 1203.9517 | 300 | 103.2% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 1154.16 | 4 | -1150.16 | 28854% | 0 | 0 | 0% | 4 | -1150.16 | 1154.16 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 310.2000. - SWC Site Work Complete (DO NOT USE) | 7.18 | 30 | 22.82 | 23.93% | 30 | 30 | 52.17% | 15.6522 | 8.4722 | 13.7617 | 30 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.1600. - TC Traffic Control | 28.58 | 300 | 271.42 | 9.527% | 300 | 300 | 1.579% | 4.7368 | -23.8432 | 1810.0667 | 300 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 420.2000. - SWC Site Work Complete (DO NOT USE) | 25.42 | 90 | 64.58 | 28.24% | 90 | 90 | 52.17% | 46.9565 | 21.5365 | 48.7217 | 90 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2760. - HO Haul Off | 21.55 | 1104 | 1082.45 | 1.952% | 1104 | 1104 | 50% | 552 | 530.45 | 43.1 | 1104 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.2750. - Unknown Phase | 322.89 | -78.34 | -401.23 |  | 0 | 3 | 0% | -78.34 | -401.23 | 322.89 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2300. - Unknown Phase | 9177.36 | 4820.67 | -4356.69 | 190.4% | 4820.67 | 4820.67 | 37.72% | 1818.3612 | -7358.9988 | 24330.1633 | 4820.67 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 100.1703. - FS Job Site Superintendent | 1003.12 | 4 | -999.12 | 25078% | 0 | 0 | 0% | 4 | -999.12 | 1003.12 | 0 | 200% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.2760. - HO Haul Off | 9.4 | 12 | 2.6 | 78.33% | 12 | 12 | 50% | 6 | -3.4 | 18.8 | 12 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 97.28 | 80 | -17.28 | 121.6% | 80 | 80 | 66.67% | 53.3333 | -43.9467 | 145.92 | 80 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.6200. - IN Insulation | 3.28 | 50 | 46.72 | 6.56% | 50 | 50 | 66.67% | 33.3333 | 30.0533 | 4.92 | 50 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2050. - RW Retaining Walls | 493.59 | 100 | -393.59 | 493.6% | 100 | 100 | 51.5% | 51.5 | -442.09 | 958.4272 | 100 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 500.6500. - Unknown Phase | 120.26 | 50 | -70.26 | 240.5% | 50 | 50 | 66.67% | 33.3333 | -86.9267 | 180.39 | 50 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 420.2300. - WPL Water Pipe Laying (DO NOT USE) | 84.04 | 240 | 155.96 | 35.02% | 240 | 240 | 47.06% | 112.9412 | 28.9012 | 178.585 | 240 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.2750. - H Hauling | 4.5 | 94.3 | 89.8 | 4.772% | 94.3 | 94.3 | 50% | 47.15 | 42.65 | 9 | 94.3 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 150.5010. - FAB Shop Steel Materials (DO NOT USE) | 159.22 | 0 | -159.22 |  | 0 | 0 | 0% | 0 | -159.22 | 159.22 | 0 | 0% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2010. - RG Grading (DO NOT USE) | 339.28 | 319.99 | -19.29 | 106% | 319.99 | 319.99 | 42.1% | 134.7302 | -204.5498 | 805.8046 | 319.99 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2610. - PT Pressure Test/Chlorinating | 79.43 | 30 | -49.43 | 264.8% | 30 | 30 | 40% | 12 | -67.43 | 198.575 | 30 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.6500. - P Painting | 298.12 | 240 | -58.12 | 124.2% | 240 | 240 | 66.67% | 160 | -138.12 | 447.18 | 240 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 200.2610. - PT Pressure Test/Chlorinating | 542.56 | 200 | -342.56 | 271.3% | 200 | 200 | 40% | 80 | -462.56 | 1356.4 | 200 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 320.2000. - SWC Site Work Complete (DO NOT USE) | 46.57 | 60 | 13.43 | 77.62% | 60 | 60 | 52.17% | 31.3043 | -15.2657 | 89.2592 | 60 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 410.3000. - CNC Concrete Work | 434.95 | 135 | -299.95 | 322.2% | 120 | 120 | 66.67% | 90 | -344.95 | 652.425 | 120 | 111.1% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 219.37 | 120 | -99.37 | 182.8% | 120 | 120 | 33.33% | 40 | -179.37 | 658.11 | 120 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2750. - H Hauling | 188.48 | 104.34 | -84.14 | 180.6% | 104.34 | 104.34 | 50% | 52.17 | -136.31 | 376.96 | 104.34 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.2060. - FE Fencing | 20.17 | 44.44 | 24.27 | 45.39% | 44.44 | 44.44 | 60.01% | 26.6664 | 6.4964 | 33.6136 | 44.44 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 400.5000. - MET Metals | 156.08 | 248 | 91.92 | 62.94% | 248 | 248 | 63.92% | 158.5155 | 2.4355 | 244.1897 | 248 | 100% |  | 2024-03-04
2311. - RLW/Clyde UDOT 4700 South Aqueduct Relocate | 300.3000. - CNC Concrete Work | 2059.92 | 1195.39 | -864.53 | 172.3% | 1195.39 | 1195.39 | 68.26% | 815.9781 | -1243.9419 | 3017.7374 | 1195.39 | 100% |  | 2024-03-04
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.3000. - CNC Concrete Work | 116.21 | 80 | -36.21 | 145.3% | 0 | 80 | 0% | 80 | -36.21 | 116.21 | 80 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.2800. - Unknown Phase | 31 | 60 | 29 | 51.67% | 0 | 60 | 0% | 60 | 29 | 60 | 60 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 350.5100. - W Welding | 22 | 60 | 38 | 36.67% | 0 | 60 | 0% | 60 | 38 | 60 | 60 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2610. - PT Pressure Test/Chlorinating | 16.33 | 5.54 | -10.79 | 294.8% | 0 | 10 | 0% | 5.54 | -10.79 | 16.33 | 10 | 19.49% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 69.27 | 50 | -19.27 | 138.5% | 0 | 50 | 0% | 50 | -19.27 | 69.27 | 50 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.2610. - PT Pressure Test/Chlorinating | 174.08 | 24.84 | -149.24 | 700.8% | 0 | 20 | 0% | 24.84 | -149.24 | 174.08 | 20 | 119.5% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1700. - FS Project Manager | 23 | 0 | -23 |  | 0 | 0 | 0% | 0 | -23 | 23 | 0 | 0% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1510. - S Surveying | 34.93 | 20 | -14.93 | 174.7% | 0 | 20 | 0% | 20 | -14.93 | 34.93 | 20 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.2910. - MP Milling/Pulverize | 27.93 | 3.85 | -24.08 | 725.5% | 0 | 3.1 | 0% | 3.85 | -24.08 | 27.93 | 3.1 | 119.5% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 600.2930. - AP Asphalt Prep (DO NOT USE) | 104.48 | 77.08 | -27.4 | 135.5% | 0 | 114.16 | 0% | 77.08 | -27.4 | 104.48 | 114.16 | 51.89% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 800.1930. - MC Misc Cleanup | 75.64 | 300 | 224.36 | 25.21% | 0 | 300 | 0% | 300 | 224.36 | 300 | 300 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 800.1940. - PL Punch List Work | 10.35 | 200 | 189.65 | 5.175% | 0 | 200 | 0% | 200 | 189.65 | 200 | 200 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 339.96 | 185.84 | -154.12 | 182.9% | 0 | 287 | 0% | 185.84 | -154.12 | 339.96 | 287 | 45.57% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1702. - FS People Superintendent | 27 | 0 | -27 |  | 0 | 0 | 0% | 0 | -27 | 27 | 0 | 0% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 150.1230. - T Transporting | 103.73 | 150 | 46.27 | 69.15% | 0 | 150 | 0% | 150 | 46.27 | 150 | 150 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 350.2300. - WPL Water Pipe Laying (DO NOT USE) | 113.22 | 282 | 168.78 | 40.15% | 0 | 282 | 0% | 282 | 168.78 | 282 | 282 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.1600. - TC Traffic Control | 207.43 | 185 | -22.43 | 112.1% | 0 | 185 | 0% | 185 | -22.43 | 207.43 | 185 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2030. - D Demolition | 7.48 | 33.24 | 25.76 | 22.5% | 0 | 60 | 0% | 33.24 | 25.76 | 33.24 | 60 | 19.49% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.2300. - Unknown Phase | 8 | 342.2 | 334.2 | 2.338% | 0 | 90 | 0% | 342.2 | 334.2 | 342.2 | 90 | 173.7% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 1311.93 | 395.67 | -916.26 | 331.6% | 0 | 336.75 | 0% | 395.67 | -916.26 | 1311.93 | 336.75 | 114.9% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 150.2750. - Unknown Phase | 43.91 | 343.73 | 299.82 | 12.77% | 0 | 187.09 | 0% | 343.73 | 299.82 | 343.73 | 187.09 | 145.6% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 200.2910. - MP Milling/Pulverize | 55.37 | 47 | -8.37 | 117.8% | 0 | 47 | 0% | 47 | -8.37 | 55.37 | 47 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 100.1703. - FS Job Site Superintendent | 177.4 | 0 | -177.4 |  | 0 | 0 | 0% | 0 | -177.4 | 177.4 | 0 | 0% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 150.2760. - Unknown Phase | 286.04 | 125.72 | -160.32 | 227.5% | 0 | 150 | 0% | 125.72 | -160.32 | 286.04 | 150 | 80.69% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 900.9015. - Re-Work Concrete | 4 | 1.2 | -2.8 | 333.3% | 0 | 0.4 | 0% | 1.2 | -2.8 | 4 | 0.4 | 166.7% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 350.3000. - CNC Concrete Work | 71.95 | 6 | -65.95 | 1199% | 0 | 6 | 0% | 6 | -65.95 | 71.95 | 6 | 100% |  | 2023-09-29
2306. - JVWCD 3300 South Pipeline Phase II Sch A | 400.2910. - MP Milling/Pulverize | 9.75 | 9.58 | -0.17 | 101.8% | 0 | 14.76 | 0% | 9.58 | -0.17 | 9.75 | 14.76 | 45.93% |  | 2023-09-29
2409. - JVWCD 2024 Vault Improvement Project | 500.7100. - IMP Interior Mech/Piping | 606.62 | 507 | -99.62 | 119.6% | 405.6 | 507 | 80% | 405.6 | -201.02 | 758.275 | 599.47 | 81.76% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1230. - T Transporting | 12.77 | 30 | 17.23 | 42.57% | 30 | 30 | 100% | 30 | 17.23 | 12.77 | 12.77 | 157.4% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1702. - FS People Superintendent | 210.89 | 139.74 | -71.15 | 150.9% | 0.66 | 138.74 | 40.5% | 56.5947 | -154.2953 | 520.716 | 228.39 | 36.56% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2760. - HO Haul Off | 2 | 2.5 | 0.5 | 80% | 2.5 | 2.5 | 100% | 2.5 | 0.5 | 2 | 2 | 120% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 180.2920. - SC Saw Cutting/Coring | 14 | 4 | -10 | 350% | 0 | 4 | 0% | 4 | -10 | 14 | 14 | -150% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2390. - WSP Welded Steel Pipe | 9.38 | 116.22 | 106.84 | 8.071% | 116.22 | 116.22 | 100% | 116.22 | 106.84 | 9.38 | 9.38 | 191.9% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.2030. - D Demolition | 43.97 | 225.38 | 181.41 | 19.51% | 241.587 | 268.43 | 90% | 202.842 | 158.872 | 48.8556 | 43.97 | 180.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.5000. - MET Metals | 4 | 30 | 26 | 13.33% | 30 | 30 | 100% | 30 | 26 | 4 | 4 | 186.7% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 900.9010. - Re-Work Pipe | 32.01 | 0.8 | -31.21 | 4001% | 0 | 0.4 | 0% | 0.8 | -31.21 | 32.01 | 25.41 | -2976% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2180. - CATH Cathodic Protection | 1 | 18 | 17 | 5.556% | 18 | 18 | 100% | 18 | 17 | 1 | 1 | 194.4% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.1200. - HOOK Hook Truck Dumpster Transporting | 24.37 | 2.5 | -21.87 | 974.8% | 2.25 | 2.5 | 90% | 2.25 | -22.12 | 27.0778 | 16 | -440% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.3000. - Unknown Phase | 12.52 | 50.12 | 37.6 | 24.98% | 50.12 | 50.12 | 100% | 50.12 | 37.6 | 12.52 | 12.52 | 175% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 900.9005. - Re-Work Surveying | 5.05 | 2 | -3.05 | 252.5% | 0 | 1 | 0% | 2 | -3.05 | 5.05 | 5.05 | -52.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1600. - TC Traffic Control | 143.91 | 40 | -103.91 | 359.8% | 32 | 40 | 80% | 32 | -111.91 | 179.8875 | 145.46 | -163.7% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2075. - FG Finish Grade | 35.5 | 20.32 | -15.18 | 174.7% | 20.32 | 20.32 | 97.22% | 19.7544 | -15.7456 | 36.5165 | 35.5 | 25.3% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1704. - FS Quality Control/Assurance | 52 | 28.45 | -23.55 | 182.8% | 0.66 | 27.45 | 40.5% | 11.5222 | -40.4778 | 128.3951 | 48 | 31.28% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.1600. - TC Traffic Control | 71.4 | 30 | -41.4 | 238% | 30 | 30 | 100% | 30 | -41.4 | 71.4 | 71.4 | -38% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2750. - H Hauling | 5 | 11.25 | 6.25 | 44.44% | 11.25 | 11.25 | 100% | 11.25 | 6.25 | 5 | 5 | 155.6% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.5000. - MET Metals | 24.37 | 38 | 13.63 | 64.13% | 30 | 38 | 100% | 38 | 13.63 | 24.37 | 24.37 | 135.9% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2610. - PT Pressure Test/Chlorinating | 1 | 10 | 9 | 10% | 10 | 10 | 100% | 10 | 9 | 1 | 1 | 190% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.1600. - TC Traffic Control | 91.62 | 0 | -91.62 |  | 0 | 0 | 0% | 0 | -91.62 | 91.62 | 111.12 | 0% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1230. - T Transporting | 37.47 | 30 | -7.47 | 124.9% | 24 | 30 | 80% | 24 | -13.47 | 46.8375 | 37.47 | 75.1% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1700. - FS Project Manager | 275.18 | 187.28 | -87.9 | 146.9% | 51.81 | 186.277 | 65.36% | 122.4034 | -152.7766 | 421.0318 | 291.43 | 44.39% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.3000. - CNC Concrete Work | 1 | 49.15 | 48.15 | 2.035% | 49.15 | 49.15 | 100% | 49.15 | 48.15 | 1 | 1 | 198% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.5000. - MET Metals | 52.16 | 64 | 11.84 | 81.5% | 60 | 64 | 100% | 64 | 11.84 | 52.16 | 52.16 | 118.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 771.76 | 192.05 | -579.71 | 401.9% | 0.66 | 191.048 | 40.5% | 77.7802 | -693.9797 | 1905.5802 | 779.59 | -205.9% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2750. - H Hauling | 13.23 | 21.6 | 8.37 | 61.25% | 21.42 | 21.42 | 100% | 21.6 | 8.37 | 13.23 | 13.23 | 138.8% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.5100. - W Welding | 22.8 | 10 | -12.8 | 228% | 9 | 10 | 90% | 9 | -13.8 | 25.3333 | 22.8 | -28% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2710. - FWF Flowable Fill | 2 | 10 | 8 | 20% | 10 | 10 | 100% | 10 | 8 | 2 | 2 | 180% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 100.1703. - FS Job Site Superintendent | 533.29 | 280.84 | -252.45 | 189.9% | 0.66 | 279.838 | 40.5% | 113.7402 | -419.5498 | 1316.7654 | 448.17 | 40.42% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.1230. - T Transporting | 140.56 | 60 | -80.56 | 234.3% | 54 | 60 | 90% | 54 | -86.56 | 156.1778 | 154.71 | -57.85% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.5100. - W Welding | 68.04 | 66.67 | -1.37 | 102.1% | 53.336 | 66.67 | 80% | 53.336 | -14.704 | 85.05 | 68.04 | 97.95% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2760. - HO Haul Off | 69.82 | 8.63 | -61.19 | 809% | 10.63 | 10.63 | 100% | 8.63 | -61.19 | 69.82 | 69.82 | -609% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2760. - HO Haul Off | 27.67 | 21 | -6.67 | 131.8% | 16.8 | 21 | 80% | 16.8 | -10.87 | 34.5875 | 27.67 | 68.24% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.5000. - MET Metals | 35.13 | 12 | -23.13 | 292.8% | 10.8 | 12 | 84.44% | 10.1333 | -24.9967 | 41.6013 | 35.33 | -94.42% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.5000. - MET Metals | 87.35 | 60 | -27.35 | 145.6% | 48 | 60 | 80% | 48 | -39.35 | 109.1875 | 87.03 | 54.95% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.3000. - CNC Concrete Work | 13.47 | 0 | -13.47 |  | 0 | 0 | 0% | 0 | -13.47 | 13.47 | 13.47 | 0% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2030. - D Demolition | 124.7 | 69.61 | -55.09 | 179.1% | 69.61 | 69.61 | 100% | 69.61 | -55.09 | 124.7 | 124.7 | 20.86% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.2760. - HO Haul Off | 36.46 | 8.88 | -27.58 | 410.6% | 8.88 | 8.88 | 100% | 8.88 | -27.58 | 36.46 | 36.46 | -210.6% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.7100. - IMP Interior Mech/Piping | 122.7 | 30 | -92.7 | 409% | 30 | 30 | 100% | 30 | -92.7 | 122.7 | 122.7 | -209% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 180.2910. - MP Milling/Pulverize | 30.37 | 15 | -15.37 | 202.5% | 0 | 15 | 0% | 15 | -15.37 | 30.37 | 30.37 | -2.467% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.7100. - IMP Interior Mech/Piping | 158.6 | 114 | -44.6 | 139.1% | 102.6 | 114 | 90% | 102.6 | -56 | 176.2222 | 158.6 | 60.88% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.1230. - T Transporting | 28.95 | 30 | 1.05 | 96.5% | 30 | 30 | 100% | 30 | 1.05 | 28.95 | 28.95 | 103.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 300.7100. - IMP Interior Mech/Piping | 261.7 | 30 | -231.7 | 872.3% | 30 | 30 | 100% | 30 | -231.7 | 261.7 | 261.7 | -672.3% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2030. - Unknown Phase | 171.99 | 112.58 | -59.41 | 152.8% | 71.58 | 71.58 | 100% | 112.58 | -59.41 | 171.99 | 171.99 | 47.23% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2390. - WSP Welded Steel Pipe | 13.68 | 111.5 | 97.82 | 12.27% | 111.5 | 111.5 | 100% | 111.5 | 97.82 | 13.68 | 13.68 | 187.7% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1930. - MC Misc Cleanup | 13.25 | 20 | 6.75 | 66.25% | 16 | 20 | 80% | 16 | 2.75 | 16.5625 | 23.25 | 83.75% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2030. - D Demolition | 96.81 | 45 | -51.81 | 215.1% | 45 | 45 | 100% | 45 | -51.81 | 96.81 | 96.81 | -15.13% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1600. - TC Traffic Control | 124.1 | 0 | -124.1 |  | 0 | 0 | 0% | 0 | -124.1 | 124.1 | 124.6 | 0% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.2120. - DIP Ductile Iron Pipe | 50.48 | -3 | -53.48 |  | 21.6 | 24 | 90% | -2.7 | -53.18 | 56.0889 | 50.48 | 1883% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.5100. - W Welding | 14.2 | 10 | -4.2 | 142% | 10 | 10 | 100% | 10 | -4.2 | 14.2 | 14.2 | 58% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1930. - MC Misc Cleanup | 10 | 20 | 10 | 50% | 20 | 20 | 100% | 20 | 10 | 10 | 10 | 150% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2075. - FG Finish Grade | 48.88 | 26.56 | -22.32 | 184% | 26.56 | 26.56 | 100% | 26.56 | -22.32 | 48.88 | 48.88 | 15.96% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2090. - MTL Materials | 56.28 | 30 | -26.28 | 187.6% | 0 | 30 | 0% | 30 | -26.28 | 56.28 | 32.74 | 90.87% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2030. - D Demolition | 161.09 | 210.69 | 49.6 | 76.46% | 189.621 | 210.69 | 90% | 189.621 | 28.531 | 178.9889 | 161.09 | 123.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.3000. - CNC Concrete Work | 191.01 | 221 | 29.99 | 86.43% | 60.35 | 221 | 59.46% | 131.4025 | -59.6075 | 321.2513 | 191.01 | 113.6% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2710. - FWF Flowable Fill | 23.54 | 6 | -17.54 | 392.3% | 6 | 6 | 100% | 6 | -17.54 | 23.54 | 23.54 | -192.3% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.1940. - PL Punch List Work | 20.86 | 30 | 9.14 | 69.53% | 30 | 30 | 100% | 30 | 9.14 | 20.86 | 20.86 | 130.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 500.2390. - WSP Welded Steel Pipe | 92.45 | 20 | -72.45 | 462.2% | 16 | 20 | 80% | 16 | -76.45 | 115.5625 | 92.45 | -262.2% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.1200. - HOOK Hook Truck Dumpster Transporting | 6.75 | 2.5 | -4.25 | 270% | 2 | 2.5 | 80% | 2 | -4.75 | 8.4375 | 6.75 | -70% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 600.2760. - HO Haul Off | 8.27 | 11 | 2.73 | 75.18% | 20.8 | 26 | 80% | 8.8 | 0.53 | 10.3375 | 8.27 | 124.8% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 900.9012. - Re-Work Mechanical | 30.19 | 0.8 | -29.39 | 3774% | 0 | 0.4 | 0% | 0.8 | -29.39 | 30.19 | 13.63 | -1504% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.2180. - CATH Cathodic Protection | 17.5 | 92.5 | 75 | 18.92% | 92.5 | 92.5 | 100% | 92.5 | 75 | 17.5 | 17.5 | 181.1% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 200.5100. - W Welding | 8.3 | 18.66 | 10.36 | 44.48% | 16.66 | 16.66 | 100% | 18.66 | 10.36 | 8.3 | 8.3 | 155.5% |  | 2026-04-01
2409. - JVWCD 2024 Vault Improvement Project | 400.2390. - WSP Welded Steel Pipe | 19.67 | 120.5 | 100.83 | 16.32% | 50.5 | 120.5 | 74.26% | 89.489 | 69.819 | 26.4863 | 19.67 | 183.7% |  | 2026-04-01
2302. - Payson Well #2 Reconstruction | 800.1700. - FS Project Manager | 2 | 40 | 38 | 5% | 40 | 40 | 50% | 20 | 18 | 4 | 40 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 900.9010. - Re-Work Pipe | 3 | 0.4 | -2.6 | 750% | 0.4 | 0.4 | 66.67% | 0.26667 | -2.7333 | 4.5 | 0.4 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 242.62 | 105 | -137.62 | 231.1% | 105 | 105 | 40.78% | 42.8155 | -199.8045 | 594.9967 | 105 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 357.14 | 0 | -357.14 |  | 0 | 0 | 0% | 0 | -357.14 | 357.14 | 0 | 0% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 900.9005. - Re-Work Surveying | 0.5 | 1 | 0.5 | 50% | 1 | 1 | 33.33% | 0.33333 | -0.16667 | 1.5 | 1 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.2080. - EXS Excavate Structure | 24 | 15 | -9 | 160% | 0 | 0 | 0% | 15 | -9 | 24 | 15 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.1230. - T Transporting | 21.17 | 75 | 53.83 | 28.23% | 75 | 75 | 50% | 37.5 | 16.33 | 42.34 | 75 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1703. - FS Job Site Superintendent | 394.85 | 42 | -352.85 | 940.1% | 0 | 42 | 0% | 42 | -352.85 | 394.85 | 0 | 200% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 200.2800. - Unknown Phase | 1.45 | 15 | 13.55 | 9.667% | 0 | 0 | 0% | 15 | 13.55 | 15 | 15 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.2750. - Unknown Phase | 96.34 | 29.11 | -67.23 | 331% | 29.11 | 29.11 | 50% | 14.555 | -81.785 | 192.68 | 29.11 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1700. - FS Project Manager | 275 | 24 | -251 | 1146% | 3 | 24 | 50% | 12 | -263 | 550 | 3 | 187.5% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 800.1930. - MC Misc Cleanup | 45.35 | 40 | -5.35 | 113.4% | 40 | 40 | 44.44% | 17.7778 | -27.5722 | 102.0375 | 40 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 400.2060. - FE Fencing | 15.47 | 30 | 14.53 | 51.57% | 30 | 30 | 50% | 15 | -0.47 | 30.94 | 30 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 200.2010. - RG Grading (DO NOT USE) | 112.84 | 51 | -61.84 | 221.3% | 0 | 0 | 0% | 51 | -61.84 | 112.84 | 51 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.3000. - CNC Concrete Work | 837.86 | 543 | -294.86 | 154.3% | 543 | 543 | 72.11% | 391.5657 | -446.2943 | 1161.8943 | 543 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.6500. - P Painting | 59.83 | 150 | 90.17 | 39.89% | 150 | 150 | 75% | 112.5 | 52.67 | 79.7733 | 150 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 800.1940. - PL Punch List Work | 82.25 | 60 | -22.25 | 137.1% | 60 | 60 | 44.44% | 26.6667 | -55.5833 | 185.0625 | 60 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.7100. - IMP Interior Mech/Piping | 397 | 233 | -164 | 170.4% | 233 | 233 | 62.24% | 145.0259 | -251.9741 | 637.8239 | 233 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 17.4 | 60 | 42.6 | 29% | 60 | 60 | 54.55% | 32.7273 | 15.3273 | 31.9 | 60 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 200.2030. - Unknown Phase | 23.44 | 84 | 60.56 | 27.9% | 0 | 0 | 0% | 84 | 60.56 | 84 | 84 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 150.2760. - Unknown Phase | 44.52 | 80 | 35.48 | 55.65% | 80 | 80 | 50% | 40 | -4.52 | 89.04 | 80 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1510. - S Surveying | 40.19 | 50 | 9.81 | 80.38% | 50 | 50 | 33.33% | 16.6667 | -23.5233 | 120.57 | 50 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.7500. - PUMP Pumps/Motors | 0.5 | 30 | 29.5 | 1.667% | 30 | 30 | 60% | 18 | 17.5 | 0.83333 | 30 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 500.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 83.67 | 211.2 | 127.53 | 39.62% | 211.2 | 211.2 | 54.55% | 115.2149 | 31.5449 | 153.3752 | 211.2 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.5000. - MET Metals | 10.5 | 37 | 26.5 | 28.38% | 37 | 37 | 60.66% | 22.4426 | 11.9426 | 17.3108 | 37 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 400.3000. - CNC Concrete Work | 39.78 | 66 | 26.22 | 60.27% | 66 | 66 | 67.35% | 44.449 | 4.669 | 59.0673 | 66 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.2010. - RG Grading (DO NOT USE) | 60.63 | 70 | 9.37 | 86.61% | 70 | 30 | 47.06% | 32.9412 | -27.6888 | 128.8388 | 70 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 900.9012. - Re-Work Mechanical | 16 | 0.4 | -15.6 | 4000% | 0.4 | 0.4 | 66.67% | 0.26667 | -15.7333 | 24 | 0.4 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 160.5310. - Fab Shop Misc Metals Fabrication | 12.28 | 40 | 27.72 | 30.7% | 40 | 40 | 50% | 20 | 7.72 | 24.56 | 40 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 100.1702. - FS People Superintendent | 119.57 | 0 | -119.57 |  | 0 | 0 | 0% | 0 | -119.57 | 119.57 | 0 | 0% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.7600. - MEQ Mechanical Equipment | 123.12 | 120 | -3.12 | 102.6% | 120 | 120 | 60% | 72 | -51.12 | 205.2 | 120 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.6300. - DAW Doors & Windows | 26.27 | 60 | 33.73 | 43.78% | 60 | 60 | 75% | 45 | 18.73 | 35.0267 | 60 | 100% |  | 2024-03-15
2302. - Payson Well #2 Reconstruction | 300.2800. - BFST Backfill (DO NOT USE) | 6.98 | 60 | 53.02 | 11.63% | 0 | 0 | 0% | 60 | 53.02 | 60 | 60 | 100% |  | 2024-03-15
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1700. - FS Project Manager | 48.87 | 50 | 1.13 | 97.74% | 0 | 50 | 0% | 50 | 1.13 | 50 | 130 | -60% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.2930. - AP Asphalt Prep (DO NOT USE) | 30.85 | 30 | -0.85 | 102.8% | 0 | 30 | 0% | 30 | -0.85 | 30.85 | 30 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.6500. - P Painting | 746.36 | 405 | -341.36 | 184.3% | 1 | 405 | 0.5556% | 2.25 | -744.11 | 134344.8 | 405 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 800.1930. - MC Misc Cleanup | 38.28 | 100 | 61.72 | 38.28% | 0 | 100 | 0% | 100 | 61.72 | 100 | 100 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 310.3000. - CNC Concrete Work | 248.51 | 0 | -248.51 |  | 0 | 0 | 0% | 0 | -248.51 | 248.51 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 8 | 0 | -8 |  | 0 | 0 | 0% | 0 | -8 | 8 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1703. - FS Job Site Superintendent | 42.24 | 0 | -42.24 |  | 0 | 0 | 0% | 0 | -42.24 | 42.24 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2030. - Unknown Phase | 33.41 | 27 | -6.41 | 123.7% | 0 | 27 | 0% | 27 | -6.41 | 33.41 | 27.41 | 98.48% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1220. - TD Tempoary Toilets for Job Site | 31.02 | 0 | -31.02 |  | 0 | 0 | 0% | 0 | -31.02 | 31.02 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2080. - EXS Excavate Structure | 148.09 | 328 | 179.91 | 45.15% | 0 | 328 | 0% | 328 | 179.91 | 328 | 98 | 170.1% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.3000. - Unknown Phase | 239.85 | 433 | 193.15 | 55.39% | 0 | 433 | 0% | 433 | 193.15 | 433 | 383 | 111.5% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 150.2760. - Unknown Phase | 131.87 | 108 | -23.87 | 122.1% | 0 | 108 | 0% | 108 | -23.87 | 131.87 | 50 | 153.7% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 150.1230. - T Transporting | 158.61 | 150 | -8.61 | 105.7% | 0 | 150 | 0% | 150 | -8.61 | 158.61 | 300 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2000. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.7900. - ELC Electrical | 367.89 | 150 | -217.89 | 245.3% | 0 | 150 | 0% | 150 | -217.89 | 367.89 | 150 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 310.2400. - IPL Irrigation Pipe Laying (DO NOT USE) | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 150.2750. - Unknown Phase | 218.8 | 104.5 | -114.3 | 209.4% | 0 | 104.5 | 0% | 104.5 | -114.3 | 218.8 | 40.5 | 161.2% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.3000. - CNC Concrete Work | 511.51 | 303 | -208.51 | 168.8% | 0 | 303 | 0% | 303 | -208.51 | 511.51 | 243 | 119.8% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.3000. - CNC Concrete Work | 607.36 | 285 | -322.36 | 213.1% | 0 | 285 | 0% | 285 | -322.36 | 607.36 | 240 | 115.8% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.2800. - BFST Backfill (DO NOT USE) | 259.96 | 60 | -199.96 | 433.3% | 0 | 60 | 0% | 60 | -199.96 | 259.96 | 60 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.7600. - MEQ Mechanical Equipment | 4.23 | 28 | 23.77 | 15.11% | 0 | 28 | 0% | 28 | 23.77 | 28 | 28 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.2000. - SWC Site Work Complete (DO NOT USE) | 354.7 | 80 | -274.7 | 443.4% | 0 | 80 | 0% | 80 | -274.7 | 354.7 | 80 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 210.2000. - SWC Site Work Complete (DO NOT USE) | 183.08 | 236 | 52.92 | 77.58% | 0 | 236 | 0% | 236 | 52.92 | 236 | 0 | 200% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 160.5310. - Fab Shop Misc Metals Fabrication | 140.63 | 0 | -140.63 |  | 0 | 0 | 0% | 0 | -140.63 | 140.63 | 118.67 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.7400. - HVAC HVAC | 3.5 | 15 | 11.5 | 23.33% | 0 | 15 | 0% | 15 | 11.5 | 15 | 15 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 400.5100. - W Welding | 3 | 10 | 7 | 30% | 0 | 10 | 0% | 10 | 7 | 10 | 10 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2020. - Unknown Phase | 80.5 | 30 | -50.5 | 268.3% | 1 | 30 | 3.333% | 1 | -79.5 | 2415 | 30 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.5000. - MET Metals | 11 | 15 | 4 | 73.33% | 0 | 15 | 0% | 15 | 4 | 15 | 15 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1510. - S Surveying | 47.5 | 55 | 7.5 | 86.36% | 0 | 55 | 0% | 55 | 7.5 | 55 | 50 | 109.1% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2800. - Unknown Phase | 209.37 | 30 | -179.37 | 697.9% | 0 | 30 | 0% | 30 | -179.37 | 209.37 | 30 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 100.1702. - FS People Superintendent | 117.78 | 0 | -117.78 |  | 0 | 0 | 0% | 0 | -117.78 | 117.78 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.6900. - EF Roofing | 37.08 | 0 | -37.08 |  | 0 | 0 | 0% | 0 | -37.08 | 37.08 | 0 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.5000. - MET Metals | 11 | 0 | -11 |  | 0 | 0 | 0% | 0 | -11 | 11 | 705 | 0% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 300.6300. - DAW Doors & Windows | 157.36 | 128 | -29.36 | 122.9% | 0 | 128 | 0% | 128 | -29.36 | 157.36 | 128 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 570.33 | 330 | -240.33 | 172.8% | 0 | 330 | 0% | 330 | -240.33 | 570.33 | 330 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 800.1940. - PL Punch List Work | 243.9 | 120 | -123.9 | 203.3% | 1 | 120 | 0.7407% | 0.88889 | -243.0111 | 32926.5 | 120 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 161.3000. - CNC Concrete Work | 43.67 | 160 | 116.33 | 27.29% | 0 | 160 | 0% | 160 | 116.33 | 160 | 160 | 100% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2060. - Unknown Phase | 10.5 | 40 | 29.5 | 26.25% | 0 | 40 | 0% | 40 | 29.5 | 40 | 20 | 150% |  | 2023-06-30
2227. - PRWUA Deer Creek O&M Building Expansion | 200.2070. - RGC Rough Grade Cut | 13.68 | 30 | 16.32 | 45.6% | 0 | 30 | 0% | 30 | 16.32 | 30 | 30 | 100% |  | 2023-06-30
2314. - JVWCD AC Mitigation Project | 800.1940. - PL Punch List Work | 46.44 | 150 | 103.56 | 30.96% | 0 | 150 | 0% | 150 | 103.56 | 150 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2930. - AP Asphalt Prep (DO NOT USE) | 27.09 | 120 | 92.91 | 22.57% | 0 | 120 | 0% | 120 | 92.91 | 120 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 100.1702. - FS People Superintendent | 52.67 | 0 | -52.67 |  | 0 | 0 | 0% | 0 | -52.67 | 52.67 | 0 | 0% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 180.2920. - SC Saw Cutting/Coring | 0.62 | 0 | -0.62 |  | 0 | 0 | 0% | 0 | -0.62 | 0.62 | 0 | 0% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 900.9010. - Re-Work Pipe | 3.45 | 0.4 | -3.05 | 862.5% | 0 | 0.4 | 0% | 0.4 | -3.05 | 3.45 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.1600. - TC Traffic Control | 955.59 | 310 | -645.59 | 308.3% | 0 | 300 | 0% | 310 | -645.59 | 955.59 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 900.9100. - Job Related Equipment Repairs | 2 | 1 | -1 | 200% | 0 | 1 | 0% | 1 | -1 | 2 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 900.9005. - Re-Work Surveying | 33.95 | 1 | -32.95 | 3395% | 0 | 1 | 0% | 1 | -32.95 | 33.95 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 100.1700. - FS Project Manager | 58.5 | 110 | 51.5 | 53.18% | 0 | 110 | 0% | 110 | 51.5 | 110 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 861.5 | 855 | -6.5 | 100.8% | 0 | 855 | 0% | 855 | -6.5 | 861.5 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2800. - Unknown Phase | 48.84 | 122 | 73.16 | 40.03% | 0 | 122 | 0% | 122 | 73.16 | 122 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 100.1703. - FS Job Site Superintendent | 192.85 | 2 | -190.85 | 9642% | 0 | 2 | 0% | 2 | -190.85 | 192.85 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.2080. - EXS Excavate Structure | 21.54 | 120 | 98.46 | 17.95% | 0 | 120 | 0% | 120 | 98.46 | 120 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 150.2760. - Unknown Phase | 18.5 | 58.5 | 40 | 31.62% | 0 | 58.5 | 0% | 58.5 | 40 | 58.5 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2080. - EXS Excavate Structure | 13.35 | 151 | 137.65 | 8.841% | 0 | 151 | 0% | 151 | 137.65 | 151 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 150.2750. - Unknown Phase | 14.59 | 34.68 | 20.09 | 42.07% | 0 | 34.68 | 0% | 34.68 | 20.09 | 34.68 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.2300. - Unknown Phase | 24.32 | 129 | 104.68 | 18.85% | 0 | 129 | 0% | 129 | 104.68 | 129 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 105.89 | 300 | 194.11 | 35.3% | 0 | 300 | 0% | 300 | 194.11 | 300 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 200.1600. - TC Traffic Control | 379.72 | 208 | -171.72 | 182.6% | 0 | 208 | 0% | 208 | -171.72 | 379.72 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 400.2930. - AP Asphalt Prep (DO NOT USE) | 38.81 | 300 | 261.19 | 12.94% | 0 | 300 | 0% | 300 | 261.19 | 300 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 150.1230. - T Transporting | 18.92 | 165 | 146.08 | 11.47% | 0 | 165 | 0% | 165 | 146.08 | 165 | 0 | 200% |  | 2024-05-31
2314. - JVWCD AC Mitigation Project | 300.2800. - BFST Backfill (DO NOT USE) | 106.8 | 0 | -106.8 |  | 0 | 0 | 0% | 0 | -106.8 | 106.8 | 0 | 0% |  | 2024-05-31
2305. - Highland Well #4 Improvements | 200.3000. - Unknown Phase | 1231.93 | 701.01 | -530.92 | 175.7% | 524 | 615.92 | 65.91% | 462.0494 | -769.8806 | 1869.0541 | 609.09 | 113.1% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2010. - RG Grading (DO NOT USE) | 7.97 | 277.62 | 269.65 | 2.871% | 123 | 125.62 | 33.88% | 94.0696 | 86.0996 | 23.5212 | 275 | 100.9% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.1510. - S Surveying | 134.01 | 60 | -74.01 | 223.3% | 60 | 60 | 33.33% | 20 | -114.01 | 402.03 | 60 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2610. - PT Pressure Test/Chlorinating | 75.29 | 20 | -55.29 | 376.4% | 20 | 20 | 54.05% | 10.8108 | -64.4792 | 139.2865 | 20 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9015. - Re-Work Concrete | 131.76 | 0 | -131.76 |  | 0 | 0 | 0% | 0 | -131.76 | 131.76 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.1700. - FS Project Manager | 4 | 60 | 56 | 6.667% | 60 | 60 | 50% | 30 | 26 | 8 | 60 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9012. - Re-Work Mechanical | 24.88 | 0 | -24.88 |  | 0 | 0 | 0% | 0 | -24.88 | 24.88 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 150.2750. - Unknown Phase | 53.75 | 32.66 | -21.09 | 164.6% | 51 | 55.27 | 60% | 19.596 | -34.154 | 89.5833 | 30.17 | 107.6% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 160.5110. - Fab Shop Pipe Fabrication | 21.43 | 10 | -11.43 | 214.3% | -10 | 10 | 0% | 10 | -11.43 | 21.43 | 0 | 200% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.6300. - DAW Doors & Windows | 127.07 | 96 | -31.07 | 132.4% | 96 | 96 | 75% | 72 | -55.07 | 169.4267 | 96 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2080. - EXS Excavate Structure | 23.58 | 69.42 | 45.84 | 33.97% | 60 | 69.42 | 50% | 34.71 | 11.13 | 47.16 | 60 | 113.6% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 331.74 | 0 | -331.74 |  | 0 | 0 | 0% | 0 | -331.74 | 331.74 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1700. - FS Project Manager | 286.68 | 0 | -286.68 |  | 0 | 0 | 0% | 0 | -286.68 | 286.68 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2300. - Unknown Phase | 384.56 | 451.5 | 66.94 | 85.17% | 1 | 254 | 0.3906% | 1.7637 | -382.7963 | 98447.36 | 198.5 | 156% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1703. - FS Job Site Superintendent | 411.14 | 0 | -411.14 |  | 0 | 0 | 0% | 0 | -411.14 | 411.14 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 150.2760. - Unknown Phase | 49.59 | 144.14 | 94.55 | 34.4% | 72 | 82.14 | 34.95% | 50.379 | 0.78903 | 141.8825 | 134 | 107% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.1600. - TC Traffic Control | 218.95 | 45 | -173.95 | 486.6% | 1 | 23.5 | 1.205% | 0.54217 | -218.4078 | 18172.85 | 22.5 | 150% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2900. - ASPH Asphalt | 19.28 | 15 | -4.28 | 128.5% | 1 | 1 | 7.143% | 1.0714 | -18.2086 | 269.92 | 15 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.3100. - CNC Rebar | 70.5 | 39 | -31.5 | 180.8% | 24 | 39 | 50% | 19.5 | -51 | 141 | 24 | 138.5% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9010. - Re-Work Pipe | 102.85 | 0 | -102.85 |  | 0 | 0 | 0% | 0 | -102.85 | 102.85 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 150.1230. - T Transporting | 66.06 | 75 | 8.94 | 88.08% | 75 | 75 | 50% | 37.5 | -28.56 | 132.12 | 75 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2110. - Unknown Phase | 6.5 | 16 | 9.5 | 40.62% | 16 | 16 | 50% | 8 | 1.5 | 13 | 16 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 100.1702. - FS People Superintendent | 189.9 | 0 | -189.9 |  | 0 | 0 | 0% | 0 | -189.9 | 189.9 | 0 | 0% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.6500. - Unknown Phase | 380.6 | 300 | -80.6 | 126.9% | 300 | 300 | 66.67% | 200 | -180.6 | 570.9 | 300 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2500. - MH Manholes (DO NOT USE) | 38.99 | 52 | 13.01 | 74.98% | 33 | 25 | 49.25% | 25.6119 | -13.3781 | 79.1615 | 60 | 84.62% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.5100. - W Welding | 57.46 | 18 | -39.46 | 319.2% | 18 | 18 | 69.23% | 12.4615 | -44.9985 | 82.9978 | 18 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.7100. - IMP Interior Mech/Piping | 275.08 | 362 | 86.92 | 75.99% | 327 | 362 | 62.29% | 225.4743 | -49.6057 | 441.6422 | 327 | 109.7% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 252.25 | 141.72 | -110.53 | 178% | 133 | 141.72 | 34.37% | 48.7048 | -203.5452 | 733.9906 | 133 | 106.2% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.7600. - MEQ Mechanical Equipment | 83.77 | 150 | 66.23 | 55.85% | 150 | 150 | 75% | 112.5 | 28.73 | 111.6933 | 150 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 800.1940. - PL Punch List Work | 26.09 | 120 | 93.91 | 21.74% | 120 | 120 | 44.44% | 53.3333 | 27.2433 | 58.7025 | 120 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.2020. - Unknown Phase | 21.32 | 40 | 18.68 | 53.3% | 21 | 21 | 25.93% | 10.3704 | -10.9496 | 82.2343 | 40 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.7400. - HVAC HVAC | 4.75 | 150 | 145.25 | 3.167% | 1 | 1 | 1.961% | 2.9412 | -1.8088 | 242.25 | 150 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 200.5000. - MET Metals | 12 | 45 | 33 | 26.67% | 45 | 45 | 69.23% | 31.1538 | 19.1538 | 17.3333 | 45 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 2.08 | -40 | -42.08 |  | 40 | -40 | 0% | -40 | -42.08 | 2.08 | 0 | 200% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 160.5310. - Fab Shop Misc Metals Fabrication | 11.97 | 6 | -5.97 | 199.5% | 6 | 6 | 50% | 3 | -8.97 | 23.94 | 6 | 100% |  | 2023-12-31
2305. - Highland Well #4 Improvements | 900.9055. - Re-Work Finishes | 13.1 | 0 | -13.1 |  | 0 | 0 | 0% | 0 | -13.1 | 13.1 | 0 | 0% |  | 2023-12-31
2303. - Provo River Trail 2230 N Improvements | 200.2070. - RGC Rough Grade Cut | 44.69 | 335.96 | 291.27 | 13.3% | 0 | 335.96 | 0% | 335.96 | 291.27 | 335.96 | 335.96 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2020. - Unknown Phase | 78.57 | 201.6 | 123.03 | 38.97% | 0 | 81.6 | 0% | 201.6 | 123.03 | 201.6 | 60 | 170.2% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 150.2760. - Unknown Phase | 125.44 | 783.33 | 657.89 | 16.01% | 0 | 783.33 | 0% | 783.33 | 657.89 | 783.33 | 772.33 | 101.4% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 900.9100. - Job Related Equipment Repairs | 56.96 | 1 | -55.96 | 5696% | 0 | 1 | 0% | 1 | -55.96 | 56.96 | 1 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2310. - WS Water Services (DO NOT USE) | 98.99 | 110 | 11.01 | 89.99% | 0 | 110 | 0% | 110 | 11.01 | 110 | 110 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2080. - EXS Excavate Structure | 8.25 | 20 | 11.75 | 41.25% | 0 | 20 | 0% | 20 | 11.75 | 20 | 20 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 900.9055. - Re-Work Finishes | 0 | 0.2 | 0.2 | 0% | 0 | 0.2 | 0% | 0.2 | 0.2 | 0.2 | 0.2 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1510. - S Surveying | 400.81 | 100 | -300.81 | 400.8% | 0 | 100 | 0% | 100 | -300.81 | 400.81 | 100 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 400.3000. - CNC Concrete Work | 577.24 | 33 | -544.24 | 1749% | 0 | 33 | 0% | 33 | -544.24 | 577.24 | 33 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 300.2010. - RG Grading (DO NOT USE) | 118.58 | 110.63 | -7.95 | 107.2% | 0 | 110.63 | 0% | 110.63 | -7.95 | 118.58 | 110.63 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1702. - FS People Superintendent | 22 | 0 | -22 |  | 0 | 0 | 0% | 0 | -22 | 22 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 400.1650. - SB Signage | 53.16 | 225 | 171.84 | 23.63% | 0 | 225 | 0% | 225 | 171.84 | 225 | 225 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2800. - Unknown Phase | 60.57 | 60 | -0.57 | 101% | 0 | 60 | 0% | 60 | -0.57 | 60.57 | 60 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1704. - FS Quality Control/Assurance | 7.42 | 0 | -7.42 |  | 0 | 0 | 0% | 0 | -7.42 | 7.42 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.1600. - TC Traffic Control | 902.44 | 255 | -647.44 | 353.9% | 0 | 255 | 0% | 255 | -647.44 | 902.44 | 0 | 200% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2030. - Unknown Phase | 13 | 1240.48 | 1227.48 | 1.048% | 0 | 0 | 0% | 1240.48 | 1227.48 | 1240.48 | 620.24 | 150% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 6 | 0 | -6 |  | 0 | 0 | 0% | 0 | -6 | 6 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2300. - Unknown Phase | 182.93 | 0 | -182.93 |  | 0 | 0 | 0% | 0 | -182.93 | 182.93 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 100.1703. - FS Job Site Superintendent | 121 | 0 | -121 |  | 0 | 0 | 0% | 0 | -121 | 121 | 0 | 0% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 150.2750. - Unknown Phase | 111.89 | 287.92 | 176.03 | 38.86% | 0 | 288.2 | 0% | 287.92 | 176.03 | 287.92 | 266.91 | 107.3% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 200.2000. - Unknown Phase | 875.22 | 866.16 | -9.06 | 101% | 0 | 116.16 | 0% | 866.16 | -9.06 | 875.22 | 375 | 156.7% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 300.6900. - EF Roofing | 11.5 | 60 | 48.5 | 19.17% | 0 | 60 | 0% | 60 | 48.5 | 60 | 60 | 100% |  | 2023-06-30
2303. - Provo River Trail 2230 N Improvements | 150.1230. - T Transporting | 31.84 | 100 | 68.16 | 31.84% | 0 | 100 | 0% | 100 | 68.16 | 100 | 100 | 100% |  | 2023-06-30
2503. - HVSSD Headworks Upgrade | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 362.38 | 154.17 | -208.21 | 235.1% | 54.6 | 154.17 | 91% | 140.2947 | -222.0853 | 398.2198 | 362.63 | -35.21% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 800.1940. - PL Punch List Work | 151.27 | 180 | 28.73 | 84.04% | 18 | 180 | 10% | 18 | -133.27 | 1512.7 | 162.28 | 109.8% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1700. - FS Project Manager | 513.25 | 173.26 | -339.99 | 296.2% | 126.4 | 173.26 | 79% | 136.8754 | -376.3746 | 649.6835 | 511.25 | -95.08% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1703. - FS Job Site Superintendent | 217.75 | 216.7 | -1.05 | 100.5% | 147.9 | 216.7 | 87% | 188.529 | -29.221 | 250.2874 | 218.25 | 99.28% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1510. - S Surveying | 32.31 | 40 | 7.69 | 80.77% | 20 | 40 | 100% | 40 | 7.69 | 32.31 | 32.31 | 119.2% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.5000. - MET Metals | 72.97 | 257 | 184.03 | 28.39% | 162.5 | 257 | 65% | 167.05 | 94.08 | 112.2615 | 95.5 | 162.8% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.7600. - MEQ Mechanical Equipment | 4 | 105 | 101 | 3.81% | 105 | 105 | 100% | 105 | 101 | 4 | 4 | 196.2% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1200. - HOOK Hook Truck Dumpster Transporting | 18 | 5 | -13 | 360% | 7 | 5 | 70% | 3.5 | -14.5 | 25.7143 | 18 | -160% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.2085. - BFST Backfill Structure | 190.13 | 20 | -170.13 | 950.7% | 20 | 20 | 100% | 20 | -170.13 | 190.13 | 190.13 | -750.6% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.3000. - Unknown Phase | 773.86 | 573.42 | -200.44 | 135% | 490 | 573.42 | 100% | 573.42 | -200.44 | 773.86 | 772.69 | 65.25% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1702. - FS People Superintendent | 128.23 | 144.42 | 16.19 | 88.79% | 108.75 | 144.42 | 87% | 125.6454 | -2.5846 | 147.3908 | 135.23 | 106.4% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 900.9015. - Re-Work Concrete | 41.01 | 0.6 | -40.41 | 6835% | 0 | 0.6 | 0% | 0.6 | -40.41 | 41.01 | 41.01 | -6635% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 150.2750. - Unknown Phase | 37.76 | 34.67 | -3.09 | 108.9% | 30 | 34.67 | 100% | 34.67 | -3.09 | 37.76 | 37.76 | 91.09% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 100.1706. - FS Executive | 2 | 1 | -1 | 200% | 2 | 1 | 100% | 1 | -1 | 2 | 2 | 0% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 150.1230. - T Transporting | 38.87 | 75 | 36.13 | 51.83% | 23.1 | 75 | 77% | 57.75 | 18.88 | 50.4805 | 38.87 | 148.2% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 300.7700. - SEQ Specialized Equipment | 989.41 | 300 | -689.41 | 329.8% | 425 | 300 | 85% | 255 | -734.41 | 1164.0118 | 989.41 | -129.8% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.2030. - Unknown Phase | 201.35 | 228 | 26.65 | 88.31% | 60 | 228 | 100% | 228 | 26.65 | 201.35 | 201.35 | 111.7% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 150.2760. - Unknown Phase | 6.98 | 5.12 | -1.86 | 136.3% | 10 | 5.12 | 100% | 5.12 | -1.86 | 6.98 | 6.98 | 63.67% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.7100. - IMP Interior Mech/Piping | 22.47 | 54 | 31.53 | 41.61% | 36 | 54 | 90% | 48.6 | 26.13 | 24.9667 | 22.47 | 158.4% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 200.2075. - FG Finish Grade | 41.26 | 56 | 14.74 | 73.68% | 40 | 56 | 100% | 56 | 14.74 | 41.26 | 41.26 | 126.3% |  | 2025-10-15
2503. - HVSSD Headworks Upgrade | 400.7700. - SEQ Specialized Equipment | 326.22 | 240 | -86.22 | 135.9% | 165 | 240 | 100% | 240 | -86.22 | 326.22 | 326.22 | 64.08% |  | 2025-10-15
2304. - Park City 9th & 10th Street Stairs & Waterline | 150.1230. - T Transporting | 79.02 | 100 | 20.98 | 79.02% | 0 | 100 | 0% | 100 | 20.98 | 100 | 100 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.1600. - TC Traffic Control | 552.45 | 60 | -492.45 | 920.8% | 0 | 60 | 0% | 60 | -492.45 | 552.45 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9005. - Re-Work Surveying | 9 | 1 | -8 | 900% | 0 | 1 | 0% | 1 | -8 | 9 | 1 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2010. - RG Grading (DO NOT USE) | 2104.5 | 120 | -1984.5 | 1754% | 0 | 120 | 0% | 120 | -1984.5 | 2104.5 | 120 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.3000. - Unknown Phase | 1751.25 | 1595 | -156.25 | 109.8% | 0 | 1595 | 0% | 1595 | -156.25 | 1751.25 | 1610 | 99.06% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2300. - Unknown Phase | 2163.6 | 825 | -1338.6 | 262.3% | 0 | 825 | 0.07299% | 0.60219 | -2162.9978 | 2964132 | 555 | 132.7% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1703. - FS Job Site Superintendent | 349.38 | 10 | -339.38 | 3494% | 0 | 10 | 0% | 10 | -339.38 | 349.38 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 150.2750. - Unknown Phase | 136.51 | 58.93 | -77.58 | 231.6% | 0 | 58.93 | 1.697% | 1 | -135.51 | 8044.5343 | 58.93 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9010. - Re-Work Pipe | 45.13 | 0.4 | -44.73 | 11282% | 0 | 0.4 | 0% | 0.4 | -44.73 | 45.13 | 0.4 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1700. - FS Project Manager | 78.42 | 15 | -63.42 | 522.8% | 0 | 15 | 0% | 15 | -63.42 | 78.42 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 150.2760. - Unknown Phase | 267.35 | 162.5 | -104.85 | 164.5% | 0 | 162.5 | 0% | 162.5 | -104.85 | 267.35 | 154 | 105.2% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2080. - EXS Excavate Structure | 449.53 | 690 | 240.47 | 65.15% | 0 | 690 | 0% | 690 | 240.47 | 690 | 690 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2040. - LR Landscaping/Restoration | 99.09 | 390 | 290.91 | 25.41% | 0 | 390 | 0% | 390 | 290.91 | 390 | 390 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9015. - Re-Work Concrete | 18.75 | 0.4 | -18.35 | 4688% | 0 | 0.4 | 0% | 0.4 | -18.35 | 18.75 | 0.4 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2610. - PT Pressure Test/Chlorinating | 137.79 | 60 | -77.79 | 229.7% | 0 | 60 | 0% | 60 | -77.79 | 137.79 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1520. - TEST Testing 3rd Party Soils/Concrete/Welding/Special | 174.72 | 50 | -124.72 | 349.4% | 0 | 0 | 0% | 50 | -124.72 | 174.72 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1702. - FS People Superintendent | 309.75 | 4 | -305.75 | 7744% | 0 | 4 | 0% | 4 | -305.75 | 309.75 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.6500. - Unknown Phase | 200.09 | 60 | -140.09 | 333.5% | 0 | 60 | 0% | 60 | -140.09 | 200.09 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9100. - Job Related Equipment Repairs | 39.84 | 1 | -38.84 | 3984% | 0 | 1 | 0% | 1 | -38.84 | 39.84 | 1 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.6900. - EF Roofing | 3709.6 | 1625 | -2084.6 | 228.3% | 0 | 1325 | 46.83% | 760.9756 | -2948.6244 | 7921.5417 | 1580 | 102.8% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9055. - Re-Work Finishes | 119.85 | 0.2 | -119.65 | 59925% | 0 | 0.2 | 0% | 0.2 | -119.65 | 119.85 | 0.2 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2070. - RGC Rough Grade Cut | 21.55 | 120 | 98.45 | 17.96% | 0 | 120 | 0% | 120 | 98.45 | 120 | 120 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 900.9020. - Re-Work Fab | 19.76 | 0.2 | -19.56 | 9880% | 0 | 0.2 | 0% | 0.2 | -19.56 | 19.76 | 0.2 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 800.1940. - PL Punch List Work | 283.06 | 60 | -223.06 | 471.8% | 0 | 60 | 0% | 60 | -223.06 | 283.06 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2020. - Unknown Phase | 304.53 | 120 | -184.53 | 253.8% | 0 | 120 | 0% | 120 | -184.53 | 304.53 | 120 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2310. - WS Water Services (DO NOT USE) | 514.62 | 60 | -454.62 | 857.7% | 0 | 60 | 0% | 60 | -454.62 | 514.62 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 160.5320. - Fab Shop Misc Metals Coatings | 454.17 | 420 | -34.17 | 108.1% | 0 | 420 | 0.4762% | 2 | -452.17 | 95375.7 | 420 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 160.5310. - Fab Shop Misc Metals Fabrication | 650.45 | 946.82 | 296.37 | 68.7% | 0 | 946.82 | 0.15% | 1.4199 | -649.0301 | 433733.069 | 946.82 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 8.55 | 6 | -2.55 | 142.5% | 0 | 6 | 0% | 6 | -2.55 | 8.55 | 0 | 200% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 800.1930. - MC Misc Cleanup | 318.01 | 60 | -258.01 | 530% | 0 | 60 | 0% | 60 | -258.01 | 318.01 | 60 | 100% |  | 2023-11-10
2304. - Park City 9th & 10th Street Stairs & Waterline | 200.2800. - Unknown Phase | 535.26 | 135 | -400.26 | 396.5% | 0 | 135 | 0% | 135 | -400.26 | 535.26 | 135 | 100% |  | 2023-11-10
2609. - JVWCD JA-1 Internal Buttstraps | 200.5100. - W Welding | 355.01 | 110 | -245.01 | 322.7% | 10 | 13 | 100% | 110 | -245.01 | 355.01 | 247.45 | -24.95% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1702. - FS People Superintendent | 15 | 6.88 | -8.12 | 218% | 6.88 | 6.88 | 100% | 6.88 | -8.12 | 15 | 30 | -236% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 200.7100. - IMP Interior Mech/Piping | 82.5 | 105 | 22.5 | 78.57% | 10 | 10 | 100% | 105 | 22.5 | 82.5 | 82.5 | 121.4% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1704. - FS Quality Control/Assurance | 20 | 3.27 | -16.73 | 611.6% | 3.27 | 3.27 | 100% | 3.27 | -16.73 | 20 | 19 | -381% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 800.1940. - PL Punch List Work | 2 | 25 | 23 | 8% | 1 | 1 | 100% | 25 | 23 | 2 | 5 | 180% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 200.3000. - Unknown Phase | 286.58 | 150 | -136.58 | 191.1% | 10 | 10 | 100% | 150 | -136.58 | 286.58 | 244.29 | 37.14% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 3 | 7.37 | 4.37 | 40.71% | 7.37 | 7.37 | 100% | 7.37 | 4.37 | 3 | 3 | 159.3% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 100.1703. - FS Job Site Superintendent | 24.23 | 9.86 | -14.37 | 245.7% | 9.86 | 9.86 | 100% | 9.86 | -14.37 | 24.23 | 33.23 | -137% |  | 2026-04-10
2609. - JVWCD JA-1 Internal Buttstraps | 150.1230. - T Transporting | 30.21 | 5 | -25.21 | 604.2% | 1 | 1 | 100% | 5 | -25.21 | 30.21 | 26.58 | -331.6% |  | 2026-04-10
2510. - Draper Pump Station #3 Improvements | 400.3000. - CNC Concrete Work | 12.75 | 136.5 | 123.75 | 9.341% | 0 | 136.5 | 0% | 136.5 | 123.75 | 136.5 | 149.25 | 90.66% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.9000. - Unknown Phase | 29.95 | 0 | -29.95 |  | 0 | 0 | 0% | 0 | -29.95 | 29.95 | 29.95 | 0% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1200. - HOOK Hook Truck Dumpster Transporting | 1.75 | 5 | 3.25 | 35% | 2.5 | 5 | 50% | 2.5 | 0.75 | 3.5 | 6.75 | 65% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.8000. - HP Helical Piers | 5 | 30 | 25 | 16.67% | 0 | 30 | 0% | 30 | 25 | 30 | 5 | 183.3% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1702. - FS People Superintendent | 99.5 | 149.49 | 49.99 | 66.56% | 74.245 | 149.49 | 50% | 74.745 | -24.755 | 199 | 129.5 | 113.4% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.2160. - WSP Welded Steel Pipe <15' Depth | 158.39 | 161.76 | 3.37 | 97.92% | 129.408 | 161.76 | 80% | 129.408 | -28.982 | 197.9875 | 198.39 | 77.36% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.2160. - WSP Welded Steel Pipe <15' Depth | 8.75 | 257.44 | 248.69 | 3.399% | 193.08 | 257.44 | 75% | 193.08 | 184.33 | 11.6667 | 48.75 | 181.1% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.7100. - IMP Interior Mech/Piping | 452.17 | 559.5 | 107.33 | 80.82% | 432.225 | 559.5 | 85% | 475.575 | 23.405 | 531.9647 | 652.17 | 83.44% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1704. - FS Quality Control/Assurance | 17 | 58.78 | 41.78 | 28.92% | 28.89 | 58.78 | 50% | 29.39 | 12.39 | 34 | 37 | 137.1% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1510. - S Surveying | 20.83 | 20 | -0.83 | 104.2% | 5 | 20 | 50% | 10 | -10.83 | 41.66 | 30.83 | 45.85% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 205 | 162.14 | -42.86 | 126.4% | 80.57 | 162.14 | 50% | 81.07 | -123.93 | 410 | 215 | 67.4% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.5100. - W Welding | 40.35 | 14.07 | -26.28 | 286.8% | 14.07 | 14.07 | 100% | 14.07 | -26.28 | 40.35 | 40.35 | -86.78% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1703. - FS Job Site Superintendent | 125 | 223.92 | 98.92 | 55.82% | 111.46 | 223.92 | 50% | 111.96 | -13.04 | 250 | 252 | 87.46% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.2080. - EXS Excavate Structure | 153.4 | 40.75 | -112.65 | 376.4% | 20.375 | 40.75 | 50% | 20.375 | -133.025 | 306.8 | 233.4 | -372.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 150.2750. - Unknown Phase | 15.66 | 30.66 | 15 | 51.08% | 15.33 | 30.66 | 50% | 15.33 | -0.33 | 31.32 | 30.66 | 100% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.2030. - Unknown Phase | 28.62 | 6 | -22.62 | 477% | 6 | 6 | 100% | 6 | -22.62 | 28.62 | 38.62 | -443.7% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 100.1700. - FS Project Manager | 279.32 | 183.01 | -96.31 | 152.6% | 88.505 | 183.01 | 50% | 91.505 | -187.815 | 558.64 | 299.32 | 36.45% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.2240. - PCS Precast Structures | 20.14 | 91.52 | 71.38 | 22.01% | 0 | 91.52 | 0% | 91.52 | 71.38 | 91.52 | 100.14 | 90.58% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.1800. - PH Potholing | 7.98 | 15 | 7.02 | 53.2% | 15 | 15 | 100% | 15 | 7.02 | 7.98 | 7.98 | 146.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.3000. - Unknown Phase | 94.26 | 178.56 | 84.3 | 52.79% | 178.56 | 178.56 | 100% | 178.56 | 84.3 | 94.26 | 134.26 | 124.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.7100. - IMP Interior Mech/Piping | 12.35 | 105 | 92.65 | 11.76% | 52.5 | 105 | 50% | 52.5 | 40.15 | 24.7 | 32.35 | 169.2% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 500.5000. - MET Metals | 41.07 | 0 | -41.07 |  | 0 | 1 | 0% | 0 | -41.07 | 41.07 | 41.07 | 0% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 150.1230. - T Transporting | 102.2 | 100 | -2.2 | 102.2% | 50 | 100 | 50% | 50 | -52.2 | 204.4 | 132.2 | 67.8% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 300.3000. - CNC Concrete Work | 263.44 | 121.5 | -141.94 | 216.8% | 60.75 | 121.5 | 50% | 60.75 | -202.69 | 526.88 | 283.44 | -33.28% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 400.2085. - BFST Backfill Structure | 31.46 | 3 | -28.46 | 1049% | 1.8 | 3 | 60% | 1.8 | -29.66 | 52.4333 | 71.46 | -2182% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 150.2760. - Unknown Phase | 17.44 | 8.95 | -8.49 | 194.9% | 0 | 8.95 | 0% | 8.95 | -8.49 | 17.44 | 27.44 | -106.6% |  | 2026-03-15
2510. - Draper Pump Station #3 Improvements | 200.1600. - TC Traffic Control | 49.05 | 60 | 10.95 | 81.75% | 36 | 60 | 60% | 36 | -13.05 | 81.75 | 75.05 | 74.92% |  | 2026-03-15
2450. - Fab Shop Jobs 2024 Projects | 408.5970. - FAB Fab Shop Misc. Metals Paint | 11.07 | 48 | 36.93 | 23.06% | 0 | 48 | 0% | 48 | 36.93 | 48 | 44.57 | 107.1%
2450. - Fab Shop Jobs 2024 Projects | 408.5960. - FAB Fab Shop Misc. Metals Fabrication | 293.3 | 1183 | 889.7 | 24.79% | 0 | 1183 | 0% | 1183 | 889.7 | 1183 | 888.29 | 124.9%
2450. - Fab Shop Jobs 2024 Projects | 407.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 330.77 | 210 | -120.77 | 157.5% | 0 | 210 | 0% | 210 | -120.77 | 330.77 | 315.19 | 49.91%
2450. - Fab Shop Jobs 2024 Projects | 403.5950. - FAB Fab Shop WSP Paint | 63.09 | 15 | -48.09 | 420.6% | 0 | 15 | 0% | 15 | -48.09 | 63.09 | 63.09 | -220.6%
2450. - Fab Shop Jobs 2024 Projects | 403.5960. - FAB Fab Shop Misc. Metals Fabrication | 23.85 | 0 | -23.85 |  | 0 | 0 | 0% | 0 | -23.85 | 23.85 | 23.85 | 0%
2450. - Fab Shop Jobs 2024 Projects | 404.5960. - FAB Fab Shop Misc. Metals Fabrication | 18 | 40 | 22 | 45% | 0 | 40 | 0% | 40 | 22 | 40 | 18 | 155%
2450. - Fab Shop Jobs 2024 Projects | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 2.13 | 10 | 7.87 | 21.3% | 0 | 10 | 0% | 10 | 7.87 | 10 | 2.13 | 178.7%
2450. - Fab Shop Jobs 2024 Projects | 408.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 362.25 | 853 | 490.75 | 42.47% | 0 | 853 | 0% | 853 | 490.75 | 853 | 392.25 | 154%
2450. - Fab Shop Jobs 2024 Projects | 409.5995. - FAB Fab Shop Change Orders | 82.04 | 0 | -82.04 |  | 0 | 0 | 0% | 0 | -82.04 | 82.04 | 85.04 | 0%
2450. - Fab Shop Jobs 2024 Projects | 409.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 253.92 | 58 | -195.92 | 437.8% | 0 | 58 | 0% | 58 | -195.92 | 253.92 | 253.92 | -237.8%
2450. - Fab Shop Jobs 2024 Projects | 404.5940. - FAB Fab Shop WSP Fabrication | 104.83 | 105 | 0.17 | 99.84% | 0 | 105 | 0% | 105 | 0.17 | 105 | 104.83 | 100.2%
2450. - Fab Shop Jobs 2024 Projects | 407.5960. - FAB Fab Shop Misc. Metals Fabrication | 436.5 | 769 | 332.5 | 56.76% | 0 | 769 | 0% | 769 | 332.5 | 769 | 436.5 | 143.2%
2450. - Fab Shop Jobs 2024 Projects | 100.5900. - FAB Fab Shop | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2450. - Fab Shop Jobs 2024 Projects | 403.5940. - FAB Fab Shop WSP Fabrication | 46.37 | 40 | -6.37 | 115.9% | 0 | 40 | 0% | 40 | -6.37 | 46.37 | 46.37 | 84.08%
2450. - Fab Shop Jobs 2024 Projects | 404.5995. - FAB Fab Shop Change Orders | 30.62 | 0 | -30.62 |  | 0 | 0 | 0% | 0 | -30.62 | 30.62 | 30.62 | 0%
2450. - Fab Shop Jobs 2024 Projects | 409.5960. - FAB Fab Shop Misc. Metals Fabrication | 373.11 | 355 | -18.11 | 105.1% | 0 | 355 | 0% | 355 | -18.11 | 373.11 | 373.11 | 94.9%
2450. - Fab Shop Jobs 2024 Projects | 403.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 72.12 | 0 | -72.12 |  | 0 | 0 | 0% | 0 | -72.12 | 72.12 | 72.12 | 0%
2450. - Fab Shop Jobs 2024 Projects | 406.5901. - FAB 2406 Management/Design/QC | 38 | 68 | 30 | 55.88% | 0 | 68 | 0% | 68 | 30 | 68 | 38 | 144.1%
2450. - Fab Shop Jobs 2024 Projects | 404.5970. - FAB Fab Shop Misc. Metals Paint | 2.97 | 15 | 12.03 | 19.8% | 0 | 15 | 0% | 15 | 12.03 | 15 | 2.97 | 180.2%
2450. - Fab Shop Jobs 2024 Projects | 404.5935. - FAB Fab Shop Deliveries | 4.5 | 20 | 15.5 | 22.5% | 0 | 20 | 0% | 20 | 15.5 | 20 | 4.5 | 177.5%
2450. - Fab Shop Jobs 2024 Projects | 220.2300. - WPL Water Pipe Laying (DO NOT USE) | 4 | 0 | -4 |  | 0 | 0 | 0% | 0 | -4 | 4 | 4 | 0%
2450. - Fab Shop Jobs 2024 Projects | 100.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
2450. - Fab Shop Jobs 2024 Projects | 406.5995. - FAB Fab Shop Change Orders | 15.62 | 0 | -15.62 |  | 0 | 0 | 0% | 0 | -15.62 | 15.62 | 15.62 | 0%
2450. - Fab Shop Jobs 2024 Projects | 407.5995. - FAB Fab Shop Change Orders | 226.12 | 0 | -226.12 |  | 0 | 0 | 0% | 0 | -226.12 | 226.12 | 71.8 | 0%
2450. - Fab Shop Jobs 2024 Projects | 408.5940. - FAB Fab Shop WSP Fabrication | 883.72 | 1335 | 451.28 | 66.2% | 0 | 1335 | 0% | 1335 | 451.28 | 1335 | 1031.3 | 122.7%
2450. - Fab Shop Jobs 2024 Projects | 406.5960. - FAB Fab Shop Misc. Metals Fabrication | 12.63 | 49 | 36.37 | 25.78% | 0 | 49 | 0% | 49 | 36.37 | 49 | 12.63 | 174.2%
2450. - Fab Shop Jobs 2024 Projects | 403.5970. - FAB Fab Shop Misc. Metals Paint | 2 | 6 | 4 | 33.33% | 0 | 6 | 0% | 6 | 4 | 6 | 2 | 166.7%
2450. - Fab Shop Jobs 2024 Projects | 407.5935. - FAB Fab Shop Deliveries | 5.3 | 60 | 54.7 | 8.833% | 0 | 60 | 0% | 60 | 54.7 | 60 | 5.3 | 191.2%
2450. - Fab Shop Jobs 2024 Projects | 404.5901. - FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 219.9 | 65 | -154.9 | 338.3% | 0 | 65 | 0% | 65 | -154.9 | 219.9 | 219.9 | -138.3%
2450. - Fab Shop Jobs 2024 Projects | 404.5950. - FAB Fab Shop WSP Paint | 109.69 | 360 | 250.31 | 30.47% | 0 | 360 | 0% | 360 | 250.31 | 360 | 109.69 | 169.5%
2450. - Fab Shop Jobs 2024 Projects | 409.5970. - FAB Fab Shop Misc. Metals Paint | 97.27 | 523 | 425.73 | 18.6% | 0 | 523 | 0% | 523 | 425.73 | 523 | 97.27 | 181.4%
2407. - So SLC Lift Station | 150.2760. - Unknown Phase | 228.47 | 229.15 | 0.68 | 99.7% | 484.938 | 229.15 | 90% | 206.235 | -22.235 | 253.8556 | 280.83 | 77.45% |  | 2026-03-31
2407. - So SLC Lift Station | 150.2750. - Unknown Phase | 213.61 | 175.6 | -38.01 | 121.6% | 119.594 | 175.6 | 65% | 114.1405 | -99.4695 | 328.6294 | 222.17 | 73.48% |  | 2026-03-31
2407. - So SLC Lift Station | 900.9010. - Re-Work Pipe | 30.8 | 0.6 | -30.2 | 5133% | 0 | 0.6 | 0% | 0.6 | -30.2 | 30.8 | 30.8 | -4933% |  | 2026-03-31
2407. - So SLC Lift Station | 700.2075. - FG Finish Grade | 171.16 | 105 | -66.16 | 163% | 0 | 180.6 | 0% | 105 | -66.16 | 171.16 | 180 | 28.57% |  | 2026-03-31
2407. - So SLC Lift Station | 600.3000. - CNC Concrete Work | 305.94 | 219.6 | -86.34 | 139.3% | 100.87 | 137.47 | 100% | 219.6 | -86.34 | 305.94 | 305.94 | 60.68% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1703. - FS Job Site Superintendent | 2104.63 | 1327 | -777.63 | 158.6% | 0.87 | 1327 | 87% | 1154.49 | -950.14 | 2419.1149 | 2674.56 | -1.549% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2065. - SFC SWPPP | 10.58 | 168.6 | 158.02 | 6.275% | 107.7 | 168 | 75% | 126.4497 | 115.8697 | 14.1067 | 30.58 | 181.9% |  | 2026-03-31
2407. - So SLC Lift Station | 500.5000. - MET Metals | 178.53 | 159.79 | -18.74 | 111.7% | 39.947 | 159.79 | 25% | 39.9471 | -138.5829 | 714.1278 | 232.53 | 54.48% |  | 2026-03-31
2407. - So SLC Lift Station | 100.9990. - OH Tools/Safety Allocation | 24.69 | 0 | -24.69 |  | 0 | 0 | 75% | 0 | -24.69 | 32.92 | 24.69 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 400.5000. - MET Metals | 162.99 | 603.29 | 440.3 | 27.02% | 249.914 | 603.29 | 64% | 386.1059 | 223.1159 | 254.6717 | 202.99 | 166.4% |  | 2026-03-31
2407. - So SLC Lift Station | 500.7600. - MEQ Mechanical Equipment | 39.49 | 150 | 110.51 | 26.33% | 0 | 150 | 0% | 150 | 110.51 | 150 | 39.49 | 173.7% |  | 2026-03-31
2407. - So SLC Lift Station | 400.7500. - PUMP Pumps/Motors | 269.13 | 125 | -144.13 | 215.3% | 147 | 125 | 100% | 125.0003 | -144.1297 | 269.1293 | 269.13 | -15.3% |  | 2026-03-31
2407. - So SLC Lift Station | 200.7100. - IMP Interior Mech/Piping | 253.88 | 756 | 502.12 | 33.58% | 187.5 | 756 | 25% | 189 | -64.88 | 1015.52 | 438.64 | 142% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2240. - PCS Precast Structures | 160.52 | 129.76 | -30.76 | 123.7% | 116.784 | 129.76 | 90% | 116.784 | -43.736 | 178.3556 | 250.52 | 6.936% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2140. - SVR Services | 218.48 | 75 | -143.48 | 291.3% | 41.25 | 75 | 55% | 41.25 | -177.23 | 397.2364 | 75 | 100% |  | 2026-03-31
2407. - So SLC Lift Station | 150.1230. - T Transporting | 264.62 | 460 | 195.38 | 57.53% | 140 | 460 | 70% | 322 | 57.38 | 378.0286 | 300.63 | 134.6% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2450. - Unknown Phase | 112.14 | 198.21 | 86.07 | 56.58% | 3 | 198.21 | 100% | 198.21 | 86.07 | 112.14 | 112.14 | 143.4% |  | 2026-03-31
2407. - So SLC Lift Station | 200.5400. - HAT Hatch/Skylights | 43.12 | 12 | -31.12 | 359.3% | 11.76 | 12 | 98% | 11.76 | -31.36 | 44 | 92.35 | -569.6% |  | 2026-03-31
2407. - So SLC Lift Station | 500.3000. - CNC Concrete Work | 22.12 | 0 | -22.12 |  | 0 | 2085.51 | 95% | 0 | -22.12 | 23.2842 | 22.12 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 300.7100. - IMP Interior Mech/Piping | 9.67 | 310 | 300.33 | 3.119% | 225 | 310 | 75% | 232.5 | 222.83 | 12.8933 | 9.67 | 196.9% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2080. - EXS Excavate Structure | 135.41 | 189 | 53.59 | 71.65% | 1038 | 1227 | 100% | 189 | 53.59 | 135.41 | 135.41 | 128.4% |  | 2026-03-31
2407. - So SLC Lift Station | 500.7700. - SEQ Specialized Equipment | 76.21 | 129 | 52.79 | 59.08% | 105.78 | 129 | 100% | 129 | 52.79 | 76.21 | 76.21 | 140.9% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1108. - TF Setup Staging Area Laydown Yard | 8.9 | 18 | 9.1 | 49.44% | 16.2 | 18 | 90% | 16.2 | 7.3 | 9.8889 | 8.9 | 150.6% |  | 2026-03-31
2407. - So SLC Lift Station | 400.6500. - P Painting | 1 | 39.9 | 38.9 | 2.506% | 422.475 | 39.9 | 25% | 9.975 | 8.975 | 4 | 1 | 197.5% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2030. - Unknown Phase | 305.67 | 321.42 | 15.75 | 95.1% | 321.42 | 321.42 | 100% | 321.42 | 15.75 | 305.67 | 320.67 | 100.2% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2085. - BFST Backfill Structure | 327.9 | 6 | -321.9 | 5465% | 264.306 | 6 | 97% | 5.82 | -322.08 | 338.0409 | 477.9 | -7765% |  | 2026-03-31
2407. - So SLC Lift Station | 200.5000. - MET Metals | 44.02 | 29 | -15.02 | 151.8% | 33.3 | 29 | 73.3% | 21.2575 | -22.7625 | 60.053 | 101.24 | -149.1% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1200. - HOOK Hook Truck Dumpster Transporting | 58.1 | 35 | -23.1 | 166% | 29.05 | 35 | 83% | 29.05 | -29.05 | 70 | 86.57 | -47.34% |  | 2026-03-31
2407. - So SLC Lift Station | 200.7900. - ELC Electrical | 396.25 | 100 | -296.25 | 396.2% | 80 | 100 | 80% | 80 | -316.25 | 495.3125 | 356.37 | -156.4% |  | 2026-03-31
2407. - So SLC Lift Station | 800.1940. - PL Punch List Work | 4 | 225 | 221 | 1.778% | 0 | 225 | 0% | 225 | 221 | 225 | 225 | 100% |  | 2026-03-31
2407. - So SLC Lift Station | 400.3000. - CNC Concrete Work | 68.2 | 200 | 131.8 | 34.1% | 4856.36 | 4856.36 | 95.25% | 190.5068 | 122.3068 | 71.5985 | 68.2 | 165.9% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1702. - FS People Superintendent | 197.09 | 675 | 477.91 | 29.2% | 0.75 | 675 | 75% | 506.25 | 309.16 | 262.7867 | 319.12 | 152.7% |  | 2026-03-31
2407. - So SLC Lift Station | 400.7100. - IMP Interior Mech/Piping | 826.77 | 1592.5 | 765.73 | 51.92% | 557.375 | 1592.5 | 35% | 557.3753 | -269.3947 | 2362.1987 | 789.87 | 150.4% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1501. - SM Safety Meetings | 6.25 | 15 | 8.75 | 41.67% | 3.75 | 15 | 75% | 11.25 | 5 | 8.3333 | 66.25 | -241.7% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2220. - ADS Pipe | 539.34 | 230.16 | -309.18 | 234.3% | 207.144 | 230.16 | 90% | 207.144 | -332.196 | 599.2667 | 629.34 | -73.44% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2081. - SHOR Shoring | 160.59 | 0 | -160.59 |  | 0 | 0 | 0% | 0 | -160.59 | 160.59 | 160.59 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2120. - DIP Ductile Iron Pipe | 635.2 | 626 | -9.2 | 101.5% | 500.8 | 626 | 80% | 500.8 | -134.4 | 794 | 636.29 | 98.36% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2130. - PVC Pipe | 60.94 | 130 | 69.06 | 46.88% | 117 | 130 | 90% | 117 | 56.06 | 67.7111 | 130.94 | 99.28% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1704. - FS Quality Control/Assurance | 10 | 129 | 119 | 7.752% | 0.4 | 129 | 40% | 51.6 | 41.6 | 25 | 100 | 122.5% |  | 2026-03-31
2407. - So SLC Lift Station | 400.6300. - DAW Doors & Windows | 22 | 87 | 65 | 25.29% | 0 | 87 | 0% | 87 | 65 | 87 | 60 | 131% |  | 2026-03-31
2407. - So SLC Lift Station | 200.6500. - Unknown Phase | 33.6 | 60 | 26.4 | 56% | 0 | 60 | 0% | 60 | 26.4 | 60 | 33.6 | 144% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1510. - S Surveying | 156.16 | 70 | -86.16 | 223.1% | 150 | 220 | 75% | 52.5 | -103.66 | 208.2133 | 212.29 | -103.3% |  | 2026-03-31
2407. - So SLC Lift Station | 800.1930. - MC Misc Cleanup | 45.7 | 300 | 254.3 | 15.23% | 30 | 300 | 10% | 30 | -15.7 | 457 | 315.58 | 94.81% |  | 2026-03-31
2407. - So SLC Lift Station | 200.3000. - Unknown Phase | 17.54 | 215 | 197.46 | 8.158% | 10.6 | 215 | 5% | 10.75 | -6.79 | 350.8 | 17.54 | 191.8% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2060. - Unknown Phase | 27.52 | 24 | -3.52 | 114.7% | 24 | 24 | 100% | 24 | -3.52 | 27.52 | 27.52 | 85.33% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2120. - DIP Ductile Iron Pipe | 46.48 | 235 | 188.52 | 19.78% | 201.48 | 235 | 92% | 216.2 | 169.72 | 50.5217 | 219 | 106.8% |  | 2026-03-31
2407. - So SLC Lift Station | 160.5000. - Unknown Phase | 120.11 | 0 | -120.11 |  | 0 | 0 | 30% | 0 | -120.11 | 400.3667 | 120.11 | 0% |  | 2026-03-31
2407. - So SLC Lift Station | 180.2081. - SHOR Shoring | 2 | 6 | 4 | 33.33% | 0 | 6 | 100% | 6 | 4 | 2 | 2 | 166.7% |  | 2026-03-31
2407. - So SLC Lift Station | 500.7100. - IMP Interior Mech/Piping | 103.72 | 142.5 | 38.78 | 72.79% | 49.875 | 142.5 | 35% | 49.875 | -53.845 | 296.3429 | 155.52 | 90.86% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 857.08 | 836 | -21.08 | 102.5% | 0.75 | 836 | 75% | 627 | -230.08 | 1142.7733 | 1142.69 | 63.31% |  | 2026-03-31
2407. - So SLC Lift Station | 300.2080. - EXS Excavate Structure | 61.43 | 165.88 | 104.45 | 37.03% | 132.704 | 165.88 | 79.7% | 132.2068 | 70.7768 | 77.0763 | 25 | 184.9% |  | 2026-03-31
2407. - So SLC Lift Station | 100.1700. - FS Project Manager | 1577.5 | 955 | -622.5 | 165.2% | 0.75 | 955 | 75% | 716.25 | -861.25 | 2103.3333 | 1862.5 | 4.974% |  | 2026-03-31
2407. - So SLC Lift Station | 700.3000. - CNC Concrete Work | 103.23 | 99.38 | -3.85 | 103.9% | 0 | 99.38 | 7.414% | 7.3684 | -95.8616 | 1392.2992 | 200 | -1.248% |  | 2026-03-31
2407. - So SLC Lift Station | 200.2600. - DW Dewatering | 155.64 | 50 | -105.64 | 311.3% | 45 | 50 | 90% | 45 | -110.64 | 172.9333 | 160.46 | -120.9% |  | 2026-03-31
2217. - Bluffdale Day Ranch Park | 100.1703. - FS Job Site Superintendent | 474.19 | 0 | -474.19 |  | 0 | 0 | 0% | 0 | -474.19 | 474.19 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2930. - AP Asphalt Prep (DO NOT USE) | 897.54 | 293.51 | -604.03 | 305.8% | 80 | 291 | 50% | 146.755 | -750.785 | 1795.08 | 162.51 | 144.6% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 800.1940. - PL Punch List Work | 272.92 | 185 | -87.92 | 147.5% | 0 | 185 | 0% | 185 | -87.92 | 272.92 | 125 | 132.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 2551.16 | 939.88 | -1611.28 | 271.4% | 600.8 | 938 | 100% | 939.88 | -1611.28 | 2551.16 | 1847.72 | 3.409% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 800.1930. - MC Misc Cleanup | 265.26 | 510 | 244.74 | 52.01% | 0 | 510 | 0% | 510 | 244.74 | 510 | 400 | 121.6% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.3000. - CNC Concrete Work | 250.66 | 260 | 9.34 | 96.41% | 0 | 260 | 0% | 260 | 9.34 | 260 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2900. - ASPH Asphalt | 34.38 | 6.87 | -27.51 | 500.4% | 0 | 6 | 0% | 6.87 | -27.51 | 34.38 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2610. - PT Pressure Test/Chlorinating | 1.3 | 22 | 20.7 | 5.909% | 0 | 22 | 0% | 22 | 20.7 | 22 | 20 | 109.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.7100. - IMP Interior Mech/Piping | 461.15 | 20 | -441.15 | 2306% | 0 | 20 | 0% | 20 | -441.15 | 461.15 | 20 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.6900. - EF Roofing | 740.16 | 540.28 | -199.88 | 137% | 0 | 540.28 | 0% | 540.28 | -199.88 | 740.16 | 530 | 101.9% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.3000. - CNC Concrete Work | 3729.67 | 879.78 | -2849.89 | 423.9% | 0 | 880.11 | 0% | 879.78 | -2849.89 | 3729.67 | 685.67 | 122.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2010. - RG Grading (DO NOT USE) | 11.13 | 163.28 | 152.15 | 6.817% | 0 | 163 | 0% | 163.28 | 152.15 | 163.28 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2050. - RW Retaining Walls | 436.77 | 268 | -168.77 | 163% | 212 | 268 | 40% | 107.2 | -329.57 | 1091.925 | 281.55 | 94.94% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2080. - EXS Excavate Structure | 593.25 | 463 | -130.25 | 128.1% | 90.6 | 463 | 10.58% | 49.0044 | -544.2456 | 5605.0993 | 453 | 102.2% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2030. - Unknown Phase | 59.58 | 55.92 | -3.66 | 106.5% | 25 | 55 | 39.68% | 22.1905 | -37.3895 | 150.1416 | 25.5 | 154.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 150.2760. - Unknown Phase | 147.59 | 87.58 | -60.01 | 168.5% | 23.2 | 87.5 | 134.1% | 117.4302 | -30.1598 | 110.0733 | 29.17 | 166.7% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 150.2750. - Unknown Phase | 1578.99 | 421.95 | -1157.04 | 374.2% | 184.45 | 428.26 | 70% | 295.365 | -1283.625 | 2255.7 | 281 | 133.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 150.1230. - T Transporting | 432.16 | 345 | -87.16 | 125.3% | 60 | 345 | 10% | 34.5 | -397.66 | 4321.6 | 300 | 113% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2300. - Unknown Phase | 2446.18 | 1152.31 | -1293.87 | 212.3% | 627.3 | 1152 | 32.1% | 369.8358 | -2076.3442 | 7621.6464 | 1044.99 | 109.3% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1700. - FS Project Manager | 1520.42 | 350 | -1170.42 | 434.4% | 54 | 350 | 16.67% | 58.3333 | -1462.0867 | 9122.52 | 735.31 | -10.09% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9010. - Re-Work Pipe | 24.17 | 0.4 | -23.77 | 6042% | 0 | 1 | 0% | 0.4 | -23.77 | 24.17 | 0.4 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9005. - Re-Work Surveying | 38 | 0 | -38 |  | 0 | 0 | 0% | 0 | -38 | 38 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.1600. - TC Traffic Control | 416.18 | 300 | -116.18 | 138.7% | 90 | 300 | 7.563% | 22.6891 | -393.4909 | 5502.8244 | 107.19 | 164.3% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2010. - RG Grading (DO NOT USE) | 4480.3 | 2890.13 | -1590.17 | 155% | 2487.6 | 2832 | 42.16% | 1218.3507 | -3261.9493 | 10628.0151 | 2766.35 | 104.3% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.3000. - CNC Concrete Work | 53.6 | 640 | 586.4 | 8.375% | 0 | 640 | 0% | 640 | 586.4 | 640 | 640 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 57.17 | 0 | -57.17 |  | 0 | 0 | 0% | 0 | -57.17 | 57.17 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9055. - Re-Work Finishes | 6.88 | 0.2 | -6.68 | 3440% | 0 | 1 | 0% | 0.2 | -6.68 | 6.88 | 0.2 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1702. - FS People Superintendent | 215.36 | 0 | -215.36 |  | 0 | 0 | 0% | 0 | -215.36 | 215.36 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.7600. - MEQ Mechanical Equipment | 4040.29 | 1770 | -2270.29 | 228.3% | 0 | 1770 | 0% | 1770 | -2270.29 | 4040.29 | 1770 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.7100. - IMP Interior Mech/Piping | 30.47 | 60 | 29.53 | 50.78% | 0 | 60 | 0% | 60 | 29.53 | 60 | 60 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.2040. - LR Landscaping/Restoration | 1062.98 | 0 | -1062.98 |  | 0 | 0 | 0% | 0 | -1062.98 | 1062.98 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.3500. - Unknown Phase | 20.46 | 126 | 105.54 | 16.24% | 0 | 126 | 0% | 126 | 105.54 | 126 | 126 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 250.2080. - EXS Excavate Structure | 60.19 | 60 | -0.19 | 100.3% | 42 | 60 | 32.31% | 19.3846 | -40.8054 | 186.3024 | 85.99 | 56.68% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.5100. - W Welding | 402.04 | 118 | -284.04 | 340.7% | 0 | 118 | 0% | 118 | -284.04 | 402.04 | 98 | 116.9% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.9015. - Re-Work Concrete | 232.15 | 0.4 | -231.75 | 58038% | 0 | 1 | 0% | 0.4 | -231.75 | 232.15 | 0.4 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.5400. - HAT Hatch/Skylights | 61.27 | 24 | -37.27 | 255.3% | 0 | 24 | 0% | 24 | -37.27 | 61.27 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.6500. - Unknown Phase | 598.63 | 146 | -452.63 | 410% | 0 | 146 | 0% | 146 | -452.63 | 598.63 | 337.05 | -30.86% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2040. - LR Landscaping/Restoration | 419.57 | 0 | -419.57 |  | 0 | 0 | 0% | 0 | -419.57 | 419.57 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.5110. - Fab Shop Pipe Fabrication | 432.9 | 0 | -432.9 |  | 0 | 0 | 0% | 0 | -432.9 | 432.9 | 73.47 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 900.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 73.89 | 0 | -73.89 |  | 0 | 0 | 0% | 0 | -73.89 | 73.89 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 260.3000. - CNC Concrete Work | 38.5 | 350 | 311.5 | 11% | 0 | 350 | 0% | 350 | 311.5 | 350 | 350 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2500. - MH Manholes (DO NOT USE) | 9.25 | 30 | 20.75 | 30.83% | 0 | 30 | 0% | 30 | 20.75 | 30 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2800. - Unknown Phase | 1554.27 | 538.19 | -1016.08 | 288.8% | 0 | 538.19 | 0% | 538.19 | -1016.08 | 1554.27 | 516 | 104.1% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.5210. - Fab Shop Structural Steel Fabrication | 439.75 | 150 | -289.75 | 293.2% | 0 | 150 | 0% | 150 | -289.75 | 439.75 | 150 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2020. - Unknown Phase | 1012.12 | 198 | -814.12 | 511.2% | 198 | 198 | 27.5% | 54.45 | -957.67 | 3680.4364 | 245.24 | 76.14% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2080. - EXS Excavate Structure | 8.31 | 90 | 81.69 | 9.233% | 0 | 90 | 0% | 90 | 81.69 | 90 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2100. - SPL Sewer Pipe Laying (DO NOT USE) | 475.41 | 475.93 | 0.52 | 99.89% | 281.4 | 475 | 28.56% | 135.9248 | -339.4852 | 1664.6108 | 469.43 | 101.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.2200. - DPL Drainage Pipe Laying (DO NOT USE) | 35.9 | 105 | 69.1 | 34.19% | 0 | 105 | 0% | 105 | 69.1 | 105 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2800. - BFST Backfill (DO NOT USE) | 269.15 | 15 | -254.15 | 1794% | 0 | 15 | 0% | 15 | -254.15 | 269.15 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2030. - D Demolition | 7.02 | 6 | -1.02 | 117% | 0 | 6 | 0% | 6 | -1.02 | 7.02 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 280.2940. - CP Concrete Prep (DO NOT USE) | 379.02 | 30 | -349.02 | 1263% | 0 | 30 | 0% | 30 | -349.02 | 379.02 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2910. - MP Milling/Pulverize | 9.6 | 12 | 2.4 | 80% | 0 | 12 | 0% | 12 | 2.4 | 12 | 12 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1510. - S Surveying | 1603.3 | 510 | -1093.3 | 314.4% | 180.8 | 500 | 13.33% | 68 | -1535.3 | 12024.75 | 452 | 111.4% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 210.1600. - TC Traffic Control | 173.55 | 90 | -83.55 | 192.8% | 0 | 90 | 0% | 90 | -83.55 | 173.55 | 0 | 200% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 350.1650. - SB Signage | 162.38 | 60 | -102.38 | 270.6% | 0 | 60 | 0% | 60 | -102.38 | 162.38 | 60 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.2300. - WPL Water Pipe Laying (DO NOT USE) | 5.18 | 0 | -5.18 |  | 0 | 0 | 0% | 0 | -5.18 | 5.18 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 200.2070. - RGC Rough Grade Cut | 300.22 | 65 | -235.22 | 461.9% | 18 | 65 | 30% | 19.5 | -280.72 | 1000.7333 | 365.48 | -362.3% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 100.1300. - Unknown Phase | 100.56 | 0 | -100.56 |  | 0 | 0 | 0% | 0 | -100.56 | 100.56 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 270.3000. - CNC Concrete Work | 120.26 | 110 | -10.26 | 109.3% | 0 | 110 | 0% | 110 | -10.26 | 120.26 | 110 | 100% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 160.5310. - Fab Shop Misc Metals Fabrication | 383.85 | 0 | -383.85 |  | 0 | 0 | 0% | 0 | -383.85 | 383.85 | 0 | 0% |  | 2023-05-31
2217. - Bluffdale Day Ranch Park | 300.2010. - RG Grading (DO NOT USE) | 7442.46 | 1089.27 | -6353.19 | 683.3% | 436 | 1090 | 21.2% | 230.8808 | -7211.5792 | 35112.7069 | 1089.27 | 100% |  | 2023-05-31
2512. - South SLC Davis Tank Lid Replacement | 100.1702. - FS People Superintendent | 23.61 | 136.82 | 113.21 | 17.26% | 96.474 | 136.82 | 70% | 95.774 | 72.164 | 33.7286 | 65.61 | 152% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 800.1930. - MC Misc Cleanup | 22.17 | 120 | 97.83 | 18.48% | 1.2 | 120 | 0.75% | 0.9 | -21.27 | 2956 | 120 | 100% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1200. - HOOK Hook Truck Dumpster Transporting | 33.93 | 15 | -18.93 | 226.2% | 9.75 | 15 | 65% | 9.75 | -24.18 | 52.2 | 43.5 | -90% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 231.5100. - W Welding | 31.85 | 0 | -31.85 |  | 0 | 0 | 0% | 0 | -31.85 | 31.85 | 31.85 | 0% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1704. - FS Quality Control/Assurance | 106.5 | 252.76 | 146.26 | 42.13% | 177.632 | 252.76 | 70% | 176.932 | 70.432 | 152.1429 | 100 | 160.4% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 900.9010. - Re-Work Pipe | 0 | 0.6 | 0.6 | 0% | 0 | 0.6 | 0% | 0.6 | 0.6 | 0.6 | 0 | 200% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1700. - FS Project Manager | 120.5 | 168.33 | 47.83 | 71.59% | 115.731 | 168.33 | 70% | 117.831 | -2.669 | 172.1429 | 161.5 | 104.1% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 119.51 | 146.12 | 26.61 | 81.79% | 102.984 | 146.12 | 70% | 102.284 | -17.226 | 170.7286 | 142.87 | 102.2% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 210.5100. - W Welding | 29.22 | 15 | -14.22 | 194.8% | 15 | 15 | 100% | 15 | -14.22 | 29.22 | 29.22 | 5.2% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 240.7100. - IMP Interior Mech/Piping | 2.18 | 9 | 6.82 | 24.22% | 0 | 9 | 0% | 9 | 6.82 | 9 | 2.18 | 175.8% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 100.1703. - FS Job Site Superintendent | 215.91 | 214.72 | -1.19 | 100.6% | 145.404 | 214.72 | 70% | 150.304 | -65.606 | 308.4429 | 208.65 | 102.8% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 200.7400. - HVAC HVAC | 24.65 | 24 | -0.65 | 102.7% | 12 | 24 | 50% | 12 | -12.65 | 49.3 | 24.65 | 97.29% |  | 2026-03-13
2512. - South SLC Davis Tank Lid Replacement | 150.1230. - T Transporting | 77.44 | 105 | 27.56 | 73.75% | 66.5 | 105 | 70% | 73.5 | -3.94 | 110.6286 | 103.93 | 101% |  | 2026-03-13
2513. - CUWCD Summit Creek Irrigation HDPE | 200.1800. - PH Potholing | 8 | 45 | 37 | 17.78% | 45 | 45 | 100% | 45 | 37 | 8 | 8 | 182.2% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1200. - HOOK Hook Truck Dumpster Transporting | 4.95 | 5 | 0.05 | 99% | 5 | 5 | 100% | 5 | 0.05 | 4.95 | 4.95 | 101% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1702. - FS People Superintendent | 130.92 | 100.81 | -30.11 | 129.9% | 95.769 | 100.81 | 47.5% | 47.8845 | -83.0355 | 275.6225 | 142.92 | 58.23% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1704. - FS Quality Control/Assurance | 39 | 20.08 | -18.92 | 194.2% | 20.08 | 20.08 | 50% | 10.04 | -28.96 | 78 | 47 | -34.06% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 230.2170. - HDPE Fusion Pipe <15' Depth | 13.48 | 15 | 1.52 | 89.87% | 15 | 15 | 42.86% | 6.4286 | -7.0514 | 31.4533 | 13.48 | 110.1% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 240.2080. - EXS Excavate Structure | 107.49 | 55.04 | -52.45 | 195.3% | 63.02 | 55.04 | 67.75% | 37.289 | -70.201 | 158.6595 | 107.49 | 4.706% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1700. - FS Project Manager | 75.23 | 171.04 | 95.81 | 43.98% | 162.488 | 171.04 | 48.08% | 82.244 | 7.014 | 156.4532 | 85.23 | 150.2% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 200.2170. - HDPE Fusion Pipe <15' Depth | 145.66 | 392.5 | 246.84 | 37.11% | 392.5 | 392.5 | 31.25% | 122.6562 | -23.0038 | 466.112 | 145.66 | 162.9% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 5.25 | 161.72 | 156.47 | 3.246% | 153.634 | 161.72 | 47.5% | 76.817 | 71.567 | 11.0526 | 30.25 | 181.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 270.2170. - HDPE Fusion Pipe <15' Depth | 1 | 12 | 11 | 8.333% | 0 | 12 | 0% | 12 | 11 | 12 | 51 | -225% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.5000. - MET Metals | 16.5 | 25.8 | 9.3 | 63.95% | 25.8 | 25.8 | 60% | 15.48 | -1.02 | 27.5 | 16.5 | 136% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 800.1930. - MC Misc Cleanup | 29.17 | 60 | 30.83 | 48.62% | 24 | 60 | 40% | 24 | -5.17 | 72.925 | 60 | 100% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1703. - FS Job Site Superintendent | 136.97 | 198.63 | 61.66 | 68.96% | 178.767 | 198.63 | 51.25% | 101.798 | -35.172 | 267.2582 | 176.97 | 110.9% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.3000. - CNC Concrete Work | 268.22 | 202.61 | -65.61 | 132.4% | 202.61 | 202.61 | 83.11% | 168.386 | -99.834 | 322.7351 | 298.22 | 52.81% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.2080. - EXS Excavate Structure | 20.15 | 41 | 20.85 | 49.15% | 41 | 41 | 48.24% | 19.7765 | -0.37353 | 41.7744 | 20.15 | 150.9% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 220.2170. - HDPE Fusion Pipe <15' Depth | 324.09 | 341.79 | 17.7 | 94.82% | 341.79 | 341.79 | 93.13% | 318.292 | -5.798 | 348.016 | 325.09 | 104.9% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 200.2610. - PT Pressure Test/Chlorinating | 69.59 | 30 | -39.59 | 232% | 54 | 30 | 140% | 42 | -27.59 | 49.7071 | 69.59 | -31.97% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 270.2240. - PCS Precast Structures | 4.27 | 40 | 35.73 | 10.67% | 40 | 40 | 34.78% | 13.913 | 9.643 | 12.2762 | 4.27 | 189.3% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 200.2030. - Unknown Phase | 38.92 | 66 | 27.08 | 58.97% | 66 | 66 | 42.86% | 28.2857 | -10.6343 | 90.8133 | 38.92 | 141% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 160.5000. - Unknown Phase | 53.79 | 0 | -53.79 |  | 0 | 0 | 49.96% | 0 | -53.79 | 107.668 | 53.79 | 0% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 150.2750. - Unknown Phase | 104.79 | 150.09 | 45.3 | 69.82% | 150.09 | 150.09 | 33.63% | 50.4784 | -54.3116 | 311.5773 | 104.79 | 130.2% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 150.2760. - Unknown Phase | 1 | 14 | 13 | 7.143% | 14 | 14 | 33.33% | 4.6667 | 3.6667 | 3 | 1 | 192.9% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 100.1510. - S Surveying | 94.62 | 65 | -29.62 | 145.6% | 65 | 65 | 100% | 65 | -29.62 | 94.62 | 95.12 | 53.66% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 290.2170. - HDPE Fusion Pipe <15' Depth | 65.78 | 46.02 | -19.76 | 142.9% | 46.02 | 46.02 | 48.94% | 22.5206 | -43.2594 | 134.4188 | 65.78 | 57.06% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 150.1230. - T Transporting | 78.29 | 40 | -38.29 | 195.7% | 40 | 40 | 68.75% | 27.5 | -50.79 | 113.8764 | 82.06 | -5.15% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 210.2170. - HDPE Fusion Pipe <15' Depth | 326.66 | 225.99 | -100.67 | 144.5% | 225.99 | 225.99 | 43.14% | 97.4987 | -229.1613 | 757.1576 | 326.66 | 55.45% |  | 2026-03-31
2513. - CUWCD Summit Creek Irrigation HDPE | 250.2600. - DW Dewatering | 1221.1 | 75 | -1146.1 | 1628% | 130 | 75 | 100% | 75 | -1146.1 | 1221.1 | 1221.1 | -1428% |  | 2026-03-31
2403. - Cedar Hills Harvey Well Pump House Upgrades | 800.1930. - MC Misc Cleanup | 45.16 | 60 | 14.84 | 75.27% | 54 | 60 | 100% | 60 | 14.84 | 45.16 | 45.16 | 124.7% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 150.1230. - T Transporting | 20.49 | 50 | 29.51 | 40.98% | 50 | 50 | 100% | 50 | 29.51 | 20.49 | 20.49 | 159% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 300.7900. - ELC Electrical | 12.41 | 30 | 17.59 | 41.37% | 30 | 30 | 100% | 30 | 17.59 | 12.41 | 12.41 | 158.6% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.6000. - IF Interior Finishes | 534.76 | 60 | -474.76 | 891.3% | 50 | 50 | 100% | 60 | -474.76 | 534.76 | 534.76 | -691.3% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.5400. - HAT Hatch/Skylights | 163.79 | 30 | -133.79 | 546% | 0 | 30 | 0% | 30 | -133.79 | 163.79 | 30 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9015. - Re-Work Concrete | 17.41 | 0.4 | -17.01 | 4352% | 0.4 | 0.4 | 100% | 0.4 | -17.01 | 17.41 | 17.41 | -4152% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 800.1940. - PL Punch List Work | 10.2 | 90 | 79.8 | 11.33% | 81 | 90 | 100% | 90 | 79.8 | 10.2 | 10.2 | 188.7% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 364.22 | 150 | -214.22 | 242.8% | 150 | 150 | 100% | 150 | -214.22 | 364.22 | 364.22 | -42.81% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.2080. - EXS Excavate Structure | 138.81 | 150 | 11.19 | 92.54% | 150 | 150 | 100% | 150 | 11.19 | 138.81 | 138.81 | 107.5% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.2030. - Unknown Phase | 292 | 195 | -97 | 149.7% | 195 | 195 | 100% | 195 | -97 | 292 | 292 | 50.26% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 150.2750. - Unknown Phase | 7.32 | 1.06 | -6.26 | 690.6% | 1.06 | 1.06 | 100% | 1.06 | -6.26 | 7.32 | 7.32 | -490.6% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.3100. - CNC Rebar | 70.24 | 15 | -55.24 | 468.3% | 15 | 15 | 100% | 15 | -55.24 | 70.24 | 70.24 | -268.3% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1700. - FS Project Manager | 314.5 | 118 | -196.5 | 266.5% | 0 | 118 | 0% | 118 | -196.5 | 314.5 | 118 | 100% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9010. - Re-Work Pipe | 23.36 | 0.4 | -22.96 | 5840% | 0.4 | 0.4 | 100% | 0.4 | -22.96 | 23.36 | 23.36 | -5640% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.3000. - Unknown Phase | 124.24 | 56 | -68.24 | 221.9% | 66 | 56 | 100% | 56 | -68.24 | 124.24 | 124.24 | -21.86% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 300.3000. - CNC Concrete Work | 108.91 | 100 | -8.91 | 108.9% | 100 | 100 | 100% | 100 | -8.91 | 108.91 | 108.91 | 91.09% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1703. - FS Job Site Superintendent | 416.07 | 200 | -216.07 | 208% | 180 | 200 | 100% | 200 | -216.07 | 416.07 | 410.23 | -5.115% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 150.2760. - Unknown Phase | 2.5 | 21 | 18.5 | 11.9% | 21 | 21 | 100% | 21 | 18.5 | 2.5 | 2.5 | 188.1% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1500. - VIS Meetings (Vision, Safety, Training) | 2.38 | 10 | 7.62 | 23.8% | 10 | 10 | 100% | 10 | 7.62 | 2.38 | 2.38 | 176.2% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1702. - FS People Superintendent | 107.7 | 100 | -7.7 | 107.7% | 100 | 100 | 100% | 100 | -7.7 | 107.7 | 107.7 | 92.3% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.6300. - DAW Doors & Windows | 29.43 | 30 | 0.57 | 98.1% | 30 | 30 | 100% | 30 | 0.57 | 29.43 | 29.43 | 101.9% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 100.1200. - HOOK Hook Truck Dumpster Transporting | 4.25 | 17.5 | 13.25 | 24.29% | 17.5 | 17.5 | 100% | 17.5 | 13.25 | 4.25 | 4.25 | 175.7% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9100. - Job Related Equipment Repairs | 59.22 | 1 | -58.22 | 5922% | 1 | 1 | 100% | 1 | -58.22 | 59.22 | 59.22 | -5722% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.7400. - HVAC HVAC | 20.38 | 150 | 129.62 | 13.59% | 150 | 150 | 100% | 150 | 129.62 | 20.38 | 20.38 | 186.4% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.7100. - IMP Interior Mech/Piping | 241.64 | 181 | -60.64 | 133.5% | 175 | 181 | 100% | 181 | -60.64 | 241.64 | 241.64 | 66.5% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 900.9055. - Re-Work Finishes | 10.23 | 3 | -7.23 | 341% | 3 | 3 | 100% | 3 | -7.23 | 10.23 | 10.23 | -141% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.6800. - CLK Caulking | 303.09 | 70 | -233.09 | 433% | 30 | 70 | 100% | 70 | -233.09 | 303.09 | 303.09 | -233% |  | 2025-03-25
2403. - Cedar Hills Harvey Well Pump House Upgrades | 200.2060. - Unknown Phase | 7.67 | 30 | 22.33 | 25.57% | 30 | 30 | 100% | 30 | 22.33 | 7.67 | 7.67 | 174.4% |  | 2025-03-25
2321. - CUWCD Santaquin Reach | 375.2750. - H Hauling | 71.88 | 323.62 | 251.74 | 22.21% | 322.59 | 323.26 | 100% | 323.62 | 251.74 | 71.88 | 71.88 | 177.8% |  | 2026-05-01
2321. - CUWCD Santaquin Reach | 650.2940. - CP Concrete Prep (DO NOT USE) | 54.69 | 30 | -24.69 | 182.3% | 21 | 30 | 70% | 21 | -33.69 | 78.1286 | 54.69 | 17.7% |  | 2026-05-01
2307. - JVWCD 2022-2023 Vault Improvements | 300.5320. - FAB Shop Misc Metals Coatings (DO NOT USE) | 5.8 | 22 | 16.2 | 26.36% | 0 | 22 | 0% | 22 | 16.2 | 22 | 22 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 821.44 | 155 | -666.44 | 530% | 0 | 155 | 0.3738% | 0.57944 | -820.8606 | 219735.2 | 155 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2030. - D Demolition | 206.34 | 60 | -146.34 | 343.9% | 0 | 60 | 0% | 60 | -146.34 | 206.34 | 60 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1230. - T Transporting | 28.29 | 30 | 1.71 | 94.3% | 0 | 30 | 0% | 30 | 1.71 | 30 | 30 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.2760. - HO Haul Off | 9.13 | 10 | 0.87 | 91.3% | 0 | 10 | 0% | 10 | 0.87 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9055. - Re-Work Finishes | 18.01 | 0.2 | -17.81 | 9005% | 0 | 0.2 | 0% | 0.2 | -17.81 | 18.01 | 0.2 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2750. - H Hauling | 16 | 12 | -4 | 133.3% | 1 | 12 | 4.167% | 0.5 | -15.5 | 384 | 12 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.1230. - T Transporting | 3 | 10 | 7 | 30% | 0 | 10 | 0% | 10 | 7 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9020. - Re-Work Fab | 9.62 | 0.2 | -9.42 | 4810% | 0 | 1 | 0% | 0.2 | -9.42 | 9.62 | 0.2 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1940. - PL Punch List Work | 143.52 | 10 | -133.52 | 1435% | 0 | 10 | 0% | 10 | -133.52 | 143.52 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5000. - MET Metals | 54.29 | 70 | 15.71 | 77.56% | 0 | 70 | 3.226% | 2.2581 | -52.0319 | 1682.99 | 50 | 128.6% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2750. - H Hauling | 24.33 | 3.87 | -20.46 | 628.7% | 2 | 3.87 | 38.76% | 1.5 | -22.83 | 62.7714 | 3.87 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2760. - HO Haul Off | 87.41 | 16 | -71.41 | 546.3% | 0 | 16 | 0% | 16 | -71.41 | 87.41 | 16 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2300. 2 - WPL Water Pipe Laying (DO NOT USE) | 10.25 | 16.5 | 6.25 | 62.12% | 0 | 16.5 | 0% | 16.5 | 6.25 | 16.5 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2930. - AP Asphalt Prep (DO NOT USE) | 92.24 | 10 | -82.24 | 922.4% | 1 | 10 | 9.412% | 0.94118 | -91.2988 | 980.05 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2030. - D Demolition | 38.91 | 40 | 1.09 | 97.28% | 0 | 40 | 0% | 40 | 1.09 | 40 | 40 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.1930. - MC Misc Cleanup | 39.72 | 40 | 0.28 | 99.3% | 0 | 40 | 0% | 40 | 0.28 | 40 | 40 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1940. - PL Punch List Work | 60.16 | 10 | -50.16 | 601.6% | 0 | 10 | 0% | 10 | -50.16 | 60.16 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.2300. 4 - WPL Water Pipe Laying (DO NOT USE) | 29.09 | 4.5 | -24.59 | 646.4% | 0 | 4.5 | 0% | 4.5 | -24.59 | 29.09 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1510. - S Surveying | 13.27 | 10 | -3.27 | 132.7% | 0 | 10 | 0% | 10 | -3.27 | 13.27 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9100. - Job Related Equipment Repairs | 2 | 1 | -1 | 200% | 0 | 1 | 0% | 1 | -1 | 2 | 2 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2300. 1 - WPL Water Pipe Laying (DO NOT USE) | 11.38 | 2 | -9.38 | 569% | 0 | 2 | 0% | 2 | -9.38 | 11.38 | 0 | 200% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.3000. - CNC Concrete Work | 68.32 | 66 | -2.32 | 103.5% | 0 | 66 | 0% | 66 | -2.32 | 68.32 | 66 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.1940. - PL Punch List Work | 58.19 | 30 | -28.19 | 194% | 0 | 30 | 0% | 30 | -28.19 | 58.19 | 30 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.5320. - FAB Shop Misc Metals Coatings (DO NOT USE) | 4.33 | 10 | 5.67 | 43.3% | 0 | 10 | 0% | 10 | 5.67 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2030. - D Demolition | 70.07 | 15 | -55.07 | 467.1% | 0 | 15 | 0% | 15 | -55.07 | 70.07 | 15 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1702. - FS People Superintendent | 95.29 | 0 | -95.29 |  | 0 | 0 | 0% | 0 | -95.29 | 95.29 | 6.5 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.2760. - HO Haul Off | 3 | 5 | 2 | 60% | 0 | 5 | 0% | 5 | 2 | 5 | 5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2300. - WPL Water Pipe Laying (DO NOT USE) | 103.08 | 170 | 66.92 | 60.64% | 2 | 170 | 1.154% | 1.9615 | -101.1185 | 8933.6 | 170 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2510. - CB Catch Basins DO NOT USE) | 23.65 | 20 | -3.65 | 118.3% | 0 | 20 | 0% | 20 | -3.65 | 23.65 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2930. - AP Asphalt Prep (DO NOT USE) | 8.5 | 10 | 1.5 | 85% | 0 | 10 | 0% | 10 | 1.5 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 900.9010. - Re-Work Pipe | 4 | 0.4 | -3.6 | 1000% | 0 | 0.4 | 0% | 0.4 | -3.6 | 4 | 0.4 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.1230. - T Transporting | 33.75 | 20 | -13.75 | 168.8% | 0 | 20 | 0% | 20 | -13.75 | 33.75 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.2930. - AP Asphalt Prep (DO NOT USE) | 9.3 | 51 | 41.7 | 18.24% | 2 | 51 | 5.291% | 2.6984 | -6.6016 | 175.77 | 51 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2750. - H Hauling | 3.02 | 11.79 | 8.77 | 25.61% | 0 | 11.79 | 0% | 11.79 | 8.77 | 11.79 | 11.79 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 6.2 | 10 | 3.8 | 62% | 0 | 10 | 0% | 10 | 3.8 | 10 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1600. - TC Traffic Control | 53.22 | 120 | 66.78 | 44.35% | 0 | 120 | 0% | 120 | 66.78 | 120 | 120 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.3000. - Unknown Phase | 149.47 | 55 | -94.47 | 271.8% | 1 | 55 | 3.478% | 1.913 | -147.557 | 4297.2625 | 55 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.1230. - T Transporting | 39.76 | 20 | -19.76 | 198.8% | 0 | 20 | 0% | 20 | -19.76 | 39.76 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 22.61 | 25 | 2.39 | 90.44% | 0 | 25 | 0% | 25 | 2.39 | 25 | 25 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1930. - MC Misc Cleanup | 76 | 27.02 | -48.98 | 281.3% | 0 | 27.02 | 0% | 27.02 | -48.98 | 76 | 20 | 126% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.1600. - TC Traffic Control | 34.61 | 90 | 55.39 | 38.46% | 0 | 90 | 0.2083% | 0.1875 | -34.4225 | 16612.8 | 90 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 27.5 | 0 | -27.5 |  | 0 | 0 | 0% | 0 | -27.5 | 27.5 | 0 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5100. - W Welding | 315.03 | 20 | -295.03 | 1575% | 0 | 20 | 0% | 20 | -295.03 | 315.03 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1700. - FS Project Manager | 133 | 0 | -133 |  | 0 | 0 | 0% | 0 | -133 | 133 | 0 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2300. - WPL Water Pipe Laying (DO NOT USE) | 436.25 | 280 | -156.25 | 155.8% | 2 | 280 | 0.5405% | 1.5135 | -434.7365 | 80706.25 | 280 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5110. - FAB Shop Pipe Fabrication (DO NOT USE) | 245.86 | 60 | -185.86 | 409.8% | 0 | 60 | 0% | 60 | -185.86 | 245.86 | 60 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.1940. - PL Punch List Work | 4 | 5 | 1 | 80% | 0 | 5 | 0% | 5 | 1 | 5 | 5 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.1930. - MC Misc Cleanup | 11.25 | 20 | 8.75 | 56.25% | 0 | 20 | 0% | 20 | 8.75 | 20 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1230. - T Transporting | 30.66 | 34 | 3.34 | 90.18% | 12 | 34 | 30% | 10.2 | -20.46 | 102.2 | 20 | 141.2% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.1600. - TC Traffic Control | 234.85 | 228 | -6.85 | 103% | 1 | 228 | 0.03076% | 0.070121 | -234.7799 | 763614.775 | 930331.86 | -407840% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2760. - HO Haul Off | 40.42 | 10 | -30.42 | 404.2% | 0 | 10 | 0% | 10 | -30.42 | 40.42 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 400.2930. - AP Asphalt Prep (DO NOT USE) | 40.51 | 60 | 19.49 | 67.52% | 0 | 60 | 0% | 60 | 19.49 | 60 | 60 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2760. - HO Haul Off | 41.64 | 22 | -19.64 | 189.3% | 0 | 22 | 0% | 22 | -19.64 | 41.64 | 14 | 136.4% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.2300. - WPL Water Pipe Laying (DO NOT USE) | 37.45 | 180 | 142.55 | 20.81% | 2 | 180 | 1.333% | 2.4 | -35.05 | 2808.75 | 180 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5310. - FAB Shop Misc Metals Fabrication (DO NOT USE) | 48.91 | 50 | 1.09 | 97.82% | 0 | 50 | 0.6667% | 0.33333 | -48.5767 | 7336.5 | 50 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 800.7100. - Unknown Phase | 29.75 | 20 | -9.75 | 148.8% | 0 | 20 | 0% | 20 | -9.75 | 29.75 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2300. - Unknown Phase | 114.75 | 379 | 264.25 | 30.28% | 0 | 331 | 0.2377% | 0.90104 | -113.849 | 48266.7188 | 210 | 144.6% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 700.2300. - WPL Water Pipe Laying (DO NOT USE) | 210.02 | 75 | -135.02 | 280% | 1 | 75 | 0.303% | 0.22727 | -209.7927 | 69306.6 | 15138.75 | -19985% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.2760. - HO Haul Off | 28.84 | 10 | -18.84 | 288.4% | 0 | 10 | 0% | 10 | -18.84 | 28.84 | 10 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 100.1703. - FS Job Site Superintendent | 412.15 | 0 | -412.15 |  | 0 | 0 | 0% | 0 | -412.15 | 412.15 | 37.78 | 0% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 600.1600. - TC Traffic Control | 8.58 | 150 | 141.42 | 5.72% | 0 | 150 | 0% | 150 | 141.42 | 150 | 150 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.3000. - CNC Concrete Work | 25.75 | 20 | -5.75 | 128.8% | 1 | 20 | 43.33% | 8.6667 | -17.0833 | 59.4231 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.5120. - FAB Shop Pipe Linings & Coatings (DO NOT USE) | 25.3 | 114 | 88.7 | 22.19% | 0 | 114 | 0% | 114 | 88.7 | 114 | 100 | 112.3% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.1930. - MC Misc Cleanup | 5.5 | 20 | 14.5 | 27.5% | 0 | 20 | 0% | 20 | 14.5 | 20 | 20 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 300.6500. - P Painting | 154.81 | 40 | -114.81 | 387% | 0 | 40 | 0% | 40 | -114.81 | 154.81 | 40 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 200.2930. - AP Asphalt Prep (DO NOT USE) | 99.01 | 15 | -84.01 | 660.1% | 0 | 15 | 0% | 15 | -84.01 | 99.01 | 15 | 100% |  | 2024-07-16
2307. - JVWCD 2022-2023 Vault Improvements | 500.1600. - TC Traffic Control | 6 | 90 | 84 | 6.667% | 0 | 90 | 0% | 90 | 84 | 90 | 90 | 100% |  | 2024-07-16
2315. - VanCon SLC Flowfill Project | 200.2710. - FWF Flowable Fill | 3484.32 | 1466.67 | -2017.65 | 237.6% | 0 | 1466.67 | 0.02597% | 0.38095 | -3483.939 | 13414666.8432 | 3484.32 | -37.57%
2315. - VanCon SLC Flowfill Project | 300.2760. - HO Haul Off | 21.53 | 2 | -19.53 | 1076% | 0 | 2 | 0% | 2 | -19.53 | 21.53 | 21.53 | -876.5%
2315. - VanCon SLC Flowfill Project | 300.1230. - T Transporting | 9 | 50 | 41 | 18% | 0 | 50 | 0% | 50 | 41 | 50 | 9 | 182%
2315. - VanCon SLC Flowfill Project | 300.2710. - FWF Flowable Fill | 87.09 | 250 | 162.91 | 34.84% | 0 | 250 | 0% | 250 | 162.91 | 250 | 87.09 | 165.2%
2315. - VanCon SLC Flowfill Project | 200.2750. - H Hauling | 611.6 | 632.5 | 20.9 | 96.7% | 0 | 632.5 | 0% | 632.5 | 20.9 | 632.5 | 611.6 | 103.3%
2315. - VanCon SLC Flowfill Project | 150.2710. - FWF Flowable Fill | 117.78 | 250 | 132.22 | 47.11% | 0 | 250 | 0% | 250 | 132.22 | 250 | 117.78 | 152.9%
2315. - VanCon SLC Flowfill Project | 300.2000. - SWC Site Work Complete (DO NOT USE) | 3 | 10 | 7 | 30% | 0 | 10 | 0% | 10 | 7 | 10 | 3 | 170%
2315. - VanCon SLC Flowfill Project | 150.1230. - T Transporting | 84.7 | 50 | -34.7 | 169.4% | 0 | 50 | 0% | 50 | -34.7 | 84.7 | 84.7 | 30.6%
2315. - VanCon SLC Flowfill Project | 150.2300. - WPL Water Pipe Laying (DO NOT USE) | 24.82 | 30 | 5.18 | 82.73% | 0 | 30 | 0% | 30 | 5.18 | 30 | 24.82 | 117.3%
2315. - VanCon SLC Flowfill Project | 150.2750. - Unknown Phase | 261.61 | 105.6 | -156.01 | 247.7% | 0 | 105.6 | 88.3% | 93.25 | -168.36 | 296.2575 | 261.61 | -47.74%
2129. - JVWCD 3600 W 10200 S Pump Station | 250.6500. - P Painting | 296.28 | 0 | -296.28 |  | 0 | 0 | 0% | 0 | -296.28 | 296.28 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.3000.10 - CNC Concrete Work | 47.86 | 58.5 | 10.64 | 81.81% | 0 | 1 | 0% | 58.5 | 10.64 | 58.5 | 0 | 200% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 282.7 | 0 | -282.7 |  | 0 | 0 | 0% | 0 | -282.7 | 282.7 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9100. - Job Related Equipment Repairs | 111.95 | 1 | -110.95 | 11195% | 0 | 1 | 0% | 1 | -110.95 | 111.95 | 1 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2070. - RGC Rough Grade Cut | 371.62 | 30 | -341.62 | 1239% | 1.5 | 30 | 2.5% | 0.75 | -370.87 | 14864.8 | 30 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9010. - Re-Work Pipe | 16.33 | 0.6 | -15.73 | 2722% | 0 | 0.6 | 0% | 0.6 | -15.73 | 16.33 | 0.6 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1700. - FS Project Manager | 203 | 0 | -203 |  | 0 | 0 | 0% | 0 | -203 | 203 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1703. - FS Job Site Superintendent | 364.03 | 0 | -364.03 |  | 0 | 0 | 0% | 0 | -364.03 | 364.03 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1510. - S Surveying | 583.02 | 400 | -183.02 | 145.8% | 0 | 400 | 3.875% | 15.5 | -567.52 | 15045.6774 | 400 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 800.1940 - Unknown Phase | 3.05 | 0 | -3.05 |  | 0 | 0 | 0% | 0 | -3.05 | 3.05 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.2080. - EXS Excavate Structure | 357.08 | 562.1 | 205.02 | 63.53% | 0 | 562.1 | 0% | 562.1 | 205.02 | 562.1 | 562.1 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.5000. - MET Metals | 160.61 | 232 | 71.39 | 69.23% | 0 | 232 | 0% | 232 | 71.39 | 232 | 232 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.3000. - Unknown Phase | 2983.12 | 423.5 | -2559.62 | 704.4% | 0 | 410 | 0% | 423.5 | -2559.62 | 2983.12 | 410 | 103.2% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 180.5000. - MET Metals | 1329.88 | 0 | -1329.88 |  | 0 | 0 | 0% | 0 | -1329.88 | 1329.88 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 180.7400. - HVAC HVAC | 342.58 | 0 | -342.58 |  | 0 | 0 | 0% | 0 | -342.58 | 342.58 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2010. - RG Grading (DO NOT USE) | 29.15 | 578 | 548.85 | 5.043% | 0 | 578 | 0% | 578 | 548.85 | 578 | 578 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1702. - FS People Superintendent | 141.76 | 0 | -141.76 |  | 0 | 0 | 0% | 0 | -141.76 | 141.76 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7100. - IMP Interior Mech/Piping | 3600.88 | 1087 | -2513.88 | 331.3% | 0 | 1087 | 0% | 1087 | -2513.88 | 3600.88 | 1087 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7600. - MEQ Mechanical Equipment | 341.23 | 111 | -230.23 | 307.4% | 0 | 111 | 0% | 111 | -230.23 | 341.23 | 111 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7300. - PLUM Plumbing | 269.1 | 810 | 540.9 | 33.22% | 0 | 810 | 0% | 810 | 540.9 | 810 | 810 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.5000. - MET Metals | 169.7 | 1166.38 | 996.68 | 14.55% | 0 | 1166.38 | 0% | 1166.38 | 996.68 | 1166.38 | 1166.38 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.5100. - W Welding | 728.65 | 83 | -645.65 | 877.9% | 0 | 83 | 0% | 83 | -645.65 | 728.65 | 83 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.2300. - WPL Water Pipe Laying (DO NOT USE) | 5452.34 | 2720 | -2732.34 | 200.5% | 0 | 2720 | 0% | 2720 | -2732.34 | 5452.34 | 2720 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9020. - Re-Work Fab | 49.78 | 0.2 | -49.58 | 24890% | 0 | 0.2 | 0% | 0.2 | -49.58 | 49.78 | 0.2 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 800.1930. - MC Misc Cleanup | 42.86 | 200 | 157.14 | 21.43% | 0 | 200 | 0% | 200 | 157.14 | 200 | 200 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.6200. - IN Insulation | 89.5 | 80 | -9.5 | 111.9% | 0 | 80 | 0% | 80 | -9.5 | 89.5 | 80 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2000. - Unknown Phase | 1992.83 | 102 | -1890.83 | 1954% | 0 | 102 | 0% | 102 | -1890.83 | 1992.83 | 102 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.5000. - MET Metals | 288.03 | 154 | -134.03 | 187% | 0 | 1 | 0% | 154 | -134.03 | 288.03 | 0 | 200% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.1704. - FS Quality Control/Assurance | 20.51 | 0 | -20.51 |  | 0 | 0 | 0% | 0 | -20.51 | 20.51 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 700.2610. - PT Pressure Test/Chlorinating | 259.42 | 200 | -59.42 | 129.7% | 0 | 200 | 0% | 200 | -59.42 | 259.42 | 200 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 800.1940. - PL Punch List Work | 648.54 | 300 | -348.54 | 216.2% | 0 | 300 | 10% | 30 | -618.54 | 6485.4 | 300 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2040. - LR Landscaping/Restoration | 8.8 | 0 | -8.8 |  | 0 | 0 | 0% | 0 | -8.8 | 8.8 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.6000. - IF Interior Finishes | 2421.71 | 9 | -2412.71 | 26908% | 0 | 9 | 0% | 9 | -2412.71 | 2421.71 | 9 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 150.2750. - Unknown Phase | 152.57 | 195.68 | 43.11 | 77.97% | 0 | 195.68 | 0% | 195.68 | 43.11 | 195.68 | 195.68 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9012. - Re-Work Mechanical | 126.79 | 0.4 | -126.39 | 31698% | 0 | 0.4 | 0% | 0.4 | -126.39 | 126.79 | 0.4 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.2800. - BFST Backfill (DO NOT USE) | 1485.97 | 300 | -1185.97 | 495.3% | 0 | 300 | 0% | 300 | -1185.97 | 1485.97 | 300 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.2030. - Unknown Phase | 60.06 | 247 | 186.94 | 24.32% | 0 | 247 | 0% | 247 | 186.94 | 247 | 247 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 200.1600. - TC Traffic Control | 10.52 | 30 | 19.48 | 35.07% | 0 | 30 | 0% | 30 | 19.48 | 30 | 30 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 150.2760. - Unknown Phase | 473.51 | 1246 | 772.49 | 38% | 0 | 1244 | 0% | 1246 | 772.49 | 1246 | 1244 | 100.2% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 180.2900.40 - ASPH Asphalt | 15.02 | 9.52 | -5.5 | 157.8% | 0 | 1 | 0% | 9.52 | -5.5 | 15.02 | 0 | 200% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.2300. - WPL Water Pipe Laying (DO NOT USE) | 22.79 | 100 | 77.21 | 22.79% | 0 | 100 | 0% | 100 | 77.21 | 100 | 100 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 185.7100. - IMP Interior Mech/Piping | 321.49 | 0 | -321.49 |  | 0 | 0 | 0% | 0 | -321.49 | 321.49 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 201.5000. - MET Metals | 6608.69 | 0 | -6608.69 |  | 0 | 0 | 0% | 0 | -6608.69 | 6608.69 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 100.2050. - RW Retaining Walls | 1 | 30 | 29 | 3.333% | 0 | 30 | 0% | 30 | 29 | 30 | 30 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.7900. - ELC Electrical | 319.09 | 289.8 | -29.29 | 110.1% | 0 | 270 | 0% | 289.8 | -29.29 | 319.09 | 270 | 106.8% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 150.1230. - T Transporting | 491.96 | 400 | -91.96 | 123% | 0 | 400 | 0% | 400 | -91.96 | 491.96 | 400 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 300.2110. - SS Sewer Services (DO NOT USE) | 140.63 | 92 | -48.63 | 152.9% | 0 | 92 | 0% | 92 | -48.63 | 140.63 | 92 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 162.5000. - MET Metals | 86.11 | 0 | -86.11 |  | 0 | 0 | 0% | 0 | -86.11 | 86.11 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 900.9015. - Re-Work Concrete | 89.93 | 0.4 | -89.53 | 22482% | 0 | 0.4 | 0% | 0.4 | -89.53 | 89.93 | 0.4 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.3000. - CNC Concrete Work | 4877.15 | 4006.71 | -870.44 | 121.7% | 0 | 4006.71 | 0% | 4006.71 | -870.44 | 4877.15 | 4006.71 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 170.2300. - WPL Water Pipe Laying (DO NOT USE) | 1245.71 | 0 | -1245.71 |  | 0 | 0 | 0% | 0 | -1245.71 | 1245.71 | 0 | 0% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 400.6500. - P Painting | 1759.43 | 780 | -979.43 | 225.6% | 0 | 780 | 0% | 780 | -979.43 | 1759.43 | 780 | 100% |  | 2023-12-31
2129. - JVWCD 3600 W 10200 S Pump Station | 350.3000. - CNC Concrete Work | 21 | 0 | -21 |  | 0 | 0 | 0% | 0 | -21 | 21 | 0 | 0% |  | 2023-12-31
2519. - Corix IEC Site Utilities | 100.1510. - S Surveying | 64.82 | 100 | 35.18 | 64.82% | 55 | 100 | 55% | 55 | -9.82 | 117.8545 | 106.4 | 93.6% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 400.7100. - IMP Interior Mech/Piping | 47.5 | 60 | 12.5 | 79.17% | 18 | 60 | 30% | 18 | -29.5 | 158.3333 | 60 | 100% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1702. - FS People Superintendent | 56.5 | 74 | 17.5 | 76.35% | 0.55 | 74 | 55% | 40.7 | -15.8 | 102.7273 | 65 | 112.2% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 200.2075. - FG Finish Grade | 41.58 | 200 | 158.42 | 20.79% | 60 | 200 | 30% | 60 | 18.42 | 138.6 | 209.9 | 95.05% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1704. - FS Quality Control/Assurance | 1 | 29 | 28 | 3.448% | 0.55 | 29 | 55% | 15.95 | 14.95 | 1.8182 | 10 | 165.5% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 200.2240. - PCS Precast Structures | 389.94 | 92.5 | -297.44 | 421.6% | 37 | 92.5 | 40% | 37 | -352.94 | 974.85 | 428.84 | -263.6% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 800.1940. - PL Punch List Work | 6.82 | 40 | 33.18 | 17.05% | 24 | 40 | 60% | 24 | 17.18 | 11.3667 | 40 | 100% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2075. - FG Finish Grade | 30.45 | 196.32 | 165.87 | 15.51% | 19.632 | 196.32 | 10% | 19.632 | -10.818 | 304.5 | 200 | 98.13% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2080. - EXS Excavate Structure | 39.6 | 160 | 120.4 | 24.75% | 80 | 160 | 50% | 80 | 40.4 | 79.2 | 181.17 | 86.77% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.3000. - CNC Concrete Work | 724.42 | 928.2 | 203.78 | 78.05% | 928.2 | 928.2 | 100% | 928.2 | 203.78 | 724.42 | 1004.76 | 91.75% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2085. - BFST Backfill Structure | 5 | 125 | 120 | 4% | 62.5 | 125 | 50% | 62.5 | 57.5 | 10 | 5 | 196% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.3100. - CNC Rebar | 99.86 | 144 | 44.14 | 69.35% | 86.4 | 144 | 60% | 86.4 | -13.46 | 166.4333 | 199.86 | 61.21% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 158.76 | 219 | 60.24 | 72.49% | 83.05 | 219 | 55% | 120.45 | -38.31 | 288.6545 | 282.76 | 70.89% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1700. - FS Project Manager | 60.5 | 138 | 77.5 | 43.84% | 28.05 | 138 | 55% | 75.9 | 15.4 | 110 | 135.5 | 101.8% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 500.2075. - FG Finish Grade | 33.15 | 12 | -21.15 | 276.2% | 1.2 | 12 | 10% | 1.2 | -31.95 | 331.5 | 50 | -216.7% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 150.1230. - T Transporting | 3.5 | 50 | 46.5 | 7% | 22.5 | 50 | 45% | 22.5 | 19 | 7.7778 | 50 | 100% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 100.1703. - FS Job Site Superintendent | 161 | 116 | -45 | 138.8% | 0.55 | 116 | 55% | 63.8 | -97.2 | 292.7273 | 181.46 | 43.57% |  | 2026-04-01
2519. - Corix IEC Site Utilities | 300.2600. - DW Dewatering | 5.92 | 180 | 174.08 | 3.289% | 180 | 180 | 100% | 180 | 174.08 | 5.92 | 5.92 | 196.7% |  | 2026-04-01
2504. - Marathon - 1900 N Sewer | 200.2075. - FG Finish Grade | 140.7 | 280 | 139.3 | 50.25% | 280 | 280 | 100% | 280 | 139.3 | 140.7 | 140.7 | 149.8% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1230. - T Transporting | 125.79 | 40 | -85.79 | 314.5% | 40 | 40 | 100% | 40 | -85.79 | 125.79 | 125.79 | -114.5% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1702. - FS People Superintendent | 62.37 | 137.14 | 74.77 | 45.48% | 137.14 | 137.14 | 100% | 137.14 | 74.77 | 62.37 | 62.37 | 154.5% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 6 | 147.23 | 141.23 | 4.075% | 147.23 | 147.23 | 100% | 147.23 | 141.23 | 6 | 6 | 195.9% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1700. - FS Project Manager | 112.48 | 50.8 | -61.68 | 221.4% | 50.8 | 50.8 | 100% | 50.8 | -61.68 | 112.48 | 112.48 | -21.42% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 250.2600. - DW Dewatering | 27.45 | 150 | 122.55 | 18.3% | 0 | 150 | 0% | 150 | 122.55 | 150 | 27.45 | 181.7% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.1600. - TC Traffic Control | 32.16 | 130 | 97.84 | 24.74% | 130 | 130 | 100% | 130 | 97.84 | 32.16 | 32.16 | 175.3% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1707. - S Survey | 51.64 | 0 | -51.64 |  | 0 | 0 | 0% | 0 | -51.64 | 51.64 | 51.64 | 0% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2071. - RGF Rough Grade Fill | 759.79 | 80 | -679.79 | 949.7% | 80 | 80 | 100% | 80 | -679.79 | 759.79 | 759.79 | -749.7% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 100.1703. - FS Job Site Superintendent | 230.69 | 75.28 | -155.41 | 306.4% | 75.28 | 75.28 | 100% | 75.28 | -155.41 | 230.69 | 230.69 | -106.4% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2240. - PCS Precast Structures | 510.7 | 92.5 | -418.2 | 552.1% | 92.5 | 92.5 | 100% | 92.5 | -418.2 | 510.7 | 510.7 | -352.1% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 250.1600. - TC Traffic Control | 781.3 | 0 | -781.3 |  | 0 | 0 | 0% | 0 | -781.3 | 781.3 | 781.3 | 0% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2130. - PVC Pipe | 1204.63 | 397.75 | -806.88 | 302.9% | 397.75 | 397.75 | 100% | 397.75 | -806.88 | 1204.63 | 1204.63 | -102.9% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 150.2750. - Unknown Phase | 275.41 | 38 | -237.41 | 724.8% | 38 | 38 | 100% | 38 | -237.41 | 275.41 | 275.41 | -524.8% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 200.2030. - Unknown Phase | 137.93 | 150 | 12.07 | 91.95% | 0 | 150 | 0% | 150 | 12.07 | 150 | 137.93 | 108% |  | 2025-07-11
2504. - Marathon - 1900 N Sewer | 150.2760. - Unknown Phase | 103.13 | 152.35 | 49.22 | 67.69% | 152.35 | 152.35 | 100% | 152.35 | 49.22 | 103.13 | 103.13 | 132.3% |  | 2025-07-11
2602. - JVWCD Rosecrest WSP Pipeline | 100.1515. - S Drone/Lidar Requirements | 46.2 | 650 | 603.8 | 7.108% | 0 | 650 | 0% | 650 | 603.8 | 650 | 650 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 164.75 | 1421.78 | 1257.03 | 11.59% | 0 | 1421.78 | 0% | 1421.78 | 1257.03 | 1421.78 | 1421.78 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 900.9100. - Job Related Equipment Repairs | 1.5 | 1 | -0.5 | 150% | 0 | 1 | 0% | 1 | -0.5 | 1.5 | 1 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 150.2750. - Unknown Phase | 4.42 | 259.86 | 255.44 | 1.701% | 0 | 259.86 | 0% | 259.86 | 255.44 | 259.86 | 259.86 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1700. - FS Project Manager | 36.75 | 1568.06 | 1531.31 | 2.344% | 0 | 1568.06 | 0% | 1568.06 | 1531.31 | 1568.06 | 1568.06 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1711. - FS Pre-Construction Video | 4.5 | 40 | 35.5 | 11.25% | 0 | 40 | 0% | 40 | 35.5 | 40 | 40 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1108. - TF Setup Staging Area Laydown Yard | 19.73 | 4 | -15.73 | 493.2% | 0 | 4 | 0% | 4 | -15.73 | 19.73 | 4 | 100% |  | 2028-05-15
2602. - JVWCD Rosecrest WSP Pipeline | 100.1702. - FS People Superintendent | 2.5 | 1312.89 | 1310.39 | 0.1904% | 0 | 1312.89 | 0% | 1312.89 | 1310.39 | 1312.89 | 1312.89 | 100% |  | 2028-05-15
2518. - Mt Pleasant Lagoon Improvement | 100.1703. - FS Job Site Superintendent | 19 | 228.02 | 209.02 | 8.333% | 0 | 228.02 | 0% | 228.02 | 209.02 | 228.02 | 228.02 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 150.1230. - T Transporting | 22 | 75 | 53 | 29.33% | 0 | 75 | 0% | 75 | 53 | 75 | 75 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1700. - FS Project Manager | 53.5 | 181.06 | 127.56 | 29.55% | 0 | 181.06 | 0% | 181.06 | 127.56 | 181.06 | 181.06 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 167.25 | 164.82 | -2.43 | 101.5% | 0 | 164.82 | 0% | 164.82 | -2.43 | 167.25 | 164.82 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 200.2030. - Unknown Phase | 68.1 | 3 | -65.1 | 2270% | 0 | 3 | 0% | 3 | -65.1 | 68.1 | 3 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1702. - FS People Superintendent | 17.75 | 151.89 | 134.14 | 11.69% | 0 | 151.89 | 0% | 151.89 | 134.14 | 151.89 | 151.89 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1200. - HOOK Hook Truck Dumpster Transporting | 5.25 | 15 | 9.75 | 35% | 0 | 15 | 0% | 15 | 9.75 | 15 | 15 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 500.2030. - D Demolition | 26.77 | 15 | -11.77 | 178.5% | 0 | 15 | 0% | 15 | -11.77 | 26.77 | 15 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1201. - HOOK Hook Truck Conex, Skid Transporting | 3 | 5 | 2 | 60% | 0 | 5 | 0% | 5 | 2 | 5 | 5 | 100% |  | 2026-11-30
2518. - Mt Pleasant Lagoon Improvement | 100.1510. - S Surveying | 30.58 | 50 | 19.42 | 61.16% | 0 | 50 | 0% | 50 | 19.42 | 50 | 50 | 100% |  | 2026-11-30
2516. - Ephraim Lower Penstock Replacement | 150.2760. - Unknown Phase | 9.35 | 9.57 | 0.22 | 97.7% | 0 | 9.57 | 0% | 9.57 | 0.22 | 9.57 | 23 | -40.33% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2130. - PVC Pipe | 220.46 | 210.8 | -9.66 | 104.6% | 217.39 | 210.8 | 54.43% | 114.7395 | -105.7205 | 405.0302 | 240.46 | 85.93% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2240. - PCS Precast Structures | 219.26 | 235.72 | 16.46 | 93.02% | 0.9 | 122.72 | 45% | 106.074 | -113.186 | 487.2444 | 209.26 | 111.2% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2140. - SVR Services | 89.85 | 141.32 | 51.47 | 63.58% | 1 | 50.32 | 50% | 70.66 | -19.19 | 179.7 | 89.85 | 136.4% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2030. - Unknown Phase | 2.75 | 63 | 60.25 | 4.365% | 38.7 | 63 | 14.73% | 9.2792 | 6.5292 | 18.6709 | 52.75 | 116.3% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.5100. - W Welding | 514.85 | 2732.5 | 2217.65 | 18.84% | 640.8 | 2136 | 5.552% | 151.7056 | -363.1444 | 9273.4062 | 1514.85 | 144.6% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1702. - FS People Superintendent | 114.8 | 248.93 | 134.13 | 46.12% | 74.379 | 247.93 | 15% | 37.3395 | -77.4605 | 765.3333 | 249.8 | 99.65% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2160. - WSP Welded Steel Pipe <15' Depth | 4822.53 | 3612.92 | -1209.61 | 133.5% | 864.021 | 2880.07 | 11.06% | 399.5769 | -4422.9531 | 43604.657 | 6492.61 | 20.29% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 900.9100. - Job Related Equipment Repairs | 8.37 | 2 | -6.37 | 418.5% | 0 | 1 | 0% | 2 | -6.37 | 8.37 | 8.37 | -218.5% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.5400. - HAT Hatch/Skylights | 13 | 36 | 23 | 36.11% | 18 | 36 | 46.15% | 16.6154 | 3.6154 | 28.1667 | 35 | 102.8% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 300.5000. - MET Metals | 173.99 | 24 | -149.99 | 725% | 0 | 0 | 0% | 24 | -149.99 | 173.99 | 173.99 | -525% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.1515. - S Drone/Lidar Requirements | 224.88 | 550 | 325.12 | 40.89% | 225 | 450 | 2.284% | 12.5635 | -212.3165 | 9844.7467 | 460.48 | 116.3% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2120. - DIP Ductile Iron Pipe | 556.01 | 202.14 | -353.87 | 275.1% | 80 | 202.14 | 50% | 101.07 | -454.94 | 1112.02 | 556.01 | -75.06% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2085. - BFST Backfill Structure | 677.65 | 1971.37 | 1293.72 | 34.37% | 501.93 | 1667.55 | 0.04287% | 0.84509 | -676.8049 | 1580776.4627 | 680.13 | 165.5% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.1800. - PH Potholing | 496.81 | 320 | -176.81 | 155.3% | 240 | 320 | 50% | 160 | -336.81 | 993.62 | 496.81 | 44.75% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 800.1930. - MC Misc Cleanup | 8.75 | 300 | 291.25 | 2.917% | 225 | 300 | 75% | 225 | 216.25 | 11.6667 | 300 | 100% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 161.5100. - W Welding | 367.81 | 220 | -147.81 | 167.2% | 220 | 44 | 43.64% | 96 | -271.81 | 842.8979 | 336.51 | 47.04% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1703. - FS Job Site Superintendent | 524.11 | 373.53 | -150.58 | 140.3% | 111.759 | 372.53 | 15% | 56.0295 | -468.0805 | 3494.0667 | 689.74 | 15.35% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2610. - PT Pressure Test/Chlorinating | 16.52 | 145.08 | 128.56 | 11.39% | 0 | 124.2 | 0% | 145.08 | 128.56 | 145.08 | 6.5 | 195.5% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.2020. - Unknown Phase | 62.7 | 250 | 187.3 | 25.08% | 250 | 250 | 99.6% | 249.004 | 186.304 | 62.9508 | 112.7 | 154.9% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.1600. - TC Traffic Control | 30.3 | 0 | -30.3 |  | 0 | 0 | 0% | 0 | -30.3 | 30.3 | 29.5 | 0% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1704. - FS Quality Control/Assurance | 102 | 97.06 | -4.94 | 105.1% | 38.424 | 96.06 | 20% | 19.412 | -82.588 | 510 | 172 | 22.79% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 150.1230. - T Transporting | 270.49 | 200 | -70.49 | 135.2% | 100 | 200 | 50% | 100 | -170.49 | 540.98 | 314.4 | 42.8% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1700. - FS Project Manager | 251.73 | 296.67 | 44.94 | 84.85% | 87.201 | 295.67 | 15% | 44.5005 | -207.2295 | 1678.2 | 298.73 | 99.31% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 446.76 | 270.1 | -176.66 | 165.4% | 80.73 | 269.1 | 15% | 40.515 | -406.245 | 2978.4 | 577.59 | -13.84% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 200.3000. - Unknown Phase | 123.67 | 130.07 | 6.4 | 95.08% | 124.75 | 124.75 | 97.65% | 127.0155 | 3.3455 | 126.644 | 129.7 | 100.3% |  | 2026-10-31
2516. - Ephraim Lower Penstock Replacement | 150.2750. - Unknown Phase | 418.46 | 343.34 | -75.12 | 121.9% | 171.67 | 343.34 | 6.739% | 23.1383 | -395.3217 | 6209.3546 | 1128.34 | -128.6% |  | 2026-10-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.3000. - Unknown Phase | 191.1 | 20 | -171.1 | 955.5% | 0 | 1 | 0% | 20 | -171.1 | 191.1 | 40 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.5000. - MET Metals | 12.94 | 30 | 17.06 | 43.13% | 0 | 30 | 0% | 30 | 17.06 | 30 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 8.63 | 0 | -8.63 |  | 0 | 0 | 0% | 0 | -8.63 | 8.63 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.5100. - W Welding | 19.95 | 10 | -9.95 | 199.5% | 0 | 10 | 0% | 10 | -9.95 | 19.95 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 150.1230. - T Transporting | 71.33 | 90 | 18.67 | 79.26% | 0 | 90 | 0% | 90 | 18.67 | 90 | 60 | 133.3% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1700. - FS Project Manager | 42 | 250 | 208 | 16.8% | 0 | 200 | 0% | 250 | 208 | 250 | 125 | 150% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.2030. - Unknown Phase | 299.58 | 395 | 95.42 | 75.84% | 0 | 395 | 0% | 395 | 95.42 | 395 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.6500. - P Painting | 131.25 | 376 | 244.75 | 34.91% | 0 | 1200 | 0% | 376 | 244.75 | 376 | 160 | 157.4% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 400.5000. - MET Metals | 58.22 | 0 | -58.22 |  | 0 | 0 | 0% | 0 | -58.22 | 58.22 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1703. - FS Job Site Superintendent | 281.66 | 0 | -281.66 |  | 0 | 0 | 0% | 0 | -281.66 | 281.66 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 160.6500. - P Painting | 58.08 | -60 | -118.08 |  | 1 | -60 | 150% | -90 | -148.08 | 38.72 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1930. - MC Misc Cleanup | 47.65 | 80 | 32.35 | 59.56% | 0 | 60 | 0% | 80 | 32.35 | 80 | 40 | 150% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.3000. - CNC Concrete Work | 637.57 | 100 | -537.57 | 637.6% | 0 | 1 | 0% | 100 | -537.57 | 637.57 | 20 | 180% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1510. - S Surveying | 13 | 45 | 32 | 28.89% | 0 | 45 | 0% | 45 | 32 | 45 | 30 | 133.3% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.5100. - W Welding | 58.34 | 10 | -48.34 | 583.4% | 0 | 10 | 0% | 10 | -48.34 | 58.34 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 160.5000. - Unknown Phase | 591.27 | 271 | -320.27 | 218.2% | 0 | 0 | 0% | 271 | -320.27 | 591.27 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1940. - PL Punch List Work | 172.48 | 80 | -92.48 | 215.6% | 0 | 60 | 0% | 80 | -92.48 | 172.48 | 40 | 150% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.7100. - IMP Interior Mech/Piping | 1236.76 | 1410 | 173.24 | 87.71% | 0 | 1 | 0% | 1410 | 173.24 | 1410 | 760 | 146.1% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.5000. - MET Metals | 10.32 | 30 | 19.68 | 34.4% | 0 | 30 | 0% | 30 | 19.68 | 30 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 300.2030. - D Demolition | 8.95 | 645 | 636.05 | 1.388% | 0 | 645 | 0% | 645 | 636.05 | 645 | 0 | 200% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 900.9012. - Re-Work Mechanical | 4 | 0 | -4 |  | 0 | 0 | 0% | 0 | -4 | 4 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 210.6500. - P Painting | 511.53 | 0 | -511.53 |  | 0 | 0 | 0% | 0 | -511.53 | 511.53 | 0 | 0% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.7100. - IMP Interior Mech/Piping | 367.78 | 1810 | 1442.22 | 20.32% | 0 | 1 | 0% | 1810 | 1442.22 | 1810 | 1500 | 117.1% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 200.6500. - Unknown Phase | 323.89 | 100 | -223.89 | 323.9% | 0 | 1200 | 0% | 100 | -223.89 | 323.89 | 160 | 40% |  | 2023-12-31
1845. - PRWUA Deer Creek Tube Valve Replacement | 100.1702. - FS People Superintendent | 100.42 | 0 | -100.42 |  | 0 | 0 | 0% | 0 | -100.42 | 100.42 | 0 | 0% |  | 2023-12-31
2606. - SLCo FAC126702 SMH HVAC Replacement | 100.1706. - FS Executive | 1 | 1 | 0 | 100% | 0 | 1 | 0% | 1 | 0 | 1 | 1 | 100% |  | 2026-02-16
2606. - SLCo FAC126702 SMH HVAC Replacement | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 41.65 | 46.81 | 5.16 | 88.98% | 0 | 46.81 | 0% | 46.81 | 5.16 | 46.81 | 46.81 | 100% |  | 2026-02-16
2606. - SLCo FAC126702 SMH HVAC Replacement | 100.1700. - FS Project Manager | 7 | 51.52 | 44.52 | 13.59% | 0 | 51.52 | 0% | 51.52 | 44.52 | 51.52 | 51.52 | 100% |  | 2026-02-16
2517. - CUWCD Ashley Valley BWRB Rehab | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 29.5 | 87.54 | 58.04 | 33.7% | 0 | 87.54 | 0% | 87.54 | 58.04 | 87.54 | 69 | 121.2% |  | 2027-04-01
2517. - CUWCD Ashley Valley BWRB Rehab | 100.1700. - FS Project Manager | 100 | 106.11 | 6.11 | 94.24% | 0 | 106.11 | 0% | 106.11 | 6.11 | 106.11 | 169 | 40.73% |  | 2027-04-01
2603. - Highland City Mitchell Hollow Trail | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 67 | 169.5 | 102.5 | 39.53% | 16.95 | 169.5 | 10% | 16.95 | -50.05 | 670 | 169.5 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 200.1600. - TC Traffic Control | 1.75 | 50 | 48.25 | 3.5% | 0 | 50 | 0% | 50 | 48.25 | 50 | 50 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1703. - FS Job Site Superintendent | 16.53 | 235.25 | 218.72 | 7.027% | 23.525 | 235.25 | 10% | 23.525 | 6.995 | 165.3 | 235.25 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1700. - FS Project Manager | 47 | 186.85 | 139.85 | 25.15% | 18.685 | 186.85 | 10% | 18.685 | -28.315 | 470 | 186.85 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 800.1940. - PL Punch List Work | 4.5 | 90 | 85.5 | 5% | 0 | 90 | 0% | 90 | 85.5 | 90 | 90 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1510. - S Surveying | 32 | 200 | 168 | 16% | 20 | 200 | 10% | 20 | -12 | 320 | 200 | 100% |  | 2026-12-16
2603. - Highland City Mitchell Hollow Trail | 100.1702. - FS People Superintendent | 17.73 | 156.59 | 138.86 | 11.32% | 15.659 | 156.59 | 10% | 15.659 | -2.071 | 177.3 | 156.59 | 100% |  | 2026-12-16
2604. - Murray 900 East Storm Drain Phase 2 | 100.1702. - FS People Superintendent | 23.5 | 242.82 | 219.32 | 9.678% | 0 | 242.82 | 0% | 242.82 | 219.32 | 242.82 | 242.82 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 200.1600. - TC Traffic Control | 19.25 | 464 | 444.75 | 4.149% | 0 | 1 | 0% | 464 | 444.75 | 464 | 464 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 100.1700. - FS Project Manager | 71 | 289.85 | 218.85 | 24.5% | 0 | 289.85 | 0% | 289.85 | 218.85 | 289.85 | 289.85 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 100.1701. - FS Project Engineer/Assitant PM/Scheduler | 17.28 | 262.89 | 245.61 | 6.573% | 0 | 262.89 | 0% | 262.89 | 245.61 | 262.89 | 262.89 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 200.2210. - RCP Reinforced Concrete Pipe | 113.24 | 2401.64 | 2288.4 | 4.715% | 0 | 2388 | 0% | 2401.64 | 2288.4 | 2401.64 | 2401.64 | 100% |  | 2026-12-31
2604. - Murray 900 East Storm Drain Phase 2 | 150.2750. - Unknown Phase | 0 | 1327.94 | 1327.94 | 0% | 0 | 4162 | 0% | 1327.94 | 1327.94 | 1327.94 | 1327.94 | 100% |  | 2026-12-31
2608. - Springville City WRF Headworks | 100.1700. - FS Project Manager | 51 | 162.93 | 111.93 | 31.3% | 0 | 162.93 | 0% | 162.93 | 111.93 | 162.93 | 224 | 62.52% |  | 2026-08-31
2605. - Highland City Well #1&#5 Chlorine | 100.1500. - VIS Meetings (Vision, Safety, Training) | 1 | 1 | 0 | 100% | 0.1 | 1 | 10% | 0.1 | -0.9 | 10 | 1 | 100% |  | 2026-05-15
2605. - Highland City Well #1&#5 Chlorine | 100.1703. - FS Job Site Superintendent | 17.58 | 60.03 | 42.45 | 29.29% | 6.003 | 60.03 | 10% | 6.003 | -11.577 | 175.8 | 86.58 | 55.77% |  | 2026-05-15
2605. - Highland City Well #1&#5 Chlorine | 100.1700. - FS Project Manager | 53 | 47.83 | -5.17 | 110.8% | 4.783 | 47.83 | 10% | 4.783 | -48.217 | 530 | 69 | 55.74% |  | 2026-05-15
2313. - CUWCD Hades Feeder Pipeline Joint Bonds | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2023-11-06
2317. - CUWCD CWP Wellhouse 17 | 300.7300. - PLUM Plumbing | 156.37 | 150 | -6.37 | 104.2% | 170 | 150 | 100% | 150 | -6.37 | 156.37 | 156.37 | 95.75% |  | 2025-12-30
2607. - CUWCD Cathodic & Pump Improvements | 100.1703. - FS Job Site Superintendent | 7 | 177.84 | 170.84 | 3.936% | 0 | 177.84 | 0% | 177.84 | 170.84 | 177.84 | 177.84 | 100%
2607. - CUWCD Cathodic & Pump Improvements | 100.1700. - FS Project Manager | 173.5 | 141.31 | -32.19 | 122.8% | 10.598 | 141.31 | 7.738% | 10.9343 | -162.5657 | 2242.2306 | 141.31 | 100%
2219. - GHID 20D Kent Booster Station | 100.1300. - Unknown Phase | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% |  | 2024-03-15
|  | 709281.75 | 489505.81 | -219775.94 |  | 397813.553 | 512331.709 |  | 398575.2464 | -310706.5036 | 21159024.419 | 1579601 |  | 0