## Projected Hours
Job | Phase | Phase Master | PR Dept | Actual Hours | Progress % Complete | Current Estimated Hours | Projected Hours Remaining | Projected Hours Allocated | Projected Hours Unallocated | Workoff Start | Workoff Comp | Mar – Mar '26 | Apr – Jun '26 | Jul – Sep '26 | Oct – Dec '26 | 2026 Totals | Jan – Mar '27 | Apr – Jun '27 | Jul – Sep '27 | Oct – Dec '27 | 2027 Totals | Jan – Mar '28 | Apr – Jun '28 | Jul – Sep '28 | Oct – Dec '28 | 2028 Totals | Jan – Mar '29 | Apr – Jun '29 | Jul – Sep '29 | Oct – Dec '29 | 2029 Totals
14924. Elberta Pit Job | 150.1220. Toilet/Dumpster | TD Tempoary Toilets for Job Site | 00 _Unknown PR Dept | 2 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 150.2700. SG Sand Processing & Loading Trucks | SG Sand & Gravel | 11 Earth Work | 5381.34 |  | 0 | 171.23 | 328.4 | -157.17 |  |  | 150 | 150 | 28.4 |  | 328.4
14924. Elberta Pit Job | 150.2710. | FWF Flowable Fill | 15 Concrete | 193.51 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 200.2700. Payson Reach | SG Sand & Gravel | 11 Earth Work | 36.71 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 210.2700. South Field Reach | SG Sand & Gravel | 11 Earth Work | 2564.6 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 220.2700. Woodland Hills 2018 Job | SG Sand & Gravel | 11 Earth Work | 8.32 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 230.2700. Woodland Hills 2110 Job | SG Sand & Gravel | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 240.2700. Springville Treatment Plant Job | SG Sand & Gravel | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 250.2700. Santaquin 2118 Job | SG Sand & Gravel | 11 Earth Work | 892.86 |  | 0 | 0 | 0 | 0
14924. Elberta Pit Job | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 602.5901. FAB 2602 Rosecrest Design/PM/PE | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 93.45 |  | 500 | 625 | 457 | 168 |  |  | 125 | 125 | 107 | 100 | 457
2650. Fab Shop Jobs 2026 Projects | 602.5935. FAB 2602 Rosecrest Shop Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 180 | 180 | 180 | 0 |  |  |  | 80 | 50 | 50 | 180
2650. Fab Shop Jobs 2026 Projects | 602.5940. FAB 2602 Rosecrest Shop WSP Fabrication | FAB Fab Shop WSP Fabrication | 20 Fabrication | 0 |  | 1247.34 | 1247 | 1247 | 0 |  |  |  | 600 | 600 | 47 | 1247
2650. Fab Shop Jobs 2026 Projects | 602.5950. FAB 2602 Rosecrest Shop WSP Blast/Paint | FAB Fab Shop WSP Paint | 20 Fabrication | 0 |  | 688.17 | 688 | 688 | 0 |  |  |  | 300 | 300 | 88 | 688
2650. Fab Shop Jobs 2026 Projects | 602.5960. FAB 2602 Rosecrest Fab Shop Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 0 |  | 532 | 532 | 532 | 0 |  |  |  | 200 | 200 | 132 | 532
2650. Fab Shop Jobs 2026 Projects | 602.5970. FAB 2602 Rosecrest Fab Shop Misc. Metals Blast/Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 90.8 | 90 | 90 | 0 |  |  |  | 30 | 30 | 30 | 90
2650. Fab Shop Jobs 2026 Projects | 602.5995. FAB 2602 Rosecrest Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 3.25 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 607.5901. FAB 2607 CU DACRWTP Management/Estimating/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 607.5940. FAB 2607 CU DACRWTP WSP Fabrication | FAB Fab Shop WSP Fabrication | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 607.5945. FAB 2607 CU DACRWTP Sand Blasting | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 607.5960. FAB 2607 CU DACRWTP Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 608.5901. FAB 2608 Springville WRF Management/Estimating/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 608.5935. FAB 2608 Springville WRF Shop Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 608.5940. FAB 2608 Springville WRF WSP Fabrication | FAB Fab Shop WSP Fabrication | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 608.5945. FAB 2608 Springville WRF Sand Blasting | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0
2650. Fab Shop Jobs 2026 Projects | 608.5960. FAB 2608 Springville WRF Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0
2607. CUWCD Cathodic & Pump Improvements | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1
2607. CUWCD Cathodic & Pump Improvements | 100.1510. S Surveying | S Surveying | 45 Survey | 0 |  | 75 | 75 | 0 | 75
2607. CUWCD Cathodic & Pump Improvements | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 141.31 | 141.31 | 0 | 141.31
2607. CUWCD Cathodic & Pump Improvements | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 0 |  | 128.21 | 128.21 | 0 | 128.21
2607. CUWCD Cathodic & Pump Improvements | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 0 |  | 118.46 | 118.46 | 0 | 118.46
2607. CUWCD Cathodic & Pump Improvements | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 0 |  | 177.84 | 177.84 | 0 | 177.84
2607. CUWCD Cathodic & Pump Improvements | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 46.23 | 46.23 | 0 | 46.23
2607. CUWCD Cathodic & Pump Improvements | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1
2607. CUWCD Cathodic & Pump Improvements | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1
2607. CUWCD Cathodic & Pump Improvements | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 50 | 50 | 0 | 50
2607. CUWCD Cathodic & Pump Improvements | 200.2030. D Demo Remove Pumps L&E (3 Ea) | D Demolition | 11 Earth Work | 0 |  | 30 | 30 | 0 | 30
2607. CUWCD Cathodic & Pump Improvements | 200.3000. CNC Pump Bases L&E (3 CY) | CNC Concrete Work | 15 Concrete | 0 |  | 75 | 75 | 0 | 75
2607. CUWCD Cathodic & Pump Improvements | 200.5100. WE Welding Pump Piping Tie in L&E (1 Ea) | W Welding | 20 Fabrication | 0 |  | 10 | 10 | 0 | 10
2607. CUWCD Cathodic & Pump Improvements | 200.7100. IMP Pump Piping Install L&E (10 Joints) | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 135 | 135 | 0 | 135
2607. CUWCD Cathodic & Pump Improvements | 200.7500. PUMP Pump Appurtenances L&E (4 Ea) | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 230 | 230 | 0 | 230
2607. CUWCD Cathodic & Pump Improvements | 400.1800. PH CP-4/A01 Potholing - (2 Ea) | PH Potholing | 10 Pipe | 0 |  | 10 | 10 | 0 | 10
2607. CUWCD Cathodic & Pump Improvements | 400.2040. LR CP-4/A01 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 400.2180. CATH CP-4/A01 Ext Joint Bond, Wire, & TS#1&2 ( 8 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 135 | 135 | 0 | 135
2607. CUWCD Cathodic & Pump Improvements | 400.2920. SC CP-4/A01 Core & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 15 | 15 | 0 | 15
2607. CUWCD Cathodic & Pump Improvements | 405.1800. PH CP-4/A02 Potholing - (1 Ea) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 405.2040. LR CP-4/A02 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 405.2180. CATH CP-4/A02 Ext Joint Bond, Wire, & TS#3 ( 8 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 85.5 | 85.5 | 0 | 85.5
2607. CUWCD Cathodic & Pump Improvements | 405.2920. SC CP-4/A02 Core & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 410.1800. PH CP-4/A03 Potholing (1 Ea) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 410.2040. LR CP-4/A03 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 410.2180. CATH CP-4/A03 Ext Joint Bond, Wire, & TS#4 ( 4 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 49.5 | 49.5 | 0 | 49.5
2607. CUWCD Cathodic & Pump Improvements | 410.2920. SC CP-4/A03 Core & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 415.1800. PH CP-4/A04 Potholing - (1 Ea) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 415.2040. LR CP-4/A04 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 415.2180. CATH CP-4/A04 Ext Joint Bond, Wire, & TS#5 ( 4 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 49.5 | 49.5 | 0 | 49.5
2607. CUWCD Cathodic & Pump Improvements | 415.2920. SC CP-4/A04 Saw/Core & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 420.1800. PH CP-4/A05 Potholing - (1 Ea) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 420.2040. LR CP-4/A05 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 420.2180. CATH CP-4/A05 Ext Joint Bond, Wire, & TS#6 ( 4 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 57 | 57 | 0 | 57
2607. CUWCD Cathodic & Pump Improvements | 420.2920. SC CP-4/A05 Core & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 425.1800. PH CP-4/A06 Potholing - (5 Ea) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 425.2040. LR CP-4/A06 Landscape Repair Gravel (200 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8
2607. CUWCD Cathodic & Pump Improvements | 425.2180. CATH CP-4/A06 Exterior Anode Bags, Wires & TS#7 (5 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 111.5 | 111.5 | 0 | 111.5
2607. CUWCD Cathodic & Pump Improvements | 425.2920. SC CP-4/A06 Core & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 430.1800. PH CP-4/A07 Potholing (2 Ea) | PH Potholing | 10 Pipe | 0 |  | 10 | 10 | 0 | 10
2607. CUWCD Cathodic & Pump Improvements | 430.2040. LR CP-4/A07 Landscape Repair (200 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8
2607. CUWCD Cathodic & Pump Improvements | 430.2180. CATH CP-4/A07 Exterior Anode Bags, Wires & TS#8&9 (6 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 153 | 153 | 0 | 153
2607. CUWCD Cathodic & Pump Improvements | 430.2920. SC CP-4/A07 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 15 | 15 | 0 | 15
2607. CUWCD Cathodic & Pump Improvements | 435.1800. PH CP-4/A08 Potholing - (2 Ea) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 435.2040. LR CP-4/A08 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 435.2180. CATH CP-4/A08 Ext Joint Bond, Wire, & TS#10&11 (4 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 49.5 | 49.5 | 0 | 49.5
2607. CUWCD Cathodic & Pump Improvements | 435.2920. SC CP-4/A08 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 440.1800. PH CP-4/A09 Potholing - (1 Ea) | PH Potholing | 10 Pipe | 0 |  | 10 | 10 | 0 | 10
2607. CUWCD Cathodic & Pump Improvements | 440.2040. LR CP-4/A09 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8
2607. CUWCD Cathodic & Pump Improvements | 440.2180. CATH CP-4/A09 Ext Joint Bond, Wire, & TS#12 (6 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 54 | 54 | 0 | 54
2607. CUWCD Cathodic & Pump Improvements | 440.2920. SC CP-4/A09 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 445.1800. PH CP-4/A10 Potholing | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 445.2040. LR CP-4/A10 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 445.2180. CATH CP-4/A10 Ext Joint Bond, Wire, & TS#13 (10 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 84 | 84 | 0 | 84
2607. CUWCD Cathodic & Pump Improvements | 445.2920. SC CP-4/A10 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 450.1800. PH CP-4/A11 Potholing - (1 Ea) | PH Potholing | 10 Pipe | 0 |  | 10 | 10 | 0 | 10
2607. CUWCD Cathodic & Pump Improvements | 450.2040. LR CP-4/A11 Landscape Repair (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8
2607. CUWCD Cathodic & Pump Improvements | 450.2180. CATH CP-4/A11 Ext Joint Bond, Wire, & TS#14 (5 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 39 | 39 | 0 | 39
2607. CUWCD Cathodic & Pump Improvements | 450.2920. SC CP-4/A11 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 455.1800. PH Potholing CP-4/A12 (1 EA) | PH Potholing | 10 Pipe | 0 |  | 5 | 5 | 0 | 5
2607. CUWCD Cathodic & Pump Improvements | 455.2040. LR CP-4/A12 Landscape Repair Sod (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 455.2180. CATH CP-4/A12 Ext Joint Bond, Wire, & TS#15 (6 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 60 | 60 | 0 | 60
2607. CUWCD Cathodic & Pump Improvements | 455.2920. SC CP-4/A12 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 460.2180. CATH CP-4/A13 Ext Joint Bond, Wire, & TS#16 (6 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 46.5 | 46.5 | 0 | 46.5
2607. CUWCD Cathodic & Pump Improvements | 460.2920. SC CP-4/A14 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 465.1800. PH CP-4/A14&15 Potholing - (3 Ea) | PH Potholing | 10 Pipe | 0 |  | 20 | 20 | 0 | 20
2607. CUWCD Cathodic & Pump Improvements | 465.2040. LR CP-4/A14&15 Landscape Repair Sod (600 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 28 | 28 | 0 | 28
2607. CUWCD Cathodic & Pump Improvements | 465.2180. CATH CP-4/A14&15 Anode Bags & Wires (15 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 303 | 303 | 0 | 303
2607. CUWCD Cathodic & Pump Improvements | 470.2180. CATH CP-4/A16 Exterior DIP Wire Joint Bond (20 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 148.5 | 148.5 | 0 | 148.5
2607. CUWCD Cathodic & Pump Improvements | 470.2920. SC CP-4/A16 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 475.2180. CATH CP-4/A17 Exterior DIP Joint Bond & TS (2 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 31.5 | 31.5 | 0 | 31.5
2607. CUWCD Cathodic & Pump Improvements | 475.2920. SC CP-4/A17 Saw Cutting & Prep | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 0 | 7.5
2607. CUWCD Cathodic & Pump Improvements | 505.1800. PH CP-4/B Pothole for TS#20-35 (16 Ea) | PH Potholing | 10 Pipe | 0 |  | 60 | 60 | 0 | 60
2607. CUWCD Cathodic & Pump Improvements | 510.2040. LR CP-4/B Landscape Repair TS#20 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 510.2180. CATH CP-4/B Test Station & Wiring #20 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 515.2040. LR CP-4/B Landscape Repair TS#21 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 515.2180. CATH CP-4/B Test Station & Wiring #21 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 520.2040. LR CP-4/B Landscape Repair TS#22 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 12 | 12 | 0 | 12
2607. CUWCD Cathodic & Pump Improvements | 520.2180. CATH CP-4/B Test Station & Wiring #22 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 43.5 | 43.5 | 0 | 43.5
2607. CUWCD Cathodic & Pump Improvements | 525.2040. LR CP-4/B Landscape Repair TS#23 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8
2607. CUWCD Cathodic & Pump Improvements | 525.2180. CATH CP-4/B Test Station & Wiring #23 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 28.5 | 28.5 | 0 | 28.5
2607. CUWCD Cathodic & Pump Improvements | 530.2040. LR CP-4/B Landscape Repair TS#24 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 530.2180. CATH CP-4/B Test Station & Wiring #24 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 535.2040. LR CP-4/B Landscape Repair TS#25 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 535.2180. CATH CP-4/B Test Station & Wiring #25 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 540.2040. LR CP-4/B Landscape Repair TS#26 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 540.2180. CATH CP-4/B Test Station & Wiring #26 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 545.2040. LR CP-4/B Landscape Repair TS#27 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 545.2180. CATH CP-4/B Test Station & Wiring #27 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 550.2040. LR CP-4/B Landscape Repair TS#28 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 550.2180. CATH CP-4/B Test Station & Wiring #28 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 555.2040. LR CP-4/B Landscape Repair TS#29 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 555.2180. CATH CP-4/B Test Station & Wiring #29 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 560.2040. LR CP-4/B Landscape Repair TS#30 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 560.2180. CATH CP-4/B Test Station & Wiring #30 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 565.2040. LR CP-4/B Landscape Repair TS#31 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 565.2180. CATH CP-4/B Test Station & Wiring #31 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 570.2040. LR CP-4/B Landscape Repair TS#32 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 570.2180. CATH CP-4/B Test Station & Wiring #32 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 575.2040. LR CP-4/B Landscape Repair TS#33 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 575.2180. CATH CP-4/B Test Station & Wiring #33 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 580.2040. LR CP-4/B Landscape Repair TS#34 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 580.2180. CATH CP-4/B Test Station & Wiring #34 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 585.2040. LR CP-4/B Landscape Repair TS#35 (100 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 4 | 4 | 0 | 4
2607. CUWCD Cathodic & Pump Improvements | 585.2180. CATH CP-4/B Test Station & Wiring #35 (1 Ea) | CATH Cathodic Protection | 10 Pipe | 0 |  | 13.5 | 13.5 | 0 | 13.5
2607. CUWCD Cathodic & Pump Improvements | 600.2040. LR Landscape Repair-External Jnts (900 SF) | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 36 | 36 | 0 | 36
2607. CUWCD Cathodic & Pump Improvements | 600.2180. CATH on Electric Isolation CP-4/C (5 Ea locations) | CATH Cathodic Protection | 10 Pipe | 0 |  | 420 | 420 | 0 | 420
2607. CUWCD Cathodic & Pump Improvements | 600.5100. WE Welding on Electrical Isolation CP-4/C (4 Ea) | W Welding | 20 Fabrication | 0 |  | 25 | 25 | 0 | 25
2607. CUWCD Cathodic & Pump Improvements | 600.6500. P Paint Repair on Electric Isolation CP-4/C (60 SF) | P Painting | 12 Finishes | 0 |  | 60 | 60 | 0 | 60
2607. CUWCD Cathodic & Pump Improvements | 650.2180. CATH Interior Joint Bond CP-4/D (664 LF) | CATH Cathodic Protection | 10 Pipe | 0 |  | 105 | 105 | 0 | 105
2607. CUWCD Cathodic & Pump Improvements | 800.1930. MC Misc Cleanup Treatment Plant & Appurtenance | MC Misc Cleanup | 12 Finishes | 0 |  | 140 | 140 | 0 | 140
2607. CUWCD Cathodic & Pump Improvements | 800.1940. PL Treatment Plant & Appurtenance | PL Punch List Work | 12 Finishes | 0 |  | 140 | 140 | 0 | 140
2607. CUWCD Cathodic & Pump Improvements | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0 | 0.6
2607. CUWCD Cathodic & Pump Improvements | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0 | 0.6
2607. CUWCD Cathodic & Pump Improvements | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0 | 0.6
2607. CUWCD Cathodic & Pump Improvements | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 3 | 0 | 3
2607. CUWCD Cathodic & Pump Improvements | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 0 | 1
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 5 |  | 51.52 | 46.52 | 0 | 46.52 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 0 |  | 46.81 | 46.81 | 0 | 46.81 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 0 |  | 43.3 | 43.3 | 0 | 43.3 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 0 |  | 64.68 | 64.68 | 0 | 64.68 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 17.29 | 17.29 | 0 | 17.29 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 200.7400. HVAC Install L&E | HVAC HVAC | 55 Mechanical | 0 |  | 495 | 495 | 0 | 495 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 0 | 1 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.4 | 0.4 | 0 | 0.4 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0.4 | 0 | 0.4 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0.4 | 0 | 0.4 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 3 | 0 | 3 | 2026-02-16 | 2026-02-16
2606. SLCo FAC126702 SMH HVAC Replacement | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 0 | 1 | 2026-02-16 | 2026-02-16
2605. Highland City Well #1&#5 Chlorine | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 12.5 | 12.5 | 0 | 12.5 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 1 |  | 1 | 0 | 0 | 0 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 5 |  | 47.83 | 42.83 | 0 | 42.83 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 0 |  | 43.46 | 43.46 | 0 | 43.46 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 0 |  | 40.21 | 40.21 | 0 | 40.21 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 6.58 |  | 60.03 | 53.45 | 0 | 53.45 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 16.1 | 16.1 | 0 | 16.1 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 40 | 40 | 0 | 40 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 0 |  | 5 | 5 | 0 | 5 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.1800. PH Potholing WH#1 - VanCon Vac Truck | PH Potholing | 10 Pipe | 0 |  | 10 | 10 | 0 | 10 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.2030. D Demo WH#1 Concrete by Hand Selective | D Demolition | 11 Earth Work | 0 |  | 27 | 27 | 0 | 27 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.2075. FG WH#1 Surface Concrete Prep - Inside & Shed Prep | FG Finish Grade | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.2080. EXS WH#1 Spot Excavation w/ Mini Ex | EXS Excavate Structure | 11 Earth Work | 0 |  | 9 | 9 | 0 | 9 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.2140. SVR WH#1 Lateral -(80 LF of 2" Poly) | SVR Services | 10 Pipe | 0 |  | 48 | 48 | 0 | 48 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.3000. CNC WH#1 Conc Finish Flatwork | CNC Concrete Work | 15 Concrete | 0 |  | 66 | 66 | 0 | 66 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.3100. CNR WH#1 Rebar VanCon Install | CNC Rebar | 15 Concrete | 0 |  | 15 | 15 | 0 | 15 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.6000. IF WH#1 Interior Finish Interior Paneling | IF Interior Finishes | 20 Fabrication | 0 |  | 20 | 20 | 0 | 20 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.6100. F WH#1 Framing Install Shed SF | F Framing | 12 Finishes | 0 |  | 30 | 30 | 0 | 30 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.7100. IMP WH#1 Piping PVC/SS/HDPE | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 122.75 | 122.75 | 0 | 122.75 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.7400. HVAC WH#1 Louvers Install | HVAC HVAC | 55 Mechanical | 0 |  | 60 | 60 | 0 | 60 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 200.7600. MEQ WH#1 Chlorination Anlyzer & Quill Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 210 | 210 | 0 | 210 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.1800. PH WH#5 Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 0 |  | 10 | 10 | 0 | 10 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.2030. D WH#5 Demo Concrete by Hand Selective | D Demolition | 11 Earth Work | 0 |  | 12 | 12 | 0 | 12 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.2075. FG WH#5 Surface Concrete Prep - Inside & Shed Prep | FG Finish Grade | 11 Earth Work | 0 |  | 8 | 8 | 0 | 8 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.2080. EXS WH#5 Spot Excavation w/ Mini Ex | EXS Excavate Structure | 11 Earth Work | 0 |  | 9 | 9 | 0 | 9 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.2140. SVR WH#5 Lateral - (80 LF of 2" Poly) | SVR Services | 10 Pipe | 0 |  | 40 | 40 | 0 | 40 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.3000. CNC WH#5 Conc Finish Flatwork | CNC Concrete Work | 15 Concrete | 0 |  | 66 | 66 | 0 | 66 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.3100. CNR WH#5 Rebar VanCon Install | CNC Rebar | 15 Concrete | 0 |  | 15 | 15 | 0 | 15 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.6000. IF WH#5 Interior Finish Interior Paneling | IF Interior Finishes | 20 Fabrication | 0 |  | 20 | 20 | 0 | 20 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.6100. F WH#5 Framing Install Shed SF | F Framing | 12 Finishes | 0 |  | 30 | 30 | 0 | 30 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.7100. IMP WH#5 Piping PVC/SS/HDPE | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 96 | 96 | 0 | 96 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.7400. HVAC WH#5 Louvers | HVAC HVAC | 55 Mechanical | 0 |  | 60 | 60 | 0 | 60 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 300.7600. MEQ WH#5 Chlorination Anlyzer & Quill Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 210 | 210 | 0 | 210 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 800.1930. MC Misc Cleanup Both Well House | MC Misc Cleanup | 12 Finishes | 0 |  | 80 | 80 | 0 | 80 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 800.1940. PL Punchlist Both Well House | PL Punch List Work | 12 Finishes | 0 |  | 40 | 40 | 0 | 40 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0 | 0.6 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0 | 0.6 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0 | 0.6 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 3 | 0 | 3 | 2026-02-06 | 2026-05-15
2605. Highland City Well #1&#5 Chlorine | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 0 | 1 | 2026-02-06 | 2026-05-15
2604. Murray 900 East Storm Drain Phase 2 | 100.1040. PR Public Relations VanCon (coordinate with City P.I.) L&E | PR Public Relations | 60 Operations (PM/PE) | 0 |  | 200 | 200 | 0 | 200 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 10 | 10 | 0 | 10 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1510. S Survey - Vancon | S Surveying | 45 Survey | 0 |  | 156 | 156 | 0 | 156 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 2 |  | 289.85 | 287.85 | 0 | 287.85 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 12.08 |  | 262.89 | 250.81 | 0 | 250.81 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 2 |  | 242.82 | 240.82 | 0 | 240.82 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 0 |  | 365.08 | 365.08 | 0 | 365.08 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 94.11 | 94.11 | 0 | 94.11 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 0 | 1 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 200 | 200 | 0 | 200 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 150.2750. H Hauling Entire Job ( per/LF) | H Hauling | 40 Drivers | 0 |  | 1327.94 | 1327.94 | 0 | 1327.94 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 150.2760. HO Haul Off Single Side Dump (Units/LF) | HO Haul Off | 40 Drivers | 0 |  | 1705.43 | 1705.43 | 0 | 1705.43 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 151.2760. HO Haul Off Millings Single Side Dump (830 CY) | HO Haul Off | 40 Drivers | 0 |  | 115.28 | 115.28 | 0 | 115.28 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 152.2760. HO Haul Off Concrete Single Side Dump (combine with curb & g | HO Haul Off | 40 Drivers | 0 |  | 11.37 | 11.37 | 0 | 11.37 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.1600. TC Traffic Control Plans | TC Traffic Control | 30 Traffic Control | 0 |  | 464 | 464 | 0 | 464 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.1610. TC Temp Conc Barrier Install | TC Concrete & Water Barrier | 30 Traffic Control | 0 |  | 40 | 40 | 0 | 40 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.1650. SB Signage Install Post w/ Sign | SB Signage | 12 Finishes | 0 |  | 20 | 20 | 0 | 20 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.1800. PH Potholing - VanCon Vac Truck (69 ea) | PH Potholing | 10 Pipe | 0 |  | 184 | 184 | 0 | 184 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.2065. SFC SWPPP Sweeper Truck (Dust Control) L&E | SFC SWPPP | 11 Earth Work | 0 |  | 326 | 326 | 0 | 326 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.2080. EXS Trench/Road Plate Install for Traffic (108EA) | EXS Excavate Structure | 11 Earth Work | 0 |  | 115.2 | 115.2 | 0 | 115.2 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.2210. 42" RCP Mainline Pipe - ST 2+00-26+00 (2388LF) | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 2401.64 | 2401.64 | 0 | 2401.64 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.2240. PCS 6' Manhole/Cleanout Box (9EA) | PCS Precast Structures | 10 Pipe | 0 |  | 411.01 | 411.01 | 0 | 411.01 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 200.2600. DW Dewatering SETUP Equipment/Frac L&E | DW Dewatering | 10 Pipe | 0 |  | 47 | 47 | 0 | 47 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 210.1800. PH City Requested Major pothole Per Location - (1 EA) | PH Potholing | 10 Pipe | 0 |  | 2.66 | 2.66 | 0 | 2.66 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 210.2210. 18" RCP Pipe - ST 4+68 (30LF) | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 50.63 | 50.63 | 0 | 50.63 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 220.2080. D Demo Existing SD -5700 S. (53LF) | EXS Excavate Structure | 11 Earth Work | 0 |  | 45.9 | 45.9 | 0 | 45.9 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 220.2220. ADS 15" Drainage Pipe - 5700 S. (71 LF) | ADS Pipe | 10 Pipe | 0 |  | 126.49 | 126.49 | 0 | 126.49 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 220.2240. PCS 3' Cleanout / Catch Basin (4EA) | PCS Precast Structures | 10 Pipe | 0 |  | 108.5 | 108.5 | 0 | 108.5 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 230.2210. 30" RCP Pipe - ST 26+26 (65LF) | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 126.37 | 126.37 | 0 | 126.37 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 230.2240. PCS 4x8 Combo Box (1EA) | PCS Precast Structures | 10 Pipe | 0 |  | 56.5 | 56.5 | 0 | 56.5 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 240.2210. 36" RCP Mainline Pipe - ST 26+00-33+92 (748LF) | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 895.21 | 895.21 | 0 | 895.21 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 240.2240. PCS 5' Manhole/Cleanout Box (3EA) | PCS Precast Structures | 10 Pipe | 0 |  | 104.31 | 104.31 | 0 | 104.31 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 250.2600. DW Dewatering Maintenance (90days) | DW Dewatering | 10 Pipe | 0 |  | 270 | 270 | 0 | 270 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 300.2075. FG Roadbase prep for Concrete (428 SF) | FG Finish Grade | 11 Earth Work | 0 |  | 63.44 | 63.44 | 0 | 63.44 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 300.2080. D Demo Concrete Curb (685 LF) | EXS Excavate Structure | 11 Earth Work | 0 |  | 41.1 | 41.1 | 0 | 41.1 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 300.3000. CNC M2 Median Curb | CNC Concrete Work | 15 Concrete | 0 |  | 162.27 | 162.27 | 0 | 162.27 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 300.7900. ELC Dry Utilities | ELC Electrical | 10 Pipe | 0 |  | 40 | 40 | 0 | 40 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 310.2080. D Demo Concrete Flatwork (108 SF) | EXS Excavate Structure | 11 Earth Work | 0 |  | 3.24 | 3.24 | 0 | 3.24 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 350.3000. CNC Monuments & Collars (73ea) | CNC Concrete Work | 15 Concrete | 0 |  | 66.68 | 66.68 | 0 | 66.68 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 400.2080. D Demo and Haul Off of Roadway Concrete | EXS Excavate Structure | 11 Earth Work | 0 |  | 60 | 60 | 0 | 60 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 400.2760. HO Haul Off Concrete Paving (2545 SY) | HO Haul Off | 40 Drivers | 0 |  | 50 | 50 | 0 | 50 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 400.2910. MP Road Mill Wirtgen 7'wide T-Patch (36000SF) | MP Milling/Pulverize | 11 Earth Work | 0 |  | 65 | 65 | 0 | 65 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 400.3000. CNC Manhole/CB Collar (14ea) | CNC Concrete Work | 15 Concrete | 0 |  | 112 | 112 | 0 | 112 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 800.1930. MC End of job Cleanup Storm Drain | MC Misc Cleanup | 12 Finishes | 0 |  | 120 | 120 | 0 | 120 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 800.1940. PL Punchlist - End of Job for Storm Drain | PL Punch List Work | 12 Finishes | 0 |  | 120 | 120 | 0 | 120 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 0 | 0 | 0 | 2026-02-02 | 2026-12-31
2604. Murray 900 East Storm Drain Phase 2 | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 0 | 1 | 2026-02-02 | 2026-12-31
2603. Highland City Mitchell Hollow Trail | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 10 | 10 | 10 | 0 | 2026-02-01 | 2026-12-16 |  | 10 |  |  | 10
2603. Highland City Mitchell Hollow Trail | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 10 | 10 | 10 | 0 | 2026-02-01 | 2026-12-16 |  | 10 |  |  | 10
2603. Highland City Mitchell Hollow Trail | 100.1500. VIS Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 11 | 11 | 11 | 0 | 2026-02-01 | 2026-12-16 |  | 11 |  |  | 11
2603. Highland City Mitchell Hollow Trail | 100.1510. S Surveying | S Surveying | 45 Survey | 10.13 |  | 200 | 189.87 | 200 | -10.13 | 2026-02-01 | 2026-12-16 | 50 | 100 | 50 |  | 200
2603. Highland City Mitchell Hollow Trail | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 24 |  | 186.85 | 162.85 | 186.8 | -23.95 | 2026-02-01 | 2026-12-16 | 60 | 60 | 60 | 6.8 | 186.8
2603. Highland City Mitchell Hollow Trail | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 17 |  | 169.5 | 152.5 | 169.5 | -17 | 2026-02-01 | 2026-12-16 | 60 | 60 | 30 | 19.5 | 169.5
2603. Highland City Mitchell Hollow Trail | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 3.23 |  | 156.59 | 153.36 | 156.6 | -3.24 | 2026-02-01 | 2026-12-16 | 60 | 90 | 6.6 |  | 156.6
2603. Highland City Mitchell Hollow Trail | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 5 |  | 235.25 | 230.25 | 235.3 | -5.05 | 2026-02-01 | 2026-12-16 | 60 | 100 | 70 | 5.3 | 235.3
2603. Highland City Mitchell Hollow Trail | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 60.91 | 60.91 | 60.9 | 0.01 | 2026-02-01 | 2026-12-16 | 10 | 30 | 20.9 |  | 60.9
2603. Highland City Mitchell Hollow Trail | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2026-02-01 | 2026-12-16 | 1 |  |  |  | 1
2603. Highland City Mitchell Hollow Trail | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2026-02-01 | 2026-12-16 | 1 |  |  |  | 1
2603. Highland City Mitchell Hollow Trail | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 150 | 150 | 150 | 0 | 2026-02-01 | 2026-12-16 | 10 | 60 | 60 | 20 | 150
2603. Highland City Mitchell Hollow Trail | 150.2750. H Hauling - Fill Borrow (3040CY) | H Hauling | 40 Drivers | 0 |  | 283.33 | 283.33 | 283.3 | 0.03 | 2026-02-01 | 2026-12-16 | 20 | 120 | 120 | 23.3 | 283.3
2603. Highland City Mitchell Hollow Trail | 150.2760. HO Haul Off RG Cut/Exc (4872 CY) | HO Haul Off | 40 Drivers | 0 |  | 304.5 | 304.5 | 304.5 | 0 | 2026-02-01 | 2026-12-16 | 50 | 200 | 54.5 |  | 304.5
2603. Highland City Mitchell Hollow Trail | 151.2750. H Hauling - 12" Layer AIA Granular Borrow (2555 CY) | H Hauling | 40 Drivers | 0 |  | 238.1 | 238.1 | 238.1 | 0 | 2026-02-01 | 2026-12-16 | 20 | 120 | 98.1 |  | 238.1
2603. Highland City Mitchell Hollow Trail | 151.2760. HO Haul Off Grubbings | HO Haul Off | 40 Drivers | 0 |  | 102.09 | 102.09 | 102.1 | -0.01 | 2026-02-01 | 2026-12-16 | 50 | 50 | 2.1 |  | 102.1
2603. Highland City Mitchell Hollow Trail | 152.2750. H Hauling - Rd Base | H Hauling | 40 Drivers | 0 |  | 1.19 | 1.19 | 1.2 | -0.01 | 2026-02-01 | 2026-12-16 |  |  | 1.2 |  | 1.2
2603. Highland City Mitchell Hollow Trail | 152.2760. HO Haul Off - MSE Walls | HO Haul Off | 40 Drivers | 0 |  | 61.66 | 61.66 | 61.7 | -0.04 | 2026-02-01 | 2026-12-16 |  | 61.7 |  |  | 61.7
2603. Highland City Mitchell Hollow Trail | 153.2760. HO Haul Off Asphalt | HO Haul Off | 40 Drivers | 0 |  | 10.42 | 10.42 | 10.4 | 0.02 | 2026-02-01 | 2026-12-16 |  | 10.4 |  |  | 10.4
2603. Highland City Mitchell Hollow Trail | 200.1600. TC Traffic Control Maintenance Easy | TC Traffic Control | 30 Traffic Control | 0 |  | 50 | 50 | 50 | 0 | 2026-02-01 | 2026-12-16 | 25 | 25 |  |  | 50
2603. Highland City Mitchell Hollow Trail | 200.2020. CG Remove Vegetaton Excavator | CG Clearing/Grubbing | 11 Earth Work | 0 |  | 44 | 44 | 44 | 0 | 2026-02-01 | 2026-12-16 |  | 44 |  |  | 44
2603. Highland City Mitchell Hollow Trail | 200.2030. D Demo Asphalt | D Demolition | 11 Earth Work | 0 |  | 17.76 | 17.76 | 17.8 | -0.04 | 2026-02-01 | 2026-12-16 |  | 17.8 |  |  | 17.8
2603. Highland City Mitchell Hollow Trail | 200.2065. SFC SWPPP Sweeper Truck (Dust Control) | SFC SWPPP | 11 Earth Work | 0 |  | 290 | 290 | 290 | 0 | 2026-02-01 | 2026-12-16 |  | 150 | 140 |  | 290
2603. Highland City Mitchell Hollow Trail | 200.2070. RGC Roadway/Trail Cut & Export (Excavator Only) | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 487.2 | 487.2 | 487.2 | 0 | 2026-02-01 | 2026-12-16 |  | 200 | 200 | 87.2 | 487.2
2603. Highland City Mitchell Hollow Trail | 200.2075. FG Fill - Granular Borrow up to Sub Base (3040 CY) | FG Finish Grade | 11 Earth Work | 0 |  | 350 | 350 | 350 | 0 | 2026-02-01 | 2026-12-16 |  | 150 | 150 | 50 | 350
2603. Highland City Mitchell Hollow Trail | 210.2030. D Demo Retaining Wall | D Demolition | 11 Earth Work | 0 |  | 30 | 30 | 30 | 0 | 2026-02-01 | 2026-12-16 |  | 30 |  |  | 30
2603. Highland City Mitchell Hollow Trail | 210.2075. FG Granular Borrow - 12" Sub Base Layer (2555 CY) | FG Finish Grade | 11 Earth Work | 0 |  | 315 | 315 | 315 | 0 | 2026-02-01 | 2026-12-16 |  | 150 | 150 | 15 | 315
2603. Highland City Mitchell Hollow Trail | 220.2075. FG Prep Pedestrian Ramp (300 SF) | FG Finish Grade | 11 Earth Work | 0 |  | 50 | 50 | 50 | 0 | 2026-02-01 | 2026-12-16 |  |  | 50 |  | 50
2603. Highland City Mitchell Hollow Trail | 300.2050. RW MSE Retaining Wall Excavation (255 LF) | RW Retaining Walls | 11 Earth Work | 0 |  | 8.32 | 8.32 | 8.3 | 0.02 | 2026-02-01 | 2026-12-16 |  | 8.3 |  |  | 8.3
2603. Highland City Mitchell Hollow Trail | 300.7850. BRG Boardwalk/Stair Base Beams/Girders | BRG Bridges | 20 Fabrication | 0 |  | 365.72 | 365.72 | 0 | 365.72 | 2026-02-01 | 2026-12-16
2603. Highland City Mitchell Hollow Trail | 310.2050. RW Modular Bock Wall (450 LF) | RW Retaining Walls | 11 Earth Work | 0 |  | 27.2 | 27.2 | 27.2 | 0 | 2026-02-01 | 2026-12-16 |  | 27.2 |  |  | 27.2
2603. Highland City Mitchell Hollow Trail | 800.1930. MC Msc Cleanup Road/Dirt Work | MC Misc Cleanup | 12 Finishes | 0 |  | 80 | 80 | 80 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 80 | 80
2603. Highland City Mitchell Hollow Trail | 800.1940. PL Road/Dirt Work | PL Punch List Work | 12 Finishes | 0 |  | 90 | 90 | 90 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 90 | 90
2603. Highland City Mitchell Hollow Trail | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 0.6 | 0.6
2603. Highland City Mitchell Hollow Trail | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 0.6 | 0.6
2603. Highland City Mitchell Hollow Trail | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 0.6 | 0.6
2603. Highland City Mitchell Hollow Trail | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 3 | 3 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 3 | 3
2603. Highland City Mitchell Hollow Trail | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 1 | 0 | 2026-02-01 | 2026-12-16 |  |  |  | 1 | 1
2602. JVWCD Rosecrest WSP Pipeline | 100.1106. TF Setup Temp Trailer | TF Setup Temp Trailer | 12 Finishes | 0 |  | 10 | 10 | 10 | 0 | 2026-02-09 | 2028-05-15 |  | 10 |  |  | 10
2602. JVWCD Rosecrest WSP Pipeline | 100.1107. TF Trailer Pad Install | TF TF Trailer Pad Install | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2026-02-09 | 2028-05-15 |  | 30 |  |  | 30
2602. JVWCD Rosecrest WSP Pipeline | 100.1108. TF Setup Staging Area Laydown Yard | TF Setup Staging Area Laydown Yard | 12 Finishes | 8.73 |  | 4 | -4.73 | 4 | -8.73 | 2026-02-09 | 2028-05-15 |  | 4 |  |  | 4
2602. JVWCD Rosecrest WSP Pipeline | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 45 | 45 | 45 | 0 | 2026-02-09 | 2028-05-15 |  | 10 | 10 | 10 | 30 | 10 | 5 |  |  | 15
2602. JVWCD Rosecrest WSP Pipeline | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 25 | 25 | 25 | 0 | 2026-02-09 | 2028-05-15 |  | 15 |  |  | 15 |  | 10 |  |  | 10
2602. JVWCD Rosecrest WSP Pipeline | 100.1500. VIS Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2026-02-09 | 2028-05-15 |  | 1 |  |  | 1
2602. JVWCD Rosecrest WSP Pipeline | 100.1515. S Survey - Vancon | S Drone/Lidar Requirements | 45 Survey | 27 |  | 650 | 623 | 650 | -27 | 2026-02-09 | 2028-05-15 |  | 100 | 200 | 150 | 450 | 100 | 100 |  |  | 200
2602. JVWCD Rosecrest WSP Pipeline | 100.1650. SB Signage Install Post w/ Sign | SB Signage | 12 Finishes | 0 |  | 20 | 20 | 20 | 0 | 2026-02-09 | 2028-05-15 |  | 20 |  |  | 20
2602. JVWCD Rosecrest WSP Pipeline | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 7 |  | 1568.06 | 1561.06 | 1568.1 | -7.04 | 2026-02-09 | 2028-05-15 |  | 250 | 300 | 300 | 850 | 300 | 300 | 118.1 |  | 718.1
2602. JVWCD Rosecrest WSP Pipeline | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 11 |  | 1421.78 | 1410.78 | 1421.8 | -11.02 | 2026-02-09 | 2028-05-15 |  | 250 | 300 | 300 | 850 | 300 | 250 | 21.8 |  | 571.8
2602. JVWCD Rosecrest WSP Pipeline | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 2.5 |  | 1312.89 | 1310.39 | 1312.9 | -2.51 | 2026-02-09 | 2028-05-15 |  | 150 | 300 | 300 | 750 | 300 | 250 | 12.9 |  | 562.9
2602. JVWCD Rosecrest WSP Pipeline | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 0 |  | 1996.14 | 1996.14 | 1996.1 | 0.04 | 2026-02-09 | 2028-05-15 |  | 250 | 500 | 500 | 1250 | 400 | 300 | 46.1 |  | 746.1
2602. JVWCD Rosecrest WSP Pipeline | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 506.15 | 506.15 | 506.1 | 0.05 | 2026-02-09 | 2028-05-15 |  | 50 | 100 | 100 | 250 | 100 | 100 | 56.1 |  | 256.1
2602. JVWCD Rosecrest WSP Pipeline | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 50 | 50 | 50 | 0 | 2026-02-09 | 2028-05-15 |  | 10 | 10 | 10 | 30 | 10 | 10 |  |  | 20
2602. JVWCD Rosecrest WSP Pipeline | 100.1711. FS Pre-Construction Video | FS Pre-Construction Video | 60 Operations (PM/PE) | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 |  | 40 |  |  | 40
2602. JVWCD Rosecrest WSP Pipeline | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 500 | 500 | 500 | 0 | 2026-02-09 | 2028-05-15 |  | 100 | 100 | 100 | 300 | 100 | 50 | 50 |  | 200
2602. JVWCD Rosecrest WSP Pipeline | 150.2750. H Pipeline Hauling Single Side Dump | H Hauling | 40 Drivers | 0 |  | 259.86 | 259.86 | 259.9 | -0.04 | 2026-02-09 | 2028-05-15 |  |  | 75 | 75 | 150 | 75 | 34.9 |  |  | 109.9
2602. JVWCD Rosecrest WSP Pipeline | 150.2760. HO Pipeline Haul Off Single Side Dump | HO Haul Off | 40 Drivers | 0 |  | 291.7 | 291.7 | 291.7 | 0 | 2026-02-09 | 2028-05-15 |  |  | 75 | 75 | 150 | 75 | 66.7 |  |  | 141.7
2602. JVWCD Rosecrest WSP Pipeline | 155.2750. H Roadway Hauling Single Side Dump | H Hauling | 40 Drivers | 0 |  | 0.24 | 0.24 | 0.2 | 0.04 | 2026-02-09 | 2028-05-15 |  |  | 0.2 |  | 0.2
2602. JVWCD Rosecrest WSP Pipeline | 155.2760. HO RoadWay Haul Off Single Side Dump | HO Haul Off | 40 Drivers | 0 |  | 4.5 | 4.5 | 4.5 | 0 | 2026-02-09 | 2028-05-15 |  |  | 4.5 |  | 4.5
2602. JVWCD Rosecrest WSP Pipeline | 200.1600. TC Pipeline Traffic Control L&E | TC Traffic Control | 30 Traffic Control | 0 |  | 750 | 750 | 750 | 0 | 2026-02-09 | 2028-05-15 |  | 50 | 200 | 200 | 450 | 150 | 150 |  |  | 300
2602. JVWCD Rosecrest WSP Pipeline | 200.2065. SFC SWPPP Sweeper Truck (Dust Control) | SFC SWPPP | 11 Earth Work | 0 |  | 420 | 420 | 420 | 0 | 2026-02-09 | 2028-05-15 |  |  | 75 | 150 | 225 | 150 | 45 |  |  | 195
2602. JVWCD Rosecrest WSP Pipeline | 200.2160. WSP Extras: Unloading Pipe | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 277.32 | 277.32 | 277.3 | 0.02 | 2026-02-09 | 2028-05-15 |  | 75 | 202.3 |  | 277.3
2602. JVWCD Rosecrest WSP Pipeline | 205.2160. WSP Extras: Fill Sand Bags | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 216.68 | 216.68 | 216.7 | -0.02 | 2026-02-09 | 2028-05-15 |  | 50 | 50 | 50 | 150 | 66.7 |  |  |  | 66.7
2602. JVWCD Rosecrest WSP Pipeline | 210.2030. D Demo Pipeline along PP-03 - PP-05 | D Demolition | 11 Earth Work | 0 |  | 7.22 | 7.22 | 7.2 | 0.02 | 2026-02-09 | 2028-05-15 |  |  | 7.2 |  | 7.2
2602. JVWCD Rosecrest WSP Pipeline | 210.2160. WSP 24" WPL along PP-03 - PP-05 | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 3307.36 | 3307.36 | 3307.4 | -0.04 | 2026-02-09 | 2028-05-15 |  | 750 | 2557.4 |  | 3307.4
2602. JVWCD Rosecrest WSP Pipeline | 210.2750. H Hauling Single Side Dump PP-03 - PP-05 | H Hauling | 40 Drivers | 0 |  | 431.9 | 431.9 | 431.9 | 0 | 2026-02-09 | 2028-05-15 |  | 100 | 331.9 |  | 431.9
2602. JVWCD Rosecrest WSP Pipeline | 210.2760. HO Haul Off Single Side Dump PP-03 - PP-05 | HO Haul Off | 40 Drivers | 0 |  | 716.8 | 716.8 | 716.8 | 0 | 2026-02-09 | 2028-05-15 |  | 100 | 616.8 |  | 716.8
2602. JVWCD Rosecrest WSP Pipeline | 220.2160. WSP 24" WPL along PP-01 - PP-02 | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 2791.56 | 2791.56 | 2791.6 | -0.04 | 2026-02-09 | 2028-05-15 |  |  | 750 | 1500 | 2250 | 541.6 |  |  |  | 541.6
2602. JVWCD Rosecrest WSP Pipeline | 220.2750. H Hauling Single Side Dump PP-01 - PP-02 | H Hauling | 40 Drivers | 0 |  | 246.9 | 246.9 | 246.9 | 0 | 2026-02-09 | 2028-05-15 |  |  | 50 | 150 | 200 | 46.9 |  |  |  | 46.9
2602. JVWCD Rosecrest WSP Pipeline | 220.2760. HO Haul Off Single Side Dump PP-01 - PP-02 | HO Haul Off | 40 Drivers | 0 |  | 411.9 | 411.9 | 411.9 | 0 | 2026-02-09 | 2028-05-15 |  |  | 50 | 250 | 300 | 111.9 |  |  |  | 111.9
2602. JVWCD Rosecrest WSP Pipeline | 230.2160. WSP 24" WPL along PP-06 - PP-11 | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 4204.11 | 4204.11 | 4204.1 | 0.01 | 2026-02-09 | 2028-05-15 | [5 empty] | 1500 | 2000 | 704.1 |  | 4204.1
2602. JVWCD Rosecrest WSP Pipeline | 230.2750. H Hauling Single Side Dump PP-06 - PP-11 | H Hauling | 40 Drivers | 0 |  | 528.09 | 528.09 | 528.1 | -0.01 | 2026-02-09 | 2028-05-15 | [5 empty] | 150 | 200 | 178.1 |  | 528.1
2602. JVWCD Rosecrest WSP Pipeline | 230.2760. HO Haul Off Single Side Dump PP-06 - PP-11 | HO Haul Off | 40 Drivers | 0 |  | 960.6 | 960.6 | 960.6 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 400 | 400 | 160.6 |  | 960.6
2602. JVWCD Rosecrest WSP Pipeline | 235.5100. WE Double Lap Welding Joints - 24" Pipeline (220 Joints) | W Welding | 20 Fabrication | 0 |  | 795.14 | 795.14 | 795.1 | 0.04 | 2026-02-09 | 2028-05-15 |  | 50 | 200 | 250 | 500 | 200 | 95.1 |  |  | 295.1
2602. JVWCD Rosecrest WSP Pipeline | 240.2240. PCS 6" Air/Vac Emmeline Dr Sta 109+17 | PCS Precast Structures | 10 Pipe | 0 |  | 80.06 | 80.06 | 80.1 | -0.04 | 2026-02-09 | 2028-05-15 |  |  |  | 40 | 40 | 40.1 |  |  |  | 40.1
2602. JVWCD Rosecrest WSP Pipeline | 240.2750. H Hauling Single Side Dump Emmeline Dr Sta 109+17 | H Hauling | 40 Drivers | 0 |  | 2.38 | 2.38 | 2.4 | -0.02 | 2026-02-09 | 2028-05-15 |  |  |  | 2.4 | 2.4
2602. JVWCD Rosecrest WSP Pipeline | 240.2760. HO Haul Off Single Side Dump Emmeline Dr Sta 109+17 | HO Haul Off | 40 Drivers | 0 |  | 3 | 3 | 3 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 3 | 3
2602. JVWCD Rosecrest WSP Pipeline | 240.3000. CNC Air/Vac Concrete Emmeline Dr Sta 109+17 | CNC Concrete Work | 15 Concrete | 0 |  | 86.01 | 86.01 | 86 | 0.01 | 2026-02-09 | 2028-05-15 |  |  |  | 45 | 45 | 41 |  |  |  | 41
2602. JVWCD Rosecrest WSP Pipeline | 240.5000. MET Air Vents Air/Vac Emmeline Dr Sta 109+17 | MET Metals | 20 Fabrication | 0 |  | 15 | 15 | 15 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 15 |  |  |  | 15
2602. JVWCD Rosecrest WSP Pipeline | 240.7100. IMP Piping Air/Vac Emmeline Dr Sta 109+17 | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 40 |  |  |  | 40
2602. JVWCD Rosecrest WSP Pipeline | 245.2130. SVR 2" Air/Vac Sta 126+35 | PVC Pipe | 10 Pipe | 0 |  | 34.56 | 34.56 | 34.6 | -0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 34.6 |  |  |  | 34.6
2602. JVWCD Rosecrest WSP Pipeline | 245.2240. PCS 2" Air/Vac Sta 126+35 | PCS Precast Structures | 10 Pipe | 0 |  | 19.32 | 19.32 | 19.3 | 0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 19.3 |  |  |  | 19.3
2602. JVWCD Rosecrest WSP Pipeline | 245.2750. H Hauling Single Side Dump 2" Air/Vac Sta 126+35 | H Hauling | 40 Drivers | 0 |  | 2.02 | 2.02 | 2 | 0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 2 |  |  |  | 2
2602. JVWCD Rosecrest WSP Pipeline | 245.2760. HO Haul Off Single Side Dump 2" Air/Vac Sta 126+35 | HO Haul Off | 40 Drivers | 0 |  | 2.5 | 2.5 | 2.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 2.5 |  |  |  | 2.5
2602. JVWCD Rosecrest WSP Pipeline | 245.3000. CNC Conc 2" Air/Vac Sta 126+35 | CNC Concrete Work | 15 Concrete | 0 |  | 48 | 48 | 48 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 48 | 48
2602. JVWCD Rosecrest WSP Pipeline | 245.5000. MET Air Vents 2" Air/Vac Sta 126+35 | MET Metals | 20 Fabrication | 0 |  | 7.5 | 7.5 | 7.5 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 7.5 | 7.5
2602. JVWCD Rosecrest WSP Pipeline | 245.5400. HAT Hatch Vault Install 2" Air/Vac Sta 126+35 | HAT Hatch/Skylights | 12 Finishes | 0 |  | 12 | 12 | 12 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 12 | 12
2602. JVWCD Rosecrest WSP Pipeline | 245.6200. IN Insulation Vault Ceiling/Walls 2" Air/Vac Sta 126+35 | IN Insulation | 12 Finishes | 0 |  | 3.6 | 3.6 | 3.6 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 3.6 | 3.6
2602. JVWCD Rosecrest WSP Pipeline | 245.7100. IMP Piping 2" Air/Vac Sta 126+35 | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 40 | 40
2602. JVWCD Rosecrest WSP Pipeline | 250.2130. PVC 2" Air/Vac Sta 175+25 | PVC Pipe | 10 Pipe | 0 |  | 33.39 | 33.39 | 33.4 | -0.01 | 2026-02-09 | 2028-05-15 |  |  |  | 33.4 | 33.4
2602. JVWCD Rosecrest WSP Pipeline | 250.2140. SVR 2" Air/Vac Sta 175+25 | SVR Services | 10 Pipe | 0 |  | 3.32 | 3.32 | 3.3 | 0.02 | 2026-02-09 | 2028-05-15 |  |  |  | 3.3 | 3.3
2602. JVWCD Rosecrest WSP Pipeline | 250.2240. PCS 2" Air/Vac Sta 175+25 | PCS Precast Structures | 10 Pipe | 0 |  | 14 | 14 | 14 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 14 | 14
2602. JVWCD Rosecrest WSP Pipeline | 250.2750. H Hauling Single Side Dump 2" Air/Vac Sta 175+25 | H Hauling | 40 Drivers | 0 |  | 1.85 | 1.85 | 1.9 | -0.05 | 2026-02-09 | 2028-05-15 |  |  |  | 1.9 | 1.9
2602. JVWCD Rosecrest WSP Pipeline | 250.2760. HO Haul Off Single Side Dump 2" Air/Vac Sta 175+25 | HO Haul Off | 40 Drivers | 0 |  | 2.3 | 2.3 | 2.3 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 2.3 | 2.3
2602. JVWCD Rosecrest WSP Pipeline | 250.5000. MET Air Vents on 2" Air/Vac Sta 175+25 | MET Metals | 20 Fabrication | 0 |  | 3.75 | 3.75 | 3.8 | -0.05 | 2026-02-09 | 2028-05-15 |  |  |  | 3.8 | 3.8
2602. JVWCD Rosecrest WSP Pipeline | 250.5400. HAT Hatch Vault Install 2" Air/Vac Sta 175+25 | HAT Hatch/Skylights | 12 Finishes | 0 |  | 12 | 12 | 12 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 12 | 12
2602. JVWCD Rosecrest WSP Pipeline | 250.6200. IN Insulation Vault 2" Air/Vac Sta 175+25 | IN Insulation | 12 Finishes | 0 |  | 3.6 | 3.6 | 3.6 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 3.6 | 3.6
2602. JVWCD Rosecrest WSP Pipeline | 250.7100. IMP Piping 2" Air/Vac Sta 175+25 | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 40 | 40
2602. JVWCD Rosecrest WSP Pipeline | 260.2130. PVC Piping to Blowoff Sta 108+00 Emmeline Drive | PVC Pipe | 10 Pipe | 0 |  | 77.84 | 77.84 | 77.8 | 0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 77.8 |  |  |  | 77.8
2602. JVWCD Rosecrest WSP Pipeline | 260.2210. RCP Piping to Blowoff Sta 108+00 Emmeline Drive | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 77.5 | 77.5 | 77.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 77.5 |  |  |  | 77.5
2602. JVWCD Rosecrest WSP Pipeline | 260.2240. PCS Precast for Blowoff Sta 108+00 Emmeline Drive | PCS Precast Structures | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 40 |  |  |  | 40
2602. JVWCD Rosecrest WSP Pipeline | 260.2750. H Hauling Single Side Dump Blowoff Sta 108+00 Emmeline Drive | H Hauling | 40 Drivers | 0 |  | 12.62 | 12.62 | 12.6 | 0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 12.6 |  |  |  | 12.6
2602. JVWCD Rosecrest WSP Pipeline | 260.2760. HO Haul Off Single Side Dump Blowoff Sta 108+00 Emmeline Dri | HO Haul Off | 40 Drivers | 0 |  | 6.5 | 6.5 | 6.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 6.5 |  |  |  | 6.5
2602. JVWCD Rosecrest WSP Pipeline | 260.3000. CNC Conc for Blowoff Sta 108+00 Emmeline Drive | CNC Concrete Work | 15 Concrete | 0 |  | 13.5 | 13.5 | 13.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 13.5 |  |  |  | 13.5
2602. JVWCD Rosecrest WSP Pipeline | 260.7100. IMP piping at Blowoff Sta 108+00 Emmeline Drive | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 30 | 30 | 30 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 30 |  |  |  | 30
2602. JVWCD Rosecrest WSP Pipeline | 265.2130. PVC piping to Blowoff Sta 145+00 Emmeline Drive | PVC Pipe | 10 Pipe | 0 |  | 92.6 | 92.6 | 92.6 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 92.6 |  |  |  | 92.6
2602. JVWCD Rosecrest WSP Pipeline | 265.2210. RCP piping for Blowoff Sta 145+00 Emmeline Drive | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 60.64 | 60.64 | 60.6 | 0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 60.6 |  |  |  | 60.6
2602. JVWCD Rosecrest WSP Pipeline | 265.2240. PCS Precast for Blowoff Sta 145+00 Emmeline Drive | PCS Precast Structures | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 40 |  |  |  | 40
2602. JVWCD Rosecrest WSP Pipeline | 265.2750. H Hauling Single Side Dump Blowoff Sta 145+00 | H Hauling | 40 Drivers | 0 |  | 18.57 | 18.57 | 18.6 | -0.03 | 2026-02-09 | 2028-05-15 | [5 empty] | 18.6 |  |  |  | 18.6
2602. JVWCD Rosecrest WSP Pipeline | 265.2760. HO Haul Off Single Side Dump Blowoff Sta 145+00 | HO Haul Off | 40 Drivers | 0 |  | 21.4 | 21.4 | 21.4 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 21.4 |  |  |  | 21.4
2602. JVWCD Rosecrest WSP Pipeline | 265.3000. CNC Conc for Blowoff Sta 145+00 Rosecrest Drive | CNC Concrete Work | 15 Concrete | 0 |  | 13.5 | 13.5 | 13.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 13.5 |  |  |  | 13.5
2602. JVWCD Rosecrest WSP Pipeline | 265.7100. IMP Piping at Blowoff Sta 145+00 Rosecrest Drive | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 30 | 30 | 30 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 30 |  |  |  | 30
2602. JVWCD Rosecrest WSP Pipeline | 270.2120. DIP Piping for 16" Waterline Loop - 6 Loops | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 377.88 | 377.88 | 377.9 | -0.02 | 2026-02-09 | 2028-05-15 |  | 150 | 100 | 127.9 | 377.9
2602. JVWCD Rosecrest WSP Pipeline | 270.2750. H Hauling Single Side Dump for16" Waterline Loop - 6 Loops | H Hauling | 40 Drivers | 0 |  | 14.52 | 14.52 | 14.5 | 0.02 | 2026-02-09 | 2028-05-15 |  |  | 14.5 |  | 14.5
2602. JVWCD Rosecrest WSP Pipeline | 270.2760. HO Haul Off Single Side Dump for 16" Waterline Loop -6 Loops | HO Haul Off | 40 Drivers | 0 |  | 22.2 | 22.2 | 22.2 | 0 | 2026-02-09 | 2028-05-15 |  |  | 22.2 |  | 22.2
2602. JVWCD Rosecrest WSP Pipeline | 275.2120. PVC for 20" PVC Waterline Loop - 1 loop | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 94.8 | 94.8 | 94.8 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 94.8 | 94.8
2602. JVWCD Rosecrest WSP Pipeline | 275.2750. H Hauling Single Side Dump 20" PVC Waterline Loop | H Hauling | 40 Drivers | 0 |  | 3.1 | 3.1 | 3.1 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 3.1 | 3.1
2602. JVWCD Rosecrest WSP Pipeline | 275.2760. HO Haul Off Single Side Dump 20" PVC Waterline Loop | HO Haul Off | 40 Drivers | 0 |  | 4.9 | 4.9 | 4.9 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 4.9 | 4.9
2602. JVWCD Rosecrest WSP Pipeline | 280.2140. SVR Lateral 1" Culinary Service Loop - 9 Loops | SVR Services | 10 Pipe | 0 |  | 112 | 112 | 112 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 112 |  |  |  | 112
2602. JVWCD Rosecrest WSP Pipeline | 280.2750. H Hauling Single Side Dump 9ea- 1" Culinary Service Loop | H Hauling | 40 Drivers | 0 |  | 15.71 | 15.71 | 15.7 | 0.01 | 2026-02-09 | 2028-05-15 | [5 empty] | 15.7 |  |  |  | 15.7
2602. JVWCD Rosecrest WSP Pipeline | 280.2760. HO Haul Off Single Side Dump 9ea-1" Culinary Service Loop | HO Haul Off | 40 Drivers | 0 |  | 22 | 22 | 22 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 22 |  |  |  | 22
2602. JVWCD Rosecrest WSP Pipeline | 285.2140. SVR Lateral 1" Irrigation Service Loop - 9 loops | SVR Services | 10 Pipe | 0 |  | 97.6 | 97.6 | 97.6 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 97.6 |  |  |  | 97.6
2602. JVWCD Rosecrest WSP Pipeline | 285.2750. H Hauling Single Side Dump 9ea- 1" Irrigation Service Loop | H Hauling | 40 Drivers | 0 |  | 15.71 | 15.71 | 15.7 | 0.01 | 2026-02-09 | 2028-05-15 | [5 empty] | 15.7 |  |  |  | 15.7
2602. JVWCD Rosecrest WSP Pipeline | 285.2760. HO Haul Off Single Side Dump 9ea 1" Irrigation Service Loop | HO Haul Off | 40 Drivers | 0 |  | 22 | 22 | 22 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 22 |  |  |  | 22
2602. JVWCD Rosecrest WSP Pipeline | 290.2160. WSP Extras: Pull Stulls & Grout All Internal Joints | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 1583.34 | 1583.34 | 1583.3 | 0.04 | 2026-02-09 | 2028-05-15 |  | 150 | 400 | 400 | 950 | 400 | 233.3 |  |  | 633.3
2602. JVWCD Rosecrest WSP Pipeline | 290.2610. PT Fill/Test/Flush WSP All piping | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 300 | 300 | 300 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 100 | 200 |  |  | 300
2602. JVWCD Rosecrest WSP Pipeline | 295.2180. CATH DC Blocker, Annodes, Wire, L&E (13 Stations) | CATH Cathodic Protection | 10 Pipe | 0 |  | 752.28 | 752.28 | 752.3 | -0.02 | 2026-02-09 | 2028-05-15 |  |  | 200 | 200 | 400 | 200 | 152.3 |  |  | 352.3
2602. JVWCD Rosecrest WSP Pipeline | 300.2080. EXC Excav for Interconnect Vault - 13400 S | EXS Excavate Structure | 11 Earth Work | 0 |  | 412.5 | 412.5 | 412.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 100 | 312.5 |  |  | 412.5
2602. JVWCD Rosecrest WSP Pipeline | 300.2085. BFST Backfill for Interconnect Vault - 13400 S | BFST Backfill Structure | 11 Earth Work | 0 |  | 149.5 | 149.5 | 149.5 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 149.5 |  |  | 149.5
2602. JVWCD Rosecrest WSP Pipeline | 300.2140. PCS Precast & Grout for Interconnect Vault - 13400 S | SVR Services | 10 Pipe | 0 |  | 275.75 | 275.75 | 275.8 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 100 | 175.8 |  |  | 275.8
2602. JVWCD Rosecrest WSP Pipeline | 300.2210. RCP Piping for Interconnect Vault - 13400 S | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 61.25 | 61.25 | 61.3 | -0.05 | 2026-02-09 | 2028-05-15 | [6 empty] | 61.3 |  |  | 61.3
2602. JVWCD Rosecrest WSP Pipeline | 300.2750. H Hauling Single Side Dump for Interconnect Vault - 134thS | H Hauling | 40 Drivers | 0 |  | 55.43 | 55.43 | 55.4 | 0.03 | 2026-02-09 | 2028-05-15 | [5 empty] | 20 | 35.4 |  |  | 55.4
2602. JVWCD Rosecrest WSP Pipeline | 300.2760. HO Haul Off Single Side Dump for Interconnect Vault - 134th | HO Haul Off | 40 Drivers | 0 |  | 94.3 | 94.3 | 94.3 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 25 | 69.3 |  |  | 94.3
2602. JVWCD Rosecrest WSP Pipeline | 300.3000. CNC Concrete L&E for Interconnect Vault - 13400 S | CNC Concrete Work | 15 Concrete | 0 |  | 1037.9 | 1037.9 | 1037.9 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 800 | 237.9 |  |  | 1037.9
2602. JVWCD Rosecrest WSP Pipeline | 300.5000. MET Metals - Interconnect Vault - 13400 S | MET Metals | 20 Fabrication | 0 |  | 652 | 652 | 652 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 652 |  |  | 652
2602. JVWCD Rosecrest WSP Pipeline | 300.5400. HAT Ring & Cover/Frame & Grate -Interconnect Vault - 134th | HAT Hatch/Skylights | 12 Finishes | 0 |  | 18 | 18 | 18 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 18 |  |  | 18
2602. JVWCD Rosecrest WSP Pipeline | 300.6200. IN Insulation Vault -Interconnect Vault - 134th | IN Insulation | 12 Finishes | 0 |  | 71.04 | 71.04 | 71 | 0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 71 |  |  | 71
2602. JVWCD Rosecrest WSP Pipeline | 300.7100. IMP Piping for Interconnect Vault - 13400 S | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 1400.5 | 1400.5 | 1400.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 500 | 900.5 |  |  | 1400.5
2602. JVWCD Rosecrest WSP Pipeline | 300.7900. ELC Electrical/Fiber/Gas Utilities Trenching -Interconnect | ELC Electrical | 10 Pipe | 0 |  | 102.9 | 102.9 | 102.9 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 102.9 |  |  | 102.9
2602. JVWCD Rosecrest WSP Pipeline | 310.2030. D Demo Remove 24" WSP at 13400 S | D Demolition | 11 Earth Work | 0 |  | 139.54 | 139.54 | 139.5 | 0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 50 | 89.5 |  |  | 139.5
2602. JVWCD Rosecrest WSP Pipeline | 310.2160. WSP 30" WPL at 134th South intersection | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 1312.9 | 1312.9 | 1312.9 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 800 | 512.9 |  |  | 1312.9
2602. JVWCD Rosecrest WSP Pipeline | 310.2760. HO Haul Off for 30" WSP 134th South intersection | HO Haul Off | 40 Drivers | 0 |  | 2.5 | 2.5 | 2.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 2.5 |  |  |  | 2.5
2602. JVWCD Rosecrest WSP Pipeline | 310.5100. WE Butt Strap Welding for 30" WSP 134th S (18 Joints) | W Welding | 20 Fabrication | 0 |  | 152.46 | 152.46 | 152.5 | -0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 50 | 102.5 |  |  | 152.5
2602. JVWCD Rosecrest WSP Pipeline | 320.2160. WSP 20" WPL at 13400th South Intersection | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 682.47 | 682.47 | 682.5 | -0.03 | 2026-02-09 | 2028-05-15 | [5 empty] | 150 | 532.5 |  |  | 682.5
2602. JVWCD Rosecrest WSP Pipeline | 320.2610. PT Fill/Test/Flush 20" WPL at 134th South intersection | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 66.25 | 66.25 | 66.3 | -0.05 | 2026-02-09 | 2028-05-15 | [6 empty] | 66.3 |  |  | 66.3
2602. JVWCD Rosecrest WSP Pipeline | 320.2750. H Hauling 20" WPL at 134th South intersection | H Hauling | 40 Drivers | 0 |  | 33.34 | 33.34 | 33.3 | 0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 33.3 |  |  |  | 33.3
2602. JVWCD Rosecrest WSP Pipeline | 320.2760. HO Haul Off 20" WPL at 134th South intersection | HO Haul Off | 40 Drivers | 0 |  | 48.8 | 48.8 | 48.8 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 48.8 |  |  |  | 48.8
2602. JVWCD Rosecrest WSP Pipeline | 320.3000. CNC Anchor Conc 20" WPL at 134th South intersection | CNC Concrete Work | 15 Concrete | 0 |  | 18.75 | 18.75 | 18.8 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 18.8 |  |  |  | 18.8
2602. JVWCD Rosecrest WSP Pipeline | 320.5100. WE Welding 20" WPL at 134th South intersection (21 Joints) | W Welding | 20 Fabrication | 0 |  | 75.36 | 75.36 | 75.4 | -0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 25 | 50.4 |  |  | 75.4
2602. JVWCD Rosecrest WSP Pipeline | 330.2160. WSP 16" WPL at Interconnect Vault | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 193 | 193 | 193 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 100 | 93 |  |  | 193
2602. JVWCD Rosecrest WSP Pipeline | 330.2610. PT Fill/Test/Flush 16" WPL at Interconnect Vault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 0.8 | 0.8 | 0.8 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 0.8 |  |  | 0.8
2602. JVWCD Rosecrest WSP Pipeline | 330.2750. H Hauling16" WPL at Interconnect Vault | H Hauling | 40 Drivers | 0 |  | 12.62 | 12.62 | 12.6 | 0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 12.6 |  |  |  | 12.6
2602. JVWCD Rosecrest WSP Pipeline | 330.2760. HO Haul Off 16" WPL at Interconnect Vault | HO Haul Off | 40 Drivers | 0 |  | 17.9 | 17.9 | 17.9 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 17.9 |  |  |  | 17.9
2602. JVWCD Rosecrest WSP Pipeline | 330.3000. CNC Conc Anchor block 16" WPL at Interconnect Vault | CNC Concrete Work | 15 Concrete | 0 |  | 26.25 | 26.25 | 26.3 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 26.3 |  |  |  | 26.3
2602. JVWCD Rosecrest WSP Pipeline | 330.5100. WE Welding 16" WPL at Interconnect Vault (7 Joints) | W Welding | 20 Fabrication | 0 |  | 35.36 | 35.36 | 35.4 | -0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 35.4 |  |  |  | 35.4
2602. JVWCD Rosecrest WSP Pipeline | 340.2030. D Cap line 12" Herriman Connection 134 S. | D Demolition | 11 Earth Work | 0 |  | 119.8 | 119.8 | 119.8 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 119.8 |  |  |  | 119.8
2602. JVWCD Rosecrest WSP Pipeline | 340.2120. DIP -12" Herriman Connection 13400 S. | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 161.48 | 161.48 | 161.5 | -0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 100 | 61.5 |  |  | 161.5
2602. JVWCD Rosecrest WSP Pipeline | 340.2750. H Hauling 12" Herriman Connection 13400 S. | H Hauling | 40 Drivers | 0 |  | 5.95 | 5.95 | 6 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 6 |  |  |  | 6
2602. JVWCD Rosecrest WSP Pipeline | 340.2760. HO Haul Off 12" Herriman Connection 13400 S. | HO Haul Off | 40 Drivers | 0 |  | 9.1 | 9.1 | 9.1 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 9.1 |  |  |  | 9.1
2602. JVWCD Rosecrest WSP Pipeline | 350.2030. D Cap line 12" Riverton Connection 134 S. | D Demolition | 11 Earth Work | 0 |  | 20 | 20 | 20 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 20 |  |  |  | 20
2602. JVWCD Rosecrest WSP Pipeline | 350.2120. DIP - 12" Riverton Connection 13400 S. | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 288.65 | 288.65 | 288.6 | 0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 200 | 88.6 |  |  | 288.6
2602. JVWCD Rosecrest WSP Pipeline | 350.2750. H Hauling 12" Riverton Connection 13400S. | H Hauling | 40 Drivers | 0 |  | 11.9 | 11.9 | 11.9 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 11.9 |  |  |  | 11.9
2602. JVWCD Rosecrest WSP Pipeline | 350.2760. HO Haul Off 12" Riverton Connection 13400 S. | HO Haul Off | 40 Drivers | 0 |  | 15 | 15 | 15 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 15 |  |  |  | 15
2602. JVWCD Rosecrest WSP Pipeline | 400.2030. D Demo Reservoir Vault | D Demolition | 11 Earth Work | 0 |  | 4.2 | 4.2 | 4.2 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 4.2 |  |  |  | 4.2
2602. JVWCD Rosecrest WSP Pipeline | 400.2080. EXE Excavation for Reservoir Vault | EXS Excavate Structure | 11 Earth Work | 0 |  | 352.5 | 352.5 | 352.5 | 0 | 2026-02-09 | 2028-05-15 |  |  | 150 | 202.5 | 352.5
2602. JVWCD Rosecrest WSP Pipeline | 400.2085. BFST Backfill for Reservoir Vault | BFST Backfill Structure | 11 Earth Work | 0 |  | 161.5 | 161.5 | 161.5 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 161.5 | 161.5
2602. JVWCD Rosecrest WSP Pipeline | 400.2750. H Hauling for Reservoir Vault | H Hauling | 40 Drivers | 0 |  | 32.86 | 32.86 | 32.9 | -0.04 | 2026-02-09 | 2028-05-15 |  |  |  | 32.9 | 32.9
2602. JVWCD Rosecrest WSP Pipeline | 400.2760. HO Haul Off for Reservoir Vault | HO Haul Off | 40 Drivers | 0 |  | 67 | 67 | 67 | 0 | 2026-02-09 | 2028-05-15 |  |  | 67 |  | 67
2602. JVWCD Rosecrest WSP Pipeline | 400.3000. CNC Concrete for Reservoir Vault | CNC Concrete Work | 15 Concrete | 0 |  | 741.77 | 741.77 | 741.8 | -0.03 | 2026-02-09 | 2028-05-15 |  |  |  | 741.8 | 741.8
2602. JVWCD Rosecrest WSP Pipeline | 400.5000. MET Misc Metals at Reservoir Vault | MET Metals | 20 Fabrication | 0 |  | 395.5 | 395.5 | 395.5 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 395.5 | 395.5
2602. JVWCD Rosecrest WSP Pipeline | 400.5400. HAT Frame & Grate Reservoir Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 9 | 9 | 9 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 9 | 9
2602. JVWCD Rosecrest WSP Pipeline | 400.6200. IN Insulation L&E Reservoir Vault | IN Insulation | 12 Finishes | 0 |  | 58.8 | 58.8 | 58.8 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 58.8 | 58.8
2602. JVWCD Rosecrest WSP Pipeline | 400.7100. IMP Mechancial & Pump Install Reservoir Vault | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 921.4 | 921.4 | 921.4 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 921.4 | 921.4
2602. JVWCD Rosecrest WSP Pipeline | 400.7900. ELC Electrical/Fiber/Gas Trenching Reservoir Vault | ELC Electrical | 10 Pipe | 0 |  | 64 | 64 | 64 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 64 | 64
2602. JVWCD Rosecrest WSP Pipeline | 410.2030. D Demo at Rosecrest Tank Connection | D Demolition | 11 Earth Work | 0 |  | 52.6 | 52.6 | 52.6 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 52.6 |  |  |  | 52.6
2602. JVWCD Rosecrest WSP Pipeline | 410.2050. RW Backfill Retaining Wall at Rosecrest Tank Connection | RW Retaining Walls | 11 Earth Work | 0 |  | 14.4 | 14.4 | 14.4 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 14.4 | 14.4
2602. JVWCD Rosecrest WSP Pipeline | 410.2070. RFG Cut - Excavate/Backfill at Rosecrest Tank Connection | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 25 | 25 | 25 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 25 | 25
2602. JVWCD Rosecrest WSP Pipeline | 410.2075. FG Fabric/Liner/Grid at Rosecrest Tank Connection | FG Finish Grade | 11 Earth Work | 0 |  | 8.49 | 8.49 | 8.5 | -0.01 | 2026-02-09 | 2028-05-15 |  |  |  | 8.5 | 8.5
2602. JVWCD Rosecrest WSP Pipeline | 410.2140. SVR CL conduits/4" vent/1"water- Rosecrest Tank Connection | SVR Services | 10 Pipe | 0 |  | 253 | 253 | 253 | 0 | 2026-02-09 | 2028-05-15 |  |  |  | 253 | 253
2602. JVWCD Rosecrest WSP Pipeline | 410.2160. WSP Rosecrest Tank Connections (5 ea) | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 145.11 | 145.11 | 145.1 | 0.01 | 2026-02-09 | 2028-05-15 | [5 empty] | 145.1 |  |  |  | 145.1
2602. JVWCD Rosecrest WSP Pipeline | 410.2240. PCS Precast at Rosecrest Tank Connection | PCS Precast Structures | 10 Pipe | 0 |  | 60.32 | 60.32 | 60.3 | 0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 60.3 |  |  |  | 60.3
2602. JVWCD Rosecrest WSP Pipeline | 410.2610. PT Fill/Test/Flusht at Rosecrest Tank Connection | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 32.86 | 32.86 | 32.9 | -0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 32.9 |  |  |  | 32.9
2602. JVWCD Rosecrest WSP Pipeline | 410.2750. H Hauling at Rosecrest Tank Connection | H Hauling | 40 Drivers | 0 |  | 41.4 | 41.4 | 41.4 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 41.4 |  |  |  | 41.4
2602. JVWCD Rosecrest WSP Pipeline | 410.2760. HO Haul Off at Rosecrest Tank Connection | HO Haul Off | 40 Drivers | 0 |  | 55.8 | 55.8 | 55.8 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 55.8 |  |  |  | 55.8
2602. JVWCD Rosecrest WSP Pipeline | 410.3000. CNC Site Concrete at Rosecrest Tank Connection | CNC Concrete Work | 15 Concrete | 0 |  | 121.5 | 121.5 | 121.5 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 121.5 |  |  |  | 121.5
2602. JVWCD Rosecrest WSP Pipeline | 410.5000. MET Misc Metal L&E at Rosecrest Tank Connection | MET Metals | 20 Fabrication | 0 |  | 114 | 114 | 114 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 114 |  |  |  | 114
2602. JVWCD Rosecrest WSP Pipeline | 410.5100. WE Welding at Rosecrest Tank Connection (10 Joints) | W Welding | 20 Fabrication | 0 |  | 40 | 40 | 40 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 40 |  |  |  | 40
2602. JVWCD Rosecrest WSP Pipeline | 410.7100. IMP Chemical Piping at Rosecrest Tank Connection | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 15 | 15 | 15 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 15 |  |  |  | 15
2602. JVWCD Rosecrest WSP Pipeline | 410.7600. MEQ Chlorine Eq at Rosecrest Tank Connection | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 30 | 30 | 30 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 30 |  |  |  | 30
2602. JVWCD Rosecrest WSP Pipeline | 420.2160. WSP 20" WPL Tie into Tank Vault North of Vault C-05 | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 79.9 | 79.9 | 79.9 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 79.9 |  |  |  | 79.9
2602. JVWCD Rosecrest WSP Pipeline | 420.2210. PCS Relocate Storm Drain at Tie-in at Tank Vault C-05 | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 83.75 | 83.75 | 83.8 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 83.8 |  |  |  | 83.8
2602. JVWCD Rosecrest WSP Pipeline | 420.2610. PT Fill/Test/Flush at 20" Tie-in at Tank Vault C-05 | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 128.55 | 128.55 | 128.6 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 128.6 |  |  |  | 128.6
2602. JVWCD Rosecrest WSP Pipeline | 420.2750. H Hauling at 20" Tie-in at Tank Vault C-05 | H Hauling | 40 Drivers | 0 |  | 30.95 | 30.95 | 30.9 | 0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 30.9 |  |  |  | 30.9
2602. JVWCD Rosecrest WSP Pipeline | 420.2760. HO Haul Off at 20" Tie-in at Tank Vault C-05 | HO Haul Off | 40 Drivers | 0 |  | 49.4 | 49.4 | 49.4 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 49.4 |  |  |  | 49.4
2602. JVWCD Rosecrest WSP Pipeline | 420.3000. CNC Concrete at 20" Tie-in at Tank Vault C-05 | CNC Concrete Work | 15 Concrete | 0 |  | 4.07 | 4.07 | 4.1 | -0.03 | 2026-02-09 | 2028-05-15 | [5 empty] | 4.1 |  |  |  | 4.1
2602. JVWCD Rosecrest WSP Pipeline | 420.5100. WE Welding at 20" Tie-in at Tank Vault North of Vault C-05 | W Welding | 20 Fabrication | 0 |  | 10 | 10 | 10 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 10 |  |  |  | 10
2602. JVWCD Rosecrest WSP Pipeline | 430.2130. PVC 16" WPL Tie into Herriman Pumpstation C-05 | PVC Pipe | 10 Pipe | 0 |  | 92.25 | 92.25 | 92.3 | -0.05 | 2026-02-09 | 2028-05-15 | [5 empty] | 92.3 |  |  |  | 92.3
2602. JVWCD Rosecrest WSP Pipeline | 430.2160. WSP 16" WPL Tie into Herriman Pumpstation C-05 | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 3.13 | 3.13 | 3.1 | 0.03 | 2026-02-09 | 2028-05-15 | [5 empty] | 3.1 |  |  |  | 3.1
2602. JVWCD Rosecrest WSP Pipeline | 430.2750. H Hauling 16" WPL Tie into Herriman Pumpstation C-05 | H Hauling | 40 Drivers | 0 |  | 2.38 | 2.38 | 2.4 | -0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 2.4 |  |  |  | 2.4
2602. JVWCD Rosecrest WSP Pipeline | 430.2760. HO Haul Off 16" WPL Tie into Herriman Pumpstation C-05 | HO Haul Off | 40 Drivers | 0 |  | 2.6 | 2.6 | 2.6 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 2.6 |  |  |  | 2.6
2602. JVWCD Rosecrest WSP Pipeline | 430.5100. WE Welding 16" WPL Tie into Herriman Pumpstation C-05 (2 Jtn | W Welding | 20 Fabrication | 0 |  | 20 | 20 | 20 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 20 |  |  |  | 20
2602. JVWCD Rosecrest WSP Pipeline | 500.2080. EXS Excavate Rocky Point Vault | EXS Excavate Structure | 11 Earth Work | 0 |  | 86.38 | 86.38 | 86.4 | -0.02 | 2026-02-09 | 2028-05-15 | [5 empty] | 86.4 |  |  |  | 86.4
2602. JVWCD Rosecrest WSP Pipeline | 500.2085. BFST Backfill Rocky Point Vault | BFST Backfill Structure | 11 Earth Work | 0 |  | 60 | 60 | 60 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 60 |  |  | 60
2602. JVWCD Rosecrest WSP Pipeline | 500.2140. SVR Vent line at Rocky Point Vault | SVR Services | 10 Pipe | 0 |  | 82.65 | 82.65 | 82.7 | -0.05 | 2026-02-09 | 2028-05-15 | [6 empty] | 82.7 |  |  | 82.7
2602. JVWCD Rosecrest WSP Pipeline | 500.2750. H Hauling Rocky Point Vault | H Hauling | 40 Drivers | 0 |  | 28.81 | 28.81 | 28.8 | 0.01 | 2026-02-09 | 2028-05-15 | [6 empty] | 28.8 |  |  | 28.8
2602. JVWCD Rosecrest WSP Pipeline | 500.2760. HO Haul Off Rocky Point Vault | HO Haul Off | 40 Drivers | 0 |  | 36.1 | 36.1 | 36.1 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 36.1 |  |  | 36.1
2602. JVWCD Rosecrest WSP Pipeline | 500.3000. CNC Concrete for Rocky Vault | CNC Concrete Work | 15 Concrete | 0 |  | 362.6 | 362.6 | 362.6 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 362.6 |  |  | 362.6
2602. JVWCD Rosecrest WSP Pipeline | 500.5000. MET Misc Metals L&E Rocky Point Vault | MET Metals | 20 Fabrication | 0 |  | 159.48 | 159.48 | 159.5 | -0.02 | 2026-02-09 | 2028-05-15 | [6 empty] | 159.5 |  |  | 159.5
2602. JVWCD Rosecrest WSP Pipeline | 500.5400. HAT Ring & Cover Rocky Point Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 3 | 3 | 3 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 3 |  |  | 3
2602. JVWCD Rosecrest WSP Pipeline | 500.6200. IN Insulation L&E Rocky Point Vault | IN Insulation | 12 Finishes | 0 |  | 14.96 | 14.96 | 15 | -0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 15 |  |  | 15
2602. JVWCD Rosecrest WSP Pipeline | 500.7100. IMP Vault Piping at Rocky Point Vault | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 314 | 314 | 314 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 314 |  |  | 314
2602. JVWCD Rosecrest WSP Pipeline | 500.7900. ELC Elc/Gas Utilities Trenching - Rocky Point Vault | ELC Electrical | 10 Pipe | 0 |  | 11.6 | 11.6 | 11.6 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 11.6 |  |  | 11.6
2602. JVWCD Rosecrest WSP Pipeline | 510.2120. DIP 10" Piping - Retail Connection Rocky Point Vault | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 256.74 | 256.74 | 256.7 | 0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 256.7 |  |  | 256.7
2602. JVWCD Rosecrest WSP Pipeline | 510.2610. PT Fill/Test/Flush 10" Piping - Retail Connection RockyVault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 0.32 | 0.32 | 0.3 | 0.02 | 2026-02-09 | 2028-05-15 | [6 empty] | 0.3 |  |  | 0.3
2602. JVWCD Rosecrest WSP Pipeline | 510.2750. H Hauling 10" Piping - Retail Connection Rocky Point Vault | H Hauling | 40 Drivers | 0 |  | 11.9 | 11.9 | 11.9 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 11.9 |  |  | 11.9
2602. JVWCD Rosecrest WSP Pipeline | 510.2760. HO Haul Off 10" Piping - Retail Connection RockyPoint Vault | HO Haul Off | 40 Drivers | 0 |  | 15.4 | 15.4 | 15.4 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 15.4 |  |  | 15.4
2602. JVWCD Rosecrest WSP Pipeline | 600.2120. DIP 8" Retail Loop piping - Retail Connection Sta159+40 | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 248.49 | 248.49 | 248.5 | -0.01 | 2026-02-09 | 2028-05-15 | [6 empty] | 248.5 |  |  | 248.5
2602. JVWCD Rosecrest WSP Pipeline | 600.2240. PCS/MH Precast L&E - Retail Connection Sta159+40 | PCS Precast Structures | 10 Pipe | 0 |  | 45.68 | 45.68 | 45.7 | -0.02 | 2026-02-09 | 2028-05-15 | [6 empty] | 45.7 |  |  | 45.7
2602. JVWCD Rosecrest WSP Pipeline | 600.2750. H Hauling - Retail Connection Sta159+40 | H Hauling | 40 Drivers | 0 |  | 10.48 | 10.48 | 10.5 | -0.02 | 2026-02-09 | 2028-05-15 | [6 empty] | 10.5 |  |  | 10.5
2602. JVWCD Rosecrest WSP Pipeline | 600.2760. HO Haul Off - Retail Connection Sta159+40 | HO Haul Off | 40 Drivers | 0 |  | 12.9 | 12.9 | 12.9 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 12.9 |  |  | 12.9
2602. JVWCD Rosecrest WSP Pipeline | 610.2075. FG Finish Grade - Herriman Fire hydrant Relocates | FG Finish Grade | 11 Earth Work | 0 |  | 6.4 | 6.4 | 6.4 | 0 | 2026-02-09 | 2028-05-15 |  | 6.4 |  |  | 6.4
2602. JVWCD Rosecrest WSP Pipeline | 610.2130. PVC Install Fire Hydrant - Herriman Fire hydrant Relocates | PVC Pipe | 10 Pipe | 0 |  | 503.25 | 503.25 | 503.3 | -0.05 | 2026-02-09 | 2028-05-15 |  | 503.3 |  |  | 503.3
2602. JVWCD Rosecrest WSP Pipeline | 610.2750. H Hauling - Herriman Fire hydrant Relocates | H Hauling | 40 Drivers | 0 |  | 6.19 | 6.19 | 6.2 | -0.01 | 2026-02-09 | 2028-05-15 |  | 6.2 |  |  | 6.2
2602. JVWCD Rosecrest WSP Pipeline | 610.2760. HO Haul Off - Herriman Fire hydrant Relocates | HO Haul Off | 40 Drivers | 0 |  | 6.6 | 6.6 | 6.6 | 0 | 2026-02-09 | 2028-05-15 |  | 6.6 |  |  | 6.6
2602. JVWCD Rosecrest WSP Pipeline | 610.3000. CNC Conc Flatwork - Herriman Fire hydrant Relocates | CNC Concrete Work | 15 Concrete | 0 |  | 65 | 65 | 65 | 0 | 2026-02-09 | 2028-05-15 |  | 65 |  |  | 65
2602. JVWCD Rosecrest WSP Pipeline | 620.2030. D Demo Concrete for Pipework - All Pipe | D Demolition | 11 Earth Work | 0 |  | 37.71 | 37.71 | 37.7 | 0.01 | 2026-02-09 | 2028-05-15 |  | 10 | 10 | 10 | 30 | 7.7 |  |  |  | 7.7
2602. JVWCD Rosecrest WSP Pipeline | 620.2075. FG Concrete sidewalk Prep for Pipework - All Pipe | FG Finish Grade | 11 Earth Work | 0 |  | 191.6 | 191.6 | 191.6 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 150 | 41.6 |  |  | 191.6
2602. JVWCD Rosecrest WSP Pipeline | 620.2750. H Hauling for Concrete Prep on Pipework - All Pipe | H Hauling | 40 Drivers | 0 |  | 1.44 | 1.44 | 1.4 | 0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 1.4 |  |  |  | 1.4
2602. JVWCD Rosecrest WSP Pipeline | 620.2760. HO Haul Off Concrete for Concrete Prep - All Pipe | HO Haul Off | 40 Drivers | 0 |  | 2.8 | 2.8 | 2.8 | 0 | 2026-02-09 | 2028-05-15 | [5 empty] | 2.8 |  |  |  | 2.8
2602. JVWCD Rosecrest WSP Pipeline | 630.2075. FG Roadbase T-Patch Asphalt Repairs | FG Finish Grade | 11 Earth Work | 0 |  | 290.36 | 290.36 | 290.4 | -0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 290.4 |  |  | 290.4
2602. JVWCD Rosecrest WSP Pipeline | 630.2750. H Hauling T-Patch Asphalt Repairs | H Hauling | 40 Drivers | 0 |  | 317.38 | 317.38 | 317.4 | -0.02 | 2026-02-09 | 2028-05-15 | [6 empty] | 317.4 |  |  | 317.4
2602. JVWCD Rosecrest WSP Pipeline | 640.2075. FG Asphalt Trench T-Patch Asphalt Repairs | FG Finish Grade | 11 Earth Work | 0 |  | 134.34 | 134.34 | 134.3 | 0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 134.3 |  |  | 134.3
2602. JVWCD Rosecrest WSP Pipeline | 640.2760. HO Haul Off T-Patch Asphalt Repairs | HO Haul Off | 40 Drivers | 0 |  | 66 | 66 | 66 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 66 |  |  | 66
2602. JVWCD Rosecrest WSP Pipeline | 650.2075. FG Asphalt Trench T-Patch Asphalt Repairs | FG Finish Grade | 11 Earth Work | 0 |  | 119.64 | 119.64 | 119.6 | 0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 119.6 |  |  | 119.6
2602. JVWCD Rosecrest WSP Pipeline | 650.2760. HO Haul Off T-Patch Asphalt Repairs | HO Haul Off | 40 Drivers | 0 |  | 162.4 | 162.4 | 162.4 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 162.4 |  |  | 162.4
2602. JVWCD Rosecrest WSP Pipeline | 700.1515. S Road Reconst Survey - Vancon | S Drone/Lidar Requirements | 45 Survey | 0 |  | 156 | 156 | 156 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 100 | 56 |  | 156
2602. JVWCD Rosecrest WSP Pipeline | 700.2030. D Demo Road Reconst Site Concrete Herriman Road Recon | D Demolition | 11 Earth Work | 0 |  | 751.16 | 751.16 | 751.2 | -0.04 | 2026-02-09 | 2028-05-15 | [5 empty] | 150 | 500 | 101.2 |  | 751.2
2602. JVWCD Rosecrest WSP Pipeline | 700.2065. SFC Road Reconst SWPPP Herriman Road Recon | SFC SWPPP | 11 Earth Work | 0 |  | 130 | 130 | 130 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 100 | 30 |  | 130
2602. JVWCD Rosecrest WSP Pipeline | 700.2070. RGC Road Reconst Herriman Road Recon | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 18.99 | 18.99 | 19 | -0.01 | 2026-02-09 | 2028-05-15 | [6 empty] | 19 |  |  | 19
2602. JVWCD Rosecrest WSP Pipeline | 700.2075. FG Surface Prep Herriman Road Recon | FG Finish Grade | 11 Earth Work | 0 |  | 701.46 | 701.46 | 701.5 | -0.04 | 2026-02-09 | 2028-05-15 | [6 empty] | 500 | 201.5 |  | 701.5
2602. JVWCD Rosecrest WSP Pipeline | 700.2750. H Hauling Herriman Road Recon | H Hauling | 40 Drivers | 0 |  | 31.91 | 31.91 | 31.9 | 0.01 | 2026-02-09 | 2028-05-15 | [6 empty] | 31.9 |  |  | 31.9
2602. JVWCD Rosecrest WSP Pipeline | 700.2760. HO Haul Off Herriman Road Recon | HO Haul Off | 40 Drivers | 0 |  | 101.2 | 101.2 | 101.2 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 75 | 26.2 |  | 101.2
2602. JVWCD Rosecrest WSP Pipeline | 800.1930. MC Steel Pipe - Misc Cleanup End of Job | MC Misc Cleanup | 12 Finishes | 0 |  | 455 | 455 | 455 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 250 | 205 |  | 455
2602. JVWCD Rosecrest WSP Pipeline | 800.1940. PL Steel Pipe - Punch List | PL Punch List Work | 12 Finishes | 0 |  | 400 | 400 | 400 | 0 | 2026-02-09 | 2028-05-15 | [6 empty] | 150 | 250 |  | 400
2602. JVWCD Rosecrest WSP Pipeline | 850.1930. MC Road ReConstruct - Misc Cleanup End of Job | MC Misc Cleanup | 12 Finishes | 0 |  | 75 | 75 | 75 | 0 | 2026-02-09 | 2028-05-15 | [7 empty] | 75 |  | 75
2602. JVWCD Rosecrest WSP Pipeline | 850.1940. PL Road ReConstruct - Punch list | PL Punch List Work | 12 Finishes | 0 |  | 100 | 100 | 100 | 0 | 2026-02-09 | 2028-05-15 | [7 empty] | 100 |  | 100
2602. JVWCD Rosecrest WSP Pipeline | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2026-02-09 | 2028-05-15 | [7 empty] | 0.6 |  | 0.6
2602. JVWCD Rosecrest WSP Pipeline | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2026-02-09 | 2028-05-15 | [7 empty] | 0.6 |  | 0.6
2602. JVWCD Rosecrest WSP Pipeline | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2026-02-09 | 2028-05-15 | [7 empty] | 0.6 |  | 0.6
2602. JVWCD Rosecrest WSP Pipeline | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 2 | 2 | 0 | 2026-02-09 | 2028-05-15 | [7 empty] | 2 |  | 2
2602. JVWCD Rosecrest WSP Pipeline | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 1.5 |  | 1 | -0.5 | 1 | -1.5 | 2026-02-09 | 2028-05-15 | [7 empty] | 1 |  | 1
2601. 2026 Misc. Jobs | 110.1510. Sanpete Cnty Race Track Survey/Drone | S Surveying | 45 Survey | 10 |  | 20 | 2 | 10 | -8 | 2026-01-01 | 2026-12-31 | 10 |  |  |  | 10
2601. 2026 Misc. Jobs | 130.7600. JVWTP NTU, Flights, Baffles | MEQ Mechanical Equipment | 55 Mechanical | 128.26 |  | 0 | 0 | 40 | -40 | 2026-01-01 | 2026-12-31 | 40 |  |  |  | 40
2601. 2026 Misc. Jobs | 180.1800. DFCM PH Pothole w/ Hydrovac | PH Potholing | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2026-01-01 | 2026-12-31
2601. 2026 Misc. Jobs | 200.6000. DR Cabin | IF Interior Finishes | 20 Fabrication | 0 |  | 0 | 6 | 0 | 6 | 2026-01-01 | 2026-12-31
2601. 2026 Misc. Jobs | 285.2300. JVWCD 48&45th Surge Tank Line Repair | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 119.72 |  | 116.8 | 0 | 20 | -20 | 2026-01-01 | 2026-12-31 | 20 |  |  |  | 20
2570. Jon Stubbs Hauling | 150.2700. Trucking / Hauling | SG Sand & Gravel | 11 Earth Work | 1248.71 |  | 0 | 0 | 0 | 0
2570. Jon Stubbs Hauling | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0
2550. Fab Shop Jobs 2025 Projects | 503.5901. FAB 2503 HVSSD Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 45.5 |  | 31 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 503.5960. FAB 2503 HVSSD Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 61.47 |  | 72 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 503.5970. FAB 2503 HVSSD Misc. Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 8.45 |  | 45 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 503.5995. FAB 2503 HVSSD Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 6.72 |  | 0 | 0 | 10 | -10 | 2025-01-01 | 2025-12-31 | 10 |  |  |  | 10
2550. Fab Shop Jobs 2025 Projects | 505.5995. FAB 2505 JVWTP Chem Changes / VE | FAB Fab Shop Change Orders | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 506.5995. FAB 2506 UDOT Culvert Changes / VE | FAB Fab Shop Change Orders | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 507.5901. FAB 2507 SLC Ind Design/PM/PE | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 6.75 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 507.5935. FAB 2507 SLC Ind Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 507.5960. FAB 2507 SLC Ind Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 9.5 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 507.5970. FAB 2507 SLC Ind Misc. Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 507.5995. FAB 2507 SLC Ind Changes /VE | FAB Fab Shop Change Orders | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 508.5901. FAB 2508 Turner Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 50 |  | 58 | 15 | 14 | 1 | 2025-01-01 | 2025-12-31 | 5 | 9 |  |  | 14
2550. Fab Shop Jobs 2025 Projects | 508.5935. FAB 2508 Turner Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 5 | 5 | 5 | 0 | 2025-01-01 | 2025-12-31 | 5 |  |  |  | 5
2550. Fab Shop Jobs 2025 Projects | 508.5960. FAB 2508 Turner Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 208.48 |  | 145 | 100 | 0 | 100 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 510.5901. FAB 2510 Draper PS3 Design/PM/PE | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 147.92 |  | 80 | 20 | 40 | -20 | 2025-01-01 | 2025-12-31 | 20 | 20 |  |  | 40
2550. Fab Shop Jobs 2025 Projects | 510.5935. FAB 2510 Draper PS3 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 15 | 15 | 15 | 0 | 2025-01-01 | 2025-12-31 | 5 | 5 | 5 |  | 15
2550. Fab Shop Jobs 2025 Projects | 510.5940. FAB 2510 Draper PS3 WSP Fab L&E | FAB Fab Shop WSP Fabrication | 20 Fabrication | 70.23 |  | 250 | 200 | 240 | -40 | 2025-01-01 | 2025-12-31 | 100 | 60 | 40 | 40 | 240
2550. Fab Shop Jobs 2025 Projects | 510.5950. FAB 2510 Draper PS3 WSP Paint L&E | FAB Fab Shop WSP Paint | 20 Fabrication | 0 |  | 60 | 60 | 60 | 0 | 2025-01-01 | 2025-12-31 | 20 | 20 | 20 |  | 60
2550. Fab Shop Jobs 2025 Projects | 510.5960. FAB 2510 Draper PS3 Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 0 |  | 58 | 58 | 58 | 0 | 2025-01-01 | 2025-12-31 | 19 | 29 | 10 |  | 58
2550. Fab Shop Jobs 2025 Projects | 510.5970. FAB 2510 Draper PS3 Misc. Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 42 | 42 | 42 | 0 | 2025-01-01 | 2025-12-31 | 21 | 21 |  |  | 42
2550. Fab Shop Jobs 2025 Projects | 510.5995. FAB 2510 Draper PS3 Changes / VE | FAB Fab Shop Change Orders | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 511.5901. FAB 2511 GHID Design/PM/PE | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 0 |  | 5 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 511.5960. FAB 2511 GHID Misc Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 0 |  | 60 | 60 | 60 | 0 | 2025-01-01 | 2025-12-31 | 30 | 30 |  |  | 60
2550. Fab Shop Jobs 2025 Projects | 511.5970. FAB 2511 GHID Misc Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 3 | 3 | 3 | 0 | 2025-01-01 | 2025-12-31 |  | 3 |  |  | 3
2550. Fab Shop Jobs 2025 Projects | 512.5901. FAB 2512 SoSL Tank Mangement/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 127.75 |  | 75 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 512.5935. FAB 2512 SoSL Tank Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 100 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 512.5945. FAB 2312 SoSL Tank Sand Blasting L&E | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 161.3 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 512.5960. FAB 2512 SoSL Tank Misc Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 417.68 |  | 726 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 512.5970. FAB 2512 SoSL Tank Misc Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 128 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 512.5995. FAB 2512 SoSL Tank Changes / VE | FAB Fab Shop Change Orders | 20 Fabrication | 1 |  | 0 | 9 | 10 | -1 | 2025-01-01 | 2025-12-31 | 10 |  |  |  | 10
2550. Fab Shop Jobs 2025 Projects | 513.5995. FAB 2513 Summit Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 1 |  | 0 | 4 | 5 | -1 | 2025-01-01 | 2025-12-31 | 5 |  |  |  | 5
2550. Fab Shop Jobs 2025 Projects | 515.5901. FAB 2515 Steinaker Gate Design/PM/PE | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 53.75 |  | 20 | 0 | 5 | -5 | 2025-01-01 | 2025-12-31 | 5 |  |  |  | 5
2550. Fab Shop Jobs 2025 Projects | 515.5960. FAB 2515 Steinaker Gate Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 37.07 |  | 105 | 15 | 0 | 15 | 2025-01-01 | 2025-12-31
2550. Fab Shop Jobs 2025 Projects | 515.5995. FAB 2515 Steinaker Gate Changes / VE | FAB Fab Shop Change Orders | 20 Fabrication | 9 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-12-31
2519. Corix IEC Site Utilities | 100.1200. HOOK Hook Truck Dumpsters Transporting/Connex | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 20 | 20 | 20 | 0 | 2025-12-03 | 2026-04-01 | 10 | 10 |  |  | 20
2519. Corix IEC Site Utilities | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 1 | -1 | 2025-12-03 | 2026-04-01 | 1 |  |  |  | 1
2519. Corix IEC Site Utilities | 100.1510. S Surveying | S Surveying | 45 Survey | 14.52 |  | 100 | 80 | 100 | -20 | 2025-12-03 | 2026-04-01 | 50 | 50 |  |  | 100
2519. Corix IEC Site Utilities | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 11.5 |  | 138 | 125 | 46 | 79 | 2025-12-03 | 2026-04-01 | 20 | 20 | 6 |  | 46
2519. Corix IEC Site Utilities | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 78.51 |  | 219 | 300 | 113.6 | 186.4 | 2025-12-03 | 2026-04-01 | 50 | 50 | 13.6 |  | 113.6
2519. Corix IEC Site Utilities | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 18 |  | 74 | 50 | 1 | 49 | 2025-12-03 | 2026-04-01 | 1 |  |  |  | 1
2519. Corix IEC Site Utilities | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 45.84 |  | 116 | 125 | -1 | 126 | 2025-12-03 | 2026-04-01 | -1 |  |  |  | -1
2519. Corix IEC Site Utilities | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 29 | 10 | 1 | 9 | 2025-12-03 | 2026-04-01 | 1 |  |  |  | 1
2519. Corix IEC Site Utilities | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 1 | -1 | 2025-12-03 | 2026-04-01 | 1 |  |  |  | 1
2519. Corix IEC Site Utilities | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 1 | -1 | 2025-12-03 | 2026-04-01 | 1 |  |  |  | 1
2519. Corix IEC Site Utilities | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 50 | 50 | 50 | 0 | 2025-12-03 | 2026-04-01 | 25 | 25 |  |  | 50
2519. Corix IEC Site Utilities | 150.2750. H Hauling Single Side Dump | H Hauling | 40 Drivers | 0 |  | 217.83 | 200 | 217 | -17 | 2025-12-03 | 2026-04-01 | 100 | 117 |  |  | 217
2519. Corix IEC Site Utilities | 180.2130. PVC Subcontractor Hot Tap | PVC Pipe | 10 Pipe | 0 |  | 260 | 250 | 260 | -10 | 2025-12-03 | 2026-04-01 | 150 | 110 |  |  | 260
2519. Corix IEC Site Utilities | 180.2240. PCS Crane SUB | PCS Precast Structures | 10 Pipe | 0 |  | 286.5 | 290 | 286.5 | 3.5 | 2025-12-03 | 2026-04-01 | 150 | 136.5 |  |  | 286.5
2519. Corix IEC Site Utilities | 200.2070. RGC Roadway/Trail Cut & Export (Excavator Only) | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 20 | 20 | 20 | 0 | 2025-12-03 | 2026-04-01 | 20 |  |  |  | 20
2519. Corix IEC Site Utilities | 200.2071. RGF Roadway Fill Borrow On-Site | RGF Rough Grade Fill | 11 Earth Work | 0 |  | 40 | 40 | 40 | 0 | 2025-12-03 | 2026-04-01 | 20 | 20 |  |  | 40
2519. Corix IEC Site Utilities | 200.2075. FG Roadbase/Gravel Small Areas | FG Finish Grade | 11 Earth Work | 9.9 |  | 200 | 200 | 200 | 0 | 2025-12-03 | 2026-04-01 | 100 | 100 |  |  | 200
2519. Corix IEC Site Utilities | 200.2220. ADS Connection/Tie-Ins | ADS Pipe | 10 Pipe | 0 |  | 230 | 250 | 230 | 20 | 2025-12-03 | 2026-04-01 | 150 | 80 |  |  | 230
2519. Corix IEC Site Utilities | 200.2240. PCS Grout Pipe Openings - 0" - 21" | PCS Precast Structures | 10 Pipe | 8.57 |  | 92.5 | 100 | 92.5 | 7.5 | 2025-12-03 | 2026-04-01 | 75 | 17.5 |  |  | 92.5
2519. Corix IEC Site Utilities | 300.2075. FG Surface Concrete Exterior Prep LF Skidster | FG Finish Grade | 11 Earth Work | 0 |  | 196.32 | 200 | 196.3 | 3.7 | 2025-12-03 | 2026-04-01 | 50 | 125 | 21.3 |  | 196.3
2519. Corix IEC Site Utilities | 300.2080. EXS Gravel Placement Over 12 Inches | EXS Excavate Structure | 11 Earth Work | 31.17 |  | 160 | 150 | 160 | -10 | 2025-12-03 | 2026-04-01 | 50 | 80 | 30 |  | 160
2519. Corix IEC Site Utilities | 300.2085. BFST Backfill Open Area w/ S&G 10' to 0' Faster | BFST Backfill Structure | 11 Earth Work | 0 |  | 125 | 125 | 125 | 0 | 2025-12-03 | 2026-04-01 | 75 | 50 |  |  | 125
2519. Corix IEC Site Utilities | 300.2600. DW Drill Caissons | DW Dewatering | 10 Pipe | 5.92 |  | 180 | 0 | 180 | -180 | 2025-12-03 | 2026-04-01 | 180 |  |  |  | 180
2519. Corix IEC Site Utilities | 300.3000. CNC Concrete for Caissons | CNC Concrete Work | 15 Concrete | 302.2 |  | 928.2 | 750 | 928.2 | -178.2 | 2025-12-03 | 2026-04-01 | 928.2 |  |  |  | 928.2
2519. Corix IEC Site Utilities | 300.3010. WP Winter Pro Maintenence Easy | WP Winter Protection | 15 Concrete | 0 |  | 180 | 180 | 180 | 0 | 2025-12-03 | 2026-04-01 | 150 | 30 |  |  | 180
2519. Corix IEC Site Utilities | 300.3100. CNR Rebar VanCon Install | CNC Rebar | 15 Concrete | 99.86 |  | 144 | 100 | 144 | -44 | 2025-12-03 | 2026-04-01 | 120 | 24 |  |  | 144
2519. Corix IEC Site Utilities | 400.7100. IMP 4"-6" Fitting/Valve Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 60 | 60 | 60 | 0 | 2025-12-03 | 2026-04-01 | 60 |  |  |  | 60
2519. Corix IEC Site Utilities | 400.7900. ELC Ground Sleeves | ELC Electrical | 10 Pipe | 0 |  | 180 | 180 | 180 | 0 | 2025-12-03 | 2026-04-01 | 180 |  |  |  | 180
2519. Corix IEC Site Utilities | 500.2075. FG Surface Concrete Exterior Prep LF Skidster | FG Finish Grade | 11 Earth Work | 0 |  | 12 | 50 | 12 | 38 | 2025-12-03 | 2026-04-01 |  | 12 |  |  | 12
2519. Corix IEC Site Utilities | 550.2075. FG Asphalt Prep 2500 SF to 10 | FG Finish Grade | 11 Earth Work | 0 |  | 172.08 | 200 | 172.1 | 27.9 | 2025-12-03 | 2026-04-01 |  | 100 | 72.1 |  | 172.1
2519. Corix IEC Site Utilities | 800.1930. MC Misc Cleanup Distribution Line / Punch List | MC Misc Cleanup | 12 Finishes | 0 |  | 80 | 80 | 80 | 0 | 2025-12-03 | 2026-04-01 |  | 30 | 50 |  | 80
2519. Corix IEC Site Utilities | 800.1940. PL Pressurized/Water/Irrigation/Transmission | PL Punch List Work | 12 Finishes | 0 |  | 40 | 40 | 40 | 0 | 2025-12-03 | 2026-04-01 |  | 40 |  |  | 40
2519. Corix IEC Site Utilities | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0.6 | -0.6 | 2025-12-03 | 2026-04-01 |  | 0.6 |  |  | 0.6
2519. Corix IEC Site Utilities | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0.6 | -0.6 | 2025-12-03 | 2026-04-01 |  | 0.6 |  |  | 0.6
2519. Corix IEC Site Utilities | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0.6 | -0.6 | 2025-12-03 | 2026-04-01 |  | 0.6 |  |  | 0.6
2519. Corix IEC Site Utilities | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 0 | 2 | -2 | 2025-12-03 | 2026-04-01 |  | 2 |  |  | 2
2519. Corix IEC Site Utilities | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 1 | -1 | 2025-12-03 | 2026-04-01 |  | 1 |  |  | 1
2518. Mt Pleasant Lagoon Improvement | 100.1108. TF Setup Staging Area Laydown Yard | TF Setup Staging Area Laydown Yard | 12 Finishes | 0 |  | 8 | 8 | 8 | 0 | 2025-11-30 | 2026-11-30 |  | 8 |  |  | 8
2518. Mt Pleasant Lagoon Improvement | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 15 | 15 | 15 | 0 | 2025-11-30 | 2026-11-30 |  | 15 |  |  | 15
2518. Mt Pleasant Lagoon Improvement | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 5 | 5 | 5 | 0 | 2025-11-30 | 2026-11-30 |  | 5 |  |  | 5
2518. Mt Pleasant Lagoon Improvement | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 21 | 21 | 21 | 0 | 2025-11-30 | 2026-11-30 |  | 21 |  |  | 21
2518. Mt Pleasant Lagoon Improvement | 100.1510. S Surveying | S Surveying | 45 Survey | 2 |  | 50 | 48 | 48 | 0 | 2025-11-30 | 2026-11-30 |  | 48 |  |  | 48
2518. Mt Pleasant Lagoon Improvement | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 30.5 |  | 181.06 | 150.56 | 172.6 | -22.04 | 2025-11-30 | 2026-11-30 | 50 | 100 | 22.6 |  | 172.6
2518. Mt Pleasant Lagoon Improvement | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 91.25 |  | 164.82 | 73.57 | 102.8 | -29.23 | 2025-11-30 | 2026-11-30 | 40 | 48 | 14.8 |  | 102.8
2518. Mt Pleasant Lagoon Improvement | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 9 |  | 151.89 | 142.89 | 142.9 | -0.01 | 2025-11-30 | 2026-11-30 | 50 | 90 | 2.9 |  | 142.9
2518. Mt Pleasant Lagoon Improvement | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 8.5 |  | 228.02 | 219.52 | 219.5 | 0.02 | 2025-11-30 | 2026-11-30 | 50 | 100 | 69.5 |  | 219.5
2518. Mt Pleasant Lagoon Improvement | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 59.08 | 59.08 | 59.1 | -0.02 | 2025-11-30 | 2026-11-30 | 10 | 40 | 9.1 |  | 59.1
2518. Mt Pleasant Lagoon Improvement | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-11-30 | 2026-11-30 | 1 |  |  |  | 1
2518. Mt Pleasant Lagoon Improvement | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-11-30 | 2026-11-30 |  | 1 |  |  | 1
2518. Mt Pleasant Lagoon Improvement | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 75 | 75 | 75 | 0 | 2025-11-30 | 2026-11-30 |  | 75 |  |  | 75
2518. Mt Pleasant Lagoon Improvement | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 0 |  | 136.05 | 136.05 | 136.1 | -0.05 | 2025-11-30 | 2026-11-30 | 30 | 80 | 26.1 |  | 136.1
2518. Mt Pleasant Lagoon Improvement | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 0 |  | 4.16 | 4.16 | 4.2 | -0.04 | 2025-11-30 | 2026-11-30 |  | 4.2 |  |  | 4.2
2518. Mt Pleasant Lagoon Improvement | 200.2030. D Lagoon Demo Concrete CY | D Demolition | 11 Earth Work | 0 |  | 3 | 3 | 3 | 0 | 2025-11-30 | 2026-11-30 | 3 |  |  |  | 3
2518. Mt Pleasant Lagoon Improvement | 200.2040. LR Lagoon Landscape Seeding | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 6 | 6 | 6 | 0 | 2025-11-30 | 2026-11-30 |  |  | 6 |  | 6
2518. Mt Pleasant Lagoon Improvement | 200.2065. SFC SWPPP Setup/Maintain | SFC SWPPP | 11 Earth Work | 0 |  | 52.98 | 52.98 | 53 | -0.02 | 2025-11-30 | 2026-11-30 | 10 | 35 | 8 |  | 53
2518. Mt Pleasant Lagoon Improvement | 200.2075. FG Lagoon Concrete Interior Prep | FG Finish Grade | 11 Earth Work | 0 |  | 12.8 | 12.8 | 12.8 | 0 | 2025-11-30 | 2026-11-30 |  | 12.8 |  |  | 12.8
2518. Mt Pleasant Lagoon Improvement | 200.2080. EXS Lagoon Excavate & Liner Support & Unloading Materials | EXS Excavate Structure | 11 Earth Work | 0 |  | 450 | 450 | 450 | 0 | 2025-11-30 | 2026-11-30 | 100 | 300 | 50 |  | 450
2518. Mt Pleasant Lagoon Improvement | 200.2085. BFST Lagoon Backfill Open | BFST Backfill Structure | 11 Earth Work | 0 |  | 10 | 10 | 10 | 0 | 2025-11-30 | 2026-11-30 |  | 10 |  |  | 10
2518. Mt Pleasant Lagoon Improvement | 200.2090. ELC Lagoon Liner Anchor Trenching & Backfill | MTL Materials | 00 _Unknown PR Dept | 0 |  | 232 | 232 | 232 | 0 | 2025-11-30 | 2026-11-30 | 70 | 100 | 62 |  | 232
2518. Mt Pleasant Lagoon Improvement | 200.2920. SC Saw Cutting/Coring In House 3/4" to 6" | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 9 | 9 | 9 | 0 | 2025-11-30 | 2026-11-30 |  | 9 |  |  | 9
2518. Mt Pleasant Lagoon Improvement | 200.3000. CNC Lagoon Conc | CNC Concrete Work | 15 Concrete | 0 |  | 124.44 | 124.44 | 124.4 | 0.04 | 2025-11-30 | 2026-11-30 | 20 | 80 | 24.4 |  | 124.4
2518. Mt Pleasant Lagoon Improvement | 300.2075. FG Lagoon Fine Grading - T&M | FG Finish Grade | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-11-30 | 2026-11-30
2518. Mt Pleasant Lagoon Improvement | 400.2075. FG Tank Surface Concrete Interior Prep | FG Finish Grade | 11 Earth Work | 0 |  | 28.16 | 28.16 | 28.2 | -0.04 | 2025-11-30 | 2026-11-30 |  | 28.2 |  |  | 28.2
2518. Mt Pleasant Lagoon Improvement | 400.2080. EXS Tank Spot Excavation | EXS Excavate Structure | 11 Earth Work | 0 |  | 33 | 33 | 33 | 0 | 2025-11-30 | 2026-11-30 | 20 | 13 |  |  | 33
2518. Mt Pleasant Lagoon Improvement | 400.2085. BFST Tank Backfill Open Area | BFST Backfill Structure | 11 Earth Work | 0 |  | 75 | 75 | 75 | 0 | 2025-11-30 | 2026-11-30 | 20 | 40 | 15 |  | 75
2518. Mt Pleasant Lagoon Improvement | 400.2130. PVC Tank Lateral | PVC Pipe | 10 Pipe | 0 |  | 15 | 15 | 15 | 0 | 2025-11-30 | 2026-11-30 |  | 15 |  |  | 15
2518. Mt Pleasant Lagoon Improvement | 400.2240. PCS Tank -Place Precast Structures | PCS Precast Structures | 10 Pipe | 0 |  | 75 | 75 | 75 | 0 | 2025-11-30 | 2026-11-30 |  | 75 |  |  | 75
2518. Mt Pleasant Lagoon Improvement | 400.3000. CNC Tank -Addon Conc | CNC Concrete Work | 15 Concrete | 0 |  | 75.24 | 75.24 | 75.2 | 0.04 | 2025-11-30 | 2026-11-30 |  |  | 75.2 |  | 75.2
2518. Mt Pleasant Lagoon Improvement | 400.5000. MET Tank Pipe Bollards | MET Metals | 20 Fabrication | 0 |  | 70.5 | 70.5 | 70.5 | 0 | 2025-11-30 | 2026-11-30 |  |  | 70.5 |  | 70.5
2518. Mt Pleasant Lagoon Improvement | 400.7600. MEQ Tank- Gate Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 15 | 15 | 15 | 0 | 2025-11-30 | 2026-11-30 |  |  | 15 |  | 15
2518. Mt Pleasant Lagoon Improvement | 500.2030. D Headworks- Demo Wood Structures | D Demolition | 11 Earth Work | 0 |  | 15 | 15 | 15 | 0 | 2025-11-30 | 2026-11-30 |  | 15 |  |  | 15
2518. Mt Pleasant Lagoon Improvement | 500.2075. FG Headworks- Surface Concrete Interior Prep | FG Finish Grade | 11 Earth Work | 0 |  | 140 | 140 | 140 | 0 | 2025-11-30 | 2026-11-30 |  | 140 |  |  | 140
2518. Mt Pleasant Lagoon Improvement | 500.2080. EXS Headworks- Spot Excavation | EXS Excavate Structure | 11 Earth Work | 0 |  | 48.6 | 48.6 | 48.6 | 0 | 2025-11-30 | 2026-11-30 |  | 48.6 |  |  | 48.6
2518. Mt Pleasant Lagoon Improvement | 500.2085. BFST Headworks- Backfill Open Area | BFST Backfill Structure | 11 Earth Work | 0 |  | 108 | 108 | 108 | 0 | 2025-11-30 | 2026-11-30 |  | 108 |  |  | 108
2518. Mt Pleasant Lagoon Improvement | 500.2130. PVC Headworks- Install Valves & Box | PVC Pipe | 10 Pipe | 0 |  | 128 | 128 | 128 | 0 | 2025-11-30 | 2026-11-30 |  | 128 |  |  | 128
2518. Mt Pleasant Lagoon Improvement | 500.2140. SVR Headworks- Meter | SVR Services | 10 Pipe | 0 |  | 4 | 4 | 4 | 0 | 2025-11-30 | 2026-11-30 |  | 4 |  |  | 4
2518. Mt Pleasant Lagoon Improvement | 500.2605. BYP Headworks- Bypass VanCon Vac Truck | BYP Bypass Pumping | 10 Pipe | 0 |  | 22 | 22 | 22 | 0 | 2025-11-30 | 2026-11-30 |  | 11 | 11 |  | 22
2518. Mt Pleasant Lagoon Improvement | 500.3000. CNC Headworks- Concrete | CNC Concrete Work | 15 Concrete | 0 |  | 385.94 | 385.94 | 385.9 | 0.04 | 2025-11-30 | 2026-11-30 |  | 150 | 200 | 35.9 | 385.9
2518. Mt Pleasant Lagoon Improvement | 500.4000. MAS Headworks- Masonry Support | MAS Masonry | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2025-11-30 | 2026-11-30 |  |  | 30 |  | 30
2518. Mt Pleasant Lagoon Improvement | 500.5000. MET Headworks- Misc Metals | MET Metals | 20 Fabrication | 0 |  | 97 | 97 | 97 | 0 | 2025-11-30 | 2026-11-30 |  |  | 97 |  | 97
2518. Mt Pleasant Lagoon Improvement | 500.5500. STE Headworks- Structural Steel Install | STE Structural Steel | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-11-30 | 2026-11-30
2518. Mt Pleasant Lagoon Improvement | 500.6100. F Headworks- Framing - Set Up Enclosure | F Framing | 12 Finishes | 0 |  | 2 | 2 | 2 | 0 | 2025-11-30 | 2026-11-30 |  |  | 2 |  | 2
2518. Mt Pleasant Lagoon Improvement | 500.6300. DAW Headworks- Door Install | DAW Doors & Windows | 12 Finishes | 0 |  | 80 | 80 | 80 | 0 | 2025-11-30 | 2026-11-30 |  | 20 | 60 |  | 80
2518. Mt Pleasant Lagoon Improvement | 500.6800. CLK Headworks- Caulking for Finished Openings | CLK Caulking | 12 Finishes | 0 |  | 20 | 20 | 20 | 0 | 2025-11-30 | 2026-11-30 |  | 20 |  |  | 20
2518. Mt Pleasant Lagoon Improvement | 500.7100. IMP Headworks- Yard Hydrant Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 6 | 6 | 6 | 0 | 2025-11-30 | 2026-11-30 |  |  | 6 |  | 6
2518. Mt Pleasant Lagoon Improvement | 500.7300. PLUM Headworks- Plumbing Rough Pipe | PLUM Plumbing | 55 Mechanical | 0 |  | 27.5 | 27.5 | 27.5 | 0 | 2025-11-30 | 2026-11-30 |  |  | 27.5 |  | 27.5
2518. Mt Pleasant Lagoon Improvement | 500.7400. HVAC Headworks- Louvers | HVAC HVAC | 55 Mechanical | 0 |  | 105 | 105 | 105 | 0 | 2025-11-30 | 2026-11-30 |  | 20 | 85 |  | 105
2518. Mt Pleasant Lagoon Improvement | 500.7600. MEQ Headworks- Chlorination Equipment Liquid System Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 60 | 60 | 60 | 0 | 2025-11-30 | 2026-11-30 |  |  | 30 | 30 | 60
2518. Mt Pleasant Lagoon Improvement | 500.7700. SEQ Headworks- Grit Screen Install | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 150 | 150 | 150 | 0 | 2025-11-30 | 2026-11-30 |  | 20 | 100 | 30 | 150
2518. Mt Pleasant Lagoon Improvement | 500.7900. ELC Headworks- Instruments Install | ELC Electrical | 10 Pipe | 0 |  | 94 | 94 | 94 | 0 | 2025-11-30 | 2026-11-30 |  | 20 | 20 | 54 | 94
2518. Mt Pleasant Lagoon Improvement | 600.7900. ELC Integration Instruments Install | ELC Electrical | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2025-11-30 | 2026-11-30 |  |  |  | 40 | 40
2518. Mt Pleasant Lagoon Improvement | 800.1930. MC Misc Cleanup Well House | MC Misc Cleanup | 12 Finishes | 0 |  | 80 | 80 | 80 | 0 | 2025-11-30 | 2026-11-30 |  |  | 20 | 60 | 80
2518. Mt Pleasant Lagoon Improvement | 800.1940. PL Well House | PL Punch List Work | 12 Finishes | 0 |  | 120 | 120 | 120 | 0 | 2025-11-30 | 2026-11-30 |  |  | 20 | 100 | 120
2518. Mt Pleasant Lagoon Improvement | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2025-11-30 | 2026-11-30 |  |  |  | 0.6 | 0.6
2518. Mt Pleasant Lagoon Improvement | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2025-11-30 | 2026-11-30 |  |  |  | 0.6 | 0.6
2518. Mt Pleasant Lagoon Improvement | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 2 | 2 | 0 | 2025-11-30 | 2026-11-30 |  |  |  | 2 | 2
2518. Mt Pleasant Lagoon Improvement | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 1 | 0 | 2025-11-30 | 2026-11-30 |  |  |  | 1 | 1
2517. CUWCD Ashley Valley BWRB Rehab | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 10 | 10 | 10 | 0 | 2025-11-01 | 2027-04-01 |  | 10 |  |  | 10
2517. CUWCD Ashley Valley BWRB Rehab | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 10 | 10 | 10 | 0 | 2025-11-01 | 2027-04-01 |  | 10 |  |  | 10
2517. CUWCD Ashley Valley BWRB Rehab | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-11-01 | 2027-04-01 |  | 1 |  |  | 1
2517. CUWCD Ashley Valley BWRB Rehab | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 67 |  | 106.11 | 89 | 130 | -41 | 2025-11-01 | 2027-04-01 | 10 | 20 | 60 | 40 | 130
2517. CUWCD Ashley Valley BWRB Rehab | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 25.75 |  | 87.54 | 61.79 | 65.8 | -4.01 | 2025-11-01 | 2027-04-01 |  | 25.8 | 20 | 20 | 65.8
2517. CUWCD Ashley Valley BWRB Rehab | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 0 |  | 80.71 | 80.71 | 80.7 | 0.01 | 2025-11-01 | 2027-04-01 |  | 20 | 40 | 20.7 | 80.7
2517. CUWCD Ashley Valley BWRB Rehab | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 0 |  | 120.93 | 120.93 | 120.9 | 0.03 | 2025-11-01 | 2027-04-01 |  | 40 | 60 | 20.9 | 120.9
2517. CUWCD Ashley Valley BWRB Rehab | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 31.68 | 31.68 | 31.7 | -0.02 | 2025-11-01 | 2027-04-01 |  | 10 | 11.7 | 10 | 31.7
2517. CUWCD Ashley Valley BWRB Rehab | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-11-01 | 2027-04-01 |  | 1 |  |  | 1
2517. CUWCD Ashley Valley BWRB Rehab | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-11-01 | 2027-04-01 |  | 1 |  |  | 1
2517. CUWCD Ashley Valley BWRB Rehab | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 60 | 60 | 60 | 0 | 2025-11-01 | 2027-04-01 |  | 20 | 20 | 20 | 60
2517. CUWCD Ashley Valley BWRB Rehab | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 0 |  | 24 | 24 | 24 | 0 | 2025-11-01 | 2027-04-01 |  |  | 24 |  | 24
2517. CUWCD Ashley Valley BWRB Rehab | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 0 |  | 20.41 | 20.41 | 20.4 | 0.01 | 2025-11-01 | 2027-04-01 |  |  | 20.4 |  | 20.4
2517. CUWCD Ashley Valley BWRB Rehab | 200.1800. PH Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2025-11-01 | 2027-04-01 |  | 40 |  |  | 40
2517. CUWCD Ashley Valley BWRB Rehab | 200.2030. D Demo Pipeline Removal - Testing for Leakage Delay | D Demolition | 11 Earth Work | 0 |  | 58.5 | 58.5 | 58.5 | 0 | 2025-11-01 | 2027-04-01 |  | 58.5 |  |  | 58.5
2517. CUWCD Ashley Valley BWRB Rehab | 200.2075. FG Subgrade Prep Scarify & Compact Small Area less than 5000 | FG Finish Grade | 11 Earth Work | 0 |  | 40 | 40 | 40 | 0 | 2025-11-01 | 2027-04-01 |  |  | 40 |  | 40
2517. CUWCD Ashley Valley BWRB Rehab | 200.2080. EXS Open Cut Upper Level 0' to 5' Vault 200 Ex | EXS Excavate Structure | 11 Earth Work | 0 |  | 45 | 45 | 45 | 0 | 2025-11-01 | 2027-04-01 |  |  | 45 |  | 45
2517. CUWCD Ashley Valley BWRB Rehab | 200.2085. BFST Backfill Open Area w/ S&G 10' to 0' Faster | BFST Backfill Structure | 11 Earth Work | 0 |  | 75 | 75 | 75 | 0 | 2025-11-01 | 2027-04-01 |  |  | 50 | 25 | 75
2517. CUWCD Ashley Valley BWRB Rehab | 200.2140. SVR Lateral | SVR Services | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2025-11-01 | 2027-04-01 |  |  | 40 |  | 40
2517. CUWCD Ashley Valley BWRB Rehab | 200.2610. PT Fill/Test Air Test Pipe | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 20 | 20 | 20 | 0 | 2025-11-01 | 2027-04-01 |  |  | 10 | 10 | 20
2517. CUWCD Ashley Valley BWRB Rehab | 200.3000. CNC Conc Form Ftng/Slab 4"-12" Thick Dim Install | CNC Concrete Work | 15 Concrete | 0 |  | 78 | 78 | 78 | 0 | 2025-11-01 | 2027-04-01 |  |  | 50 | 28 | 78
2517. CUWCD Ashley Valley BWRB Rehab | 200.5000. MET Unistrut Install | MET Metals | 20 Fabrication | 0 |  | 130 | 130 | 130 | 0 | 2025-11-01 | 2027-04-01 |  | 30 | 75 | 25 | 130
2517. CUWCD Ashley Valley BWRB Rehab | 200.5400. HAT Hatch Vault Install | HAT Hatch/Skylights | 12 Finishes | 0 |  | 12 | 12 | 12 | 0 | 2025-11-01 | 2027-04-01 |  |  | 12 |  | 12
2517. CUWCD Ashley Valley BWRB Rehab | 200.6800. CLK Caulking for Concrete | CLK Caulking | 12 Finishes | 0 |  | 6 | 6 | 6 | 0 | 2025-11-01 | 2027-04-01 |  |  | 6 |  | 6
2517. CUWCD Ashley Valley BWRB Rehab | 200.7100. IMP 1" PVC Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 480 | 480 | 480 | 0 | 2025-11-01 | 2027-04-01 |  | 80 | 300 | 100 | 480
2517. CUWCD Ashley Valley BWRB Rehab | 200.7500. PUMP Pump Install Small | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 75 | 75 | 75 | 0 | 2025-11-01 | 2027-04-01 |  |  | 75 |  | 75
2517. CUWCD Ashley Valley BWRB Rehab | 200.7600. MEQ Gate Remvoal 24" to 48" | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 90 | 90 | 90 | 0 | 2025-11-01 | 2027-04-01 |  |  | 90 |  | 90
2517. CUWCD Ashley Valley BWRB Rehab | 800.1930. MC Misc Cleanup Pump Station | MC Misc Cleanup | 12 Finishes | 0 |  | 40 | 40 | 40 | 0 | 2025-11-01 | 2027-04-01 |  |  |  | 40 | 40
2517. CUWCD Ashley Valley BWRB Rehab | 800.1940. PL Pump Station | PL Punch List Work | 12 Finishes | 0 |  | 40 | 40 | 40 | 0 | 2025-11-01 | 2027-04-01 |  |  |  | 40 | 40
2517. CUWCD Ashley Valley BWRB Rehab | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-11-01 | 2027-04-01
2517. CUWCD Ashley Valley BWRB Rehab | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-11-01 | 2027-04-01
2517. CUWCD Ashley Valley BWRB Rehab | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-11-01 | 2027-04-01
2517. CUWCD Ashley Valley BWRB Rehab | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 0 | 0 | 0 | 2025-11-01 | 2027-04-01
2517. CUWCD Ashley Valley BWRB Rehab | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-11-01 | 2027-04-01
2516. Ephraim Lower Penstock Replacement | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 166 |  | 296.67 | 125 | 175 | -50 | 2025-10-31 | 2026-10-31 | 50 | 100 |  | 25 | 175
2516. Ephraim Lower Penstock Replacement | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 370.92 |  | 270.1 | 200 | 250 | -50 | 2025-10-31 | 2026-10-31 | 75 | 100 |  | 75 | 250
2516. Ephraim Lower Penstock Replacement | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 92.3 |  | 248.93 | 150 | 150 | 0 | 2025-10-31 | 2026-10-31 | 50 | 50 |  | 50 | 150
2516. Ephraim Lower Penstock Replacement | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 393.05 |  | 373.53 | 300 | 300 | 0 | 2025-10-31 | 2026-10-31 | 100 | 120 |  | 80 | 300
2516. Ephraim Lower Penstock Replacement | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 72 |  | 97.06 | 100 | 100 | 0 | 2025-10-31 | 2026-10-31 | 50 | 50 |  |  | 100
2516. Ephraim Lower Penstock Replacement | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 2 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 2 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 150.1230. T Transporting | T Transporting | 40 Drivers | 179.68 |  | 200 | 150 | 200 | -50 | 2025-10-31 | 2026-10-31 | 75 | 100 |  | 25 | 200
2516. Ephraim Lower Penstock Replacement | 150.2750. H Hauling Single Side Dump - 30 ton | H Hauling | 40 Drivers | 135.12 |  | 343.34 | 1000 | 1000 | 0 | 2025-10-31 | 2026-10-31 | 500 | 400 |  | 100 | 1000
2516. Ephraim Lower Penstock Replacement | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 3 |  | 9.57 | 20 | 25 | -5 | 2025-10-31 | 2026-10-31 |  | 25 |  |  | 25
2516. Ephraim Lower Penstock Replacement | 161.5100. WE Welding/Painting Hold Holes | W Welding | 20 Fabrication | 0 |  | 220 | 220 | 200 | 20 | 2025-10-31 | 2026-10-31 | 50 | 100 |  | 50 | 200
2516. Ephraim Lower Penstock Replacement | 200.1515. S Survey (for Welded steel only - per specs.) | S Drone/Lidar Requirements | 45 Survey | 165.73 |  | 550 | 300 | 350 | -50 | 2025-10-31 | 2026-10-31 | 150 | 150 |  | 50 | 350
2516. Ephraim Lower Penstock Replacement | 200.1600. Traffic Control | TC Traffic Control | 30 Traffic Control | 9.5 |  | 0 | 20 | 20 | 0 | 2025-10-31 | 2026-10-31 | 5 | 15 |  |  | 20
2516. Ephraim Lower Penstock Replacement | 200.1650. SB Signage Install Post w/ Sign | SB Signage | 12 Finishes | 0 |  | 15 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.1800. PH Potholing - VanCon 200 Ex | PH Potholing | 10 Pipe | 487.01 |  | 320 | 0 | 50 | -50 | 2025-10-31 | 2026-10-31 | 10 | 40 |  |  | 50
2516. Ephraim Lower Penstock Replacement | 200.2020. CG Remove Vegetaton Excavator | CG Clearing/Grubbing | 11 Earth Work | 62.7 |  | 250 | 50 | 50 | 0 | 2025-10-31 | 2026-10-31 | 25 | 25 |  |  | 50
2516. Ephraim Lower Penstock Replacement | 200.2030. D Demo Pipeline Removal (trackhoe with breaker | D Demolition | 11 Earth Work | 2.75 |  | 63 | 50 | 50 | 0 | 2025-10-31 | 2026-10-31 | 25 | 25 |  |  | 50
2516. Ephraim Lower Penstock Replacement | 200.2065. SFC SWPPP Plans & Inspections | SFC SWPPP | 11 Earth Work | 0 |  | 75.01 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.2075. FG Roadbase Leveling | FG Finish Grade | 11 Earth Work | 0 |  | 382.2 | 380 | 380 | 0 | 2025-10-31 | 2026-10-31 | 180 | 180 |  | 20 | 380
2516. Ephraim Lower Penstock Replacement | 200.2085. SG1 On-Site Allu Bucket Screening | BFST Backfill Structure | 11 Earth Work | 580.13 |  | 1971.37 | 500 | 100 | 400 | 2025-10-31 | 2026-10-31 | 50 | 50 |  |  | 100
2516. Ephraim Lower Penstock Replacement | 200.2120. DIP Fitting/Valve | DIP Ductile Iron Pipe | 10 Pipe | 556.01 |  | 202.14 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.2130. PVC Install Conc Valve Collar | PVC Pipe | 10 Pipe | 220.46 |  | 210.8 | 20 | 20 | 0 | 2025-10-31 | 2026-10-31 | 15 | 5 |  |  | 20
2516. Ephraim Lower Penstock Replacement | 200.2140. IMP 4"-6" Fitting/Valve Install | SVR Services | 10 Pipe | 89.85 |  | 141.32 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.2160. WSP Addon: Connections/Tie-Ins | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 1921.57 |  | 3612.92 | 2800 | 2500 | 300 | 2025-10-31 | 2026-10-31 | 1100 | 1100 |  | 300 | 2500
2516. Ephraim Lower Penstock Replacement | 200.2170. HDPE Extras: Air Vac Assembly | HDPE Fusion Pipe <15' Depth | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2025-10-31 | 2026-10-31 |  | 40 |  |  | 40
2516. Ephraim Lower Penstock Replacement | 200.2240. PCS Backfill | PCS Precast Structures | 10 Pipe | 3.85 |  | 235.72 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.2610. PT Fill/Test/Flush WSP | PT Pressure Test/Chlorinating | 10 Pipe | 6.5 |  | 145.08 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.2710. FWF Flowfill Utility Support | FWF Flowable Fill | 15 Concrete | 0 |  | 12 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.3000. CNC Addon Conc Access Dowels - Drill & Epoxy #4-#6 10"-24" | CNC Concrete Work | 15 Concrete | 0 |  | 130.07 | 125 | 125 | 0 | 2025-10-31 | 2026-10-31 | 45 | 80 |  |  | 125
2516. Ephraim Lower Penstock Replacement | 200.3100. CNR Rebar VanCon Install | CNC Rebar | 15 Concrete | 0 |  | 13.5 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 200.5000. MET Air Vents on Vault | MET Metals | 20 Fabrication | 0 |  | 30 | 30 | 30 | 0 | 2025-10-31 | 2026-10-31 |  | 30 |  |  | 30
2516. Ephraim Lower Penstock Replacement | 200.5100. WE Butt Weld 0.375 Wall <20 inch | W Welding | 20 Fabrication | 411.36 |  | 2732.5 | 1500 | 1500 | 0 | 2025-10-31 | 2026-10-31 | 600 | 750 |  | 150 | 1500
2516. Ephraim Lower Penstock Replacement | 200.5400. HAT Hatch Vault Install | HAT Hatch/Skylights | 12 Finishes | 0 |  | 36 | 35 | 35 | 0 | 2025-10-31 | 2026-10-31 |  | 35 |  |  | 35
2516. Ephraim Lower Penstock Replacement | 300.5000. UN Unloading Pipe | MET Metals | 20 Fabrication | 173.99 |  | 24 | 0 | 25 | -25 | 2025-10-31 | 2026-10-31 | 25 |  |  |  | 25
2516. Ephraim Lower Penstock Replacement | 800.1930. MC Misc Cleanup Pressurized Water/Irrigation Transmission | MC Misc Cleanup | 12 Finishes | 0 |  | 300 | 300 | 300 | 0 | 2025-10-31 | 2026-10-31 |  |  |  | 300 | 300
2516. Ephraim Lower Penstock Replacement | 800.1940. PL Pressurized/Water/Irrigation/Transmission | PL Punch List Work | 12 Finishes | 0 |  | 225 | 225 | 225 | 0 | 2025-10-31 | 2026-10-31 |  |  |  | 225 | 225
2516. Ephraim Lower Penstock Replacement | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 6 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2516. Ephraim Lower Penstock Replacement | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 8.37 |  | 2 | 0 | 0 | 0 | 2025-10-31 | 2026-10-31
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1300. PD Per Diem & Travel | PDT Per Diem for Budget Only | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 3 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 34.5 |  | 12.83 | 5 | 5 | 0 | 2025-10-07 | 2026-04-15 | 5 |  |  |  | 5
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 9.17 |  | 11.77 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 5 |  | 10.92 | 10 | 10 | 0 | 2025-10-07 | 2026-04-15 | 10 |  |  |  | 10
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 58.4 |  | 15.92 | 60 | 10 | 50 | 2025-10-07 | 2026-04-15 | 10 |  |  |  | 10
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 4.82 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 150.1230. T Transporting | T Transporting | 40 Drivers | 26.23 |  | 40 | 20 | 0 | 20 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 200.2180. CATH Test Station Steel Coupon L&E | CATH Cathodic Protection | 10 Pipe | 0 |  | 20 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 200.7600. MEQ Removal of Gate L&E | MEQ Mechanical Equipment | 55 Mechanical | 24.6 |  | 30 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 300.7600. MEQ Installation of Gate L&E | MEQ Mechanical Equipment | 55 Mechanical | 22.4 |  | 60 | 200 | 100 | 100 | 2025-10-07 | 2026-04-15 | 100 |  |  |  | 100
2515. UWCD Steinaker Service Canal Gate Rahab | 800.1930. MC Misc Cleanup Pump Station | MC Misc Cleanup | 12 Finishes | 0 |  | 20 | 20 | 20 | 0 | 2025-10-07 | 2026-04-15 | 20 |  |  |  | 20
2515. UWCD Steinaker Service Canal Gate Rahab | 800.1940. PL Pump Station | PL Punch List Work | 12 Finishes | 0 |  | 20 | 20 | 20 | 0 | 2025-10-07 | 2026-04-15 | 20 |  |  |  | 20
2515. UWCD Steinaker Service Canal Gate Rahab | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2515. UWCD Steinaker Service Canal Gate Rahab | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-07 | 2026-04-15
2513. CUWCD Summit Creek Irrigation HDPE | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 4.95 |  | 5 | 10 | 10 | 0 | 2025-10-01 | 2026-03-31 | 10 |  |  |  | 10
2513. CUWCD Summit Creek Irrigation HDPE | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 100.1510. S Surveying | S Surveying | 45 Survey | 80.62 |  | 65 | 15 | 50 | -35 | 2025-10-01 | 2026-03-31 | 50 |  |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 100.1515. S Drone/Lidar Requirements for Job | S Drone/Lidar Requirements | 45 Survey | 0 |  | 20 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 44.5 |  | 171.04 | 40 | 50 | -10 | 2025-10-01 | 2026-03-31 | 40 | 10 |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 5.25 |  | 161.72 | 50 | 50 | 0 | 2025-10-01 | 2026-03-31 | 40 | 10 |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 115.92 |  | 100.81 | 30 | 50 | -20 | 2025-10-01 | 2026-03-31 | 30 | 20 |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 115.97 |  | 198.63 | 90 | 100 | -10 | 2025-10-01 | 2026-03-31 | 100 |  |  |  | 100
2513. CUWCD Summit Creek Irrigation HDPE | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 36 |  | 20.08 | 25 | 25 | 0 | 2025-10-01 | 2026-03-31 | 25 |  |  |  | 25
2513. CUWCD Summit Creek Irrigation HDPE | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 11 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 150.1230. T Transporting | T Transporting | 40 Drivers | 48.45 |  | 40 | 40 | 50 | -10 | 2025-10-01 | 2026-03-31 | 50 |  |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 150.2750. H Hauling Single Side Dump | H Hauling | 40 Drivers | 92.16 |  | 150.09 | 0 | 50 | -50 | 2025-10-01 | 2026-03-31 | 50 |  |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 150.2760. HO Haul Off Single Side Dump | HO Haul Off | 40 Drivers | 1 |  | 14 | 0 | 25 | -25 | 2025-10-01 | 2026-03-31 | 25 |  |  |  | 25
2513. CUWCD Summit Creek Irrigation HDPE | 160.5000. MET Misc. Metals Material Field Materials | MET Metals | 20 Fabrication | 39.77 |  | 0 | 0 | 10 | -10 | 2025-10-01 | 2026-03-31 | 10 |  |  |  | 10
2513. CUWCD Summit Creek Irrigation HDPE | 200.1800. PH Potholing - VanCon 200 Ex | PH Potholing | 10 Pipe | 8 |  | 45 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 200.2030. D Demo 20" Pipeline Removal | D Demolition | 11 Earth Work | 38.92 |  | 66 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 200.2170. HDPE 30" Trench/Shore | HDPE Fusion Pipe <15' Depth | 10 Pipe | 145.66 |  | 392.5 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 200.2610. PT Fill/Test/Flush HDPE | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 30 | 50 | 30 | 20 | 2025-10-01 | 2026-03-31 | 30 |  |  |  | 30
2513. CUWCD Summit Creek Irrigation HDPE | 210.2170. HDPE 30" Pipe Fusion | HDPE Fusion Pipe <15' Depth | 10 Pipe | 323.66 |  | 225.99 | 0 | 15 | -15 | 2025-10-01 | 2026-03-31 | 15 |  |  |  | 15
2513. CUWCD Summit Creek Irrigation HDPE | 220.2170. HDPE Backfill Trench | HDPE Fusion Pipe <15' Depth | 10 Pipe | 21.8 |  | 341.79 | 350 | 300 | 50 | 2025-10-01 | 2026-03-31 | 300 |  |  |  | 300
2513. CUWCD Summit Creek Irrigation HDPE | 230.2170. HDPE 30" Connection to CUWCD | HDPE Fusion Pipe <15' Depth | 10 Pipe | 13.48 |  | 15 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 240.2080. EXS Bore Pit Excavation | EXS Excavate Structure | 11 Earth Work | 107.49 |  | 55.04 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 240.2085. BFST Bore Pit Backfil | BFST Backfill Structure | 11 Earth Work | 0 |  | 40 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 250.2080. BFST Energy Vault Backfill | EXS Excavate Structure | 11 Earth Work | 10.15 |  | 41 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 250.2170. HDPE Energy Vault Pipe Fusion | HDPE Fusion Pipe <15' Depth | 10 Pipe | 0 |  | 3 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 250.2595. CD Coffer Dam Removal | CD Coffer Dams | 10 Pipe | 0 |  | 80 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 250.2600. DW Energy Vault Dewatering | DW Dewatering | 10 Pipe | 1097.02 |  | 75 | 35 | 175 | -140 | 2025-10-01 | 2026-03-31 | 175 |  |  |  | 175
2513. CUWCD Summit Creek Irrigation HDPE | 250.3000. CNC Energy Vault Concrete L&E | CNC Concrete Work | 15 Concrete | 268.22 |  | 202.61 | 0 | 15 | -15 | 2025-10-01 | 2026-03-31 | 15 |  |  |  | 15
2513. CUWCD Summit Creek Irrigation HDPE | 250.3100. CNR Energy Vault Rebar L&E | CNC Rebar | 15 Concrete | 0 |  | 39 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 250.5000. MET Energy Vault Misc Metals Install | MET Metals | 20 Fabrication | 16.5 |  | 25.8 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 270.2170. HDPE Flow Meter MH Connections | HDPE Fusion Pipe <15' Depth | 10 Pipe | 1 |  | 12 | 50 | 50 | 0 | 2025-10-01 | 2026-03-31 |  |  |  | 50 | 50
2513. CUWCD Summit Creek Irrigation HDPE | 270.2240. PCS Flow Meter Manhole Install | PCS Precast Structures | 10 Pipe | 4.27 |  | 40 | 0 | 60 | -60 | 2025-10-01 | 2026-03-31 |  |  |  | 60 | 60
2513. CUWCD Summit Creek Irrigation HDPE | 280.2130. PVC 20" PVC Connection Install | PVC Pipe | 10 Pipe | 0 |  | 92.78 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 290.2170. HDPE 30" Cross & Valve Install | HDPE Fusion Pipe <15' Depth | 10 Pipe | 57.78 |  | 46.02 | 20 | 50 | -30 | 2025-10-01 | 2026-03-31 | 50 |  |  |  | 50
2513. CUWCD Summit Creek Irrigation HDPE | 300.2130. PVC 18" PVC Waterline w/ Valve | PVC Pipe | 10 Pipe | 0 |  | 76.12 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 300.2610. PT Fill/Test/Flush PVC/DIP | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 6 | 0 | 6 | -6 | 2025-10-01 | 2026-03-31 | 6 |  |  |  | 6
2513. CUWCD Summit Creek Irrigation HDPE | 800.1930. MC Misc Cleanup Pressurized Water/Irrigation Transmission | MC Misc Cleanup | 12 Finishes | 0 |  | 60 | 60 | 60 | 0 | 2025-10-01 | 2026-03-31 |  | 60 |  |  | 60
2513. CUWCD Summit Creek Irrigation HDPE | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2513. CUWCD Summit Creek Irrigation HDPE | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-31
2512. South SLC Davis Tank Lid Replacement | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 6.25 |  | 15 | 8.75 | 12.8 | -4.05 | 2025-10-01 | 2026-03-13 | 6 | 6.8 |  |  | 12.8
2512. South SLC Davis Tank Lid Replacement | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 5 | 5 | 5 | 0 | 2025-10-01 | 2026-03-13 | 2 | 3 |  |  | 5
2512. South SLC Davis Tank Lid Replacement | 100.1500. VIS Meetings (Vision MTG) | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 51 | 20 | 20 | 0 | 2025-10-01 | 2026-03-13 | 10 | 10 |  |  | 20
2512. South SLC Davis Tank Lid Replacement | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 87.5 |  | 168.33 | 74 | 86 | -12 | 2025-10-01 | 2026-03-13 | 40 | 46 |  |  | 86
2512. South SLC Davis Tank Lid Replacement | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 92.17 |  | 146.12 | 50.7 | 73.5 | -22.8 | 2025-10-01 | 2026-03-13 | 25 | 48.5 |  |  | 73.5
2512. South SLC Davis Tank Lid Replacement | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 20.61 |  | 136.82 | 94.72 | 86.7 | 8.02 | 2025-10-01 | 2026-03-13 | 40 | 46.7 |  |  | 86.7
2512. South SLC Davis Tank Lid Replacement | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 97.09 |  | 214.72 | 111.56 | 154.5 | -42.94 | 2025-10-01 | 2026-03-13 | 100 | 54.5 |  |  | 154.5
2512. South SLC Davis Tank Lid Replacement | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 15 |  | 252.76 | 85 | 100 | -15 | 2025-10-01 | 2026-03-13 | 50 | 50 |  |  | 100
2512. South SLC Davis Tank Lid Replacement | 100.1705. | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | -1 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 100.1706. | FS Executive | 60 Operations (PM/PE) | 0 |  | -1 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 150.1230. T Transporting | T Transporting | 40 Drivers | 77.44 |  | 105 | 26.49 | 22.3 | 4.19 | 2025-10-01 | 2026-03-13 | 10 | 12.3 |  |  | 22.3
2512. South SLC Davis Tank Lid Replacement | 200.2610. PT Fill/Test Hydraulic Structures L&E | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 150 | 150 | 150 | 0 | 2025-10-01 | 2026-03-13 | 75 | 75 |  |  | 150
2512. South SLC Davis Tank Lid Replacement | 200.5100. WE Welding - Safety Posts & Access L&E | W Welding | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 200.7400. HVAC Louvers | HVAC HVAC | 55 Mechanical | 24.65 |  | 24 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 210.5100. WE Welding - Cutting in Access & Prep - 40 LF | W Welding | 20 Fabrication | 29.22 |  | 15 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 220.2030. WE Demo Existing Tank Lid | D Demolition | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 220.3000. CNC Conc Form Lid & Shoring | CNC Concrete Work | 15 Concrete | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 230.5100. WE Welding C Channel Welding & Fitting | W Welding | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 231.5100. WE Welding - Structural Steel Frame | W Welding | 20 Fabrication | 31.85 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 232.5100. WE Welding - Hatch Openings | W Welding | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 233.5100. WE Welding - New Sheets/Skin - 70 Total | W Welding | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 234.5100. WE Welding - Attach Existing Columns - 7 ea | W Welding | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 240.5100. MET Ladder & Handrail Install | W Welding | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 240.7100. IMP Install Flanged Coupling Adapter | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 9 | 9 | 0 | 9 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 250.5400. HAT Hatch Install | HAT Hatch/Skylights | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 800.1930. MC Misc Cleanup Water Tank | MC Misc Cleanup | 12 Finishes | 5 |  | 120 | 115 | 120 | -5 | 2025-10-01 | 2026-03-13 | 100 | 20 |  |  | 120
2512. South SLC Davis Tank Lid Replacement | 800.1940. PL Water Tanks | PL Punch List Work | 12 Finishes | 0 |  | 135 | 135 | 135 | 0 | 2025-10-01 | 2026-03-13 | 120 | 15 |  |  | 135
2512. South SLC Davis Tank Lid Replacement | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2512. South SLC Davis Tank Lid Replacement | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-10-01 | 2026-03-13
2511. GHID 25H East Rec. & Decker N. Improvements | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 95.5 |  | 3 | 30 | 10 | 20 | 2025-09-30 | 2025-12-31 | 8 | 2 |  |  | 10
2511. GHID 25H East Rec. & Decker N. Improvements | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 102.46 |  | 4.73 | 0 | 10 | -10 | 2025-09-30 | 2025-12-31 | 5 | 5 |  |  | 10
2511. GHID 25H East Rec. & Decker N. Improvements | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 9 |  | 2.66 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 215.96 |  | 3.5 | 40 | 35 | 5 | 2025-09-30 | 2025-12-31 | 20 | 15 |  |  | 35
2511. GHID 25H East Rec. & Decker N. Improvements | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 0 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 20 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 0 |  | 1.04 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 200.1800. PH Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 0 |  | 15 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 200.2030. D Demo | D Demolition | 11 Earth Work | 1.5 |  | 6 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 200.2605. BYP Bypass VanCon Vac Truck | BYP Bypass Pumping | 10 Pipe | 5 |  | 23 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 200.2606. Bypass Watch Vancon | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 200.3000. CNC Conc Form & Pour | CNC Concrete Work | 15 Concrete | 39.43 |  | 48.96 | 9.53 | 19.1 | -9.57 | 2025-09-30 | 2025-12-31 | 19.1 |  |  |  | 19.1
2511. GHID 25H East Rec. & Decker N. Improvements | 200.3100. CNR Rebar VanCon Install | CNC Rebar | 15 Concrete | 4.5 |  | 3 | 0 | 1 | -1 | 2025-09-30 | 2025-12-31 | 1 |  |  |  | 1
2511. GHID 25H East Rec. & Decker N. Improvements | 200.5000. MET Misc Metals Install | MET Metals | 20 Fabrication | 17.82 |  | 204 | 186.18 | 190.9 | -4.72 | 2025-09-30 | 2025-12-31 | 80 | 110.9 |  |  | 190.9
2511. GHID 25H East Rec. & Decker N. Improvements | 200.6300. DAW Door Removal & Install | DAW Doors & Windows | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2025-09-30 | 2025-12-31 |  | 30 |  |  | 30
2511. GHID 25H East Rec. & Decker N. Improvements | 200.7400. HVAC Louvers L&E | HVAC HVAC | 55 Mechanical | 0 |  | 12 | 12 | 12 | 0 | 2025-09-30 | 2025-12-31 | 12 |  |  |  | 12
2511. GHID 25H East Rec. & Decker N. Improvements | 200.7900. ELC Instruments L&E | ELC Electrical | 10 Pipe | 0 |  | 12 | 12 | 12 | 0 | 2025-09-30 | 2025-12-31 | 12 |  |  |  | 12
2511. GHID 25H East Rec. & Decker N. Improvements | 800.1940. PL Pump Station | PL Punch List Work | 12 Finishes | 0 |  | 45 | 45 | 45 | 0 | 2025-09-30 | 2025-12-31 |  | 45 |  |  | 45
2511. GHID 25H East Rec. & Decker N. Improvements | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2511. GHID 25H East Rec. & Decker N. Improvements | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-09-30 | 2025-12-31
2510. Draper Pump Station #3 Improvements | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 5 | 5 | 5 | 0 | 2025-09-01 | 2026-03-15 | 5 |  |  |  | 5
2510. Draper Pump Station #3 Improvements | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 5 | 5 | 5 | 0 | 2025-09-01 | 2026-03-15 | 5 |  |  |  | 5
2510. Draper Pump Station #3 Improvements | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 21 | 21 | 21 | 0 | 2025-09-01 | 2026-03-15 | 21 |  |  |  | 21
2510. Draper Pump Station #3 Improvements | 100.1510. S Surveying | S Surveying | 45 Survey | 13.33 |  | 20 | 5 | 10 | -5 | 2025-09-01 | 2026-03-15 | 5 | 5 |  |  | 10
2510. Draper Pump Station #3 Improvements | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 218.82 |  | 177.01 | 60 | 100 | -40 | 2025-09-01 | 2026-03-15 | 50 | 50 |  |  | 100
2510. Draper Pump Station #3 Improvements | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 197 |  | 161.14 | 20 | 50 | -30 | 2025-09-01 | 2026-03-15 | 25 | 25 |  |  | 50
2510. Draper Pump Station #3 Improvements | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 47.5 |  | 148.49 | 80 | 120 | -40 | 2025-09-01 | 2026-03-15 | 60 | 60 |  |  | 120
2510. Draper Pump Station #3 Improvements | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 77 |  | 222.92 | 180 | 200 | -20 | 2025-09-01 | 2026-03-15 | 100 | 100 |  |  | 200
2510. Draper Pump Station #3 Improvements | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 57.78 | 60 | 60 | 0 | 2025-09-01 | 2026-03-15 | 35 | 25 |  |  | 60
2510. Draper Pump Station #3 Improvements | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 150.1230. T Transporting | T Transporting | 40 Drivers | 28.02 |  | 100 | 100 | 80 | 20 | 2025-09-01 | 2026-03-15 | 60 | 20 |  |  | 80
2510. Draper Pump Station #3 Improvements | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 2.83 |  | 30.66 | 40 | 40 | 0 | 2025-09-01 | 2026-03-15 | 30 | 10 |  |  | 40
2510. Draper Pump Station #3 Improvements | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 0 |  | 8.95 | 10 | 10 | 0 | 2025-09-01 | 2026-03-15 | 10 |  |  |  | 10
2510. Draper Pump Station #3 Improvements | 161.2090. MTL WSP Pipe Materials | MTL Materials | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 161.3000. CNC Mix Concrete Polymer Bag | CNC Concrete Work | 15 Concrete | 0 |  | 30 | 30 | 30 | 0 | 2025-09-01 | 2026-03-15 | 20 | 10 |  |  | 30
2510. Draper Pump Station #3 Improvements | 180.6500. P Paint & Coating Sub | P Painting | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 200.1600. TC Traffic Control Reports | TC Traffic Control | 30 Traffic Control | 35.55 |  | 60 | 40 | 40 | 0 | 2025-09-01 | 2026-03-15 | 30 | 10 |  |  | 40
2510. Draper Pump Station #3 Improvements | 200.2030. D PS-3 Demo Concrete L&E | D Demolition | 11 Earth Work | 28.62 |  | 6 | 10 | 10 | 0 | 2025-09-01 | 2026-03-15 | 10 |  |  |  | 10
2510. Draper Pump Station #3 Improvements | 200.2040. LR PS-3 Landscape Seeding L&E | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 3 | 3 | 3 | 0 | 2025-09-01 | 2026-03-15 |  | 3 |  |  | 3
2510. Draper Pump Station #3 Improvements | 200.2065. SFC SWPPP Plans & Inspections | SFC SWPPP | 11 Earth Work | 0 |  | 59.64 | 10 | 10 | 0 | 2025-09-01 | 2026-03-15 | 5 | 5 |  |  | 10
2510. Draper Pump Station #3 Improvements | 200.2075. FG PS-3 Roadbase/Gravel Small Areas | FG Finish Grade | 11 Earth Work | 0 |  | 12 | 12 | 12 | 0 | 2025-09-01 | 2026-03-15 |  | 12 |  |  | 12
2510. Draper Pump Station #3 Improvements | 200.2080. EXS PS-3 Excavation L&E | EXS Excavate Structure | 11 Earth Work | 0 |  | 80 | 80 | 80 | 0 | 2025-09-01 | 2026-03-15 | 50 | 30 |  |  | 80
2510. Draper Pump Station #3 Improvements | 200.3000. CNC PS-3 Concrete L&E | CNC Concrete Work | 15 Concrete | 4.5 |  | 178.56 | 175 | 175 | 0 | 2025-09-01 | 2026-03-15 | 120 | 55 |  |  | 175
2510. Draper Pump Station #3 Improvements | 200.5000. MET PS-3 Pipe Supports L&E | MET Metals | 20 Fabrication | 0 |  | 60 | 60 | 60 | 0 | 2025-09-01 | 2026-03-15 | 20 | 40 |  |  | 60
2510. Draper Pump Station #3 Improvements | 200.5400. HAT PS-3 Hatch Vault L&E | HAT Hatch/Skylights | 12 Finishes | 0 |  | 15 | 15 | 15 | 0 | 2025-09-01 | 2026-03-15 |  | 15 |  |  | 15
2510. Draper Pump Station #3 Improvements | 200.6100. F PS-3 Visqueen Install L&E | F Framing | 12 Finishes | 0 |  | 15 | 15 | 15 | 0 | 2025-09-01 | 2026-03-15 |  | 15 |  |  | 15
2510. Draper Pump Station #3 Improvements | 200.7100. PS3 MEQ Pipe Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 508.5 | 600 | 508 | 92 | 2025-09-01 | 2026-03-15 | 300 | 208 |  |  | 508
2510. Draper Pump Station #3 Improvements | 200.7300. PLUM PS-3 Underground Trench Drains L&E | PLUM Plumbing | 55 Mechanical | 0 |  | 120 | 120 | 120 | 0 | 2025-09-01 | 2026-03-15 | 60 | 60 |  |  | 120
2510. Draper Pump Station #3 Improvements | 200.7500. PUMP PS-3 Pump Install L&E | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 60 | 60 | 60 | 0 | 2025-09-01 | 2026-03-15 |  | 60 |  |  | 60
2510. Draper Pump Station #3 Improvements | 200.7600. MEQ PS-3 Surge Tank Finishes Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 90 | 90 | 90 | 0 | 2025-09-01 | 2026-03-15 | 20 | 70 |  |  | 90
2510. Draper Pump Station #3 Improvements | 200.7900. ELC PS-3 Electrical/Fiber/Dry Utilities Trenching | ELC Electrical | 10 Pipe | 0 |  | 20 | 20 | 20 | 0 | 2025-09-01 | 2026-03-15 | 20 |  |  |  | 20
2510. Draper Pump Station #3 Improvements | 200.8000. PS3 Paint Removal Change Order | HP Helical Piers | 11 Earth Work | 5 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 200.9000. PS3 Floor Drain Concrete Removeal | _Unknown Phase Master | 00 _Unknown PR Dept | 29.95 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 300.2040. LR Lower Drain Landscape Seeding | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 3 | 3 | 3 | 0 | 2025-09-01 | 2026-03-15 |  | 3 |  |  | 3
2510. Draper Pump Station #3 Improvements | 300.2075. FG Lower Drain Surface Prep | FG Finish Grade | 11 Earth Work | 0 |  | 17 | 17 | 17 | 0 | 2025-09-01 | 2026-03-15 |  | 17 |  |  | 17
2510. Draper Pump Station #3 Improvements | 300.2160. WSP Lower Drain Steel Pipe Excavation L&E | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 0 |  | 161.76 | 160 | 160 | 0 | 2025-09-01 | 2026-03-15 | 130 | 30 |  |  | 160
2510. Draper Pump Station #3 Improvements | 300.2210. RCP Lower Drain Connection/Tie-Ins | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 50 | 50 | 50 | 0 | 2025-09-01 | 2026-03-15 | 50 |  |  |  | 50
2510. Draper Pump Station #3 Improvements | 300.2240. PCS Lower Drain Precast L&E | PCS Precast Structures | 10 Pipe | 0 |  | 91.52 | 92 | 92 | 0 | 2025-09-01 | 2026-03-15 | 92 |  |  |  | 92
2510. Draper Pump Station #3 Improvements | 300.2710. FWF Lower Drain Flowfill L&E | FWF Flowable Fill | 15 Concrete | 0 |  | 1.5 | 2 | 2 | 0 | 2025-09-01 | 2026-03-15 | 2 |  |  |  | 2
2510. Draper Pump Station #3 Improvements | 300.3000. CNC Lower Drain Concrete | CNC Concrete Work | 15 Concrete | 45.68 |  | 121.5 | 80 | 122 | -42 | 2025-09-01 | 2026-03-15 | 100 | 22 |  |  | 122
2510. Draper Pump Station #3 Improvements | 300.5000. MET Lower Drain Air Vent Off Vault w/ Excavation | MET Metals | 20 Fabrication | 0 |  | 84 | 84 | 84 | 0 | 2025-09-01 | 2026-03-15 | 60 | 24 |  |  | 84
2510. Draper Pump Station #3 Improvements | 300.5100. WE Lower Drain Double Lap Welding | W Welding | 20 Fabrication | 3.47 |  | 14.07 | 20 | 20 | 0 | 2025-09-01 | 2026-03-15 | 20 |  |  |  | 20
2510. Draper Pump Station #3 Improvements | 300.7100. IMP Lower Drain Mechanical Piping L&E | IMP Interior Mech/Piping | 55 Mechanical | 1 |  | 105 | 105 | 105 | 0 | 2025-09-01 | 2026-03-15 | 80 | 25 |  |  | 105
2510. Draper Pump Station #3 Improvements | 400.1650. SB Upper Drain Signage Install Sign Only | SB Signage | 12 Finishes | 0 |  | 36 | 36 | 36 | 0 | 2025-09-01 | 2026-03-15 |  | 36 |  |  | 36
2510. Draper Pump Station #3 Improvements | 400.1800. PH Upper Drain Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 7.98 |  | 15 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 400.2030. D Demo Upper Drain Pipeline Removal | D Demolition | 11 Earth Work | 0 |  | 36 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 400.2075. FG Upper Drain Rip Rap | FG Finish Grade | 11 Earth Work | 0 |  | 32 | 32 | 32 | 0 | 2025-09-01 | 2026-03-15 |  | 32 |  |  | 32
2510. Draper Pump Station #3 Improvements | 400.2080. EXS Upper Drain Excavation | EXS Excavate Structure | 11 Earth Work | 153.4 |  | 40.75 | 40 | 40 | 0 | 2025-09-01 | 2026-03-15 | 20 | 20 |  |  | 40
2510. Draper Pump Station #3 Improvements | 400.2085. BFST Upper Drain Backfill w/ CLSM | BFST Backfill Structure | 11 Earth Work | 31.46 |  | 3 | 80 | 80 | 0 | 2025-09-01 | 2026-03-15 | 40 | 40 |  |  | 80
2510. Draper Pump Station #3 Improvements | 400.2160. WSP Upper Drain Steel Pipe Excavation L&E | WSP Welded Steel Pipe <15' Depth | 10 Pipe | 8.75 |  | 257.44 | 350 | 350 | 0 | 2025-09-01 | 2026-03-15 | 250 | 100 |  |  | 350
2510. Draper Pump Station #3 Improvements | 400.2180. CATH Test Station / Cathodics | CATH Cathodic Protection | 10 Pipe | 0 |  | 72 | 80 | 80 | 0 | 2025-09-01 | 2026-03-15 | 20 | 60 |  |  | 80
2510. Draper Pump Station #3 Improvements | 400.2240. PCS Upper Drain Precast L&E | PCS Precast Structures | 10 Pipe | 0 |  | 91.52 | 92 | 92 | 0 | 2025-09-01 | 2026-03-15 | 30 | 62 |  |  | 92
2510. Draper Pump Station #3 Improvements | 400.2710. FWF Upper Drain Flowfill L&E | FWF Flowable Fill | 15 Concrete | 0 |  | 1.5 | 2 | 2 | 0 | 2025-09-01 | 2026-03-15 |  | 2 |  |  | 2
2510. Draper Pump Station #3 Improvements | 400.3000. CNC Upper Drain Concrete | CNC Concrete Work | 15 Concrete | 4 |  | 136.5 | 137 | 137 | 0 | 2025-09-01 | 2026-03-15 | 37 | 100 |  |  | 137
2510. Draper Pump Station #3 Improvements | 400.5000. MET Upper Drain Pipe Bollards | MET Metals | 20 Fabrication | 0 |  | 12 | 12 | 12 | 0 | 2025-09-01 | 2026-03-15 |  | 12 |  |  | 12
2510. Draper Pump Station #3 Improvements | 400.5100. WE Upper Drain Double Lap Welding | W Welding | 20 Fabrication | 0 |  | 14.07 | 14 | 14.1 | -0.1 | 2025-09-01 | 2026-03-15 | 14.1 |  |  |  | 14.1
2510. Draper Pump Station #3 Improvements | 400.7100. IMP Upper Drain Mechanical Piping | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 87 | 87 | 87 | 0 | 2025-09-01 | 2026-03-15 | 87 |  |  |  | 87
2510. Draper Pump Station #3 Improvements | 500.5000. Upper Drain Steel Pipe Changes 6" to 8" Modifications | MET Metals | 20 Fabrication | 41.07 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 800.1930. MC Misc Cleanup Pump Station | MC Misc Cleanup | 12 Finishes | 0 |  | 120 | 120 | 120 | 0 | 2025-09-01 | 2026-03-15 |  | 120 |  |  | 120
2510. Draper Pump Station #3 Improvements | 800.1940. PL Pump Station | PL Punch List Work | 12 Finishes | 0 |  | 135 | 135 | 135 | 0 | 2025-09-01 | 2026-03-15 |  | 135 |  |  | 135
2510. Draper Pump Station #3 Improvements | 900.9005. | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2510. Draper Pump Station #3 Improvements | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-09-01 | 2026-03-15
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 8.25 |  | 20 | 15 | 15 | 0 | 2025-08-01 | 2025-12-31 | 15 |  |  |  | 15
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 1.25 |  | 10 | 10 | 9 | 1 | 2025-08-01 | 2025-12-31 | 9 |  |  |  | 9
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1510. S Surveying | S Surveying | 45 Survey | 321.25 |  | 106.5 | 150 | 200 | -50 | 2025-08-01 | 2025-12-31 | 75 | 125 |  |  | 200
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1600. TC Traffic Control | TC Traffic Control | 30 Traffic Control | 8.25 |  | 140 | 50 | 50 | 0 | 2025-08-01 | 2025-12-31 | 25 | 25 |  |  | 50
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 210.25 |  | 483.4 | 250 | 300 | -50 | 2025-08-01 | 2025-12-31 | 150 | 150 |  |  | 300
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 454.49 |  | 453.26 | 300 | 350 | -50 | 2025-08-01 | 2025-12-31 | 250 | 100 |  |  | 350
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 253.2 |  | 377.66 | 150 | 220 | -70 | 2025-08-01 | 2025-12-31 | 150 | 70 |  |  | 220
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 446.84 |  | 570.11 | 250 | 300 | -50 | 2025-08-01 | 2025-12-31 | 200 | 100 |  |  | 300
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 120 |  | 146.24 | 65 | 75 | -10 | 2025-08-01 | 2025-12-31 | 50 | 25 |  |  | 75
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 150.1230. T Transporting | T Transporting | 40 Drivers | 59.96 |  | 152 | 75 | 90 | -15 | 2025-08-01 | 2025-12-31 | 75 | 15 |  |  | 90
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 150.2750. H Hauling | H Hauling | 40 Drivers | 410.06 |  | 1099.29 | 650 | 750 | -100 | 2025-08-01 | 2025-12-31 | 500 | 250 |  |  | 750
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 160.5000. MTL Pipe Materials Waterworks ISCO | MET Metals | 20 Fabrication | 21.1 |  | 0 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.1710. FS Startup/Commissioning | FS Starup/Commissioning | 55 Mechanical | 0 |  | 40 | 40 | 40 | 0 | 2025-08-01 | 2025-12-31 | 40 |  |  |  | 40
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2065. SFC SWPPP | SFC SWPPP | 11 Earth Work | 0 |  | 802 | 200 | 200 | 0 | 2025-08-01 | 2025-12-31 | 100 | 100 |  |  | 200
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2075. FG Asphalt Trench Prep w/ Mill | FG Finish Grade | 11 Earth Work | 1.63 |  | 63 | 65 | 65 | 0 | 2025-08-01 | 2025-12-31 |  | 65 |  |  | 65
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2170. HDPE Excavation, Pipe Install, Backfill, Road Crossings | HDPE Fusion Pipe <15' Depth | 10 Pipe | 3177.56 |  | 4466.59 | 2500 | 3000 | -500 | 2025-08-01 | 2025-12-31 | 1500 | 1500 |  |  | 3000
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2600. DW Dewatering | DW Dewatering | 10 Pipe | 0 |  | 116 | 50 | 50 | 0 | 2025-08-01 | 2025-12-31 | 20 | 30 |  |  | 50
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 200.2610. PT Fill/Test/Flush HDPE | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 300 | 300 | 300 | 0 | 2025-08-01 | 2025-12-31 |  | 300 |  |  | 300
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 205.2170. HDPE Pipe Fusion | HDPE Fusion Pipe <15' Depth | 10 Pipe | 2439.56 |  | 2227.99 | 1500 | 1500 | 0 | 2025-08-01 | 2025-12-31 | 700 | 800 |  |  | 1500
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 210.2170. HDPE Valve Install | HDPE Fusion Pipe <15' Depth | 10 Pipe | 34.05 |  | 382.68 | 250 | 300 | -50 | 2025-08-01 | 2025-12-31 | 150 | 150 |  |  | 300
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 215.2170. HDPE High Point Vents | HDPE Fusion Pipe <15' Depth | 10 Pipe | 9.6 |  | 1056 | 1000 | 1000 | 0 | 2025-08-01 | 2025-12-31 | 500 | 500 |  |  | 1000
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 220.2170. HDPE Extras: Low Point Drains | HDPE Fusion Pipe <15' Depth | 10 Pipe | 0 |  | 720 | 750 | 750 | 0 | 2025-08-01 | 2025-12-31 | 350 | 400 |  |  | 750
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 300.5100. Welding Ball Valves | W Welding | 20 Fabrication | 229.6 |  | 0 | 40 | 5 | 35 | 2025-08-01 | 2025-12-31 | 5 |  |  |  | 5
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 350.2170. T&M Change Order | HDPE Fusion Pipe <15' Depth | 10 Pipe | 500.47 |  | 0 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2509. Corix Utah City Heating & Cooling Distribution Piping 1.1 | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-08-01 | 2025-12-31
2508. Turner Dam & Joint Diversion Rehab | 100.1107. TF Trailer Pad / Parking Install (for 10'x40' trailer and 3 | TF TF Trailer Pad Install | 12 Finishes | 0 |  | 30 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 1 |  | 10 | 9 | 9 | 0 | 2025-06-23 |  | 4 | 5 |  |  | 9
2508. Turner Dam & Joint Diversion Rehab | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 100.1510. S Surveying | S Surveying | 45 Survey | 48.73 |  | 20 | 10 | 11.5 | -1.5 | 2025-06-23 |  | 2 | 9.5 |  |  | 11.5
2508. Turner Dam & Joint Diversion Rehab | 100.1515. | S Drone/Lidar Requirements | 45 Survey | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 303 |  | 191.9 | 30 | 40 | -10 | 2025-06-23 |  | 20 | 10 | 10 |  | 40
2508. Turner Dam & Joint Diversion Rehab | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 297.07 |  | 196.29 | 20 | 28.5 | -8.5 | 2025-06-23 |  | 15 | 5 | 8.5 |  | 28.5
2508. Turner Dam & Joint Diversion Rehab | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 176.41 |  | 160.77 | 30 | 44 | -14 | 2025-06-23 |  | 30 | 14 |  |  | 44
2508. Turner Dam & Joint Diversion Rehab | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 204.85 |  | 236.62 | 95.24 | 186.2 | -90.96 | 2025-06-23 |  | 50 | 54.2 |  | 82 | 186.2
2508. Turner Dam & Joint Diversion Rehab | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 60.68 | 0 | 50 | -50 | 2025-06-23 |  | 10 | 20 |  | 20 | 50
2508. Turner Dam & Joint Diversion Rehab | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 3.5 |  | 1 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 150.1230. T Transporting | T Transporting | 40 Drivers | 194.79 |  | 75 | 10 | 58.7 | -48.7 | 2025-06-23 |  | 20 | 18.7 |  | 20 | 58.7
2508. Turner Dam & Joint Diversion Rehab | 150.2750. H Hauling | H Hauling | 40 Drivers | 227.39 |  | 149.86 | 10 | 125 | -115 | 2025-06-23 |  | 48 | 27 |  | 50 | 125
2508. Turner Dam & Joint Diversion Rehab | 150.2760. HO Haul Off | HO Haul Off | 40 Drivers | 91.68 |  | 109.72 | 13.69 | 100 | -86.31 | 2025-06-23 |  | 40 | 40 |  | 20 | 100
2508. Turner Dam & Joint Diversion Rehab | 250.2030. Turner - D Demo Concrete | D Demolition | 11 Earth Work | 19.95 |  | 21 | 0 | 2 | -2 | 2025-06-23 |  | 2 |  |  |  | 2
2508. Turner Dam & Joint Diversion Rehab | 250.2075. Turner - FG Surface Concrete Interior Prep | FG Finish Grade | 11 Earth Work | 0 |  | 20 | 0 | 20 | -20 | 2025-06-23 |  | 20 |  |  |  | 20
2508. Turner Dam & Joint Diversion Rehab | 250.2595. Turner - CD Coffer Dam | CD Coffer Dams | 10 Pipe | 23.17 |  | 100 | 77 | 80 | -3 | 2025-06-23 |  | 40 |  |  | 40 | 80
2508. Turner Dam & Joint Diversion Rehab | 250.2600. Turner - DW Dewatering | DW Dewatering | 10 Pipe | 0 |  | 60 | 60 | 60 | 0 | 2025-06-23 |  | 60 |  |  |  | 60
2508. Turner Dam & Joint Diversion Rehab | 250.3000. Turner - CNC Concrete | CNC Concrete Work | 15 Concrete | 266.28 |  | 45 | 80 | 40 | 40 | 2025-06-23 |  | 40 |  |  |  | 40
2508. Turner Dam & Joint Diversion Rehab | 250.3100. Turner - CNR Rebar Install | CNC Rebar | 15 Concrete | 0 |  | 7.5 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 250.5000. Turner - WE Welding | MET Metals | 20 Fabrication | 1 |  | 88 | 87 | 87 | 0 | 2025-06-23 |  | 57 | 30 |  |  | 87
2508. Turner Dam & Joint Diversion Rehab | 250.7600. Turner - MEQ Gate Install | MEQ Mechanical Equipment | 55 Mechanical | 2 |  | 1290 | 1288 | 1288 | 0 | 2025-06-23 |  | 1100 | 188 |  |  | 1288
2508. Turner Dam & Joint Diversion Rehab | 260.2080. PCO6 - Dredging Turner Dam Forebay | EXS Excavate Structure | 11 Earth Work | 64.93 |  | 90 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 300.2030. East Jordon - D Demo Concrete | D Demolition | 11 Earth Work | 4.7 |  | 60 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 300.2075. East Jordon - FG Surface Concrete Prep | FG Finish Grade | 11 Earth Work | 0 |  | 20 | 0 | 10 | -10 | 2025-06-23 |  | 10 |  |  |  | 10
2508. Turner Dam & Joint Diversion Rehab | 300.2085. East Jordon - BFST Backfill | BFST Backfill Structure | 11 Earth Work | 42.2 |  | 9 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 300.2710. East Jordon - FWF Flowfill | FWF Flowable Fill | 15 Concrete | 0 |  | 6 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 300.3000. East Jordon - CNC Concrete | CNC Concrete Work | 15 Concrete | 27.75 |  | 223.04 | 0 | 100 | -100 | 2025-06-23 |  | 100 |  |  |  | 100
2508. Turner Dam & Joint Diversion Rehab | 300.3100. East Jordon - CNR Rebar Install | CNC Rebar | 15 Concrete | 0 |  | 22.5 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 300.5000. East Jordon - MET Metals Install | MET Metals | 20 Fabrication | 0 |  | 50.4 | 50 | 50 | 0 | 2025-06-23 |  | 25 |  |  | 25 | 50
2508. Turner Dam & Joint Diversion Rehab | 300.7600. East Jordon - MEQ Gate Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 90 | 90 | 90 | 0 | 2025-06-23 |  | 90 |  |  |  | 90
2508. Turner Dam & Joint Diversion Rehab | 350.2020. Log Boom - CG Remove Vegetaton | CG Clearing/Grubbing | 11 Earth Work | 160.53 |  | 10 | 0 | 10 | -10 | 2025-06-23 |  | 10 |  |  |  | 10
2508. Turner Dam & Joint Diversion Rehab | 350.2050. Log Boom - RW Excavation | RW Retaining Walls | 11 Earth Work | 78.72 |  | 23.36 | 20 | 24 | -4 | 2025-06-23 |  | 24 |  |  |  | 24
2508. Turner Dam & Joint Diversion Rehab | 350.2070. Log Boom - RFG Exterior Subgrade | RGC Rough Grade Cut | 11 Earth Work | 9.93 |  | 64.8 | 20 | 65 | -45 | 2025-06-23 |  | 65 |  |  |  | 65
2508. Turner Dam & Joint Diversion Rehab | 350.2075. Log Boom - FG Rip Rap Placement | FG Finish Grade | 11 Earth Work | 227.73 |  | 315.56 | 30 | 315 | -285 | 2025-06-23 |  | 315 |  |  |  | 315
2508. Turner Dam & Joint Diversion Rehab | 350.2085. Log Boom - BFST Backfill | BFST Backfill Structure | 11 Earth Work | 224.07 |  | 81 | 25 | 81 | -56 | 2025-06-23 |  | 81 |  |  |  | 81
2508. Turner Dam & Joint Diversion Rehab | 350.2210. Log Boom - RCP Pipe Install | RCP Reinforced Concrete Pipe | 10 Pipe | 3 |  | 12.5 | 0 | 12.5 | -12.5 | 2025-06-23 |  | 12.5 |  |  |  | 12.5
2508. Turner Dam & Joint Diversion Rehab | 350.2240. Log Boom - Armorflex Placement | PCS Precast Structures | 10 Pipe | 72.19 |  | 110 | 35 | 140 | -105 | 2025-06-23 |  | 140 |  |  |  | 140
2508. Turner Dam & Joint Diversion Rehab | 350.3000. Log Boom - CNC Concrete | CNC Concrete Work | 15 Concrete | 356.65 |  | 189.8 | 25 | 190 | -165 | 2025-06-23 |  | 190 |  |  |  | 190
2508. Turner Dam & Joint Diversion Rehab | 350.3100. Log Boom - CNR Rebar | CNC Rebar | 15 Concrete | 0 |  | 30 | 0 | 30 | -30 | 2025-06-23 |  | 30 |  |  |  | 30
2508. Turner Dam & Joint Diversion Rehab | 350.5000. Log Boom - MET Misc Metals install | MET Metals | 20 Fabrication | 0 |  | 15 | 0 | 15 | -15 | 2025-06-23 |  | 15 |  |  |  | 15
2508. Turner Dam & Joint Diversion Rehab | 350.7600. Log Boom - MEQ Install Log Booms | MEQ Mechanical Equipment | 55 Mechanical | 4 |  | 50 | 0 | 46 | -46 | 2025-06-23 |  | 46 |  |  |  | 46
2508. Turner Dam & Joint Diversion Rehab | 400.2065. Joint Diversion - SFC SWPPP | SFC SWPPP | 11 Earth Work | 0 |  | 40 | 0 | 40 | -40 | 2025-06-23 |  | 40 |  |  |  | 40
2508. Turner Dam & Joint Diversion Rehab | 400.2180. Joint Diversion - CATH Test Station Anode Bags | CATH Cathodic Protection | 10 Pipe | 0 |  | 18 | 18 | 18 | 0 | 2025-06-23 |  | 18 |  |  |  | 18
2508. Turner Dam & Joint Diversion Rehab | 400.2595. Joint Diversion - CD Coffer Dam | CD Coffer Dams | 10 Pipe | 0 |  | 100 | 50 | 100 | -50 | 2025-06-23 |  | 100 |  |  |  | 100
2508. Turner Dam & Joint Diversion Rehab | 400.2600. Joint Diversion - DW Dewatering | DW Dewatering | 10 Pipe | 0 |  | 90 | 45 | 90 | -45 | 2025-06-23 |  | 90 |  |  |  | 90
2508. Turner Dam & Joint Diversion Rehab | 400.5000. Joint Diversion - MET Staff Gauge | MET Metals | 20 Fabrication | 0 |  | 22.5 | 23 | 23 | 0 | 2025-06-23 |  | 23 |  |  |  | 23
2508. Turner Dam & Joint Diversion Rehab | 400.7600. Joint Diversion - MEQ Gate Install 48" & Larger | MEQ Mechanical Equipment | 55 Mechanical | 73.23 |  | 240 | 167 | 167 | 0 | 2025-06-23 |  | 167 |  |  |  | 167
2508. Turner Dam & Joint Diversion Rehab | 420.5000. PCO 10 - Vancon Stop Gates | MET Metals | 20 Fabrication | 12.63 |  | 0 | 40 | 0 | 40 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 420.7600. PCO 7 - Joint Diversion Radial gate Repair | MEQ Mechanical Equipment | 55 Mechanical | 140.58 |  | 115.92 | 100 | 5.6 | 94.4 | 2025-06-23 |  | 5.6 |  |  |  | 5.6
2508. Turner Dam & Joint Diversion Rehab | 430.7600. WCD10 - PCO 8 Turner & E Jordan Fence Mods | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 4 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 440.7600. WCD 12 - PCO 13b Joint Diversion Fence upgrade | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 1 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 450.5000. WCD 11 - PCO 9 Utah Lake Bridge removal | MET Metals | 20 Fabrication | 30.27 |  | 64 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 500.2030. Concrete Repair - D Demo Concrete | D Demolition | 11 Earth Work | 27.85 |  | 92 | 0 | 92 | -92 | 2025-06-23 |  | 92 |  |  |  | 92
2508. Turner Dam & Joint Diversion Rehab | 500.2065. Concrete Repair - SFC Concrete Washing | SFC SWPPP | 11 Earth Work | 0 |  | 3.71 | 0 | 4 | -4 | 2025-06-23 |  | 4 |  |  |  | 4
2508. Turner Dam & Joint Diversion Rehab | 500.2240. Concrete Repair - PCS Manhole Collar | PCS Precast Structures | 10 Pipe | 0 |  | 24 | 0 | 12 | -12 | 2025-06-23 |  | 12 |  |  |  | 12
2508. Turner Dam & Joint Diversion Rehab | 500.3000. Concrete Repair - CNC Conc Form | CNC Concrete Work | 15 Concrete | 502.48 |  | 60 | 300 | 140 | 160 | 2025-06-23 |  | 140 |  |  |  | 140
2508. Turner Dam & Joint Diversion Rehab | 500.3010. Concrete Repair - WP Winter Conditions | WP Winter Protection | 15 Concrete | 20.92 |  | 18 | 0 | 18 | -18 | 2025-06-23 |  | 18 |  |  |  | 18
2508. Turner Dam & Joint Diversion Rehab | 500.7600. WCD 1 - PCO 14 Elec Trench Markers | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 0.5 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.1930. MC Misc Cleanup Utah Lake Staff Guage | MC Misc Cleanup | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.1940. PL Punchlist Utah Lake Staff Guage | PL Punch List Work | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2030. D Demo/Prep pipe - Utah Lake Staff Guage | D Demolition | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2040. LR Landscape Restoration - Utah Lake Staff Guage | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2070. RFG Exterior Earthwork - Utah Lake Staff Guage | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2075. PCO 16 - Utah Lake Outlet Gage | FG Finish Grade | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2140. PVC Piping - Utah Lake Staff Guage | SVR Services | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2210. RCP Piping & Manhole L&E - Utah Lake Staff Guage | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2595. CD Coffer Dam Install Earthen - Utah Lake Staff Guage | CD Coffer Dams | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2600. DW Dewatering & Maintenance - Utah Lake Staff Guage | DW Dewatering | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2750. H Hauling - Utah Lake Staff Guage | H Hauling | 40 Drivers | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.2760. HO Haul Off - Utah Lake Staff Guage | HO Haul Off | 40 Drivers | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.3000. CNC Sloped Concrete Wing Walls L&E - Utah Lake Staff Guage | CNC Concrete Work | 15 Concrete | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.3100. CNR Rebar VanCon Install - Utah Lake Staff Guage | CNC Rebar | 15 Concrete | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.5000. MET Staff Gauge M | MET Metals | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 600.7100. IMP Small Piping / Guage Install - Utah Lake Staff Guage | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 610.2075. FG Fabric Under Riprap L&E - Utah Lake Staff Guage | FG Finish Grade | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 620.2075. FG Place Rip Rap L&E - Utah Lake Staff Guage | FG Finish Grade | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 665.5000. MET Misc Metals (shelf) - Utah Lake Staff Guage | MET Metals | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 800.1930. MC Misc Cleanup | MC Misc Cleanup | 12 Finishes | 0 |  | 180 | 180 | 180 | 0 | 2025-06-23 |  | 180 |  |  |  | 180
2508. Turner Dam & Joint Diversion Rehab | 800.1940. PL Punchlist | PL Punch List Work | 12 Finishes | 0 |  | 135 | 135 | 135 | 0 | 2025-06-23 |  | 100 | 35 |  |  | 135
2508. Turner Dam & Joint Diversion Rehab | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-06-23
2508. Turner Dam & Joint Diversion Rehab | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 5.57 |  | 1 | 0 | 0 | 0 | 2025-06-23
2507. SLC Industrial Lift Station | 100.1110. TU Temporay Utilties Hookup Fees | TU Temporary Utilities Hookup | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 21 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 100.1510. S Surveying | S Surveying | 45 Survey | 30.36 |  | 40 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 231 |  | 155.5 | 15 | 18 | -3 | 2025-07-01 |  | 9 | 9 |  |  | 18
2507. SLC Industrial Lift Station | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 388.26 |  | 101.36 | 0 | 6 | -6 | 2025-07-01 |  | 3 | 3 |  |  | 6
2507. SLC Industrial Lift Station | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 28.5 |  | 92.17 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 323.57 |  | 138.75 | 10 | 20 | -10 | 2025-07-01 |  |  | 20 |  |  | 20
2507. SLC Industrial Lift Station | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 15.5 |  | 36.15 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 1 |  | 1 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 150.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 10 |  | 7.5 | 0 | 3 | -3 | 2025-07-01 |  |  | 3 |  |  | 3
2507. SLC Industrial Lift Station | 150.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 6 |  | 7.5 | 0 | 3 | -3 | 2025-07-01 |  |  | 3 |  |  | 3
2507. SLC Industrial Lift Station | 150.1230. T Transporting | T Transporting | 40 Drivers | 41.73 |  | 101 | 0 | 9 | -9 | 2025-07-01 |  |  | 9 |  |  | 9
2507. SLC Industrial Lift Station | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 72.19 |  | 37.38 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 19.77 |  | 6.66 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 180.1600. Traffic Control Sub | TC Traffic Control | 30 Traffic Control | 2.5 |  | 0 | 0 | 2.5 | -2.5 | 2025-07-01 |  |  | 2.5 |  |  | 2.5
2507. SLC Industrial Lift Station | 200.1600. TC Temp Conc Barrier Install | TC Traffic Control | 30 Traffic Control | 31.33 |  | 142 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.1800. PH Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 50.57 |  | 150 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2030. D Demo Pipeline Abandon | D Demolition | 11 Earth Work | 24.64 |  | 134.16 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2065. SFC SWPPP Sweeper Truck (Dust Control) | SFC SWPPP | 11 Earth Work | 0 |  | 40 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2075. FG Roadbase/Gravel Small Areas | FG Finish Grade | 11 Earth Work | 100.54 |  | 45.25 | 0 | 25 | -25 | 2025-07-01 |  | 8 | 17 |  |  | 25
2507. SLC Industrial Lift Station | 200.2085. BFST Backfill Interior of Building w/ Gravel | BFST Backfill Structure | 11 Earth Work | 34.81 |  | 36 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2140. SVR Service Assembly | SVR Services | 10 Pipe | 6.32 |  | 40 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2170. HDPE Addons: Utility Crossings (HDPE MAINLINE) | HDPE Fusion Pipe <15' Depth | 10 Pipe | 389.76 |  | 471.74 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2240. PCS Manhole Collar | PCS Precast Structures | 10 Pipe | 95.34 |  | 28 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2600. DW Dewatering Maintenance Medium | DW Dewatering | 10 Pipe | 7.62 |  | 124.96 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2605. BYP Bypass VanCon Vac Truck | BYP Bypass Pumping | 10 Pipe | 65.14 |  | 50 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2610. PT Fill/Test/Flush HDPE | PT Pressure Test/Chlorinating | 10 Pipe | 28.63 |  | 60 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.2710. FWF Flowfill Utility Support | FWF Flowable Fill | 15 Concrete | 0 |  | 6 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.3000. CNC Conc Finish Flatwork Steel Trowel 1st 0-1000 SF Lump | CNC Concrete Work | 15 Concrete | 167.01 |  | 451.2 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.3100. CNR Rebar VanCon Install | CNC Rebar | 15 Concrete | 0 |  | 24 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.5000. MET Ladder Install | MET Metals | 20 Fabrication | 5.93 |  | 85.5 | 79.07 | 81.1 | -2.03 | 2025-07-01 |  |  | 81.1 |  |  | 81.1
2507. SLC Industrial Lift Station | 200.5400. HAT Ring & Cover/Frame & Grate Install | HAT Hatch/Skylights | 12 Finishes | 1 |  | 15 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.6500. P Paint Powerwash | P Painting | 12 Finishes | 0 |  | 30 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.7100. IMP 4"-6" Fitting/Valve Install | IMP Interior Mech/Piping | 55 Mechanical | 161.62 |  | 259.89 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.7500. PUMP Sum Pump Install | PUMP Pumps/Motors | 55 Mechanical | 20.55 |  | 78 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 200.7900. ELC Electrical/Fiber/Dry Utilities Trenching | ELC Electrical | 10 Pipe | 11.55 |  | 20 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 800.1930. MC Misc Cleanup Pump Station | MC Misc Cleanup | 12 Finishes | 98.96 |  | 120 | 21.51 | 21.5 | 0.01 | 2025-07-01 |  |  | 21.5 |  |  | 21.5
2507. SLC Industrial Lift Station | 800.1940. PL Pump Station | PL Punch List Work | 12 Finishes | 53.78 |  | 135 | 80 | 80 | 0 | 2025-07-01 |  |  | 80 |  |  | 80
2507. SLC Industrial Lift Station | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 6.85 |  | 0.6 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 39.97 |  | 0.6 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-07-01
2507. SLC Industrial Lift Station | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 3 |  | 1 | 0 | 0 | 0 | 2025-07-01
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1040. PR Public Relations VanCon | PR Public Relations | 60 Operations (PM/PE) | 0 |  | 20 | 0 | 0 | 0 | 2025-05-05 | 2025-10-31
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-05-05 | 2025-10-31 |  |  | 1 |  | 1
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1510. S Surveying | S Surveying | 45 Survey | 1 |  | 20 | 19 | 20 | -1 | 2025-05-05 | 2025-10-31 |  |  | 10 | 10 | 20
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 46.5 |  | 53.47 | 89.5 | 100 | -10.5 | 2025-05-05 | 2025-10-31 |  | 12.5 | 80 | 7.5 | 100
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 116.15 |  | 47.66 | 11.5 | 20 | -8.5 | 2025-05-05 | 2025-10-31 |  |  | 20 |  | 20
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 16 |  | 44.68 | 30 | 30 | 0 | 2025-05-05 | 2025-10-31 |  | 10 | 15 | 5 | 30
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 16 |  | 67 | 150 | 151 | -1 | 2025-05-05 | 2025-10-31 |  | 25 | 100 | 26 | 151
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 17.85 | 20 | 17.9 | 2.1 | 2025-05-05 | 2025-10-31 |  |  | 9.9 | 8 | 17.9
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 1 | -1 | 2025-05-05 | 2025-10-31 |  |  | 1 |  | 1
2506. UDOT Big Cottonwood Creek Culvert Preservation | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 1 |  | 1 | 0 | 0 | 0 | 2025-05-05 | 2025-10-31
2506. UDOT Big Cottonwood Creek Culvert Preservation | 150.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 7.5 | 7.5 | 7.5 | 0 | 2025-05-05 | 2025-10-31 |  |  | 7.5 |  | 7.5
2506. UDOT Big Cottonwood Creek Culvert Preservation | 150.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 7.5 | 7.5 | 7.5 | 0 | 2025-05-05 | 2025-10-31 |  |  | 7.5 |  | 7.5
2506. UDOT Big Cottonwood Creek Culvert Preservation | 150.1230. T Transporting | T Transporting | 40 Drivers | 0 |  | 50 | 50 | 50 | 0 | 2025-05-05 | 2025-10-31 |  |  | 25 | 25 | 50
2506. UDOT Big Cottonwood Creek Culvert Preservation | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 0 |  | 3.33 | 3.33 | 3.3 | 0.03 | 2025-05-05 | 2025-10-31 |  |  | 3.3 |  | 3.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 0 |  | 6.25 | 6.25 | 6.3 | -0.05 | 2025-05-05 | 2025-10-31 |  |  | 6.3 |  | 6.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 200.1600. TC Traffic Control Reports | TC Traffic Control | 30 Traffic Control | 0.75 |  | 10 | 9.25 | 9.3 | -0.05 | 2025-05-05 | 2025-10-31 |  |  | 9.3 |  | 9.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 200.2065. SFC SWPPP Silt Fence/Waddle Install | SFC SWPPP | 11 Earth Work | 0 |  | 15.96 | 15.96 | 16 | -0.04 | 2025-05-05 | 2025-10-31 |  |  | 16 |  | 16
2506. UDOT Big Cottonwood Creek Culvert Preservation | 200.2170. HDPE Pipe Fusion | HDPE Fusion Pipe <15' Depth | 10 Pipe | 0 |  | 15 | 0 | 0 | 0 | 2025-05-05 | 2025-10-31
2506. UDOT Big Cottonwood Creek Culvert Preservation | 200.2595. CD Coffer Dam Removal | CD Coffer Dams | 10 Pipe | 0 |  | 270 | 270 | 270 | 0 | 2025-05-05 | 2025-10-31 |  | 200 | 70 |  | 270
2506. UDOT Big Cottonwood Creek Culvert Preservation | 210.2030. D Demo UHPC Concrete SF | D Demolition | 11 Earth Work | 0 |  | 158.25 | 158.25 | 158.3 | -0.05 | 2025-05-05 | 2025-10-31 |  | 58.3 | 100 |  | 158.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 210.3000. CNC UHPC Prep & Placement | CNC Concrete Work | 15 Concrete | 0 |  | 396 | 396 | 396 | 0 | 2025-05-05 | 2025-10-31 |  |  | 200 | 196 | 396
2506. UDOT Big Cottonwood Creek Culvert Preservation | 210.6500. UHPC Sandblasting Floors/Walls | P Painting | 12 Finishes | 0 |  | 42.2 | 45 | 42.2 | 2.8 | 2025-05-05 | 2025-10-31 |  |  | 20 | 22.2 | 42.2
2506. UDOT Big Cottonwood Creek Culvert Preservation | 220.2030. D Demo Structural Concrete L&E | D Demolition | 11 Earth Work | 0 |  | 11.25 | 12 | 11.3 | 0.7 | 2025-05-05 | 2025-10-31 |  |  | 11.3 |  | 11.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 220.3000. CNC Structural Concrete L&E | CNC Concrete Work | 15 Concrete | 0 |  | 19.2 | 19.2 | 19.2 | 0 | 2025-05-05 | 2025-10-31 |  |  |  | 19.2 | 19.2
2506. UDOT Big Cottonwood Creek Culvert Preservation | 220.6500. Sandblasting for Structural Concretee Floors/Walls | P Painting | 12 Finishes | 0 |  | 8.34 | 8.34 | 8.3 | 0.04 | 2025-05-05 | 2025-10-31 |  |  | 8.3 |  | 8.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 230.2030. D Demo Structural Plus Concrete | D Demolition | 11 Earth Work | 0 |  | 9.75 | 9.75 | 9.8 | -0.05 | 2025-05-05 | 2025-10-31 |  |  | 9.8 |  | 9.8
2506. UDOT Big Cottonwood Creek Culvert Preservation | 230.3000. CNR Structural Plus L&E | CNC Concrete Work | 15 Concrete | 0 |  | 142.2 | 142.2 | 142.2 | 0 | 2025-05-05 | 2025-10-31 |  |  | 42.2 | 100 | 142.2
2506. UDOT Big Cottonwood Creek Culvert Preservation | 230.6500. Sandblasting for Structural Plus Floors/Walls | P Painting | 12 Finishes | 0 |  | 7.22 | 7.22 | 7.2 | 0.02 | 2025-05-05 | 2025-10-31 |  |  | 7.2 |  | 7.2
2506. UDOT Big Cottonwood Creek Culvert Preservation | 240.2030. D Demo Cracks Concrete | D Demolition | 11 Earth Work | 0 |  | 13.5 | 13.5 | 13.5 | 0 | 2025-05-05 | 2025-10-31 |  |  | 13.5 |  | 13.5
2506. UDOT Big Cottonwood Creek Culvert Preservation | 240.3000. CNC Crack Repair/ Finish Walls L&E | CNC Concrete Work | 15 Concrete | 0 |  | 120 | 120 | 120 | 0 | 2025-05-05 | 2025-10-31 |  |  | 60 | 60 | 120
2506. UDOT Big Cottonwood Creek Culvert Preservation | 240.6500. Sandblasting for Crack Repair Floors/Walls | P Painting | 12 Finishes | 0 |  | 10 | 10 | 10 | 0 | 2025-05-05 | 2025-10-31 |  |  | 10 |  | 10
2506. UDOT Big Cottonwood Creek Culvert Preservation | 250.2030. D Demo Pothole patching & Prep Concrete | D Demolition | 11 Earth Work | 0 |  | 62.25 | 62.25 | 62.3 | -0.05 | 2025-05-05 | 2025-10-31 |  |  | 62.3 |  | 62.3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 250.2920. SC Saw Cutting/Coring for pothole patching | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 7.5 | 7.5 | 7.5 | 0 | 2025-05-05 | 2025-10-31 |  |  | 7.5 |  | 7.5
2506. UDOT Big Cottonwood Creek Culvert Preservation | 250.6500. Sandblasting for Pothole patching Floors/Walls | P Painting | 12 Finishes | 0 |  | 41.5 | 41.5 | 41.5 | 0 | 2025-05-05 | 2025-10-31 |  |  | 41.5 |  | 41.5
2506. UDOT Big Cottonwood Creek Culvert Preservation | 800.1930. MC Misc Cleanup Concrete/Vaults/Canals | MC Misc Cleanup | 12 Finishes | 0 |  | 60 | 60 | 60 | 0 | 2025-05-05 | 2025-10-31 |  |  |  | 60 | 60
2506. UDOT Big Cottonwood Creek Culvert Preservation | 800.1940. PL Concrete Structure/Vaults/Canals | PL Punch List Work | 12 Finishes | 0 |  | 45 | 45 | 45 | 0 | 2025-05-05 | 2025-10-31 |  |  |  | 45 | 45
2506. UDOT Big Cottonwood Creek Culvert Preservation | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0.6 | -0.6 | 2025-05-05 | 2025-10-31 |  |  | 0.6 |  | 0.6
2506. UDOT Big Cottonwood Creek Culvert Preservation | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0.6 | -0.6 | 2025-05-05 | 2025-10-31 |  |  | 0.6 |  | 0.6
2506. UDOT Big Cottonwood Creek Culvert Preservation | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0.6 | -0.6 | 2025-05-05 | 2025-10-31 |  |  | 0.6 |  | 0.6
2506. UDOT Big Cottonwood Creek Culvert Preservation | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 3 | -3 | 2025-05-05 | 2025-10-31 |  |  | 3 |  | 3
2506. UDOT Big Cottonwood Creek Culvert Preservation | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 1 | -1 | 2025-05-05 | 2025-10-31 |  |  | 1 |  | 1
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 2.5 | 2.5 | 2.5 | 0 | 2025-05-19 | 2026-01-30 | 2.5 |  |  |  | 2.5
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 163.5 |  | 43.2 | 9 | 20 | -11 | 2025-05-19 | 2026-01-30 | 20 |  |  |  | 20
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 4.72 |  | 38.42 | 35 | 35 | 0 | 2025-05-19 | 2026-01-30 | 35 |  |  |  | 35
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 8 |  | 35.98 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 144.75 |  | 54.36 | 16.18 | 28.7 | -12.52 | 2025-05-19 | 2026-01-30 | 28.7 |  |  |  | 28.7
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 13.87 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 4 |  | 1 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 150.1230. T Transporting | T Transporting | 40 Drivers | 3.5 |  | 45 | 5 | 5 | 0 | 2025-05-19 | 2026-01-30 | 5 |  |  |  | 5
2505. JVWCD JVWTP Chemical Bldg Upgrade | 161.5000. PCO 2 - Skylight guard | MET Metals | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 182.7900. PCO 3 - Sub 9 Elec relay Cntrls and Skylight covers | ELC Electrical | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 200.3000. CNC Addon Conc Access Dowels - Drill & Epoxy #4-#6 0"-9" | CNC Concrete Work | 15 Concrete | 63.86 |  | 34.8 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 200.5000. MET Em Generator Exhaust ext and support install | MET Metals | 20 Fabrication | 44.88 |  | 0 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 200.7300. PLUM Plumbing Rough Pipe Fittings PVC 6" to 12" | PLUM Plumbing | 55 Mechanical | 0 |  | 60 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 200.7400. HVAC Support L&E | HVAC HVAC | 55 Mechanical | 72.42 |  | 1122 | 20 | 20 | 0 | 2025-05-19 | 2026-01-30 | 20 |  |  |  | 20
2505. JVWCD JVWTP Chemical Bldg Upgrade | 800.1930. MC Misc Cleanup Treatment Plant & Appurtenance | MC Misc Cleanup | 12 Finishes | 0 |  | 120 | 120 | 120 | 0 | 2025-05-19 | 2026-01-30 | 120 |  |  |  | 120
2505. JVWCD JVWTP Chemical Bldg Upgrade | 800.1940. PL Treatment Plant & Appurtenance | PL Punch List Work | 12 Finishes | 0 |  | 80 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2505. JVWCD JVWTP Chemical Bldg Upgrade | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 1 |  | 1 | 0 | 0 | 0 | 2025-05-19 | 2026-01-30
2503. HVSSD Headworks Upgrade | 100.1108. TF Setup Staging Area Laydown Yard | TF Setup Staging Area Laydown Yard | 12 Finishes | 0 |  | 30 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 10.75 |  | 5 | 10 | 10 | 0 | 2025-04-15 | 2025-10-15 | 10 |  |  |  | 10
2503. HVSSD Headworks Upgrade | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 5 | 0 | 10 | -10 | 2025-04-15 | 2025-10-15 | 10 |  |  |  | 10
2503. HVSSD Headworks Upgrade | 100.1500. VIS Meetings (Vision | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 76 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 100.1510. S Surveying | S Surveying | 45 Survey | 32.31 |  | 40 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 439.75 |  | 173.26 | 20 | 40 | -20 | 2025-04-15 | 2025-10-15 | 40 |  |  |  | 40
2503. HVSSD Headworks Upgrade | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 354.13 |  | 154.17 | 0 | 20 | -20 | 2025-04-15 | 2025-10-15 | 20 |  |  |  | 20
2503. HVSSD Headworks Upgrade | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 122.73 |  | 144.42 | 10 | 20 | -10 | 2025-04-15 | 2025-10-15 | 20 |  |  |  | 20
2503. HVSSD Headworks Upgrade | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 176.42 |  | 216.7 | 20 | 20 | 0 | 2025-04-15 | 2025-10-15 | 20 |  |  |  | 20
2503. HVSSD Headworks Upgrade | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 55.3 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 2 |  | 1 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 150.1230. T Transporting | T Transporting | 40 Drivers | 34.87 |  | 75 | 4 | 0 | 4 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 37.76 |  | 34.67 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 4.18 |  | 5.12 | 5 | 0 | 5 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 160.3000. CNC Concrete Ready Mix Materials | CNC Concrete Work | 15 Concrete | 0 |  | 6 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.1800. PH Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 0 |  | 15 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.2030. DEMO Job | D Demolition | 11 Earth Work | 194.35 |  | 228 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.2040. PVC Install L&E | LR Landscaping/Restoration | 11 Earth Work | 0 |  | 31 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.2075. FG Roadbase/Gravel Small Areas | FG Finish Grade | 11 Earth Work | 41.26 |  | 56 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.2085. BFST Backfill Interior of Building w/ Gravel | BFST Backfill Structure | 11 Earth Work | 190.13 |  | 20 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.3000. CNC Concrete L&E | CNC Concrete Work | 15 Concrete | 755.69 |  | 573.42 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.5000. MET Misc Metals Install | MET Metals | 20 Fabrication | 16.45 |  | 249 | 80 | 100 | -20 | 2025-04-15 | 2025-10-15 | 100 |  |  |  | 100
2503. HVSSD Headworks Upgrade | 200.7100. IMP Misc Pipe | IMP Interior Mech/Piping | 55 Mechanical | 22.47 |  | 54 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.7600. IMP Tank Cover support And Unloading L&E | MEQ Mechanical Equipment | 55 Mechanical | 4 |  | 105 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 200.7900. ELC Electrical/Fiber/Dry Utilities Trenching | ELC Electrical | 10 Pipe | 0 |  | 8 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 300.7100. IMP Slide Gate Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | -23 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 300.7700. SEQ Odor Equipment Install | SEQ Specialized Equipment | 55 Mechanical | 989.41 |  | 300 | 0 | 200 | -200 | 2025-04-15 | 2025-10-15 | 200 |  |  |  | 200
2503. HVSSD Headworks Upgrade | 400.7700. SEQ Huber Screen Install L&E | SEQ Specialized Equipment | 55 Mechanical | 326.22 |  | 240 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 800.1930. MC Misc Cleanup (End Of Job) | MC Misc Cleanup | 12 Finishes | 0 |  | 180 | 180 | 180 | 0 | 2025-04-15 | 2025-10-15 | 180 |  |  |  | 180
2503. HVSSD Headworks Upgrade | 800.1940. PL Punch List (End Of Job) | PL Punch List Work | 12 Finishes | 0 |  | 180 | 100 | 180 | -80 | 2025-04-15 | 2025-10-15 | 180 |  |  |  | 180
2503. HVSSD Headworks Upgrade | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 41.01 |  | 0.6 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2503. HVSSD Headworks Upgrade | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-04-15 | 2025-10-15
2450. Fab Shop Jobs 2024 Projects | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 30 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 2.13 |  | 10 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 5 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 100.5900. FAB Fab Shop 2024 Project | FAB Fab Shop | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 100.5901. FAB Fab Shop Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 220.2300. | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 4 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 403.5901. FAB 2403 Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 72.12 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 403.5935. FAB 2403 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 10 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 403.5940. FAB 2403 WSP Fabrication | FAB Fab Shop WSP Fabrication | 20 Fabrication | 46.37 |  | 40 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 403.5950. FAB 2403 WSP Paint | FAB Fab Shop WSP Paint | 20 Fabrication | 63.09 |  | 15 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 403.5960. FAB 2403 Misc Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 23.85 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 403.5970. FAB 2403 Misc Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 2 |  | 6 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5901. FAB 2404 Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 219.9 |  | 65 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5935. FAB 2404 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 4.5 |  | 20 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5940. FAB 2404 WSP Fabrication | FAB Fab Shop WSP Fabrication | 20 Fabrication | 104.83 |  | 105 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5950. FAB 2404 WSP Paint | FAB Fab Shop WSP Paint | 20 Fabrication | 109.69 |  | 360 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5960. FAB 2404 Misc Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 18 |  | 40 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5970. FAB 2404 Misc Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 2.97 |  | 15 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 404.5995. FAB 2404 Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 30.62 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 406.5901. FAB 2406 Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 38 |  | 68 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 406.5935. FAB 2406 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 40 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 406.5960. FAB 2406 Misc Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 12.63 |  | 49 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 406.5970. FAB 2406 Misc Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 30 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 406.5995. FAB 2406 Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 15.62 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 407.5901. FAB 2407 Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 294.19 |  | 210 | 50 | 0 | 50 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 407.5935. FAB 2407 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 5.3 |  | 60 | 10 | 10 | 0 | 2024-01-01 |  | 10 |  |  |  | 10
2450. Fab Shop Jobs 2024 Projects | 407.5960. FAB 2407 Misc Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 434 |  | 769 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 407.5970. FAB 2407 Misc Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 342 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 407.5995. FAB 2407 Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 41.55 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 408.5901. FAB 2408 Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 333 |  | 853 | 140 | 150 | -10 | 2024-01-01 |  | 40 | 50 | 30 | 30 | 150
2450. Fab Shop Jobs 2024 Projects | 408.5935. FAB 2408 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 30 | 30 | 30 | 0 | 2024-01-01 |  | 10 | 10 | 10 |  | 30
2450. Fab Shop Jobs 2024 Projects | 408.5940. FAB 2408 WSP Fabrication | FAB Fab Shop WSP Fabrication | 20 Fabrication | 809.22 |  | 1335 | 200 | 880 | -680 | 2024-01-01 |  | 400 | 380 |  |  | 780 | 100 |  |  |  | 100
2450. Fab Shop Jobs 2024 Projects | 408.5960. FAB 2408 Misc. Metals Fabrication L&E | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 136.29 |  | 1183 | 995 | 1000 | -5 | 2024-01-01 |  | 200 | 350 | 350 |  | 900 | 100 |  |  |  | 100
2450. Fab Shop Jobs 2024 Projects | 408.5970. FAB 2408 Misc. Metals Paint L&E | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 0 |  | 48 | 48 | 48 | 0 | 2024-01-01 |  | 24 | 24 |  |  | 48
2450. Fab Shop Jobs 2024 Projects | 408.5995. FAB 2408 Change / VE | FAB Fab Shop Change Orders | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 409.5901. FAB 2409 Management/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 244.67 |  | 58 | 10 | 0 | 10 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 409.5935. FAB 2409 Deliveries | FAB Fab Shop Deliveries | 20 Fabrication | 0 |  | 0 | 20 | 20 | 0 | 2024-01-01 |  | 10 | 10 |  |  | 20
2450. Fab Shop Jobs 2024 Projects | 409.5960. FAB 2409 Misc. Metals Fabrication | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 341.65 |  | 355 | 70 | 58 | 12 | 2024-01-01 |  | 48 | 10 |  |  | 58
2450. Fab Shop Jobs 2024 Projects | 409.5970. FAB 2409 Misc. Metals Paint | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 86.53 |  | 523 | 575 | 69 | 506 | 2024-01-01 |  | 59 | 10 |  |  | 69
2450. Fab Shop Jobs 2024 Projects | 409.5995. FAB 2409 Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2024-01-01
2450. Fab Shop Jobs 2024 Projects | 999.9999. Reallocate Cost on Internal Jobs | OH Overhead Allocation | 00 _Unknown PR Dept | 0 |  | 20 | 0 | 0 | 0 | 2024-01-01
2411. CWSID Dewatering Bldg HVACV Project | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 37.01 |  | 25 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 100.1500. VIS Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 1 | 1 | 1 | 0 | 2025-01-01 | 2026-07-31 | 1 |  |  |  | 1
2411. CWSID Dewatering Bldg HVACV Project | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 405.83 |  | 622 | 197.67 | 224.5 | -26.83 | 2025-01-01 | 2026-07-31 | 40 | 120 | 50 | 14.5 | 224.5
2411. CWSID Dewatering Bldg HVACV Project | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 22.5 |  | 679 | 239 | 239 | 0 | 2025-01-01 | 2026-07-31 | 50 | 50 | 41.5 | 97.5 | 239
2411. CWSID Dewatering Bldg HVACV Project | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 37.7 |  | 437 | 50 | 50 | 0 | 2025-01-01 | 2026-07-31 | 25 | 25 |  |  | 50
2411. CWSID Dewatering Bldg HVACV Project | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 450.74 |  | 892 | 427.42 | 449.6 | -22.18 | 2025-01-01 | 2026-07-31 | 84.9 | 160 | 160 | 44.7 | 449.6
2411. CWSID Dewatering Bldg HVACV Project | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 84 | 25 | 25 | 0 | 2025-01-01 | 2026-07-31 | 25 |  |  |  | 25
2411. CWSID Dewatering Bldg HVACV Project | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 150.1230. T Transporting | T Transporting | 40 Drivers | 5 |  | 150 | 20 | 20 | 0 | 2025-01-01 | 2026-07-31 | 20 |  |  |  | 20
2411. CWSID Dewatering Bldg HVACV Project | 150.2760. HO Haul Off | HO Haul Off | 40 Drivers | 0 |  | 12.5 | 12.5 | 12.5 | 0 | 2025-01-01 | 2026-07-31 | 6 | 6.5 |  |  | 12.5
2411. CWSID Dewatering Bldg HVACV Project | 180.7400. HVAC HVAC & Plumbing Rock Mtn Mechanical | HVAC HVAC | 55 Mechanical | 31.6 |  | 30 | 10 | 10 | 0 | 2025-01-01 | 2026-07-31 | 10 |  |  |  | 10
2411. CWSID Dewatering Bldg HVACV Project | 200.3000. CNR Concrete Installation | CNC Concrete Work | 15 Concrete | 56.23 |  | 300 | 50 | 50 | 0 | 2025-01-01 | 2026-07-31 |  | 50 |  |  | 50
2411. CWSID Dewatering Bldg HVACV Project | 200.5000. MET Metals Install | MET Metals | 20 Fabrication | 124.12 |  | 510 | 275.88 | 400 | -124.12 | 2025-01-01 | 2026-07-31 | 150 | 150 | 100 |  | 400
2411. CWSID Dewatering Bldg HVACV Project | 200.5400. HAT Hatch Install | HAT Hatch/Skylights | 12 Finishes | 0 |  | 60 | 0 | 20 | -20 | 2025-01-01 | 2026-07-31 | 10 | 10 |  |  | 20
2411. CWSID Dewatering Bldg HVACV Project | 200.6300. DAW Door Install | DAW Doors & Windows | 12 Finishes | 0 |  | 470 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 200.6800. CLK Caulking for Finished Openings | CLK Caulking | 12 Finishes | 0 |  | 40 | 40 | 40 | 0 | 2025-01-01 | 2026-07-31 | 40 |  |  |  | 40
2411. CWSID Dewatering Bldg HVACV Project | 200.7400. HVAC Support | HVAC HVAC | 55 Mechanical | 0 |  | 300 | 200 | 200 | 0 | 2025-01-01 | 2026-07-31 | 20 | 100 | 80 |  | 200
2411. CWSID Dewatering Bldg HVACV Project | 300.7400. PCO1 HVAC hatch Corner reinfore & lift eyes | HVAC HVAC | 55 Mechanical | 14 |  | 15 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 310.7400. PCO 2 - Patch east wall Press Room | HVAC HVAC | 55 Mechanical | 38.81 |  | 49.5 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 320.7400. PCO 3 - Patch metal ceiling | HVAC HVAC | 55 Mechanical | 83.31 |  | 105 | 30 | 30 | 0 | 2025-01-01 | 2026-07-31 | 10 | 10 | 10 |  | 30
2411. CWSID Dewatering Bldg HVACV Project | 340.7400. PCO 7 - Mezzanine ceiling | HVAC HVAC | 55 Mechanical | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 800.1940. PL Punchlist | PL Punch List Work | 12 Finishes | 0 |  | 300 | 200 | 200 | 0 | 2025-01-01 | 2026-07-31 |  | 50 | 50 | 100 | 200
2411. CWSID Dewatering Bldg HVACV Project | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2411. CWSID Dewatering Bldg HVACV Project | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2026-07-31
2410. Wellington Waterline Coal Creek PRV | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 186 |  | 38 | 5 | 10 | -5 | 2025-01-01 | 2025-05-30 | 10 |  |  |  | 10
2410. Wellington Waterline Coal Creek PRV | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 0 |  | 16.8 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 35 |  | 13.1 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 4.25 |  | 27 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 2.6 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 150.1230. T Transporting | T Transporting | 40 Drivers | 34.9 |  | 30 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 6 |  | 14.41 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 150.2760. HO Haul Off Truck Only | HO Haul Off | 40 Drivers | 0 |  | 20.06 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.1600. TC Traffic Control Removal | TC Traffic Control | 30 Traffic Control | 21.25 |  | 92 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.2010. RG Rough Grading, Placing to Subgrade | RG Grading (DO NOT USE) | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.2080. CB Excavation Crew L&E | EXS Excavate Structure | 11 Earth Work | 0 |  | 20 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.2200. DPL Storm Drain Piping L&E | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 72.72 |  | 30 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.2610. PT Pressure Test/Chlorinating L&E | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.2800. BFST Backfill PRV Vault L&E | BFST Backfill (DO NOT USE) | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.3000. CNC Concrete Vault L&E | CNC Concrete Work | 15 Concrete | 0 |  | 135 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.3010. WP Winter Protection L&E | WP Winter Protection | 15 Concrete | 0 |  | 40 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 200.7100. IMP Piping & Pipe Supports L&E | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 300.2030. D Demo Storm Drain Concrete Sidewalk And Gutter | D Demolition | 11 Earth Work | 0 |  | 30 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 300.2075. FG Asphalt Prep | FG Finish Grade | 11 Earth Work | 0 |  | 15 | 15 | 15 | 0 | 2025-01-01 | 2025-05-30 |  | 15 |  |  | 15
2410. Wellington Waterline Coal Creek PRV | 300.2300. WPL Excavate And Backfill Storm Drain | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 49.54 |  | 120 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 300.3000. CNC Form Prep & Pour Storm Drain Concrete | CNC Concrete Work | 15 Concrete | 37.27 |  | 90 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 400.2300. WPL Excavate& Replace Waterline on 300 N. | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 62.95 |  | 21 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2410. Wellington Waterline Coal Creek PRV | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 3.63 |  | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-05-30
2409. JVWCD 2024 Vault Improvement Project | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 208 |  | 187.28 | 75 | 84 | -9 | 2024-11-22 | 2026-04-01 | 60 | 24 |  |  | 84
2409. JVWCD 2024 Vault Improvement Project | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 533.58 |  | 192.05 | 200 | 241 | -41 | 2024-11-22 | 2026-04-01 | 200 | 41 |  |  | 241
2409. JVWCD 2024 Vault Improvement Project | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 115.68 |  | 139.74 | 50 | 48 | 2 | 2024-11-22 | 2026-04-01 | 38 | 10 |  |  | 48
2409. JVWCD 2024 Vault Improvement Project | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 233.4 |  | 280.84 | 200 | 76 | 124 | 2024-11-22 | 2026-04-01 | 50 | 26 |  |  | 76
2409. JVWCD 2024 Vault Improvement Project | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 4 |  | 28.45 | 20 | 21 | -1 | 2024-11-22 | 2026-04-01 | 14 | 7 |  |  | 21
2409. JVWCD 2024 Vault Improvement Project | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 3 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 3 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 180.1605. TC Flagger Sub | TC Flaggers | 30 Traffic Control | 32 |  | 0 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 180.2120. DIP Install Conc Valve Collar | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | 30 | 60 | 30 | 30 | 2024-11-22 | 2026-04-01 | 15 | 15 |  |  | 30
2409. JVWCD 2024 Vault Improvement Project | 180.2910. MP Milling/Pulverize Sub | MP Milling/Pulverize | 11 Earth Work | 30.37 |  | 15 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 180.2920. SC Saw Cutting/Coring Sub | SC Saw Cutting/Coring | 55 Mechanical | 0 |  | 4 | 0 | 15 | -15 | 2024-11-22 | 2026-04-01 | 4 | 11 |  |  | 15
2409. JVWCD 2024 Vault Improvement Project | 200.1200. HOOK Hook Truck Dumpsters Transporting 4390 S 2200 W Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 2.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.1230. T Transporting 4390 S 2200 W Vault | T Transporting | 40 Drivers | 12.77 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.1600. TC Traffic Control | TC Traffic Control | 30 Traffic Control | 114.6 |  | 0 | 10 | 0 | 10 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.1930. MC Misc. Cleanup 4390 S 2200 W Vault | MC Misc Cleanup | 12 Finishes | 10 |  | 20 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.1940. PL Punch List Work 4390 S 2200 W Vault | PL Punch List Work | 12 Finishes | 20.86 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2030. D Demo 4390 S 2200 W Vault | D Demolition | 11 Earth Work | 171.99 |  | 112.58 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2075. FG Finish Grading Prep 4390 S 2200 W Vault | FG Finish Grade | 11 Earth Work | 48.88 |  | 26.56 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2140. SVR Exterior Pipe Work 4390 S 2200 W Vault | SVR Services | 10 Pipe | 0 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2180. CATH Cathodic Install 4390 S 2200 W Vault | CATH Cathodic Protection | 10 Pipe | 17.5 |  | 92.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2390. WSP Exterior Pipe Work 4390 S 2200 W Vault | WSP Welded Steel Pipe | 10 Pipe | 13.68 |  | 111.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2610. PT Fill/Test/Flush WSP 4390 S 2200 W Vault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 10 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2710. FWF Flowable Fill Utility Support 4390 S 2200 W Vault | FWF Flowable Fill | 15 Concrete | 23.54 |  | 6 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2750. H Hauling 4390 S 2200 W Vault | H Hauling | 40 Drivers | 5 |  | 11.25 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.2760. HO Haul Off 4390 S 2200 W Vault | HO Haul Off | 40 Drivers | 69.82 |  | 8.63 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.3000. CNC Concrete Install 4390 S 2200 W Vault | CNC Concrete Work | 15 Concrete | 12.52 |  | 50.12 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.5000. MET Metals Install 4390 S 2200 W Vault | MET Metals | 20 Fabrication | 4 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.5100. WE Butt Strap Welding 4390 S 2200 W Vault | W Welding | 20 Fabrication | 8.3 |  | 18.66 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 200.7100. IMP Interior Piping Install 4390 S 2200 W Vault | IMP Interior Mech/Piping | 55 Mechanical | 122.7 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.1200. HOOK Hook Truck Dumpsters Transporting 4330 S 300 W Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 2.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.1230. T Transporting 4330 S 300 W Vault | T Transporting | 40 Drivers | 28.95 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.1930. MC Misc. Cleanup 4330 S 300 W Vault | MC Misc Cleanup | 12 Finishes | 0 |  | 20 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.1940. PL Punch List Work 4330 S 300 W Vault | PL Punch List Work | 12 Finishes | 0 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2030. D Demo 4330 S 300 W Vault | D Demolition | 11 Earth Work | 124.7 |  | 69.61 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2075. FG Finshing Grading 4330 S 300 W Vault | FG Finish Grade | 11 Earth Work | 35.5 |  | 20.32 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2180. CATH Cathodic Install 4330 S 300 W Vault | CATH Cathodic Protection | 10 Pipe | 1 |  | 18 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2390. WSP Welding Steel Pipe Install 4330 S 300 W Vault | WSP Welded Steel Pipe | 10 Pipe | 9.38 |  | 116.22 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2610. PT Fill/Test/Flush WSP 4330 S 300 W Vault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 10 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2710. FWF Flowable Fill Utility Support 4330 S 300 W Vault | FWF Flowable Fill | 15 Concrete | 2 |  | 10 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2750. H Hauling 4330 S 300 W Vault | H Hauling | 40 Drivers | 13.23 |  | 21.6 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.2760. HO Haul Off 4330 S 300 W Vault | HO Haul Off | 40 Drivers | 36.46 |  | 8.88 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.3000. CNC Concrete Install 4330 S 300 W Vault | CNC Concrete Work | 15 Concrete | 1 |  | 49.15 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.5000. MET Metals Install 4330 S 300 W Vault | MET Metals | 20 Fabrication | 24.37 |  | 38 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 300.7100. IMP Interior Piping Install 4330 S 300 W Vault | IMP Interior Mech/Piping | 55 Mechanical | 261.7 |  | 30 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.1230. T Transporting 4500 S 350 E Vault | T Transporting | 40 Drivers | 0 |  | 10 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.1600. TC Traffic Control 4500 S 350 E Vault | TC Traffic Control | 30 Traffic Control | 71.4 |  | 30 | 2.5 | 2.5 | 0 | 2024-11-22 | 2026-04-01 | 2.5 |  |  |  | 2.5
2409. JVWCD 2024 Vault Improvement Project | 400.2030. D Demo 4500 S 350 E Vault | D Demolition | 11 Earth Work | 96.81 |  | 45 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.2180. CATH Cathodic Install 4500 S 350 E Vault | CATH Cathodic Protection | 10 Pipe | 0 |  | 3 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.2390. WSP Exterior Pipe Install 4500 S 350 E Vault | WSP Welded Steel Pipe | 10 Pipe | 19.67 |  | 120.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.2610. PT Fill/Test/Flush WSP 4500 S 350 E Vault | PT Pressure Test/Chlorinating | 10 Pipe | 1 |  | 10 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.2760. HO Haul Off 4500 S 350 E Vault | HO Haul Off | 40 Drivers | 2 |  | 2.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.5000. MET Metals Install 4500 S 350 E Vault | MET Metals | 20 Fabrication | 52.16 |  | 64 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 400.5100. WE Welding 4500 S 350 E Vault | W Welding | 20 Fabrication | 14.2 |  | 10 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 500.1200. HOOK Hook Truck Dumpsters Transporting 11400 S 100 E Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 2.5 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 500.1230. T Transporting 11400 S 100 E Vault | T Transporting | 40 Drivers | 0 |  | 60 | 60 | 60 | 0 | 2024-11-22 | 2026-04-01 | 60 |  |  |  | 60
2409. JVWCD 2024 Vault Improvement Project | 500.1600. TC Traffic Control | TC Traffic Control | 30 Traffic Control | 0 |  | 0 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 500.1930. MC Misc. Cleanup 11400 S 100 E Vault | MC Misc Cleanup | 12 Finishes | 0 |  | 20 | 20 | 20 | 0 | 2024-11-22 | 2026-04-01 | 20 |  |  |  | 20
2409. JVWCD 2024 Vault Improvement Project | 500.1940. PL Punch List Work 11400 S 100 E Vault | PL Punch List Work | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2024-11-22 | 2026-04-01 | 30 |  |  |  | 30
2409. JVWCD 2024 Vault Improvement Project | 500.2030. D Demo 11400 S 100 E Vault | D Demolition | 11 Earth Work | 0 |  | 210.69 | 210 | 210 | 0 | 2024-11-22 | 2026-04-01 | 210 |  |  |  | 210
2409. JVWCD 2024 Vault Improvement Project | 500.2090. MTL Pipe Materials Concrete Lid Install | MTL Materials | 00 _Unknown PR Dept | 0 |  | 30 | 30 | 0 | 30 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 500.2180. CATH Cathodic Install 11400 S 100 E Vault | CATH Cathodic Protection | 10 Pipe | 0 |  | 18 | 18 | 18 | 0 | 2024-11-22 | 2026-04-01 | 18 |  |  |  | 18
2409. JVWCD 2024 Vault Improvement Project | 500.2390. PCS Backfill 11400 S 100 E Vault | WSP Welded Steel Pipe | 10 Pipe | 0 |  | 20 | 60 | 20 | 40 | 2024-11-22 | 2026-04-01 | 20 |  |  |  | 20
2409. JVWCD 2024 Vault Improvement Project | 500.2610. PT Fill/Test/Flush WSP 11400 S 100 E Vault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 20 | 20 | 20 | 0 | 2024-11-22 | 2026-04-01 | 20 |  |  |  | 20
2409. JVWCD 2024 Vault Improvement Project | 500.2710. FWF Flowable Fill Utility Support 11400 S 100 E Vault | FWF Flowable Fill | 15 Concrete | 0 |  | 15 | 15 | 15 | 0 | 2024-11-22 | 2026-04-01 | 15 |  |  |  | 15
2409. JVWCD 2024 Vault Improvement Project | 500.2760. HO Haul Off 11400 S 100 E Vault | HO Haul Off | 40 Drivers | 0 |  | 21 | 21 | 21 | 0 | 2024-11-22 | 2026-04-01 | 21 |  |  |  | 21
2409. JVWCD 2024 Vault Improvement Project | 500.3000. CNC Concrete Install 11400 S 100 E Vault | CNC Concrete Work | 15 Concrete | 170.91 |  | 221 | 20 | 175 | -155 | 2024-11-22 | 2026-04-01 | 175 |  |  |  | 175
2409. JVWCD 2024 Vault Improvement Project | 500.5000. MET Metals Install 11400 S 100 E Vault | MET Metals | 20 Fabrication | 0 |  | 60 | 60 | 60 | 0 | 2024-11-22 | 2026-04-01 | 60 |  |  |  | 60
2409. JVWCD 2024 Vault Improvement Project | 500.5100. WE Wedling 11400 S 100 E Vault | W Welding | 20 Fabrication | 0 |  | 66.67 | 70 | 70 | 0 | 2024-11-22 | 2026-04-01 | 70 |  |  |  | 70
2409. JVWCD 2024 Vault Improvement Project | 500.6500. P Paint Prep / Power Wash 11400 S 100 E Vault | P Painting | 12 Finishes | 0 |  | 12 | 0 | 12 | -12 | 2024-11-22 | 2026-04-01 | 12 |  |  |  | 12
2409. JVWCD 2024 Vault Improvement Project | 500.7100. IMP Interior Pipe Install 11400 S 100 E Vault | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 507 | 500 | 500 | 0 | 2024-11-22 | 2026-04-01 | 500 |  |  |  | 500
2409. JVWCD 2024 Vault Improvement Project | 600.1200. HOOK Hook Truck Dumpsters Transporting 11400 S 700 E Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 2.25 |  | 2.5 | 0 | 2 | -2 | 2024-11-22 | 2026-04-01 | 2 |  |  |  | 2
2409. JVWCD 2024 Vault Improvement Project | 600.1230. T Transporting 11400 S 700 E Vault | T Transporting | 40 Drivers | 0 |  | 30 | 30 | 30 | 0 | 2024-11-22 | 2026-04-01 | 30 |  |  |  | 30
2409. JVWCD 2024 Vault Improvement Project | 600.1600. TC Traffic Control 11400 S 700 E Vault | TC Traffic Control | 30 Traffic Control | 3.25 |  | 40 | 250 | 110 | 140 | 2024-11-22 | 2026-04-01 | 110 |  |  |  | 110
2409. JVWCD 2024 Vault Improvement Project | 600.1930. MC Misc. Cleanup 11400 S 700 E Vault | MC Misc Cleanup | 12 Finishes | 0 |  | 20 | 20 | 20 | 0 | 2024-11-22 | 2026-04-01 | 20 |  |  |  | 20
2409. JVWCD 2024 Vault Improvement Project | 600.1940. PL Punch List Work 11400 S 700 E Vault | PL Punch List Work | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2024-11-22 | 2026-04-01 | 30 |  |  |  | 30
2409. JVWCD 2024 Vault Improvement Project | 600.2030. D Demo 11400 S 700 E Vault | D Demolition | 11 Earth Work | 0 |  | 225.38 | 270 | 270 | 0 | 2024-11-22 | 2026-04-01 | 270 |  |  |  | 270
2409. JVWCD 2024 Vault Improvement Project | 600.2075. FG Finish Grade 11400 S 700 E Vault | FG Finish Grade | 11 Earth Work | 0 |  | 8.64 | 0 | 20 | -20 | 2024-11-22 | 2026-04-01 | 20 |  |  |  | 20
2409. JVWCD 2024 Vault Improvement Project | 600.2120. DIP Exterior Pipe Install11400 S 700 E Vault | DIP Ductile Iron Pipe | 10 Pipe | 0 |  | -3 | 25 | 0 | 25 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 600.2610. PT Fill/Test/Flush WSP 11400 S 700 E Vault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 20 | 20 | 20 | 0 | 2024-11-22 | 2026-04-01 | 20 |  |  |  | 20
2409. JVWCD 2024 Vault Improvement Project | 600.2710. FWF Flowable Fill Utility Support 11400 S 700 E Vault | FWF Flowable Fill | 15 Concrete | 0 |  | 30 | 0 | 42 | -42 | 2024-11-22 | 2026-04-01 | 42 |  |  |  | 42
2409. JVWCD 2024 Vault Improvement Project | 600.2760. HO Haul Off 11400 S 700 E Vault | HO Haul Off | 40 Drivers | 0 |  | 11 | 25 | 25 | 0 | 2024-11-22 | 2026-04-01 | 25 |  |  |  | 25
2409. JVWCD 2024 Vault Improvement Project | 600.3000. CNC Concrete Install | CNC Concrete Work | 15 Concrete | 3.22 |  | 0 | 10 | 0 | 10 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 600.5000. MET Metals Install 11400 S 700 E Vault | MET Metals | 20 Fabrication | 0 |  | 12 | 12 | 12 | 0 | 2024-11-22 | 2026-04-01 | 12 |  |  |  | 12
2409. JVWCD 2024 Vault Improvement Project | 600.5100. WE Welding 11400 S 700 E Vault | W Welding | 20 Fabrication | 0 |  | 10 | 10 | 10 | 0 | 2024-11-22 | 2026-04-01 | 10 |  |  |  | 10
2409. JVWCD 2024 Vault Improvement Project | 600.6500. P Paint Piping 11400 S 700 E Vault | P Painting | 12 Finishes | 0 |  | 162 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 600.7100. IMP Interior Pipe Install 11400 S 700 E Vault | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 114 | 115 | 115 | 0 | 2024-11-22 | 2026-04-01 | 115 |  |  |  | 115
2409. JVWCD 2024 Vault Improvement Project | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 5.05 |  | 2 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 25.41 |  | 0.8 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.8 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.8 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 6 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2409. JVWCD 2024 Vault Improvement Project | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2024-11-22 | 2026-04-01
2408. Santaquin City WRF Phase 3 Upgrades | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 20.85 |  | 56.25 | 10 | 5.8 | 4.2 | 2024-09-30 | 2026-08-31 | 2 | 3.8 |  |  | 5.8
2408. Santaquin City WRF Phase 3 Upgrades | 100.1500. VIS Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 101 | 50 | 50 | 0 | 2024-09-30 | 2026-08-31 |  | 20 | 9 | 21 | 50
2408. Santaquin City WRF Phase 3 Upgrades | 100.1510. S Surveying | S Surveying | 45 Survey | 293.56 |  | 250 | 85.09 | 118.8 | -33.71 | 2024-09-30 | 2026-08-31 | 48 | 40 | 30.8 |  | 118.8
2408. Santaquin City WRF Phase 3 Upgrades | 100.1515. | S Drone/Lidar Requirements | 45 Survey | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 850.58 |  | 2250 | 319.75 | 384.3 | -64.55 | 2024-09-30 | 2026-08-31 | 120 | 120 | 120 | 24.3 | 384.3
2408. Santaquin City WRF Phase 3 Upgrades | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 466.53 |  | 500 | 123.06 | 163.6 | -40.54 | 2024-09-30 | 2026-08-31 | 30 | 34.5 | 50 | 49.1 | 163.6
2408. Santaquin City WRF Phase 3 Upgrades | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 513.02 |  | 1000 | 484.5 | 540 | -55.5 | 2024-09-30 | 2026-08-31 | 150 | 150 | 140 | 100 | 540
2408. Santaquin City WRF Phase 3 Upgrades | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 1501.99 |  | 3000 | 1498.01 | 1670.4 | -172.39 | 2024-09-30 | 2026-08-31 | 400 | 400 | 470.4 | 400 | 1670.4
2408. Santaquin City WRF Phase 3 Upgrades | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 223 |  | 500 | 277 | 288 | -11 | 2024-09-30 | 2026-08-31 | 80 | 80 | 80 | 48 | 288
2408. Santaquin City WRF Phase 3 Upgrades | 100.1705. | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 100.1706. | FS Executive | 60 Operations (PM/PE) | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 150.1230. T Transporting | T Transporting | 40 Drivers | 131.23 |  | 150 | 11.54 | 45.6 | -34.06 | 2024-09-30 | 2026-08-31 | 15 | 15 | 15.6 |  | 45.6
2408. Santaquin City WRF Phase 3 Upgrades | 150.2750. H Hauling Truck Only | H Hauling | 40 Drivers | 245.4 |  | 348.7 | 96.15 | 154.8 | -58.65 | 2024-09-30 | 2026-08-31 | 80 | 50 | 24.8 |  | 154.8
2408. Santaquin City WRF Phase 3 Upgrades | 150.2760. HO Haul Off Truck Only Bank Yards | HO Haul Off | 40 Drivers | 72.6 |  | 565.5 | 360 | 466.3 | -106.3 | 2024-09-30 | 2026-08-31 | 170 | 146.3 | 150 |  | 466.3
2408. Santaquin City WRF Phase 3 Upgrades | 200.1600. TC Traffic Control | TC Traffic Control | 30 Traffic Control | 0 |  | 25 | 25 | 25 | 0 | 2024-09-30 | 2026-08-31 | 6 | 7 | 12 |  | 25
2408. Santaquin City WRF Phase 3 Upgrades | 200.1700. | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 200.2065. SFC SWPPP Sweeper Truck (Dust Control) | SFC SWPPP | 11 Earth Work | 275.87 |  | 51 | 32.38 | 32.4 | -0.02 | 2024-09-30 | 2026-08-31 | 25 | 7.4 |  |  | 32.4
2408. Santaquin City WRF Phase 3 Upgrades | 220.1800. LIFT STA - PH Potholing - VanCon Vac Truck | PH Potholing | 10 Pipe | 11 |  | 9 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 220.2030. LIFT STA - D Demo Pipe & Vault Removal | D Demolition | 11 Earth Work | 0 |  | 61.2 | 61.2 | 61.2 | 0 | 2024-09-30 | 2026-08-31 | 40 | 21.2 |  |  | 61.2
2408. Santaquin City WRF Phase 3 Upgrades | 220.2060. LIFT STA - FE Temp Fence (Chainlink) Labor | FE Fencing | 11 Earth Work | 0 |  | 12.8 | 12.8 | 12.8 | 0 | 2024-09-30 | 2026-08-31 | 12.8 |  |  |  | 12.8
2408. Santaquin City WRF Phase 3 Upgrades | 220.2075. LIFT STA - FG Roadbase Level | FG Finish Grade | 11 Earth Work | 0 |  | 142.5 | 142.5 | 142.5 | 0 | 2024-09-30 | 2026-08-31 | 142.5 |  |  |  | 142.5
2408. Santaquin City WRF Phase 3 Upgrades | 220.2080. LIFT STA - EXS Open Cut Upper Level 5' to 10' Vault 300 Ex | EXS Excavate Structure | 11 Earth Work | 118.15 |  | 120 | 1.85 | 1.9 | -0.05 | 2024-09-30 | 2026-08-31 | 1.9 |  |  |  | 1.9
2408. Santaquin City WRF Phase 3 Upgrades | 220.2085. LIFT STA - BFST Backfill Interior of Building w/ Gravel | BFST Backfill Structure | 11 Earth Work | 0 |  | 110 | 110 | 110 | 0 | 2024-09-30 | 2026-08-31 | 70 | 40 |  |  | 110
2408. Santaquin City WRF Phase 3 Upgrades | 220.2130. LIFT STA - Site Piping & SVR Meter | PVC Pipe | 10 Pipe | 348.24 |  | 458.08 | 109.84 | 109.8 | 0.04 | 2024-09-30 | 2026-08-31 | 44 | 25 | 40.8 |  | 109.8
2408. Santaquin City WRF Phase 3 Upgrades | 220.2605. LIFT STA - BYP Bypass VanCon Vac Truck | BYP Bypass Pumping | 10 Pipe | 0 |  | 50 | 50 | 50 | 0 | 2024-09-30 | 2026-08-31 | 50 |  |  |  | 50
2408. Santaquin City WRF Phase 3 Upgrades | 220.3000. LIFT STA - CNC Concrete | CNC Concrete Work | 15 Concrete | 704.62 |  | 754.76 | 50.14 | 50.1 | 0.04 | 2024-09-30 | 2026-08-31 | 50.1 |  |  |  | 50.1
2408. Santaquin City WRF Phase 3 Upgrades | 220.5000. LIFT STA - MET Air Vents on Vault | MET Metals | 20 Fabrication | 0 |  | 313.5 | 313.5 | 313.5 | 0 | 2024-09-30 | 2026-08-31 | 200 | 113.5 |  |  | 313.5
2408. Santaquin City WRF Phase 3 Upgrades | 220.6100. LIFT STA - CLK Caulking for Paint | F Framing | 12 Finishes | 19.56 |  | 5.12 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 220.6200. LIFT STA - IN Insulation Foundation Install | IN Insulation | 12 Finishes | 0 |  | 9.6 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 220.6300. LIFT STA - DAW Door Install | DAW Doors & Windows | 12 Finishes | 52.66 |  | 60 | 14 | 14 | 0 | 2024-09-30 | 2026-08-31 | 10 | 4 |  |  | 14
2408. Santaquin City WRF Phase 3 Upgrades | 220.6500. LIFT STA - P Powerwash Floors/Walls | P Painting | 12 Finishes | 0 |  | 16 | 16 | 16 | 0 | 2024-09-30 | 2026-08-31 | 16 |  |  |  | 16
2408. Santaquin City WRF Phase 3 Upgrades | 220.7100. LIFT STA - IMP 8"-12" Piping, Fitting/Valve Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 551.91 | 551.91 | 551.9 | 0.01 | 2024-09-30 | 2026-08-31 | 251.9 | 300 |  |  | 551.9
2408. Santaquin City WRF Phase 3 Upgrades | 220.7400. LIFT STA - HVAC & Louvers | HVAC HVAC | 55 Mechanical | 0 |  | 45 | 45 | 45 | 0 | 2024-09-30 | 2026-08-31 | 45 |  |  |  | 45
2408. Santaquin City WRF Phase 3 Upgrades | 220.7500. LIFT STA - PUMP Remove & Replace Submersible Pump | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 30 | 30 | 30 | 0 | 2024-09-30 | 2026-08-31 | 30 |  |  |  | 30
2408. Santaquin City WRF Phase 3 Upgrades | 220.7600. LIFT STA - MEQ Davit Crane Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 90 | 90 | 90 | 0 | 2024-09-30 | 2026-08-31 | 90 |  |  |  | 90
2408. Santaquin City WRF Phase 3 Upgrades | 220.7900. LIFT STA - ELC Ductbank Trenching - 150 LF | ELC Electrical | 10 Pipe | 0 |  | 40 | 40 | 40 | 0 | 2024-09-30 | 2026-08-31 |  | 40 |  |  | 40
2408. Santaquin City WRF Phase 3 Upgrades | 250.1650. WRF Site - SB Signage Install Post w/ Sign | SB Signage | 12 Finishes | 0 |  | 9 | 9 | 9 | 0 | 2024-09-30 | 2026-08-31 | 9 |  |  |  | 9
2408. Santaquin City WRF Phase 3 Upgrades | 250.2030. WRF Site - D Demo Pipeline Removal | D Demolition | 11 Earth Work | 0 |  | 66.8 | 66.8 | 66.8 | 0 | 2024-09-30 | 2026-08-31 | 30 | 30 | 6.8 |  | 66.8
2408. Santaquin City WRF Phase 3 Upgrades | 250.2065. WRF Site - SFC SWPPP Sweeper Truck (Dust Control) | SFC SWPPP | 11 Earth Work | 0.5 |  | 26 | 25.5 | 25.5 | 0 | 2024-09-30 | 2026-08-31 | 25.5 |  |  |  | 25.5
2408. Santaquin City WRF Phase 3 Upgrades | 250.2070. WRF Site - RGF Site Fill | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 222.5 | 222.5 | 222.5 | 0 | 2024-09-30 | 2026-08-31 | 222.5 |  |  |  | 222.5
2408. Santaquin City WRF Phase 3 Upgrades | 250.2075. WRF Site - FG Asphalt Prep | FG Finish Grade | 11 Earth Work | 0 |  | 638.75 | 638.75 | 638.8 | -0.05 | 2024-09-30 | 2026-08-31 |  | 638.8 |  |  | 638.8
2408. Santaquin City WRF Phase 3 Upgrades | 250.2120. WRF Site - DIP Piping Install | DIP Ductile Iron Pipe | 10 Pipe | 127.01 |  | 511.55 | 384.54 | 511.6 | -127.06 | 2024-09-30 | 2026-08-31 | 260 | 251.6 |  |  | 511.6
2408. Santaquin City WRF Phase 3 Upgrades | 250.2130. WRF Site - HDPE Piping Install | PVC Pipe | 10 Pipe | 77.61 |  | 171.5 | 93.89 | 171.5 | -77.61 | 2024-09-30 | 2026-08-31 | 171.5 |  |  |  | 171.5
2408. Santaquin City WRF Phase 3 Upgrades | 250.2150. WRF Site - RSFM PVC Piping Install | PSR Pipe w/ Slide Rail | 10 Pipe | 9.63 |  | 280 | 270.37 | 280 | -9.63 | 2024-09-30 | 2026-08-31 | 280 |  |  |  | 280
2408. Santaquin City WRF Phase 3 Upgrades | 250.2210. WRF Site - RCP & Storm Trench Drains | RCP Reinforced Concrete Pipe | 10 Pipe | 434.13 |  | 417.95 | 20 | 88.5 | -68.5 | 2024-09-30 | 2026-08-31 | 50 | 38.5 |  |  | 88.5
2408. Santaquin City WRF Phase 3 Upgrades | 250.2705. WRF Site - SG1 On-Site Fill Processing | SG1 On-Site Sand & Gravel | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 250.3000. WRF Site - CNC Concrete Flatwork | CNC Concrete Work | 15 Concrete | 0 |  | 245.52 | 245.52 | 245.5 | 0.02 | 2024-09-30 | 2026-08-31 |  | 245.5 |  |  | 245.5
2408. Santaquin City WRF Phase 3 Upgrades | 250.3100. WRF Site - CNR Rebar VanCon Install | CNC Rebar | 15 Concrete | 0 |  | 18 | 18 | 18 | 0 | 2024-09-30 | 2026-08-31 | 18 |  |  |  | 18
2408. Santaquin City WRF Phase 3 Upgrades | 250.5000. WRF Site - IMP & Misc Metals | MET Metals | 20 Fabrication | 0 |  | 176 | 176 | 176 | 0 | 2024-09-30 | 2026-08-31 |  | 176 |  |  | 176
2408. Santaquin City WRF Phase 3 Upgrades | 250.7900. WRF Site - ELC Electrical/Fiber/Dry Utilities Trenching | ELC Electrical | 10 Pipe | 10.97 |  | 180 | 169.03 | 180 | -10.97 | 2024-09-30 | 2026-08-31 | 180 |  |  |  | 180
2408. Santaquin City WRF Phase 3 Upgrades | 260.2210. PCO 2 Stormdrain sump in lieu of pond | RCP Reinforced Concrete Pipe | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 300.5000. Process BLDG - MET Misc Metals Install | MET Metals | 20 Fabrication | 0 |  | 177 | 177 | 177 | 0 | 2024-09-30 | 2026-08-31 | 80 | 97 |  |  | 177
2408. Santaquin City WRF Phase 3 Upgrades | 300.6500. Process Bldg - Paint - Membrane Tank aissist | P Painting | 12 Finishes | 2.5 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 300.7100. Process BLDG - IMP SS Piping & Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 2987.7 | 2987.7 | 2987.7 | 0 | 2024-09-30 | 2026-08-31 | 2000 | 987.7 |  |  | 2987.7
2408. Santaquin City WRF Phase 3 Upgrades | 300.7500. Process BLDG - Equipment & pump Install | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 160 | 160 | 160 | 0 | 2024-09-30 | 2026-08-31 | 160 |  |  |  | 160
2408. Santaquin City WRF Phase 3 Upgrades | 300.7600. Process BLDG - MEQ Gates, CL Anaylizers & Turbidity Install | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 100 | 100 | 100 | 0 | 2024-09-30 | 2026-08-31 | 100 |  |  |  | 100
2408. Santaquin City WRF Phase 3 Upgrades | 300.7700. Process BLDG - SEQ Mixing Equipment & Startup | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 100 | 100 | 100 | 0 | 2024-09-30 | 2026-08-31 | 100 |  |  |  | 100
2408. Santaquin City WRF Phase 3 Upgrades | 340.2030. Blower Rm - D Demo Concrete | D Demolition | 11 Earth Work | 0 |  | 15 | 15 | 15 | 0 | 2024-09-30 | 2026-08-31 | 15 |  |  |  | 15
2408. Santaquin City WRF Phase 3 Upgrades | 340.3000. Blower Rm - CNC Conc Repair Blower Pad | CNC Concrete Work | 15 Concrete | 0 |  | 25 | 25 | 25 | 0 | 2024-09-30 | 2026-08-31 | 25 |  |  |  | 25
2408. Santaquin City WRF Phase 3 Upgrades | 340.5100. Blower Rm - WE Site Welding | W Welding | 20 Fabrication | 0 |  | 20 | 20 | 20 | 0 | 2024-09-30 | 2026-08-31 | 20 |  |  |  | 20
2408. Santaquin City WRF Phase 3 Upgrades | 340.7100. Blower Rm - IMP Dewatering Pumps & Pipe | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 85 | 85 | 85 | 0 | 2024-09-30 | 2026-08-31 | 85 |  |  |  | 85
2408. Santaquin City WRF Phase 3 Upgrades | 340.7700. Blower Rm - SEQ Compressor Piping | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 150 | 150 | 150 | 0 | 2024-09-30 | 2026-08-31 | 150 |  |  |  | 150
2408. Santaquin City WRF Phase 3 Upgrades | 400.2075. DW Bldg - Geo Pier Support | FG Finish Grade | 11 Earth Work | 0 |  | 108.75 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 400.2080. DW Bldg - EXS Excavation | EXS Excavate Structure | 11 Earth Work | 0 |  | 80 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 400.2085. DW Bldg - BFST Backfill | BFST Backfill Structure | 11 Earth Work | 188.15 |  | 100 | 39.07 | 39.1 | -0.03 | 2024-09-30 | 2026-08-31 | 39.1 |  |  |  | 39.1
2408. Santaquin City WRF Phase 3 Upgrades | 400.2120. DW Bldg - DIP Pipe & Fittings | DIP Ductile Iron Pipe | 10 Pipe | 89.1 |  | 30 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 400.3000. DW Bldg - CNC Concrete | CNC Concrete Work | 15 Concrete | 544.14 |  | 388.56 | 0 | 34.3 | -34.3 | 2024-09-30 | 2026-08-31 | 34.3 |  |  |  | 34.3
2408. Santaquin City WRF Phase 3 Upgrades | 400.5000. DW Bldg - MET Misc Metals Install | MET Metals | 20 Fabrication | 0 |  | 291 | 291 | 291 | 0 | 2024-09-30 | 2026-08-31 | 100 | 191 |  |  | 291
2408. Santaquin City WRF Phase 3 Upgrades | 400.6100. DW Bldg - Install Trusses/Roofing | F Framing | 12 Finishes | 74.24 |  | 60 | 10 | 10 | 0 | 2024-09-30 | 2026-08-31 |  | 10 |  |  | 10
2408. Santaquin City WRF Phase 3 Upgrades | 400.6200. DW Bldg - IN Insulation Foundation Install | IN Insulation | 12 Finishes | 0 |  | 12.45 | 12.45 | 12.4 | 0.05 | 2024-09-30 | 2026-08-31 | 12.4 |  |  |  | 12.4
2408. Santaquin City WRF Phase 3 Upgrades | 400.6300. DW Bldg - DAW Window Install | DAW Doors & Windows | 12 Finishes | 13.92 |  | 105 | 91.08 | 91.1 | -0.02 | 2024-09-30 | 2026-08-31 |  | 91.1 |  |  | 91.1
2408. Santaquin City WRF Phase 3 Upgrades | 400.6800. DW Bldg - CLK Caulking for Finished Openings | CLK Caulking | 12 Finishes | 0 |  | 42.76 | 42.76 | 42.8 | -0.04 | 2024-09-30 | 2026-08-31 | 42.8 |  |  |  | 42.8
2408. Santaquin City WRF Phase 3 Upgrades | 400.7100. DW Bldg - IMP Piping PVC/HDPE Fittings | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 57 | 57 | 57 | 0 | 2024-09-30 | 2026-08-31 | 57 |  |  |  | 57
2408. Santaquin City WRF Phase 3 Upgrades | 400.7300. DW Bldg - PLUM Plumbing | PLUM Plumbing | 55 Mechanical | 0 |  | 78 | 78 | 78 | 0 | 2024-09-30 | 2026-08-31 | 78 |  |  |  | 78
2408. Santaquin City WRF Phase 3 Upgrades | 400.7400. DW Bldg - HVAC Louvers | HVAC HVAC | 55 Mechanical | 0 |  | 60 | 60 | 60 | 0 | 2024-09-30 | 2026-08-31 | 60 |  |  |  | 60
2408. Santaquin City WRF Phase 3 Upgrades | 400.7700. DW Bldg - SEQ Screw Conveyor | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 250 | 250 | 250 | 0 | 2024-09-30 | 2026-08-31 |  | 250 |  |  | 250
2408. Santaquin City WRF Phase 3 Upgrades | 400.7900. DW PCO Elec Ground ring trench | ELC Electrical | 10 Pipe | 33.18 |  | 0 | 0 | 5.3 | -5.3 | 2024-09-30 | 2026-08-31 | 5.3 |  |  |  | 5.3
2408. Santaquin City WRF Phase 3 Upgrades | 500.2075. Solids Tank - FG Roadbase Fine Grade | FG Finish Grade | 11 Earth Work | 0 |  | 70 | 70 | 70 | 0 | 2024-09-30 | 2026-08-31 | 60 | 10 |  |  | 70
2408. Santaquin City WRF Phase 3 Upgrades | 500.2080. Solids Tank - EXS Excavation | EXS Excavate Structure | 11 Earth Work | 1084.23 |  | 300 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 500.2085. Solids Tank - BFST Backfill | BFST Backfill Structure | 11 Earth Work | 769.52 |  | 625 | 19.09 | 19.1 | -0.01 | 2024-09-30 | 2026-08-31 | 19.1 |  |  |  | 19.1
2408. Santaquin City WRF Phase 3 Upgrades | 500.2610. Solids Tank - Pressure Test | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 40 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 500.3000. Solids Tank - CNC Concrete | CNC Concrete Work | 15 Concrete | 1523.74 |  | 2353.6 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 500.3300. Solids Tank - CNC Addon Conc Seal Boss Leaks | CNC Seal Boss Leaks | 15 Concrete | 0 |  | 60 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 500.5000. Solids Tank - MET Tank Connection | MET Metals | 20 Fabrication | 0 |  | 144 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 500.7100. Solids Tank - IMP Installation | IMP Interior Mech/Piping | 55 Mechanical | 11.31 |  | 80 | 68.69 | 68.7 | -0.01 | 2024-09-30 | 2026-08-31 | 68.7 |  |  |  | 68.7
2408. Santaquin City WRF Phase 3 Upgrades | 500.7600. Solids Tank - Tank Leak Test | MEQ Mechanical Equipment | 55 Mechanical | 12.08 |  | 20 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 500.7700. Solids Tank - SEQ Startup & Support | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 50 | 50 | 50 | 0 | 2024-09-30 | 2026-08-31 | 50 |  |  |  | 50
2408. Santaquin City WRF Phase 3 Upgrades | 550.2075. Solids Bldg - FG GeoPier Prep | FG Finish Grade | 11 Earth Work | 0 |  | 158.75 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 550.2080. Solids Bldg - EXS Excavation | EXS Excavate Structure | 11 Earth Work | 75.63 |  | 80 | 17.59 | 17.6 | -0.01 | 2024-09-30 | 2026-08-31 | 17.6 |  |  |  | 17.6
2408. Santaquin City WRF Phase 3 Upgrades | 550.2085. Solids Bldg - BFST Backfill | BFST Backfill Structure | 11 Earth Work | 0 |  | 160 | 160 | 160 | 0 | 2024-09-30 | 2026-08-31 | 100 | 60 |  |  | 160
2408. Santaquin City WRF Phase 3 Upgrades | 550.3000. Solids Bldg - CNC Concrete | CNC Concrete Work | 15 Concrete | 393.33 |  | 897.35 | 504.02 | 702.5 | -198.48 | 2024-09-30 | 2026-08-31 | 702.5 |  |  |  | 702.5
2408. Santaquin City WRF Phase 3 Upgrades | 550.5000. Solids Bldg - MET SS Pipe & Supports | MET Metals | 20 Fabrication | 0 |  | 432 | 432 | 432 | 0 | 2024-09-30 | 2026-08-31 | 380 | 52 |  |  | 432
2408. Santaquin City WRF Phase 3 Upgrades | 550.6200. Solids Bldg - IN Insulation Foundation Install | IN Insulation | 12 Finishes | 0 |  | 19.79 | 19.79 | 19.8 | -0.01 | 2024-09-30 | 2026-08-31 |  | 19.8 |  |  | 19.8
2408. Santaquin City WRF Phase 3 Upgrades | 550.6300. Solids Bldg - DAW Door Install | DAW Doors & Windows | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2024-09-30 | 2026-08-31 | 30 |  |  |  | 30
2408. Santaquin City WRF Phase 3 Upgrades | 550.6500. Solids Bldg - F Finish L&E | P Painting | 12 Finishes | 0 |  | 13.25 | 13.25 | 13.3 | -0.05 | 2024-09-30 | 2026-08-31 | 13.3 |  |  |  | 13.3
2408. Santaquin City WRF Phase 3 Upgrades | 550.6800. Solids Bldg - CLK Caulking for Finished Openings | CLK Caulking | 12 Finishes | 0 |  | 45.88 | 45.88 | 45.9 | -0.02 | 2024-09-30 | 2026-08-31 | 45.9 |  |  |  | 45.9
2408. Santaquin City WRF Phase 3 Upgrades | 550.7100. Solids Bldg - IMP Piping Install | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 645.22 | 645.22 | 645.2 | 0.02 | 2024-09-30 | 2026-08-31 | 300 | 345.2 |  |  | 645.2
2408. Santaquin City WRF Phase 3 Upgrades | 550.7300. Solids Bldg - PLUM Underground Pipe | PLUM Plumbing | 55 Mechanical | 0 |  | 60 | 60 | 60 | 0 | 2024-09-30 | 2026-08-31 | 30 | 30 |  |  | 60
2408. Santaquin City WRF Phase 3 Upgrades | 550.7400. Solids Bldg - HVAC Louvers | HVAC HVAC | 55 Mechanical | 0 |  | 90 | 90 | 90 | 0 | 2024-09-30 | 2026-08-31 | 90 |  |  |  | 90
2408. Santaquin City WRF Phase 3 Upgrades | 550.7500. Solids Bldg - PUMP Pump Install | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 60 | 60 | 60 | 0 | 2024-09-30 | 2026-08-31 | 60 |  |  |  | 60
2408. Santaquin City WRF Phase 3 Upgrades | 550.7600. Solids Bldg - MEQ Davit Crane | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 15 | 15 | 15 | 0 | 2024-09-30 | 2026-08-31 | 15 |  |  |  | 15
2408. Santaquin City WRF Phase 3 Upgrades | 550.7700. Solids Bldg - SEQ Blower Equipment Install | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 100 | 100 | 100 | 0 | 2024-09-30 | 2026-08-31 |  | 100 |  |  | 100
2408. Santaquin City WRF Phase 3 Upgrades | 600.1800. Stor Ponds - PH Potholing | PH Potholing | 10 Pipe | 0 |  | 60 | 0 | 60 | -60 | 2024-09-30 | 2026-08-31 | 60 |  |  |  | 60
2408. Santaquin City WRF Phase 3 Upgrades | 600.2071. Stor Ponds - RFG Rough Grade | RGF Rough Grade Fill | 11 Earth Work | 0 |  | 7.2 | 0 | 7.2 | -7.2 | 2024-09-30 | 2026-08-31 | 7.2 |  |  |  | 7.2
2408. Santaquin City WRF Phase 3 Upgrades | 600.2080. Stor Ponds - EXS Open Cut | EXS Excavate Structure | 11 Earth Work | 180.71 |  | 40 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 600.2085. Stor Ponds - BFST Backfill | BFST Backfill Structure | 11 Earth Work | 334.07 |  | 40 | 0 | 150 | -150 | 2024-09-30 | 2026-08-31 | 100 | 50 |  |  | 150
2408. Santaquin City WRF Phase 3 Upgrades | 600.2130. Stor Ponds - PVC Piping | PVC Pipe | 10 Pipe | 96.62 |  | 400.69 | 0 | 100 | -100 | 2024-09-30 | 2026-08-31 | 100 |  |  |  | 100
2408. Santaquin City WRF Phase 3 Upgrades | 600.2240. Stor Ponds - PCS Precast Boxes & Vaults Placement | PCS Precast Structures | 10 Pipe | 0 |  | 40 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 600.2610. Stor Ponds - PT Fill/Test/Flush PVC/DIP | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 150 | 0 | 20 | -20 | 2024-09-30 | 2026-08-31 | 20 |  |  |  | 20
2408. Santaquin City WRF Phase 3 Upgrades | 600.3000. Stor Ponds - CNC Concrete | CNC Concrete Work | 15 Concrete | 570.14 |  | 140 | 0 | 50 | -50 | 2024-09-30 | 2026-08-31 | 50 |  |  |  | 50
2408. Santaquin City WRF Phase 3 Upgrades | 600.5000. Stor Ponds - MET Grating Install | MET Metals | 20 Fabrication | 0 |  | 12 | 12 | 12 | 0 | 2024-09-30 | 2026-08-31 | 12 |  |  |  | 12
2408. Santaquin City WRF Phase 3 Upgrades | 600.7100. Stor Ponds - IMP Mech Piping | IMP Interior Mech/Piping | 55 Mechanical | 5.37 |  | 60 | 0 | 60 | -60 | 2024-09-30 | 2026-08-31 | 30 | 30 |  |  | 60
2408. Santaquin City WRF Phase 3 Upgrades | 600.7600. Stor Ponds - MEQ Slide Gate Install | MEQ Mechanical Equipment | 55 Mechanical | 108.81 |  | 30 | 0 | 20 | -20 | 2024-09-30 | 2026-08-31 |  | 20 |  |  | 20
2408. Santaquin City WRF Phase 3 Upgrades | 700.7100. PCO 1 - Santaquin ULS Connection | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-08-31
2408. Santaquin City WRF Phase 3 Upgrades | 800.1930. MC Misc Cleanup - End of Job | MC Misc Cleanup | 12 Finishes | 9.73 |  | 412.5 | 402.77 | 402.8 | -0.03 | 2024-09-30 | 2026-08-31 |  |  | 200 | 202.8 | 402.8
2408. Santaquin City WRF Phase 3 Upgrades | 800.1940. PL Punchlist - End of Job | PL Punch List Work | 12 Finishes | 14.67 |  | 840 | 825.33 | 825.3 | 0.03 | 2024-09-30 | 2026-08-31 |  |  | 400 | 425.3 | 825.3
2408. Santaquin City WRF Phase 3 Upgrades | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 10 | 10 | 0 | 2024-09-30 | 2026-08-31 | 10 |  |  |  | 10
2408. Santaquin City WRF Phase 3 Upgrades | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2024-09-30 | 2026-08-31 | 0.6 |  |  |  | 0.6
2408. Santaquin City WRF Phase 3 Upgrades | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0.6 | 0.6 | 0 | 2024-09-30 | 2026-08-31 | 0.6 |  |  |  | 0.6
2408. Santaquin City WRF Phase 3 Upgrades | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 3 | 3 | 0 | 2024-09-30 | 2026-08-31 | 3 |  |  |  | 3
2408. Santaquin City WRF Phase 3 Upgrades | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 1 | 1 | 0 | 2024-09-30 | 2026-08-31 | 1 |  |  |  | 1
2407. So SLC Lift Station | 100.1103. TF Temporary Conex/Dumpsters Internal Rate | TF Temporary Field Lab | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 100.1106. TF Setup Temp Trailer | TF Setup Temp Trailer | 12 Finishes | 0 |  | 15 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 100.1107. TF Trailer Pad Install | TF TF Trailer Pad Install | 12 Finishes | 0 |  | 30 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 100.1108. TF Setup Staging Area Laydown Yard | TF Setup Staging Area Laydown Yard | 12 Finishes | 8.9 |  | 18 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 100.1200. HOOK Hook Truck Dumpsters Transporting | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 48.07 |  | 35 | 38.5 | 40.5 | -2 | 2024-09-30 | 2026-03-31 | 20 | 20 | 0.5 |  | 40.5
2407. So SLC Lift Station | 100.1201. HOOK Hook Truck Conex Transporting | HOOK Hook Truck Conex, Skid Transporting | 40 Drivers | 0 |  | 5 | 5 | 5 | 0 | 2024-09-30 | 2026-03-31 | 3 | 2 |  |  | 5
2407. So SLC Lift Station | 100.1500. TR Training Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 310 | 50 | 50 | 0 | 2024-09-30 | 2026-03-31 | 20 | 20 | 10 |  | 50
2407. So SLC Lift Station | 100.1501. SM Safety Meetings | SM Safety Meetings | 61 HR/Safety | 6.25 |  | 10 | 60 | 60 | 0 | 2024-09-30 | 2026-03-31 | 20 | 40 |  |  | 60
2407. So SLC Lift Station | 100.1510. S Surveying | S Surveying | 45 Survey | 117.29 |  | 70 | 95 | 40 | 55 | 2024-09-30 | 2026-03-31 | 10 | 30 |  |  | 40
2407. So SLC Lift Station | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 1412 |  | 909 | 241 | 374 | -133 | 2024-09-30 | 2026-03-31 | 80 | 250 | 44 |  | 374
2407. So SLC Lift Station | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 620.11 |  | 825 | 422.56 | 555.4 | -132.84 | 2024-09-30 | 2026-03-31 | 80 | 400 | 75.4 |  | 555.4
2407. So SLC Lift Station | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 187.59 |  | 654 | 131.53 | 139.3 | -7.77 | 2024-09-30 | 2026-03-31 | 30 | 80 | 29.3 |  | 139.3
2407. So SLC Lift Station | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 1802.21 |  | 1326 | 448.71 | 621.6 | -172.89 | 2024-09-30 | 2026-03-31 | 300 | 300 | 21.6 |  | 621.6
2407. So SLC Lift Station | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 10 |  | 128 | 90 | 100 | -10 | 2024-09-30 | 2026-03-31 | 10 | 80 | 10 |  | 100
2407. So SLC Lift Station | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 2 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 2 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 100.9990. Overhead Safety & Small Tools | OH Tools/Safety Allocation | 00 _Unknown PR Dept | 24.69 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 150.1230. T Transporting | T Transporting | 40 Drivers | 205.38 |  | 460 | 95.25 | 100 | -4.75 | 2024-09-30 | 2026-03-31 | 15 | 60 | 25 |  | 100
2407. So SLC Lift Station | 150.2750. H Hauling | H Hauling | 40 Drivers | 122.54 |  | 161.32 | 47.94 | 92 | -44.06 | 2024-09-30 | 2026-03-31 | 15 | 70 | 7 |  | 92
2407. So SLC Lift Station | 150.2760. HO Haul Off | HO Haul Off | 40 Drivers | 150.83 |  | 201.37 | 130 | 80 | 50 | 2024-09-30 | 2026-03-31 | 20 | 50 | 10 |  | 80
2407. So SLC Lift Station | 160.5000. MET FAB Metals Material Field | MET Metals | 20 Fabrication | 120.11 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 180.1800. PH Potholing - Sub | PH Potholing | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 180.2081. SHOR Shoring Sub Malcom | SHOR Shoring | 10 Pipe | 0 |  | 6 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 200.2030. D Demo on Site | D Demolition | 11 Earth Work | 305.67 |  | 321.42 | 15 | 15 | 0 | 2024-09-30 | 2026-03-31 |  | 15 |  |  | 15
2407. So SLC Lift Station | 200.2060. FE Demo Fence Labor | FE Fencing | 11 Earth Work | 27.52 |  | 24 | 0 | 16 | -16 | 2024-09-30 | 2026-03-31 |  | 16 |  |  | 16
2407. So SLC Lift Station | 200.2065. SFC SWPPP Install & Maintenance | SFC SWPPP | 11 Earth Work | 10.58 |  | 156.6 | 20 | 20 | 0 | 2024-09-30 | 2026-03-31 | 5 | 15 |  |  | 20
2407. So SLC Lift Station | 200.2080. EX Excavation of Structures | EXS Excavate Structure | 11 Earth Work | 135.41 |  | 30 | 116.29 | 150 | -33.71 | 2024-09-30 | 2026-03-31 | 120 | 30 |  |  | 150
2407. So SLC Lift Station | 200.2081. Shoring Removal | SHOR Shoring | 10 Pipe | 160.59 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 200.2085. BFST Backfill of Structures | BFST Backfill Structure | 11 Earth Work | 327.9 |  | 6 | 75 | 75 | 0 | 2024-09-30 | 2026-03-31 | 70 | 5 |  |  | 75
2407. So SLC Lift Station | 200.2120. DIP Ductile Iron Piping Install Site Piping | DIP Ductile Iron Pipe | 10 Pipe | 12.85 |  | 219 | 206.15 | 219 | -12.85 | 2024-09-30 | 2026-03-31 | 200 | 19 |  |  | 219
2407. So SLC Lift Station | 200.2220. ADS Mainline Site Piping | ADS Pipe | 10 Pipe | 539.34 |  | 230.16 | 90 | 90 | 0 | 2024-09-30 | 2026-03-31 |  | 90 |  |  | 90
2407. So SLC Lift Station | 200.2240. PCS Precast Structure Install Site Piping | PCS Precast Structures | 10 Pipe | 160.52 |  | 129.76 | 90 | 90 | 0 | 2024-09-30 | 2026-03-31 | 50 | 40 |  |  | 90
2407. So SLC Lift Station | 200.2450. HDPE Pipe Install Site Piping | _Unknown Phase Master | 00 _Unknown PR Dept | 112.14 |  | 198.21 | 0 | 20 | -20 | 2024-09-30 | 2026-03-31 | 20 |  |  |  | 20
2407. So SLC Lift Station | 200.2510. CB Backfill PRV Vault | CB Catch Basins DO NOT USE) | 10 Pipe | 0 |  | 94 | 94 | 94 | 0 | 2024-09-30 | 2026-03-31 | 90 | 4 |  |  | 94
2407. So SLC Lift Station | 200.2600. DW Dewatering | DW Dewatering | 10 Pipe | 115.69 |  | 50 | 6 | 30 | -24 | 2024-09-30 | 2026-03-31 | 15 | 15 |  |  | 30
2407. So SLC Lift Station | 200.3000. CNC Concrete Site Piping | CNC Concrete Work | 15 Concrete | 15.54 |  | 212 | 34.08 | 34.1 | -0.02 | 2024-09-30 | 2026-03-31 | 34.1 |  |  |  | 34.1
2407. So SLC Lift Station | 200.5000. MET Pipe Supports Install Site Piping Vault | MET Metals | 20 Fabrication | 44.02 |  | 45 | 57.22 | 57.2 | 0.02 | 2024-09-30 | 2026-03-31 | 50 | 7.2 |  |  | 57.2
2407. So SLC Lift Station | 200.5400. HAT Hatch Vault Install Site Piping Vault | HAT Hatch/Skylights | 12 Finishes | 43.12 |  | 12 | 49.23 | 70 | -20.77 | 2024-09-30 | 2026-03-31 | 20 | 50 |  |  | 70
2407. So SLC Lift Station | 200.6500. Install Waterproofing | P Painting | 12 Finishes | 33.6 |  | 60 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 200.7100. IMP Sump Pump & Piping Install Site Piping Vaults | IMP Interior Mech/Piping | 55 Mechanical | 253.88 |  | 750 | 184.76 | 320 | -135.24 | 2024-09-30 | 2026-03-31 | 120 | 200 |  |  | 320
2407. So SLC Lift Station | 200.7900. ELC Electrical/Fiber/Dry Utilities Trenching | ELC Electrical | 10 Pipe | 200.02 |  | 100 | 100 | 20.3 | 79.7 | 2024-09-30 | 2026-03-31 | 20.3 |  |  |  | 20.3
2407. So SLC Lift Station | 300.2080. EXS Fabric/Liner Site Pipiing | EXS Excavate Structure | 11 Earth Work | 0 |  | 165.88 | 65 | 65 | 0 | 2024-09-30 | 2026-03-31 | 65 |  |  |  | 65
2407. So SLC Lift Station | 300.2120. DIP Ductile Iron Piping Installed | DIP Ductile Iron Pipe | 10 Pipe | 79.79 |  | 626 | 350 | 626 | -276 | 2024-09-30 | 2026-03-31 | 450 | 176 |  |  | 626
2407. So SLC Lift Station | 300.2130. PVC Pipe Installed | PVC Pipe | 10 Pipe | 60.94 |  | 130 | 70 | 70 | 0 | 2024-09-30 | 2026-03-31 | 50 | 20 |  |  | 70
2407. So SLC Lift Station | 300.2140. SVR Lateral Pipe Installed | SVR Services | 10 Pipe | 0 |  | 75 | 75 | 75 | 0 | 2024-09-30 | 2026-03-31 | 20 | 55 |  |  | 75
2407. So SLC Lift Station | 300.2605. BYP Bypass VanCon Vac Truck | BYP Bypass Pumping | 10 Pipe | 0 |  | 60 | 60 | 60 | 0 | 2024-09-30 | 2026-03-31 | 30 | 30 |  |  | 60
2407. So SLC Lift Station | 300.7100. IMP 14"-20" Fitting/Valve Install | IMP Interior Mech/Piping | 55 Mechanical | 9.67 |  | 300 | 290 | 290 | 0 | 2024-09-30 | 2026-03-31 | 250 | 40 |  |  | 290
2407. So SLC Lift Station | 400.3000. CNC Concrete Pump Station | CNC Concrete Work | 15 Concrete | 68.2 |  | 200 | 0 | 291.8 | -291.8 | 2024-09-30 | 2026-03-31 | 150 | 141.8 |  |  | 291.8
2407. So SLC Lift Station | 400.5000. MET Metals Install Pump Station | MET Metals | 20 Fabrication | 162.99 |  | 603.29 | 150 | 253.1 | -103.1 | 2024-09-30 | 2026-03-31 | 200 | 53.1 |  |  | 253.1
2407. So SLC Lift Station | 400.5400. HAT Hatch Install Pump Station | HAT Hatch/Skylights | 12 Finishes | 0 |  | 195 | 50 | 50 | 0 | 2024-09-30 | 2026-03-31 |  | 50 |  |  | 50
2407. So SLC Lift Station | 400.6070. IF Batton Boards Install Pump Station | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 15 | 15 | 15 | 0 | 2024-09-30 | 2026-03-31 |  | 15 |  |  | 15
2407. So SLC Lift Station | 400.6300. DAW Door Install Pump Station | DAW Doors & Windows | 12 Finishes | 22 |  | 60 | 38 | 38 | 0 | 2024-09-30 | 2026-03-31 | 38 |  |  |  | 38
2407. So SLC Lift Station | 400.6500. P Paint Floors Standard Pump Station | P Painting | 12 Finishes | 1 |  | 39.9 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 400.7100. IMP Interior Piping Install Pump Station | IMP Interior Mech/Piping | 55 Mechanical | 633.82 |  | 1592.5 | 256.72 | 265 | -8.28 | 2024-09-30 | 2026-03-31 | 200 | 65 |  |  | 265
2407. So SLC Lift Station | 400.7500. PUMP Pump Install Pump Station | PUMP Pumps/Motors | 55 Mechanical | 233.47 |  | 140 | 200 | 200 | 0 | 2024-09-30 | 2026-03-31 | 180 | 20 |  |  | 200
2407. So SLC Lift Station | 500.3000. CNC Concrete Screening Structure | CNC Concrete Work | 15 Concrete | 22.12 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 500.4000. MAS Masonry Support Screening Structure | MAS Masonry | 12 Finishes | 0 |  | 40 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 500.5000. MET Metals Install Screening Structure | MET Metals | 20 Fabrication | 178.53 |  | 159.79 | 54 | 54 | 0 | 2024-09-30 | 2026-03-31 | 25 | 29 |  |  | 54
2407. So SLC Lift Station | 500.6300. P Paint Install Screening Structure | DAW Doors & Windows | 12 Finishes | 0 |  | 6.58 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 500.7100. IMP Interior Piping Install Screening Structure | IMP Interior Mech/Piping | 55 Mechanical | 5.52 |  | 142.5 | 150 | 150 | 0 | 2024-09-30 | 2026-03-31 | 75 | 75 |  |  | 150
2407. So SLC Lift Station | 500.7600. MEQ Equipment Install Screening Structure | MEQ Mechanical Equipment | 55 Mechanical | 39.49 |  | 150 | 110.51 | 121.5 | -10.99 | 2024-09-30 | 2026-03-31 | 80 | 41.5 |  |  | 121.5
2407. So SLC Lift Station | 500.7700. SEQ Muffin Monster Install Screening Structure | SEQ Specialized Equipment | 55 Mechanical | 67.49 |  | 129 | 61.51 | 104 | -42.49 | 2024-09-30 | 2026-03-31 | 80 | 24 |  |  | 104
2407. So SLC Lift Station | 600.3000. CNC Concrete Genertor & Odor Control Install | CNC Concrete Work | 15 Concrete | 233.19 |  | 183 | 29.85 | 29.9 | -0.05 | 2024-09-30 | 2026-03-31 | 29.9 |  |  |  | 29.9
2407. So SLC Lift Station | 600.5500. STE Structural Steel Install - Catwalk | STE Structural Steel | 20 Fabrication | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 600.7700. SEQ Oder Control Install | SEQ Specialized Equipment | 55 Mechanical | 0 |  | 66 | 65 | 65 | 0 | 2024-09-30 | 2026-03-31 | 30 | 35 |  |  | 65
2407. So SLC Lift Station | 600.7900. ELC Generator Install | ELC Electrical | 10 Pipe | 0 |  | 30 | 30 | 30 | 0 | 2024-09-30 | 2026-03-31 | 30 |  |  |  | 30
2407. So SLC Lift Station | 700.2075. FG Finish Grade Site, Concrete, & Asphalt Prep | FG Finish Grade | 11 Earth Work | 32.96 |  | 105 | 147.04 | 180 | -32.96 | 2024-09-30 | 2026-03-31 | 180 |  |  |  | 180
2407. So SLC Lift Station | 700.3000. CNC Concerte Exterior Site end of Job | CNC Concrete Work | 15 Concrete | 0 |  | 99.38 | 200 | 100 | 100 | 2024-09-30 | 2026-03-31 | 100 |  |  |  | 100
2407. So SLC Lift Station | 800.1930. MC Misc Cleanup Pump Station | MC Misc Cleanup | 12 Finishes | 34.6 |  | 300 | 280.98 | 300 | -19.02 | 2024-09-30 | 2026-03-31 | 200 | 100 |  |  | 300
2407. So SLC Lift Station | 800.1940. PL Punch List Pump Station | PL Punch List Work | 12 Finishes | 4 |  | 225 | 221 | 221 | 0 | 2024-09-30 | 2026-03-31 | 80 | 120 | 21 |  | 221
2407. So SLC Lift Station | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.6 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 3 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 2 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2407. So SLC Lift Station | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2024-09-30 | 2026-03-31
2350. Fab Shop Jobs 2023 Projects | 200.5690. DO NOT USE | _Unknown Phase Master | 00 _Unknown PR Dept | 1.38 |  | 0 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5900. FAB 2321 | FAB Fab Shop | 20 Fabrication | 84.68 |  | 900 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5901. FAB 2321 Management/Estimating/Design/QC | FAB Fab Shop Management/Estimating/Design/QCFAB Fab Shop Man | 20 Fabrication | 973.66 |  | 900 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5935. FAB 2321 Deliveries L&E | FAB Fab Shop Deliveries | 20 Fabrication | 76.82 |  | 100 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5940. FAB 2321 WSP Fabrication L&E | FAB Fab Shop WSP Fabrication | 20 Fabrication | 1685.39 |  | 880.34 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5950 DO NOT USE | FAB Fab Shop WSP Paint | 20 Fabrication | 5 |  | 0 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5950. FAB 2321 WSP Paint L&E | FAB Fab Shop WSP Paint | 20 Fabrication | 2465.34 |  | 2190 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5960. FAB 2321 Misc. Metals Fabrication L&E | FAB Fab Shop Misc. Metals Fabrication | 20 Fabrication | 1394.58 |  | 1660.25 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5970. FAB 2321 Misc. Metals Paint L&E | FAB Fab Shop Misc. Metals Paint | 20 Fabrication | 83.71 |  | 798.25 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5980. FAB 2321 Northwest Pipe Repair | FAB Fab Shop Struc. Steel Fabrication | 20 Fabrication | 49.88 |  | 0 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5990. FAB 60" Ball Valve Revisions | FAB Fab Shop Struc. Steel Paint | 20 Fabrication | 227.08 |  | 0 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 200.5995. FAB 2321 Changes/VE | FAB Fab Shop Change Orders | 20 Fabrication | 939.61 |  | 0 | 0 | 0 | 0
2350. Fab Shop Jobs 2023 Projects | 220.2300. | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 14.67 |  | 0 | 0 | 0 | 0
2325. Santaquin Flowfill/CLSM Project | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 6 |  | 1 | -1 | 0 | -1 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 7.5 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 150.1230. T Transporting Plant | T Transporting | 40 Drivers | 40.08 |  | 120 | 44 | 50 | -6 | 2023-12-01 | 2026-05-01 | [6 empty] | 50 |  |  | 50
2325. Santaquin Flowfill/CLSM Project | 150.2750. H Hauling Sand & Gravel | H Hauling | 40 Drivers | 1689.48 |  | 2383.33 | 7 | 32 | -25 | 2023-12-01 | 2026-05-01 | 32 |  |  |  | 32
2325. Santaquin Flowfill/CLSM Project | 150.2760. HO Haul Off | HO Haul Off | 40 Drivers | 47.3 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 155.2750. H Hauling Cement Powder | H Hauling | 40 Drivers | 676.29 |  | 458.33 | 0.38 | 14.2 | -13.82 | 2023-12-01 | 2026-05-01 | 14.2 |  |  |  | 14.2
2325. Santaquin Flowfill/CLSM Project | 200.2130. PVC Water & Power Install On Site | PVC Pipe | 10 Pipe | 178.86 |  | 100 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 200.2700. | SG Sand & Gravel | 11 Earth Work | 21.05 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 200.2715. FWF1 Setup Batch Plant | FWF1 Flowfill/CLSM Inhouse | 11 Earth Work | 378.89 |  | 160 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 200.5950. | FAB Fab Shop WSP Paint | 20 Fabrication | 9.33 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 250.2715. FWF1 Batch CLSM/Concrete | FWF1 Flowfill/CLSM Inhouse | 11 Earth Work | 3664.08 |  | 2733.42 | 121.16 | 126.2 | -5.04 | 2023-12-01 | 2026-05-01 | 126.2 |  |  |  | 126.2
2325. Santaquin Flowfill/CLSM Project | 260.2715. FWF1 Deliver CLSM/Concrete | FWF1 Flowfill/CLSM Inhouse | 11 Earth Work | 8458.47 |  | 5466.83 | 73.55 | 77.9 | -4.35 | 2023-12-01 | 2026-05-01 | 77.9 |  |  |  | 77.9
2325. Santaquin Flowfill/CLSM Project | 270.2715. FWF1 Maintain Batch Plant | FWF1 Flowfill/CLSM Inhouse | 11 Earth Work | 8.78 |  | 100 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2325. Santaquin Flowfill/CLSM Project | 500.2715. FWF1 Tear Down Batch Plant | FWF1 Flowfill/CLSM Inhouse | 11 Earth Work | 0 |  | 80 | 80 | 80 | 0 | 2023-12-01 | 2026-05-01 | [6 empty] | 80 |  |  | 80
2325. Santaquin Flowfill/CLSM Project | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 100.1100. TF Temporary Office VanCon & Setup Yard | TF Temporary Office Trailer, Conex, Dumpsters, Skids | 00 _Unknown PR Dept | 170.77 |  | 0 | 30 | 5 | 25 | 2023-12-01 | 2026-05-01 | 5 |  |  |  | 5
2321. CUWCD Santaquin Reach | 100.1200. HOOK Hook Truck Dumpsters/Conex | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 266.05 |  | 60 | 30 | 40 | -10 | 2023-12-01 | 2026-05-01 | 30 | 10 |  |  | 40
2321. CUWCD Santaquin Reach | 100.1500. TR Training Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 144.8 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 100.1501. SM Safety Meetings | SM Safety Meetings | 61 HR/Safety | 267.53 |  | 0 | 50 | 40 | 10 | 2023-12-01 | 2026-05-01 | 20 | 20 |  |  | 40
2321. CUWCD Santaquin Reach | 100.1510. S Surveying Santaquin Reach Only (Other Vaults Serperate) | S Surveying | 45 Survey | 4978.3 |  | 2301 | 150 | 200 | -50 | 2023-12-01 | 2026-05-01 | 100 | 100 |  |  | 200
2321. CUWCD Santaquin Reach | 100.1515. S Drone/Lidar Requirements for Job | S Drone/Lidar Requirements | 45 Survey | 216.32 |  | 11 | 15 | 15 | 0 | 2023-12-01 | 2026-05-01 |  | 15 |  |  | 15
2321. CUWCD Santaquin Reach | 100.1650. SB Install Job Site Signs | SB Signage | 12 Finishes | 19.5 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 3792.83 |  | 4180.8 | 350 | 350 | 0 | 2023-12-01 | 2026-05-01 | 150 | 200 |  |  | 350
2321. CUWCD Santaquin Reach | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 6764.18 |  | 3884.88 | 525 | 600 | -75 | 2023-12-01 | 2026-05-01 | 250 | 250 | 100 |  | 600
2321. CUWCD Santaquin Reach | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 7467.77 |  | 2901.22 | 350 | 400 | -50 | 2023-12-01 | 2026-05-01 | 200 | 150 | 50 |  | 400
2321. CUWCD Santaquin Reach | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 7734.87 |  | 6138.16 | 400 | 400 | 0 | 2023-12-01 | 2026-05-01 | 250 | 150 |  |  | 400
2321. CUWCD Santaquin Reach | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 2230.15 |  | 681.21 | 150 | 150 | 0 | 2023-12-01 | 2026-05-01 | 50 | 100 |  |  | 150
2321. CUWCD Santaquin Reach | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 16.88 |  | 10 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 10 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 150.1230. T Transporting Santaquin Pipeline & Santaquin Vaults | T Transporting | 40 Drivers | 2541.79 |  | 867 | 100 | 175 | -75 | 2023-12-01 | 2026-05-01 | 75 | 100 |  |  | 175
2321. CUWCD Santaquin Reach | 150.2070. SFC SWPPP Sweeper Truck & Water Truck | RGC Rough Grade Cut | 11 Earth Work | 61.99 |  | 1099 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 150.2300. WPL Potholing Job | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 363.53 |  | 1076 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 150.2750. | H Hauling | 40 Drivers | 4.22 |  | 2 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 150.2760. HO Haul Off | HO Haul Off | 40 Drivers | 10.75 |  | 10 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 160.2090. MTL Pipe Materials Waterworks Ferguson/Mtnland | MTL Materials | 00 _Unknown PR Dept | 0 |  | 56 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 160.5000. MET Metals Material Field Entire Project | MET Metals | 20 Fabrication | 38.83 |  | 197 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 160.6500. P Paint Materials for Entire Project | P Painting | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 161.2090. MTL Pipe Materials Precast & FO Box Old Castle | MTL Materials | 00 _Unknown PR Dept | 0 |  | 13.6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 161.3000. CNC Concrete Formwork Materials | CNC Concrete Work | 15 Concrete | 8.55 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 175.2300. FAB Summit Creek Irrigation | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 123.33 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 180.2040. LR Seeding Sub - Rocky Mountain | LR Landscaping/Restoration | 11 Earth Work | 10.83 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 180.2060. FE Fencing Permanent All Sites UT Fence | FE Fencing | 11 Earth Work | 6 |  | 8.53 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 180.3100. CNC Rebar Supply & Install Fabco | CNC Rebar | 15 Concrete | 0 |  | 36 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 181.3100. CNC Rebar In-House | CNC Rebar | 15 Concrete | 264.02 |  | 0 | 0 | 50 | -50 | 2023-12-01 | 2026-05-01 | 25 | 25 |  |  | 50
2321. CUWCD Santaquin Reach | 200.1650. SB Demo/Removals Signage on Pipeline Alignment | SB Signage | 12 Finishes | 0 |  | 12 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2020. CG Clear & Strip Topsoil Pipeline Alignment | CG Clearing/Grubbing | 11 Earth Work | 1003.32 |  | 1704.6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2030. D Demo/Removals on Pipeline Alignment | D Demolition | 11 Earth Work | 305.51 |  | 1583.47 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2060. FE Remove Wire Fencing on Pipeline Alignment | FE Fencing | 11 Earth Work | 137.11 |  | 652.6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2070. SFC SWPPP & Water Truck/Sweeping | RGC Rough Grade Cut | 11 Earth Work | 3994.2 |  | 1067.7 | 24 | 24 | 0 | 2023-12-01 | 2026-05-01 | 24 |  |  |  | 24
2321. CUWCD Santaquin Reach | 200.2100. SPL Steel Casing Extensions | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 0 |  | 30 | 20 | 20 | 0 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 200.2400. DW Dewatering Santaquin South | IPL Irrigation Pipe Laying (DO NOT USE) | 10 Pipe | 180.91 |  | 342 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2760. HO Haul Off Demo/Removals | HO Haul Off | 40 Drivers | 137.24 |  | 2855.51 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2800. BFST Fine Grade Alignment before Seeding | BFST Backfill (DO NOT USE) | 11 Earth Work | 237.33 |  | 38.49 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.2910. MP Milling Road Crossings Pipeline Alignment | MP Milling/Pulverize | 11 Earth Work | 34.48 |  | 235.79 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.5100. WE Welding Santaquin Casings | W Welding | 20 Fabrication | 4 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 200.7900. ELC Remove & Replace Light Pole on Pipeline Alignment | ELC Electrical | 10 Pipe | 61.7 |  | 90 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2100. SPL Utility Relocations Sewer Lines | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 1061.65 |  | 832.52 | 80 | 80 | 0 | 2023-12-01 | 2026-05-01 |  | 80 |  |  | 80
2321. CUWCD Santaquin Reach | 205.2110. SS Utility Relocations Sewer Services | SS Sewer Services (DO NOT USE) | 10 Pipe | 249.08 |  | 580.67 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2200. DPL Utiltiy Relocations Drainage | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 61.63 |  | 501.34 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2300. WPL Utility Relocations Water Lines | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 824.01 |  | 416.3 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2310. WS Utility Relocations Water Services | WS Water Services (DO NOT USE) | 10 Pipe | 251.14 |  | 267 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2400. IPL Utility Relocations Irrigation Lines | IPL Irrigation Pipe Laying (DO NOT USE) | 10 Pipe | 962.88 |  | 906.06 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2410. IS Utility Relocations Irrigaiton Services | IS Irrigation Services (DO NOT USE) | 10 Pipe | 117.52 |  | 658.84 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2605. BYP Bypass Pumping for Utility Relocations | BYP Bypass Pumping | 10 Pipe | 20.15 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2750. H Hauling Utility Relocations | H Hauling | 40 Drivers | 288.54 |  | 1197.64 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.2760. HO Haul Off Utility Relocations | HO Haul Off | 40 Drivers | 40.27 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.3000. CNC Concrete Resotration Utility Relocations | CNC Concrete Work | 15 Concrete | 492.05 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.5100. 32 | W Welding | 20 Fabrication | 7.27 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.7800. WPL Cathodic Install Utility Relocations | PRK Park Equipment | 12 Finishes | 344.01 |  | 36.66 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 205.7900. ELC Remove & Replace Light Pole Utility Relocations | ELC Electrical | 10 Pipe | 0 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 210.2300. WPL 60 Inch WSP East of I-15 Installation | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 6976.85 |  | 1514.64 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 210.2710. FWF Flowable Fill Utility Support East of I-15 Installation | FWF Flowable Fill | 15 Concrete | 0 |  | 230.16 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 210.2750. H Hauling East of I-15 Installation | H Hauling | 40 Drivers | 156.16 |  | 271.82 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 210.2760. HO Haul Off East of I-15 Installation | HO Haul Off | 40 Drivers | 411.1 |  | 777 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.1510. S Surveying Monitoring Points for I-15 Bore | S Surveying | 45 Survey | 0 |  | 24 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.2080. EXS Excavation I-15 Bore & Exit Pits Installation | EXS Excavate Structure | 11 Earth Work | 365.63 |  | 360 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.2300. WPL 60 Inch WSP in Casing on I-15 Bore | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 433.22 |  | 270 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.2750. H Hauling 60 Inch WSP in Casing on I-15 Bore | H Hauling | 40 Drivers | 0 |  | 6.82 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.2760. HO Haul Off 60 Inch WSP in Casing on I-15 Bore | HO Haul Off | 40 Drivers | 0 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.2800. BFST Backfill Bore Pits & Remove Slide Rail 60 Inch WSP in C | BFST Backfill (DO NOT USE) | 11 Earth Work | 98.3 |  | 360 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 215.7900. ELC Power Relocation on Cul-de-Sac Homes | ELC Electrical | 10 Pipe | 63.15 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 220.2300. WPL 60 Inch WSP I-15 to Santaquin North Vault Installation | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 12929.58 |  | 4532.89 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 220.2710. FWF Flowable Fill Utility Support I-15 to Santaquin North V | FWF Flowable Fill | 15 Concrete | 7.62 |  | 408.88 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 220.2750. H Hauling I-15 to Santaquin North Vault Installation | H Hauling | 40 Drivers | 155.51 |  | 804.73 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 220.2760. HO Haul Off I-15 to Santaquin North Vault Installation | HO Haul Off | 40 Drivers | 531.4 |  | 1645 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 225.2300. WPL 60 Inch WSP Start in Cul-de-Sac to Santaquin North Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 18808.9 |  | 6207.75 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 225.2710. FWF Flowable Fill Utility Support Santaquin North Vault to E | FWF Flowable Fill | 15 Concrete | 52.03 |  | 419.04 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 225.2750. H Hauling Start in Cul-de-Sac to Santaquin North Vault | H Hauling | 40 Drivers | 1033.17 |  | 1431.99 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 225.2760. HO Haul OffStart in Cul-de-Sac to Santaquin North Vault | HO Haul Off | 40 Drivers | 2058.74 |  | 2149 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 230.2300. WPL 60 Inch WSP Cul-de-Sac to Hwy 6 Bore Installation | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 8535.86 |  | 2445.34 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 230.2700. SG Sand & Gravel | SG Sand & Gravel | 11 Earth Work | 11.37 |  | -10 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 230.2710. FWF Flowable Fill Utility Support 60 Inch WSP Cul-de-Sac to | FWF Flowable Fill | 15 Concrete | 11.35 |  | 295.88 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 230.2750. H Hauling 60 Inch WSP Cul-de-Sac to Hwy 6 Bore Installation | H Hauling | 40 Drivers | 182.19 |  | 1185.24 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 230.2760. HO Haul 60 Inch WSP Cul-de-Sac to Hwy 6 Bore Installation | HO Haul Off | 40 Drivers | 1307.21 |  | 1657 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 235.1510. S Surveying Surface Monitoring Points for Hwy 6 Bore | S Surveying | 45 Survey | 0 |  | 8 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 235.2080. EXS Excavation Hwy 6 Bore & Exit Pits Installation | EXS Excavate Structure | 11 Earth Work | 374.39 |  | 360 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 235.2300. WPL 60 Inch WSP in Casing on Hwy 6 Bore | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 250.67 |  | 205.38 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 235.2750. H Hauling 60 Inch WSP in Casing on Hwy 6 Bore | H Hauling | 40 Drivers | 0 |  | 6.82 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 235.2760. HO Haul Off 60 Inch WSP in Casing on Hwy 6 Bore | HO Haul Off | 40 Drivers | 0 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 235.2800. BFST Backfill Bore Pits & Remove Slide Rail 60 Inch WSP in C | BFST Backfill (DO NOT USE) | 11 Earth Work | 75.86 |  | 402 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 240.2300. WPL 60 Inch WSP Hwy 6 Bore to Railroad Bore Install | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 6937.48 |  | 1784 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 240.2710. FWF Flowable Fill Utility Support 60 Inch WSP Hwy 6 Bore to | FWF Flowable Fill | 15 Concrete | 0 |  | 277.8 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 240.2750. H Hauling 60 Inch WSP Hwy 6 Bore to Railroad Bore Install | H Hauling | 40 Drivers | 26.07 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 240.2760. HO Haul Off 60 Inch WSP Hwy 6 Bore to Railroad Bore Install | HO Haul Off | 40 Drivers | 481.14 |  | 625.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.1510. S Surveying Monitoring Points for Railroad Bore | S Surveying | 45 Survey | 36.08 |  | 88 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.2080. EXS Excavation Railroad Bore & Exit Pits Installation | EXS Excavate Structure | 11 Earth Work | 422.53 |  | 485 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.2300. WPL 60 Inch WSP in Casing on Railroad Bore | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 0 |  | 117.69 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.2400. IPL Railroad Bore Extras | IPL Irrigation Pipe Laying (DO NOT USE) | 10 Pipe | 35.54 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.2750. H Hauling 60 Inch WSP in Casing on Railroad Bore | H Hauling | 40 Drivers | 0 |  | 6.82 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.2760. HO Haul Off 60 Inch WSP in Casing on Railroad Bore | HO Haul Off | 40 Drivers | 0 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 245.2800. BFST Backfill Bore Pits & Remove Slide Rail 60 Inch WSP in C | BFST Backfill (DO NOT USE) | 11 Earth Work | 100.75 |  | 360 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 250.2300. WPL 60 Inch WSP Railroad Bore to Santaquin South Vault Insta | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 2275.03 |  | 855.14 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 250.2710. FWF Flowable Fill Utility 60 Inch WSP Railroad Bore | FWF Flowable Fill | 15 Concrete | 0 |  | 87.44 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 250.2760. HO Haul Off 60 Inch WSP Railroad Bore to Santaquin | HO Haul Off | 40 Drivers | 0 |  | 102.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 255.2020. CG Clear & Grub Santaquin South Pond Sitework | CG Clearing/Grubbing | 11 Earth Work | 62.16 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 255.2080. EXS Excavate Santaquin South Pond Sitework | EXS Excavate Structure | 11 Earth Work | 963.28 |  | 457.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 255.2750. H Hauling Santaquin South Pond Sitework | H Hauling | 40 Drivers | 122.12 |  | 228.87 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 255.2800. BFST Shaping/Riprap Santaquin South Pond Sitework | BFST Backfill (DO NOT USE) | 11 Earth Work | 291.91 |  | 263.67 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 255.3000. CNC Concrete Install Santaquin South Pond Sitework | CNC Concrete Work | 15 Concrete | 5 |  | 84 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2020. CG Clear & Grub Santaquin South Access Road | CG Clearing/Grubbing | 11 Earth Work | 57.92 |  | 17.72 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2030. D Demo Santaquin South Access Road | D Demolition | 11 Earth Work | 0 |  | 87.4 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2050. BFST Santaquin South Access Road | RW Retaining Walls | 11 Earth Work | 88.86 |  | 63.92 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2080. EXS Excavate Roadway Santaquin South Access Road | EXS Excavate Structure | 11 Earth Work | 1330.33 |  | 231.67 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2200. DPL Bridge Install Santaquin South Access Road | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 96 |  | 174.8 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2400. IPL Relocate Pipe Santaquin South Access Road | IPL Irrigation Pipe Laying (DO NOT USE) | 10 Pipe | 97.08 |  | 172 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2750. H Hauling Santaquin South Access Road | H Hauling | 40 Drivers | 93.41 |  | 458.86 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2760. HO Haul Off Santaquin South Access Road | HO Haul Off | 40 Drivers | 0 |  | 32.15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2800. BFST Backfill Footings / Wingwalls Santaquin South Access Ro | BFST Backfill (DO NOT USE) | 11 Earth Work | 256.17 |  | 633.46 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.2940. CP Concrete Exterior Prep Santaquin South Access Road | CP Concrete Prep (DO NOT USE) | 11 Earth Work | 0 |  | 5.6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.3000. CNC Concrete Install Santaquin South Access Road | CNC Concrete Work | 15 Concrete | 11.33 |  | 378 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 260.5000. MET Handrail Install Santaquin South Access Road | MET Metals | 20 Fabrication | 0 |  | 20 | 20 | 20 | 0 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 260.7900. ELC Elec Trenching Santaquin South Access Road | ELC Electrical | 10 Pipe | 199.25 |  | 253.33 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 270.2300. W Welding 48 Inch WSP Install Santaquin South Site | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 348.27 |  | 345.26 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 270.2710. FWF Flowable Fill Utility 48 Inch WSP Install Santaqu | FWF Flowable Fill | 15 Concrete | 0 |  | 33.92 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 270.2750. H Hauling 48 Inch WSP Install Santaquin South Site | H Hauling | 40 Drivers | 9.55 |  | 32.96 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 270.2760. HO Haul Off 48 Inch WSP Install Santaquin South Site | HO Haul Off | 40 Drivers | 67.13 |  | 65 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 275.2200. DPL 8 Inch WSP Drainline Install Santaquin South Site | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 85.56 |  | 83 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 275.2300. WPL 42 Inch WSP Install Santaquin South Site | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1269.56 |  | 724.9 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 275.2710. FWF Flowable Fill Utility42 Inch WSP Install Santaqu | FWF Flowable Fill | 15 Concrete | 3 |  | 68.92 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 275.2750. H Hauling 42 Inch WSP Install Santaquin South Site | H Hauling | 40 Drivers | 122.18 |  | 95.4 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 275.2760. HO Haul Off 42 Inch WSP Install Santaquin South Site | HO Haul Off | 40 Drivers | 21.87 |  | 152.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 275.3000. CNC Pipe Encasement 42 Inch WSP Install Santaquin South Site | CNC Concrete Work | 15 Concrete | 134.58 |  | 350 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 280.2300. WPL 20 Inch WSP Install Santaquin South Site | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 34.23 |  | 40 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 280.2710. FWF Flowable Fill Utility 20 Inch WSP Install Santaqu | FWF Flowable Fill | 15 Concrete | 0 |  | 0.96 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 280.2750. H Hauling 20 Inch WSP Install Santaquin South Site | H Hauling | 40 Drivers | 0 |  | 2.27 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 280.2760. HO Haul Off 20 Inch WSP Install Santaquin South Site | HO Haul Off | 40 Drivers | 0 |  | 3 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 285.2300. WPL 24 Inch WSP Install Santaquin South Site | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 522.87 |  | 387.38 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 285.2710. FWF Flowable Fill Utility 24 Inch WSP Install Santaqu | FWF Flowable Fill | 15 Concrete | 0 |  | 26.6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 285.2750. H Hauling 24 Inch WSP Install Santaquin South Site | H Hauling | 40 Drivers | 18.21 |  | 92.18 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 285.2760. HO Haul Off 24 Inch WSP Install Santaquin South Site | HO Haul Off | 40 Drivers | 41.77 |  | 98.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 290.7800. CATH Test Stations, Anodes Install Entire Santaquin Pipeline | PRK Park Equipment | 12 Finishes | 1462.33 |  | 1202.4 | 30 | 30 | 0 | 2023-12-01 | 2026-05-01 | 30 |  |  |  | 30
2321. CUWCD Santaquin Reach | 295.2750. H Hauling Fiber Optic System | H Hauling | 40 Drivers | 0 |  | 3.41 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 295.7900. ELC Fiber Conduit, Setting Boxes, Mule Tape Install Santaqui | ELC Electrical | 10 Pipe | 699.42 |  | 1931.34 | 0 | 20 | -20 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 300.2080. EXS Excavation Pond Inlet Strucuture Santaquin South | EXS Excavate Structure | 11 Earth Work | 0 |  | 85 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 300.2750. H Hauling Pond Inlet Strucuture Santaquin South | H Hauling | 40 Drivers | 20.45 |  | 3.41 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 300.2800. BFST Backfill Pond Inlet Strucuture Santaquin South | BFST Backfill (DO NOT USE) | 11 Earth Work | 32.39 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 300.3000. CNC Concrete Install Pond Inlet Strucuture Santaquin South | CNC Concrete Work | 15 Concrete | 28.32 |  | 840 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 20 | 100 |  |  | 120
2321. CUWCD Santaquin Reach | 300.5000. MET Metals Install Pond Inlet Strucuture Santaquin South | MET Metals | 20 Fabrication | 38.86 |  | 114 | 47 | 50 | -3 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 300.5400. HAT Hatch Install Pond Inlet Strucuture Santaquin South | HAT Hatch/Skylights | 12 Finishes | 0 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 300.6200. IN Insulation Install Pond Inlet Strucuture Santaquin South | IN Insulation | 12 Finishes | 0 |  | 30 | 30 | 30 | 0 | 2023-12-01 | 2026-05-01 | 30 |  |  |  | 30
2321. CUWCD Santaquin Reach | 300.6500. P Paint Piping Pond Inlet Strucuture Santaquin South | P Painting | 12 Finishes | 5 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 300.7100. IMP Pipe Fitting Pond Inlet Strucuture Santaquin South | IMP Interior Mech/Piping | 55 Mechanical | 128.57 |  | 150 | 45 | 50 | -5 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 300.7500. PUMP Sump Pump Install Pond Inlet Strucuture Santaquin Sout | PUMP Pumps/Motors | 55 Mechanical | 15.59 |  | 45 | 0 | 30 | -30 | 2023-12-01 | 2026-05-01 | 30 |  |  |  | 30
2321. CUWCD Santaquin Reach | 305.2080. EXS Excavation Pond Outlet Structure Santaquin South | EXS Excavate Structure | 11 Earth Work | 0 |  | 36 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 305.2750. H Hauling Pond Outlet Structure Santaquin South | H Hauling | 40 Drivers | 0 |  | 0.68 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 305.2800. BFST Backfill StructurePond Outlet Structure Santaquin South | BFST Backfill (DO NOT USE) | 11 Earth Work | 37.8 |  | 15.99 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 305.3000. CNC Concrete Install Pond Outlet Structure Santaquin South | CNC Concrete Work | 15 Concrete | 0 |  | 135.45 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 305.5000. MET Metals Install Pond Outlet Structure Santaquin South | MET Metals | 20 Fabrication | 15.5 |  | 28 | 10 | 10 | 0 | 2023-12-01 | 2026-05-01 | 10 |  |  |  | 10
2321. CUWCD Santaquin Reach | 310.2080. EXS Excavation Pond Dishcharge Structure Santaquin South | EXS Excavate Structure | 11 Earth Work | 10.02 |  | 45 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 310.2750. H Hauling Pond Dishcharge Structure Santaquin South | H Hauling | 40 Drivers | 53.27 |  | 1.14 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 310.2800. BFST Backfill Structure Pond Dishcharge Structure Santaquin | BFST Backfill (DO NOT USE) | 11 Earth Work | 60.78 |  | 15.99 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 310.3000. CNC Concrete Install Pond Dishcharge Structure Santaquin So | CNC Concrete Work | 15 Concrete | 0 |  | 375.16 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 310.7100. IMP Pipe Fitting Pond Dishcharge Structure Santaquin Sout | IMP Interior Mech/Piping | 55 Mechanical | 9.82 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.2080. EXS Excavate Structure Pigging Vault | EXS Excavate Structure | 11 Earth Work | 64.54 |  | 26 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.2300. WPL WSP Pipe Install Pigging Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 72.65 |  | 62 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.2750. H Hauling Pigging Vault | H Hauling | 40 Drivers | 38.92 |  | 0.09 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.2800. BFST Backfill Structure Install Pigging Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 128.45 |  | 45 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.3000. CNC Concrete Install Pigging Vault | CNC Concrete Work | 15 Concrete | 421.34 |  | 180 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.6500. P Paint Piping Pigging Vault | P Painting | 12 Finishes | 20.03 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 315.7100. IMP Pipe Fitting Pigging Vault | IMP Interior Mech/Piping | 55 Mechanical | 377.38 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.2080. EXS Excavation Access Manways Santaquin Pipeline | EXS Excavate Structure | 11 Earth Work | 0 |  | 108 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.2300. WPL Manway Prep & Backfill Access Manways Santaquin Pipeline | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 38 |  | 210 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.2750. H Hauling Access Manways Santaquin Pipeline | H Hauling | 40 Drivers | 21.1 |  | 0.68 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.2760. HO Haul Off Access Manways Santaquin Pipeline | HO Haul Off | 40 Drivers | 0 |  | 1.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.2800. BFST Backfill Access Manways Santaquin Pipeline | BFST Backfill (DO NOT USE) | 11 Earth Work | 233.23 |  | 180 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.3000. CNC Concrete Install Access Manways Santaquin Pipeline | CNC Concrete Work | 15 Concrete | 1183.16 |  | 1830 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.5000. MET Metals Install Access Manways Santaquin Pipeline | MET Metals | 20 Fabrication | 125.13 |  | 171 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.6200. IN Insulation Install Access Manways Santaquin Pipeline | IN Insulation | 12 Finishes | 73.89 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.6500. P Paint Piping Access Manways Santaquin Pipeline | P Painting | 12 Finishes | 4 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 320.7100. IMP Pipe Fitting Access Manways Santaquin Pipeline | IMP Interior Mech/Piping | 55 Mechanical | 140.48 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.1650. SB Resotration/Finishes Signage | SB Signage | 12 Finishes | 0 |  | 18 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.2040. LR Load Topsoil on Haul Trucks Resotration/Finishes | LR Landscaping/Restoration | 11 Earth Work | 48.69 |  | 2865.59 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.2080. EXS Place Topsoil Resotration/Finishes | EXS Excavate Structure | 11 Earth Work | 1146.96 |  | 404.49 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.2760. HO Haul Onsite Resotration/Finishes | HO Haul Off | 40 Drivers | 49.11 |  | 777.33 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.2800. BFST Building Roadway Resotration/Finishes | BFST Backfill (DO NOT USE) | 11 Earth Work | 99.53 |  | 1653.73 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.2930. AP Asphalt Prep Resotration/Finishes | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 1986.39 |  | 274.73 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 |  | 120 |  |  | 120
2321. CUWCD Santaquin Reach | 325.2940. CP Concrete Exterior Prep Resotration/Finishes | CP Concrete Prep (DO NOT USE) | 11 Earth Work | 344.02 |  | 790.02 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.5500. STE Re-assemble Kennels & Farmstead Items Resotration/Finish | STE Structural Steel | 20 Fabrication | 0 |  | 250 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 325.6100. F Build new shed & Pens Resotration/Finishes | F Framing | 12 Finishes | 0 |  | 250 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 330.1600. TC Traffic Control Santaquin Pipeline | TC Traffic Control | 30 Traffic Control | 3277.3 |  | 800 | 30 | 50 | -20 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 330.1610. TC Jersey & Water Barrier Santaquin Pipeline | TC Concrete & Water Barrier | 30 Traffic Control | 0 |  | 192 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 335.2600. DW Dewatering Install, Maintain | DW Dewatering | 10 Pipe | 0 |  | 210 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 340.2300. WPL Fill Sand Bags Santaquin Pipeline | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 516.5 |  | 540.98 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 345.2300. WPL Loading & Unloading Pipe Santaquin Pipeline | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1778.9 |  | 1050 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.1200. HOOK Hook Truck Dumpsters/Conex | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 18 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.1230. T Transporting Santaquin South Vault | T Transporting | 40 Drivers | 82.46 |  | 100 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.1510. S Surveying Santaquin South Vault | S Surveying | 45 Survey | 22.46 |  | 110 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.1710. FS Startup/Commissioning Santaquin South Vault | FS Starup/Commissioning | 55 Mechanical | 5.07 |  | 60 | 100 | 100 | 0 | 2023-12-01 | 2026-05-01 | 70 | 30 |  |  | 100
2321. CUWCD Santaquin Reach | 350.1930. MC Misc. Cleanup Santaquin South Vault | MC Misc Cleanup | 12 Finishes | 207.36 |  | 120 | 73.29 | 100 | -26.71 | 2023-12-01 | 2026-05-01 |  | 100 |  |  | 100
2321. CUWCD Santaquin Reach | 350.1940. PL Punch List Work Santaquin South Vault | PL Punch List Work | 12 Finishes | 5.08 |  | 200 | 150 | 150 | 0 | 2023-12-01 | 2026-05-01 | 150 |  |  |  | 150
2321. CUWCD Santaquin Reach | 350.2070. SFC SWPPP Sanatquin South Vault | RGC Rough Grade Cut | 11 Earth Work | 13.32 |  | 12 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2080. EXS Excavate Structure Sanatquin South Vault | EXS Excavate Structure | 11 Earth Work | 366.29 |  | 340 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2200. DPL Site Drainage Around Structure | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 27.75 |  | 380 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2300. WPL Exterior WSP Install Sanatquin South Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 356.64 |  | 546.19 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2710. FWF Flowfill Placement Sanatquin South Vault | FWF Flowable Fill | 15 Concrete | 13.27 |  | 64 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2750. H Hauling Sanatquin South Vault | H Hauling | 40 Drivers | 263.78 |  | 99.84 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2760. HO Haul Off Sanatquin South Vault | HO Haul Off | 40 Drivers | 18.24 |  | 67.33 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.2800. BSFT Backfill Structure Sanatquin South Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 407.9 |  | 388.41 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.3000. CNC Concrete Install Sanatquin South Vault | CNC Concrete Work | 15 Concrete | 12643.11 |  | 8105.6 | 750 | 1000 | -250 | 2023-12-01 | 2026-05-01 | 1000 |  |  |  | 1000
2321. CUWCD Santaquin Reach | 350.5000. MET Metals Install Sanatquin South Vault | MET Metals | 20 Fabrication | 87.91 |  | 557.5 | 500 | 500 | 0 | 2023-12-01 | 2026-05-01 | 200 | 300 |  |  | 500
2321. CUWCD Santaquin Reach | 350.5100. W Welding WSP Sanatquin South Vault | W Welding | 20 Fabrication | 54.99 |  | 50 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 |  | 50 |  |  | 50
2321. CUWCD Santaquin Reach | 350.5400. HAT Hatch Vault Install Sanatquin South Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 45 | 0 | 40 | -40 | 2023-12-01 | 2026-05-01 |  | 40 |  |  | 40
2321. CUWCD Santaquin Reach | 350.6000. IF Sealants Install Sanatquin South Vault | IF Interior Finishes | 20 Fabrication | 0 |  | 30 | 30 | 30 | 0 | 2023-12-01 | 2026-05-01 |  | 30 |  |  | 30
2321. CUWCD Santaquin Reach | 350.6100. F Framing Around Hatch Install Sanatquin South Vault | F Framing | 12 Finishes | 0 |  | 75 | 75 | 75 | 0 | 2023-12-01 | 2026-05-01 |  | 75 |  |  | 75
2321. CUWCD Santaquin Reach | 350.6200. IN Insulation Install Sanatquin South Vault | IN Insulation | 12 Finishes | 12.5 |  | 150 | 150 | 150 | 0 | 2023-12-01 | 2026-05-01 |  | 150 |  |  | 150
2321. CUWCD Santaquin Reach | 350.6300. DAW Door Install Sanatquin South Vault | DAW Doors & Windows | 12 Finishes | 64.97 |  | 90 | 50 | 35 | 15 | 2023-12-01 | 2026-05-01 | 35 |  |  |  | 35
2321. CUWCD Santaquin Reach | 350.6500. P Paint Sanatquin South Vault | P Painting | 12 Finishes | 2.2 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 350.7100. IMP Pipe Fitting Sanatquin South Vault | IMP Interior Mech/Piping | 55 Mechanical | 47.92 |  | 1028 | 1000 | 750 | 250 | 2023-12-01 | 2026-05-01 | 250 | 500 |  |  | 750
2321. CUWCD Santaquin Reach | 350.7500. PUMP Sump Pump Install Sanatquin South Vault | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 180.45 | 180 | 180 | 0 | 2023-12-01 | 2026-05-01 |  | 180 |  |  | 180
2321. CUWCD Santaquin Reach | 350.7600. MEQ Beams/Fire Extinguisher/Key Box Install Sanatquin South | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 42 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 350.7900. ELC Trenching/Conduit Proofing/Mule Tape Install Santaquin S | ELC Electrical | 10 Pipe | 93.34 |  | 200.28 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 360.5100. WE Welding Pigging Door & Paint | W Welding | 20 Fabrication | 53.43 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.1200. HOOK Hook Truck Dumpsters/Conex Santaquin North Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 3.92 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.1230. T Transporting Santaquin North Vault | T Transporting | 40 Drivers | 12 |  | 40 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.1510. S Surveying Santaquin North Vault | S Surveying | 45 Survey | 0 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.1700. FS Start Up Santaquin North Vault | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 40 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 375.1710. FS Startup/Commissioning Santaquin North Vault | FS Starup/Commissioning | 55 Mechanical | 1.29 |  | 40 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 375.1930. MC Misc. Cleanup Santaquin North Vault | MC Misc Cleanup | 12 Finishes | 101.06 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.1940. PL Punch List Work Santaquin North Vault | PL Punch List Work | 12 Finishes | 10.17 |  | 90 | 80 | 80 | 0 | 2023-12-01 | 2026-05-01 | 80 |  |  |  | 80
2321. CUWCD Santaquin Reach | 375.2060. FE Temp Fence/Construction Fence (Field) Labor Santaquin Nor | FE Fencing | 11 Earth Work | 0 |  | 18 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2070. SFC SWPPP Washout Santaquin North Vault | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 56 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2080. EXS Excavate Vault Santaquin North Vault | EXS Excavate Structure | 11 Earth Work | 100.76 |  | 117.26 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2200. DPL Drainage Install Santaquin North Vault | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 88.86 |  | 105.12 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2300. WPL WSP Instal Santaquin North Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 61.92 |  | 113.06 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2610. PT Pressure Test Santaquin North Vault | PT Pressure Test/Chlorinating | 10 Pipe | 2.78 |  | 10 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2750. H Hauling Santaquin North Vault | H Hauling | 40 Drivers | 71.88 |  | 323.62 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2760. HO Haul Off Santaquin North Vault | HO Haul Off | 40 Drivers | 5.32 |  | 28.57 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.2800. BFST Backfill Structure Install Santaquin North Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 222.12 |  | 271.72 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.3000. CNC Concrete Install Santaquin North Vault | CNC Concrete Work | 15 Concrete | 862.79 |  | 937.75 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 60 | 60 |  |  | 120
2321. CUWCD Santaquin Reach | 375.5000. MET Metals Install Santaquin North Vault | MET Metals | 20 Fabrication | 32.71 |  | 75 | 25 | 25 | 0 | 2023-12-01 | 2026-05-01 | 25 |  |  |  | 25
2321. CUWCD Santaquin Reach | 375.5100. W Welding WSP Santaquin North Vault | W Welding | 20 Fabrication | 24.9 |  | 7.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.5400. HAT Hatch Vault Install Santaquin North Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 24 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.6000. IF Sealants Install Santaquin North Vault | IF Interior Finishes | 20 Fabrication | 0 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.6200. IF Insulation Install Santaquin North Vault | IN Insulation | 12 Finishes | 110.99 |  | 102.27 | 10 | 10 | 0 | 2023-12-01 | 2026-05-01 | 10 |  |  |  | 10
2321. CUWCD Santaquin Reach | 375.6500. P Paint Piping Santaquin North Vault | P Painting | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.7100. IMP Pipe Fitting Santaquin North Vault | IMP Interior Mech/Piping | 55 Mechanical | 128.93 |  | 131.5 | 50 | 75 | -25 | 2023-12-01 | 2026-05-01 | 75 |  |  |  | 75
2321. CUWCD Santaquin Reach | 375.7500. PUMP Sump Pump Install Santaquin North Vault | PUMP Pumps/Motors | 55 Mechanical | 0 |  | 30 | 30 | 0 | 30 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.7800. CATH Install Type A Stations & Anodes Santaquin North Vault | PRK Park Equipment | 12 Finishes | 17.73 |  | 81.2 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 375.7900. ELC Trenching/Conduit Proofing/Mule Tape Install Santaquin N | ELC Electrical | 10 Pipe | 42.33 |  | 170.28 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 380.2610. PT Fill/Test/FLush WSP Santaquin Pipeline | PT Pressure Test/Chlorinating | 10 Pipe | 493.73 |  | 310 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 385.2300. WPL Canausa & Diaper Installation Santaquin Pipeline | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1202.26 |  | 2968.34 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 390.2300. WPL Pulling Stulls/Grouting Pipe/Cleanup Santaquin Pipeline | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 5213.88 |  | 3512.71 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 395.5100. W Welding WSP on Santaquin Pipeline & Santaquin Vaults | W Welding | 20 Fabrication | 4701.18 |  | 3797 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.1200. HOOK Hook Truck Dumpsters/Conex Mapletion Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 3 |  | 10 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.1230. T Transporting Mapletion Vault | T Transporting | 40 Drivers | 166.05 |  | 122 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.1510. S Surveying Mapletion Vault | S Surveying | 45 Survey | 86.77 |  | 75 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.1700. FS Start Up Mapleton Vault | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 20 | 20 | 20 | 0 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 400.1930. MC Misc. Cleanup Mapletion Vault | MC Misc Cleanup | 12 Finishes | 78.68 |  | 80 | 25 | 25 | 0 | 2023-12-01 | 2026-05-01 |  | 25 |  |  | 25
2321. CUWCD Santaquin Reach | 400.1940. PL Punch List Work Mapletion Vault | PL Punch List Work | 12 Finishes | 24.6 |  | 150 | 150 | 120 | 30 | 2023-12-01 | 2026-05-01 |  | 120 |  |  | 120
2321. CUWCD Santaquin Reach | 400.2060. FE Temp Fence/Construction Fence (Field) Labor Mapletion Vau | FE Fencing | 11 Earth Work | 48.5 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2080. EXS Excavation Mapleton Vault | EXS Excavate Structure | 11 Earth Work | 253.27 |  | 90 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2090. IMP Pipe Fitting Mapeltion Vault | MTL Materials | 00 _Unknown PR Dept | 27.35 |  | 144.12 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 400.2140. SVR 2 Inch Water Service | SVR Services | 10 Pipe | 269.15 |  | 171 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2300. WPL 20" and 12" | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1125.23 |  | 809.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2750. H Hauling Mapleton Vault | H Hauling | 40 Drivers | 122.34 |  | 135.16 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2760. HO Haul Off Mapleton Vault | HO Haul Off | 40 Drivers | 231.76 |  | 74.29 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2800. BFST Backfill Vault Install Mapleton Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 236.35 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.2930. AP Asphalt Prep Mapleton Vault | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 409.39 |  | 321.46 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.3000. CNC Concrete & Encasement Install Mapleton Vault | CNC Concrete Work | 15 Concrete | 807.63 |  | 1041.99 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 60 | 60 |  |  | 120
2321. CUWCD Santaquin Reach | 400.5000. MET Metals Install Mapleton Vault | MET Metals | 20 Fabrication | 10.53 |  | 103 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 400.5100. W Welding Pipe Mapleton Vault | W Welding | 20 Fabrication | 160.21 |  | 55 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.5400. HAT Hatch Vault Install Mapleton Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.6200. IN Insulation Vault Install Mapleton Vault | IN Insulation | 12 Finishes | 368.74 |  | 84.48 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.6500. P Paint Piping Mapleton Vault | P Painting | 12 Finishes | 12.67 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.7100. IMP Pipe Fitting Mapleton Vault | IMP Interior Mech/Piping | 55 Mechanical | 355.01 |  | 13.5 | 0 | 50 | -50 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 400.7800. CATH Test Station & Anode Install Mapleton Vault | PRK Park Equipment | 12 Finishes | 46.83 |  | 70 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 400.7900. ELC Trenching/Mule Tape Install Mapleton Vault | ELC Electrical | 10 Pipe | 10.77 |  | 114 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.1200. HOOK Hook Truck Dumpsters/Conex Salem East Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 7.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.1230. T Transporting Salem East Vault | T Transporting | 40 Drivers | 52.81 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.1510. S Surveying Salem East Vault | S Surveying | 45 Survey | 35.11 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.1700. FS Start Up Salem East Vault | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 20 | 20 | 20 | 0 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 450.1930. MC Misc. Cleanup Salem East Vault | MC Misc Cleanup | 12 Finishes | 29.47 |  | 40 | 10 | 10 | 0 | 2023-12-01 | 2026-05-01 | 10 |  |  |  | 10
2321. CUWCD Santaquin Reach | 450.1940. PL Punch List Work Salem East Vault | PL Punch List Work | 12 Finishes | 6.44 |  | 90 | 90 | 90 | 0 | 2023-12-01 | 2026-05-01 | 90 |  |  |  | 90
2321. CUWCD Santaquin Reach | 450.2020. CG Clear & Grub Salem East Vault | CG Clearing/Grubbing | 11 Earth Work | 0 |  | 5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2060. FE Temp Fence/Construction Fence (Field) Labor Salem East V | FE Fencing | 11 Earth Work | 0 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2070. SFC SWPPP Salem East Vault | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2080. EXS Excavate Vault Salem East Vault | EXS Excavate Structure | 11 Earth Work | 371.96 |  | 320 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2300. WPL WSP Install Salem East Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 70.73 |  | 209.56 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2710. FWF Flowfill Placement Salem East Vault | FWF Flowable Fill | 15 Concrete | 20.55 |  | 40 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2750. H Hauling Salem East Vault | H Hauling | 40 Drivers | 0 |  | 44.68 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2760. HO Haul Off Salem East Vault | HO Haul Off | 40 Drivers | 0 |  | 79.57 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.2800. BFST Backfill Structure Install Salem East Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 280.64 |  | 210 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.3000. CNC Concrete Install Salem East Vault | CNC Concrete Work | 15 Concrete | 1063.67 |  | 1317.13 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 60 | 60 |  |  | 120
2321. CUWCD Santaquin Reach | 450.5000. MET Metals Install Salem East Vault | MET Metals | 20 Fabrication | 68.44 |  | 43 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.5100. W Welding Pipe Salem East Vault | W Welding | 20 Fabrication | 111.3 |  | 17.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.5400. HAT Hatch Vault Install Salem East Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.6000. IF Interior Finishes Salem East East | IF Interior Finishes | 20 Fabrication | 15.25 |  | 6 | 20 | 20 | 0 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 450.6200. IF Insulation Install Salem East Vault | IN Insulation | 12 Finishes | 134.34 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.6500. P Paint Piping Salem East Vault | P Painting | 12 Finishes | 3 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.7100. IMP Pipe Fitting Salem East Vault | IMP Interior Mech/Piping | 55 Mechanical | 200.89 |  | 269 | 100 | 200 | -100 | 2023-12-01 | 2026-05-01 | 150 | 50 |  |  | 200
2321. CUWCD Santaquin Reach | 450.7500. PUMP Sump Pump Install Salem East Vault | PUMP Pumps/Motors | 55 Mechanical | 4.6 |  | 45 | 0 | 10 | -10 | 2023-12-01 | 2026-05-01 | 10 |  |  |  | 10
2321. CUWCD Santaquin Reach | 450.7800. MEQ Salem East Vault | PRK Park Equipment | 12 Finishes | 0 |  | 38 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 450.7900. ELC Trenching & Conduit Salem East Vault | ELC Electrical | 10 Pipe | 62.83 |  | 188 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.1200. HOOK Hook Truck Dumpsters/Conex Salem Woodland | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 6.47 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.1230. T Transporting Salem Woodland | T Transporting | 40 Drivers | 102.86 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.1510. S Surveying Salem Woodland | S Surveying | 45 Survey | 215.02 |  | 115 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.1600. TC Traffic Control Salem/Woodland | TC Traffic Control | 30 Traffic Control | 171.94 |  | 65 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.1700. FS Start Up Salem/Woodland | FS Project Manager | 60 Operations (PM/PE) | 9.72 |  | 40 | 30 | 30 | 0 | 2023-12-01 | 2026-05-01 | 30 |  |  |  | 30
2321. CUWCD Santaquin Reach | 500.1930. MC Misc. Cleanup Salem Woodland | MC Misc Cleanup | 12 Finishes | 21.16 |  | 120 | 100 | 100 | 0 | 2023-12-01 | 2026-05-01 | 100 |  |  |  | 100
2321. CUWCD Santaquin Reach | 500.1940. PL Punch List Work Salem Woodland | PL Punch List Work | 12 Finishes | 22.96 |  | 180 | 160 | 160 | 0 | 2023-12-01 | 2026-05-01 |  | 160 |  |  | 160
2321. CUWCD Santaquin Reach | 500.2020. CG Remove Top Soil & Replace Salem/Woodland | CG Clearing/Grubbing | 11 Earth Work | 84.83 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2030. D Demo Salem/Woodland | D Demolition | 11 Earth Work | 28.08 |  | 39 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2050. Retaining Wall | RW Retaining Walls | 11 Earth Work | 343.34 |  | 80 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2070. SFC SWPPP Salem/Woodland | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2080. EXS Excavate Structure & Site Salem/Woodland | EXS Excavate Structure | 11 Earth Work | 578.56 |  | 114.3 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2200. DPL Drainage Install Salem/Woodland | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 263.03 |  | 201 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2300. WPL 36 Inch & 12 Inch WSP Salem/Woodland | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1014.7 |  | 1124.71 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2610. PT Pressure Test WSP Salem/Woodland | PT Pressure Test/Chlorinating | 10 Pipe | 206.67 |  | 40 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2700. | SG Sand & Gravel | 11 Earth Work | 0 |  | 5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2710. FWF CLSM Placement Salem/Woodland | FWF Flowable Fill | 15 Concrete | 61.05 |  | 125 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2750. H Hauling Salem/Woodland | H Hauling | 40 Drivers | 318.1 |  | 500.61 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2760. HO Haul Off Salem/Woodland | HO Haul Off | 40 Drivers | 52.08 |  | 113.51 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.2800. BFST Backfill Structure Salem/Woodland | BFST Backfill (DO NOT USE) | 11 Earth Work | 476.68 |  | 486.22 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.3000. CNC Concrete & Encasement Install Salem/Woodland | CNC Concrete Work | 15 Concrete | 1568.17 |  | 1909.25 | 240 | 240 | 0 | 2023-12-01 | 2026-05-01 | 120 | 120 |  |  | 240
2321. CUWCD Santaquin Reach | 500.5000. MET Metals Instal Salem/Woodland | MET Metals | 20 Fabrication | 175.26 |  | 42.02 | 5 | 5 | 0 | 2023-12-01 | 2026-05-01 | 5 |  |  |  | 5
2321. CUWCD Santaquin Reach | 500.5100. W Welding WSP Salem/Woodland | W Welding | 20 Fabrication | 551.58 |  | 61 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.5110. Top of Wall Rework Salem/Woodland | FAB Shop Pipe Fabrication (DO NOT USE) | 20 Fabrication | 329.95 |  | 77 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.6200. IN Insulation Salem/Woodland | IN Insulation | 12 Finishes | 19.45 |  | 0.12 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.6300. DAW Door Install Salem/Woodland | DAW Doors & Windows | 12 Finishes | 21.85 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.6500. P Paint Install Salem/Woodland | P Painting | 12 Finishes | 32.03 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.7100. IMP Pipe Fitting Salem/Woodland | IMP Interior Mech/Piping | 55 Mechanical | 399.63 |  | 410.33 | 250 | 399 | -149 | 2023-12-01 | 2026-05-01 | 350 | 49 |  |  | 399
2321. CUWCD Santaquin Reach | 500.7500. PUMP Sump Pump Install Salem/Woodland | PUMP Pumps/Motors | 55 Mechanical | 25.56 |  | 45 | 0 | 35 | -35 | 2023-12-01 | 2026-05-01 | 35 |  |  |  | 35
2321. CUWCD Santaquin Reach | 500.7600. MEQ Fire Extinguisher/Key Boxes Install Salem/Woodland | MEQ Mechanical Equipment | 55 Mechanical | 0 |  | 12 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.7800. CATH Install Type A Stations & Andoes Salem/Woodland | PRK Park Equipment | 12 Finishes | 12.77 |  | 142 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 500.7900. ELC Trenching/Conduit/Mule Tape Salem/Woodland | ELC Electrical | 10 Pipe | 278.85 |  | 427 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.1200. HOOK Hook Truck Dumpsters/Conex Salem 250 W Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.1230. T Transporting Salem 250 W Vault | T Transporting | 40 Drivers | 100.69 |  | 62 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.1510. S Surveying Salem 250 W Vault | S Surveying | 45 Survey | 75.66 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.1700. FS Start Up Salem 250 W Blowoff | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 40 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 550.1930. MC Misc. Cleanup Salem 250 W Vault | MC Misc Cleanup | 12 Finishes | 22.05 |  | 60 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 550.1940. PL Punch List Work Salem 250 W Vault | PL Punch List Work | 12 Finishes | 7.25 |  | 150 | 150 | 145.8 | 4.2 | 2023-12-01 | 2026-05-01 |  | 145.8 |  |  | 145.8
2321. CUWCD Santaquin Reach | 550.2020. CG Remove Vegetation Salem 250 W Blowoff | CG Clearing/Grubbing | 11 Earth Work | 10.58 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2030. D Demo Concrete Strucutures Salem 250 W Blowoff | D Demolition | 11 Earth Work | 0 |  | 11 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2060. FE Temp Fencing Salem 250 W Vaut | FE Fencing | 11 Earth Work | 29.45 |  | 24 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2070. SFC SWPPP Salem 250 W Blowoff | RGC Rough Grade Cut | 11 Earth Work | 145.32 |  | 48 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2080. EXS Excavate Vault Salem 250 W Blowoff | EXS Excavate Structure | 11 Earth Work | 1096.25 |  | 319 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2200. DPL Drainage Install Salem 250 W Blowoff | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 37.02 |  | 90 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2300. WPL WSP Install Salem 250 W Blowoff | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 92.88 |  | 220.77 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2610. PT Pressure Test Salem 250 W Blowoff | PT Pressure Test/Chlorinating | 10 Pipe | 2 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2710. FWF Flowfill Placement Salem 250 W Blowoff | FWF Flowable Fill | 15 Concrete | 0 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2750. H Hauling Salem 250 W Blowoff | H Hauling | 40 Drivers | 44.85 |  | 61.79 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2760. HO Haul Off Salem 250 W Blowoff | HO Haul Off | 40 Drivers | 61.01 |  | 28.79 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2800. BFST Backfill Salem 250 W Blowoff | BFST Backfill (DO NOT USE) | 11 Earth Work | 311.59 |  | 64 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.2940. CP Concrete Exterior Prep Salem 250 W Blowoff | CP Concrete Prep (DO NOT USE) | 11 Earth Work | 15.6 |  | 20.8 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.3000. CNC Concrete Install Salem 250 W Blowoff | CNC Concrete Work | 15 Concrete | 1782.25 |  | 1325.87 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 60 | 60 |  |  | 120
2321. CUWCD Santaquin Reach | 550.5000. MET Metals Install Salem 250 W Blowoff | MET Metals | 20 Fabrication | 74.68 |  | 147 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.5100. W Welding WSP Salem 250 W Blowoff | W Welding | 20 Fabrication | 109.5 |  | 30.17 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.5400. HAT Hatch Vault Install Salem 250 W Blowoff | HAT Hatch/Skylights | 12 Finishes | 0 |  | 24 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.6000. IF Sealants Install Salem 250 W Blowoff | IF Interior Finishes | 20 Fabrication | 0 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.6200. IF Insulation Install Salem 250 W Blowoff | IN Insulation | 12 Finishes | 80.26 |  | 111 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.6500. P Paint Piping Salem 250 W Blowoff | P Painting | 12 Finishes | 3 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 550.7100. IMP Pipe Fitting Salem 250 W Blowoff | IMP Interior Mech/Piping | 55 Mechanical | 109.94 |  | 224.34 | 100 | 148 | -48 | 2023-12-01 | 2026-05-01 | 100 | 48 |  |  | 148
2321. CUWCD Santaquin Reach | 550.7500. PUMP Sump Pump Install Salem 250 W Blowoff | PUMP Pumps/Motors | 55 Mechanical | 36.66 |  | 45 | 0 | 20 | -20 | 2023-12-01 | 2026-05-01 | 20 |  |  |  | 20
2321. CUWCD Santaquin Reach | 550.7800. CATH Install Type A Stations & Anodes Salem 250 W Blowoff | PRK Park Equipment | 12 Finishes | 10.98 |  | 72 | 0 | 5 | -5 | 2023-12-01 | 2026-05-01 |  | 5 |  |  | 5
2321. CUWCD Santaquin Reach | 550.7900. ELC Trenching/Conduit/Mule Tape Salem 250 W Blowoff | ELC Electrical | 10 Pipe | 82.38 |  | 76 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.1200. HOOK Hook Truck Dumpsters/Conex Payson East Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.1230. T Transporting Payson East Vault | T Transporting | 40 Drivers | 128.94 |  | 90 | 50 | 23.6 | 26.4 | 2023-12-01 | 2026-05-01 | 23.6 |  |  |  | 23.6
2321. CUWCD Santaquin Reach | 600.1510. S Surveying Payson East Vault | S Surveying | 45 Survey | 111.78 |  | 50 | 50 | 22.1 | 27.9 | 2023-12-01 | 2026-05-01 | 22.1 |  |  |  | 22.1
2321. CUWCD Santaquin Reach | 600.1700. FS Start Up Payson East Vault | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 40 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 600.1930. MC Misc. Cleanup Payson East Vault | MC Misc Cleanup | 12 Finishes | 42.8 |  | 80 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 |  | 50 |  |  | 50
2321. CUWCD Santaquin Reach | 600.1940. PL Punch List Work Payson East Vault | PL Punch List Work | 12 Finishes | 0 |  | 180 | 180 | 180 | 0 | 2023-12-01 | 2026-05-01 |  | 180 |  |  | 180
2321. CUWCD Santaquin Reach | 600.2020. CG Remove Vegetation Payson East Vault | CG Clearing/Grubbing | 11 Earth Work | 69.76 |  | 4 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.2050. RW Retaining Wall Payson East Vault | RW Retaining Walls | 11 Earth Work | 10.25 |  | 126.66 | 125 | 125 | 0 | 2023-12-01 | 2026-05-01 | 50 | 75 |  |  | 125
2321. CUWCD Santaquin Reach | 600.2060. FE Temp Fence/Construction Fence (Field) Labor Payson East V | FE Fencing | 11 Earth Work | 0 |  | 18 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.2080. EXS Excavate Structure Payson East Vault | EXS Excavate Structure | 11 Earth Work | 799.08 |  | 180 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.2200. DPL Drainage Install Payson East Vault | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 86.57 |  | 311 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.2300. WPL 60 Inch WSP & Bypass Install Payson East Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 867.93 |  | 543.83 | 10 | 15 | -5 | 2023-12-01 | 2026-05-01 | 15 |  |  |  | 15
2321. CUWCD Santaquin Reach | 600.2750. H Hauling Payson East Vault | H Hauling | 40 Drivers | 108.16 |  | 196.95 | 100 | 73.5 | 26.5 | 2023-12-01 | 2026-05-01 | 73.5 |  |  |  | 73.5
2321. CUWCD Santaquin Reach | 600.2760. HO Haul Off Payson East Vault | HO Haul Off | 40 Drivers | 388.36 |  | 257.08 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.2800. BFST Backfill Vault Install Payson East Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 44.6 |  | 303 | 400 | 400 | 0 | 2023-12-01 | 2026-05-01 | 400 |  |  |  | 400
2321. CUWCD Santaquin Reach | 600.2930. AP Asphalt Prep Payson East Vault | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 35.91 |  | 48 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 | 50 |  |  |  | 50
2321. CUWCD Santaquin Reach | 600.2940. CP Concrete Exterior Prep Payson East Vault | CP Concrete Prep (DO NOT USE) | 11 Earth Work | 3.4 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.3000. CNC Concrete Install Payson East Vault | CNC Concrete Work | 15 Concrete | 1383.69 |  | 1879.27 | 1000 | 1700 | -700 | 2023-12-01 | 2026-05-01 | 750 | 950 |  |  | 1700
2321. CUWCD Santaquin Reach | 600.5000. MET Metals Install Payson East Vault | MET Metals | 20 Fabrication | 33.57 |  | 132 | 130 | 119.6 | 10.4 | 2023-12-01 | 2026-05-01 |  | 119.6 |  |  | 119.6
2321. CUWCD Santaquin Reach | 600.5100. W Welding WSP Payson East Vault | W Welding | 20 Fabrication | 260.84 |  | 65 | 50 | 100 | -50 | 2023-12-01 | 2026-05-01 | 100 |  |  |  | 100
2321. CUWCD Santaquin Reach | 600.5400. HAT Hatch Install Payson East Vault | HAT Hatch/Skylights | 12 Finishes | 2 |  | 56 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 |  | 50 |  |  | 50
2321. CUWCD Santaquin Reach | 600.6200. IN Insulation Install Payson East Vault | IN Insulation | 12 Finishes | 0 |  | 153.72 | 150 | 150 | 0 | 2023-12-01 | 2026-05-01 |  | 150 |  |  | 150
2321. CUWCD Santaquin Reach | 600.6500. P Paint Piping Payson East Vault | P Painting | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 600.7100. IMP Pipe Fitting Payson East Vault | IMP Interior Mech/Piping | 55 Mechanical | 179.01 |  | 357 | 450 | 500 | -50 | 2023-12-01 | 2026-05-01 | 400 | 100 |  |  | 500
2321. CUWCD Santaquin Reach | 600.7500. PUMP Sump Pump Install | PUMP Pumps/Motors | 55 Mechanical | 58.34 |  | 45 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 40 |  |  |  | 40
2321. CUWCD Santaquin Reach | 600.7800. CATH Install Test Station & Anodes Payson East Vault | PRK Park Equipment | 12 Finishes | 24.12 |  | 42.5 | 25 | 27.9 | -2.9 | 2023-12-01 | 2026-05-01 |  | 27.9 |  |  | 27.9
2321. CUWCD Santaquin Reach | 600.7900. ELC Conduit Proofing/Mule Tape Install Payson East Vault | ELC Electrical | 10 Pipe | 0 |  | 172.4 | 170 | 170 | 0 | 2023-12-01 | 2026-05-01 | 50 | 120 |  |  | 170
2321. CUWCD Santaquin Reach | 650.1200. HOOK Hook Truck Dumpsters/Conex Payson Main St Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 3.7 |  | 20 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.1230. T Transporting Payson Main St Vault | T Transporting | 40 Drivers | 146.52 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.1510. S Surveying Payson Main St Vault | S Surveying | 45 Survey | 100.83 |  | 90 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.1700. FS Start Up Payson Main St Vault | FS Project Manager | 60 Operations (PM/PE) | 0 |  | 40 | 40 | 40 | 0 | 2023-12-01 | 2026-05-01 | 20 | 20 |  |  | 40
2321. CUWCD Santaquin Reach | 650.1710. FS Startup/Commissioning Payson Main St Vault | FS Starup/Commissioning | 55 Mechanical | 0 |  | 80 | 80 | 80 | 0 | 2023-12-01 | 2026-05-01 | 40 | 40 |  |  | 80
2321. CUWCD Santaquin Reach | 650.1930. MC Misc. Cleanup Payson Main St Vault | MC Misc Cleanup | 12 Finishes | 69.48 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.1940. PL Punch List Work Payson Main St Vault | PL Punch List Work | 12 Finishes | 60.17 |  | 90 | 90 | 61 | 29 | 2023-12-01 | 2026-05-01 |  | 61 |  |  | 61
2321. CUWCD Santaquin Reach | 650.2020. CG Remove Vegetation Payson Main St Vault | CG Clearing/Grubbing | 11 Earth Work | 0 |  | 13 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2030. D Demo Payson Main St Vault | D Demolition | 11 Earth Work | 10.35 |  | 66.81 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2060. FE Temp Fence/Construction Fence (Field) Labor PL Punch List | FE Fencing | 11 Earth Work | 2 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2070. SFC SWPPP Payson Main St Vault | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 37 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2080. EXS Excavate Vault Payson Main St Vault | EXS Excavate Structure | 11 Earth Work | 735.55 |  | 558 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2200. DPL Drainage Install Payson Main St Vault | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 116.36 |  | 92 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2300. WPL WSP Install Payson Main St Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 105.2 |  | 363.9 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2610. PT Pressure Test Payson Main St Vault | PT Pressure Test/Chlorinating | 10 Pipe | 0 |  | 40 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2710. FWF CLSM Placement Payson Main St Vault | FWF Flowable Fill | 15 Concrete | 0 |  | 83.52 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2750. H Hauling Payson Main St Vault | H Hauling | 40 Drivers | 169.99 |  | 141.27 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2760. HO Haul Off Payson Main St Vault | HO Haul Off | 40 Drivers | 143.6 |  | 158.94 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2800. BFST Backfill Vault Payson Main St Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 520.02 |  | 153.99 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.2940. CP Concrete Exterior Prep Payson Main St Vault | CP Concrete Prep (DO NOT USE) | 11 Earth Work | 54.69 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.3000. CNC Concrete Install Payson Main St Vault | CNC Concrete Work | 15 Concrete | 2342.7 |  | 2364.5 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 60 | 60 |  |  | 120
2321. CUWCD Santaquin Reach | 650.5000. MET Metals Install Payson Main St Vault | MET Metals | 20 Fabrication | 737.9 |  | 404.4 | 50 | 175 | -125 | 2023-12-01 | 2026-05-01 | 75 | 100 |  |  | 175
2321. CUWCD Santaquin Reach | 650.5100. W Welding WSP Payson Main St Vault | W Welding | 20 Fabrication | 133.24 |  | 152.8 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.5400. HAT Hatch Vault Install Payson Main St Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 30 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.6000. IF Sealants Install Payson Main St Vault | IF Interior Finishes | 20 Fabrication | 10.23 |  | 6 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.6200. IF Insulation Install Payson Main St Vault | IN Insulation | 12 Finishes | 130.48 |  | 210 | 50 | 200 | -150 | 2023-12-01 | 2026-05-01 | 50 | 150 |  |  | 200
2321. CUWCD Santaquin Reach | 650.6500. P Paint Payson Main St Vault | P Painting | 12 Finishes | 10.02 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.7100. IMP Pipe Fitting Payson Main St Vault | IMP Interior Mech/Piping | 55 Mechanical | 740.79 |  | 361.86 | 100 | 400 | -300 | 2023-12-01 | 2026-05-01 | 300 | 100 |  |  | 400
2321. CUWCD Santaquin Reach | 650.7500. PUMP Sump Pump Install Payson Main St Vault | PUMP Pumps/Motors | 55 Mechanical | 69.46 |  | 45 | 0 | 25 | -25 | 2023-12-01 | 2026-05-01 | 25 |  |  |  | 25
2321. CUWCD Santaquin Reach | 650.7800. CATH Install Type A Stations & Anodes Payson Main St Vault | PRK Park Equipment | 12 Finishes | 21.87 |  | 79.52 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 650.7900. ELC Conduit Proofing/Mule Tape Install Payson Main St Vault | ELC Electrical | 10 Pipe | 5 |  | 122.67 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1200. HOOK Hook Truck Dumpsters/Conex Payson South Vault | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 0 |  | 15 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1230. T Transporting Payson South Vault | T Transporting | 40 Drivers | 67.07 |  | 90 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1510. S Surveying Payson South Vault | S Surveying | 45 Survey | 127.84 |  | 50 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1600. TC Traffic Control SR 198 Payson South Vault | TC Traffic Control | 30 Traffic Control | 448.62 |  | 400 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1610. TC Jersey & Water Barrier Payson South Vault | TC Concrete & Water Barrier | 30 Traffic Control | 10 |  | 110.67 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1650. SB Replace Sign & Delineators Payson South Vault | SB Signage | 12 Finishes | 0 |  | 36 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.1700. FS Start Up Payson South Vault | FS Project Manager | 60 Operations (PM/PE) | 20.25 |  | 20 | 50 | 50 | 0 | 2023-12-01 | 2026-05-01 |  | 50 |  |  | 50
2321. CUWCD Santaquin Reach | 700.1930. MC Misc. Cleanup Payson South Vault | MC Misc Cleanup | 12 Finishes | 29.67 |  | 80 | 93.6 | 100 | -6.4 | 2023-12-01 | 2026-05-01 |  | 100 |  |  | 100
2321. CUWCD Santaquin Reach | 700.1940. PL Punch List Work Payson South Vault | PL Punch List Work | 12 Finishes | 5.95 |  | 180 | 180 | 176.4 | 3.6 | 2023-12-01 | 2026-05-01 |  | 176.4 |  |  | 176.4
2321. CUWCD Santaquin Reach | 700.2030. D Demo Asphalt/Concrete Payson South Vault | D Demolition | 11 Earth Work | 0 |  | 78 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2060. FE Temp Fence/Construction Fence (Field) Labor Payson South | FE Fencing | 11 Earth Work | 30.69 |  | 18 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2080. EXS Excavate Structure Payson South Vault | EXS Excavate Structure | 11 Earth Work | 301.18 |  | 75 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2300. WPL 20 Inch & 12 Inch WSP Payson South Vault | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1174.3 |  | 756 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2610. PT Pressure Test Payson South | PT Pressure Test/Chlorinating | 10 Pipe | 212.51 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2750. H Hauling Payson South Vault | H Hauling | 40 Drivers | 121.54 |  | 103.29 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2760. HO Haul Off Payson South Vault | HO Haul Off | 40 Drivers | 186.17 |  | 95.36 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2800. BFST Backfill Vault Install Payson South Vault | BFST Backfill (DO NOT USE) | 11 Earth Work | 523.61 |  | 135 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2910. MP Mill SR-198 Payson South Vault | MP Milling/Pulverize | 11 Earth Work | 0 |  | 5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.2930. AP Asphalt Prep SR-198 Payson South Vault | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 339.38 |  | 88.88 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.3000. CNC Concrete & Encasment Install Payson South Vault | CNC Concrete Work | 15 Concrete | 1047.23 |  | 1410 | 120 | 120 | 0 | 2023-12-01 | 2026-05-01 | 60 | 60 |  |  | 120
2321. CUWCD Santaquin Reach | 700.5000. MET Metals Install Payson South Vault | MET Metals | 20 Fabrication | 19.72 |  | 79 | 5 | 5 | 0 | 2023-12-01 | 2026-05-01 | 5 |  |  |  | 5
2321. CUWCD Santaquin Reach | 700.5100. W Welding WSP Payson South Vault | W Welding | 20 Fabrication | 351.62 |  | 120 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.5400. HAT Hatch Vault Install Payson South Vault | HAT Hatch/Skylights | 12 Finishes | 0 |  | 60 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.6200. IN Insulation Install Payson South Vault | IN Insulation | 12 Finishes | 340.3 |  | 84.48 | 10 | 10 | 0 | 2023-12-01 | 2026-05-01 | 10 |  |  |  | 10
2321. CUWCD Santaquin Reach | 700.6500. P Paint Piping Payson South Vault | P Painting | 12 Finishes | 0 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.7100. IMP Pipe Fitting Payson South Vault | IMP Interior Mech/Piping | 55 Mechanical | 424.98 |  | 171 | 50 | 117.1 | -67.1 | 2023-12-01 | 2026-05-01 | 117.1 |  |  |  | 117.1
2321. CUWCD Santaquin Reach | 700.7800. CATH Install Type A Stations & Anodes Payson South Vault | PRK Park Equipment | 12 Finishes | 64.41 |  | 47.5 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 700.7900. ELC Trenching/Conduit Proofing/Mule Tape Install Payson Sout | ELC Electrical | 10 Pipe | 12 |  | 215.48 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 750.2300. CONE Cone Valve Replacement | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 375.48 |  | 455.4 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 800.1930. MC Misc. Cleanup Santaqin Pipeline & Santaquin Vaults | MC Misc Cleanup | 12 Finishes | 338.91 |  | 300 | 300 | 391.9 | -91.9 | 2023-12-01 | 2026-05-01 |  | 391.9 |  |  | 391.9
2321. CUWCD Santaquin Reach | 800.1940. PL Punch List Work Santaqin Pipeline & Santaquin Vaults | PL Punch List Work | 12 Finishes | 4 |  | 300 | 300 | 300 | 0 | 2023-12-01 | 2026-05-01 |  | 300 |  |  | 300
2321. CUWCD Santaquin Reach | 850.7100. Rework Ball Valves | IMP Interior Mech/Piping | 55 Mechanical | 92.7 |  | 0 | 10 | 0 | 10 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 6.5 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 128.38 |  | 0.4 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 20.83 |  | 0.4 | 0 | 5 | -5 | 2023-12-01 | 2026-05-01 | 5 |  |  |  | 5
2321. CUWCD Santaquin Reach | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 46.49 |  | 0.4 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 24.77 |  | 3 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 38.06 |  | 1 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2321. CUWCD Santaquin Reach | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2023-12-01 | 2026-05-01
2318. CUWCD CWP Wellhouse 7 | 100.1103. TF Temporary Conex/Dumpsters Internal Rate | TF Temporary Field Lab | 00 _Unknown PR Dept | 0 |  | 0 | 10 | 10 | 0 | 2023-06-30 | 2025-12-31 | 10 |  |  |  | 10
2318. CUWCD CWP Wellhouse 7 | 100.1500. TR Training Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 100.1510. S Surveying Well 7 | S Surveying | 45 Survey | 246.56 |  | 100 | 0 | 10 | -10 | 2023-06-30 | 2025-12-31 | 10 |  |  |  | 10
2318. CUWCD CWP Wellhouse 7 | 100.1650. SB Install Sign Well 7 | SB Signage | 12 Finishes | 2.5 |  | 15 | 0 | 12 | -12 | 2023-06-30 | 2025-12-31 | 12 |  |  |  | 12
2318. CUWCD CWP Wellhouse 7 | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 654 |  | 417.54 | 20 | 20 | 0 | 2023-06-30 | 2025-12-31 | 20 |  |  |  | 20
2318. CUWCD CWP Wellhouse 7 | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 472.28 |  | 387.63 | 20 | 20 | 0 | 2023-06-30 | 2025-12-31 | 20 |  |  |  | 20
2318. CUWCD CWP Wellhouse 7 | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 500.27 |  | 303.31 | 20 | 20 | 0 | 2023-06-30 | 2025-12-31 | 20 |  |  |  | 20
2318. CUWCD CWP Wellhouse 7 | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 1121.4 |  | 622.24 | 20 | 40 | -20 | 2023-06-30 | 2025-12-31 | 40 |  |  |  | 40
2318. CUWCD CWP Wellhouse 7 | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 485.25 |  | 60.8 | 20 | 10 | 10 | 2023-06-30 | 2025-12-31 | 10 |  |  |  | 10
2318. CUWCD CWP Wellhouse 7 | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 150.1230. T Transporting Well 7 | T Transporting | 40 Drivers | 81.58 |  | 152 | 10 | 10 | 0 | 2023-06-30 | 2025-12-31 | 10 |  |  |  | 10
2318. CUWCD CWP Wellhouse 7 | 150.2750. H Hauling Well 7 | H Hauling | 40 Drivers | 351.1 |  | 500.21 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 150.2760. HO Haul Off Well 7 | HO Haul Off | 40 Drivers | 136.93 |  | 609.14 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 160.5110. Fab Shop Pipe Fabrication Well 7 | FAB Shop Pipe Fabrication (DO NOT USE) | 20 Fabrication | 458.48 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 160.5120. Fab Shop Pipe Linings & Coatings Well 7 | FAB Shop Pipe Linings & Coatings (DO NOT USE) | 20 Fabrication | 568.14 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 160.5310. Fab Shop Misc Metals Fabrication Well 7 | FAB Shop Misc Metals Fabrication (DO NOT USE) | 20 Fabrication | 101.03 |  | 238.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 160.5320. Fab Shop Misc Metals Coatings Well 7 | FAB Shop Misc Metals Coatings (DO NOT USE) | 20 Fabrication | 13.83 |  | 460 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.1600. TC Traffic Control Well 7 | TC Traffic Control | 30 Traffic Control | 36.56 |  | 20 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2030. D Demo I-Beam Camera Pole Well 7 | D Demolition | 11 Earth Work | 0 |  | 15 | 15 | 15 | 0 | 2023-06-30 | 2025-12-31 | 15 |  |  |  | 15
2318. CUWCD CWP Wellhouse 7 | 200.2040. SFC Landscape Fabric | LR Landscaping/Restoration | 11 Earth Work | 88.01 |  | 44.92 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2070. SWPPP Installation, Maintenence, Inspections Well 7 | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 98 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2080. EXS Excavate Surge Tank Well 7 | EXS Excavate Structure | 11 Earth Work | 160.18 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2200. DPL Drainage System Install Well 7 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 702.26 |  | 295.8 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2300. WPL Welded Steel Pipe Yard Piping Well 7 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 407.16 |  | 302.44 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2610. PT Pressure Test/Chlorinating Well 7 | PT Pressure Test/Chlorinating | 10 Pipe | 83.17 |  | 140 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2710. FWF Flowable Fill Surge Tank Well 7 | FWF Flowable Fill | 15 Concrete | 41.35 |  | 3.56 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.2800. BFST Backfill Surge Well 7 | BFST Backfill (DO NOT USE) | 11 Earth Work | 355.72 |  | 165 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.3000. CNC Concrete Vault Surge Tank Well 7 | CNC Concrete Work | 15 Concrete | 638.24 |  | 561 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.5000. MET Metals Install Surge Tank Well 7 | MET Metals | 20 Fabrication | 3 |  | 35 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.5100. W Welding WSP for Site Piping Well 7 | W Welding | 20 Fabrication | 58.06 |  | 40 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.6200. IN Insulation Install Surge Tank Well 7 | IN Insulation | 12 Finishes | 96.25 |  | 16 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.7100. IMP Mechanical Surge Tank Well 7 | IMP Interior Mech/Piping | 55 Mechanical | 348.29 |  | 200 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 200.7900. ELC On-Site Electrical Trenching Well 7 | ELC Electrical | 10 Pipe | 226.1 |  | 103.14 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 210.2200. DPL Fuse HDPE Pipe Well 7 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 2.03 |  | 26.25 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 220.2300. WPL Cathodic System Install Well 7 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 50.28 |  | 87 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.1650. SB Sign Install Sign on Building Well 7 | SB Signage | 12 Finishes | 0 |  | 10 | 0 | 8 | -8 | 2023-06-30 | 2025-12-31 | 8 |  |  |  | 8
2318. CUWCD CWP Wellhouse 7 | 300.2080. EXS Excavation & Prep Pumphouse Structure Well 7 | EXS Excavate Structure | 11 Earth Work | 474.47 |  | 250 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.2800. BFST Backfill Pumphouse Well 7 | BFST Backfill (DO NOT USE) | 11 Earth Work | 233.09 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.3000. CNC Concrete Fnd/Floor Pumphouse Structure Well 7 | CNC Concrete Work | 15 Concrete | 795.68 |  | 930 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.5000. MET Metals Install Well 7 | MET Metals | 20 Fabrication | 62.52 |  | 75 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.6100. F Misc Framing on Pumphouse Well 7 | F Framing | 12 Finishes | 48.83 |  | 20 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.6300. DAW Install Doors Well 7 | DAW Doors & Windows | 12 Finishes | 51.08 |  | 60 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.6400. DRY Install Plywood for Wet Wall & Alucoboard Panels Well 7 | DRY Drywall & Metal Studs | 12 Finishes | 59.86 |  | 68 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.7100. IMP Mecahnical Install Pumphouse Well 7 | IMP Interior Mech/Piping | 55 Mechanical | 643.39 |  | 414 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.7300. PLUM Plumbing Piping on Pumphouse Well 7 | PLUM Plumbing | 55 Mechanical | 154.69 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.7500. PUMP Pump Support Well 7 | PUMP Pumps/Motors | 55 Mechanical | 20.48 |  | 40 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 300.7600. MEQ Install Pipe Pump Station to Surge Tank | MEQ Mechanical Equipment | 55 Mechanical | 3.5 |  | 110 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 400.2000. SWC Site Work Complete - Cut/Fill Site Grading Well 7 | SWC Site Work Complete (DO NOT USE) | 11 Earth Work | 441.48 |  | 195.29 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 400.2010. RG Sitework Concrete Prep Well 7 | RG Grading (DO NOT USE) | 11 Earth Work | 616.04 |  | 263.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 400.2930. AP Asphalt Prep - 8" Well 7 | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 400.3000. CNC Exterior Site Concrete Well 7 | CNC Concrete Work | 15 Concrete | 102.43 |  | 683.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 400.5000. M Install Bollards Well 7 | MET Metals | 20 Fabrication | 0 |  | 45 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 500.2010. RG Off-Site Concrete Prep Well 7 | RG Grading (DO NOT USE) | 11 Earth Work | 0 |  | 20.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 500.2030. D Demo Off-Site Concrete/Asphalt/Landscaping Well 7 | D Demolition | 11 Earth Work | 6.43 |  | 52 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 500.2930. AP Off-Site Asphalt Prep Well 7 | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 0 |  | 6 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 500.3000. CNC Off-Site Concrete Form/Pour Strip Site Concrete Well 7 | CNC Concrete Work | 15 Concrete | 0 |  | 40 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 500.7900. ELC Off-Site Electrical Trenching & Pull Boxes Well 7 | ELC Electrical | 10 Pipe | 159.33 |  | 253.99 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 800.1700. FS Start Up Well 7 | FS Project Manager | 60 Operations (PM/PE) | 40.94 |  | 400 | 20 | 60 | -40 | 2023-06-30 | 2025-12-31 | 60 |  |  |  | 60
2318. CUWCD CWP Wellhouse 7 | 800.1930. MC Misc. Cleanup Well 7 | MC Misc Cleanup | 12 Finishes | 13.1 |  | 100 | 60 | 100 | -40 | 2023-06-30 | 2025-12-31 | 100 |  |  |  | 100
2318. CUWCD CWP Wellhouse 7 | 800.1940. PL Punch List Work Well 7 | PL Punch List Work | 12 Finishes | 64.11 |  | 200 | 40 | 100 | -60 | 2023-06-30 | 2025-12-31 | 100 |  |  |  | 100
2318. CUWCD CWP Wellhouse 7 | 900.9005. Re-Work Surveying Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 2 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9010. Re-Work Pipe Well 7 | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9012. Re-Work Mechanical Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 50.15 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9015. Re-Work Concrete Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9020. Re-Work Fab Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 28.6 |  | 0.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9040. Re-Work Drivers Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9055. Re-Work Finishes Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 7.52 |  | 0.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2318. CUWCD CWP Wellhouse 7 | 900.9100. Job Related Equipment Repairs Well 7 | _Unknown Phase Master | 00 _Unknown PR Dept | 34.76 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2317. CUWCD CWP Wellhouse 17 | 100.1103. TF Temporary Conex/Dumpsters Internal Rate | TF Temporary Field Lab | 00 _Unknown PR Dept | 0 |  | 0 | 10 | 10 | 0 | 2023-06-30 | 2025-12-30 | 10 |  |  |  | 10
2317. CUWCD CWP Wellhouse 17 | 100.1500. TR Training Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 100.1510. S Surveying Well 17 | S Surveying | 45 Survey | 219.2 |  | 106 | 0 | 20 | -20 | 2023-06-30 | 2025-12-30 | 20 |  |  |  | 20
2317. CUWCD CWP Wellhouse 17 | 100.1650. SB Install Sign Well 17 | SB Signage | 12 Finishes | 2.5 |  | 15 | 0 | 12 | -12 | 2023-06-30 | 2025-12-30 | 12 |  |  |  | 12
2317. CUWCD CWP Wellhouse 17 | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 755.75 |  | 400.64 | 20 | 20 | 0 | 2023-06-30 | 2025-12-30 | 20 |  |  |  | 20
2317. CUWCD CWP Wellhouse 17 | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 498.84 |  | 372.02 | 20 | 20 | 0 | 2023-06-30 | 2025-12-30 | 20 |  |  |  | 20
2317. CUWCD CWP Wellhouse 17 | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 499.65 |  | 291.32 | 20 | 20 | 0 | 2023-06-30 | 2025-12-30 | 20 |  |  |  | 20
2317. CUWCD CWP Wellhouse 17 | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 1033.88 |  | 596.54 | 20 | 40 | -20 | 2023-06-30 | 2025-12-30 | 40 |  |  |  | 40
2317. CUWCD CWP Wellhouse 17 | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 455.24 |  | 58.23 | 10 | 8 | 2 | 2023-06-30 | 2025-12-30 | 8 |  |  |  | 8
2317. CUWCD CWP Wellhouse 17 | 100.1705. | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 100.1706. | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 150.1230. T Transporting Well 17 | T Transporting | 40 Drivers | 108.24 |  | 152 | 10 | 10 | 0 | 2023-06-30 | 2025-12-30 | 10 |  |  |  | 10
2317. CUWCD CWP Wellhouse 17 | 150.2710. FWF Flowable Fill Well 17 | FWF Flowable Fill | 15 Concrete | 83.41 |  | 0.28 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 150.2750. H Hauling Well 17 | H Hauling | 40 Drivers | 149.48 |  | 267.33 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 150.2760. HO Haul Off Well 17 | HO Haul Off | 40 Drivers | 197.74 |  | 387.72 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 160.5110. Fab Shop Pipe Fabrication Well 17 | FAB Shop Pipe Fabrication (DO NOT USE) | 20 Fabrication | 294.83 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 160.5120. Fab Shop Pipe Linings & Coatings Well 17 | FAB Shop Pipe Linings & Coatings (DO NOT USE) | 20 Fabrication | 559.2 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 160.5310. Fab Shop Misc Metals Fabrication Well 17 | FAB Shop Misc Metals Fabrication (DO NOT USE) | 20 Fabrication | 33.18 |  | 253.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 160.5320. Fab Shop Misc Metals Coatings Well 17 | FAB Shop Misc Metals Coatings (DO NOT USE) | 20 Fabrication | 20.4 |  | 480 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2030. D Demo I-beam Camera Well 17 | D Demolition | 11 Earth Work | 0 |  | 15 | 15 | 15 | 0 | 2023-06-30 | 2025-12-30 | 15 |  |  |  | 15
2317. CUWCD CWP Wellhouse 17 | 200.2040. LR Landscape Rock Install | LR Landscaping/Restoration | 11 Earth Work | 10.53 |  | 44.62 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2070. SWPPP Installation, Maintenence, Inspections Well 17 | RGC Rough Grade Cut | 11 Earth Work | 1 |  | 106 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2200. DPL Drainage System Install Well 17 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 545.67 |  | 233.72 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2300. WPL Welded Steel Pipe Yard Piping Well 17 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 533.42 |  | 438.37 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2610. PT Pressure Test/Chlorinating Well 17 | PT Pressure Test/Chlorinating | 10 Pipe | 239.87 |  | 140 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2710. FWF Flowfill Support Well 17 | FWF Flowable Fill | 15 Concrete | 32.98 |  | 3.56 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.2800. BFST Backfill Surge Tank Well 17 | BFST Backfill (DO NOT USE) | 11 Earth Work | 216.64 |  | 165 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.3000. CNC Concrete Vault Surge Tank Wel l17 | CNC Concrete Work | 15 Concrete | 822.68 |  | 513 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.5000. MET Metals Install Surge Tank Well 17 | MET Metals | 20 Fabrication | 127.89 |  | 40 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.5100. W Welding WSP for Site Piping Well 17 | W Welding | 20 Fabrication | 191.8 |  | 80 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.6200. IN Install Insulation Well 17 | IN Insulation | 12 Finishes | 104.41 |  | 16 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.7100. IMP Mechanical Install Surge Tank Well 17 | IMP Interior Mech/Piping | 55 Mechanical | 436 |  | 100 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 200.7900. ELC Trenching Electrical Conduit Well 17 | ELC Electrical | 10 Pipe | 220.57 |  | 144.75 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 210.2200. WPL Fusing HDPE Pipe Well 17 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 378.44 |  | 37.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 220.2300. WPL Cathodic System Install Well 17 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 58.4 |  | 135 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.1650. SB Sign Install Sign on Building Well 17 | SB Signage | 12 Finishes | 1 |  | 10 | 0 | 8 | -8 | 2023-06-30 | 2025-12-30 | 8 |  |  |  | 8
2317. CUWCD CWP Wellhouse 17 | 300.2080. EXS Excavation & Prep Pumphouse Structure Well 17 | EXS Excavate Structure | 11 Earth Work | 66.28 |  | 400 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.2800. BFST Backfill Pumphouse Well 17 | BFST Backfill (DO NOT USE) | 11 Earth Work | 263.92 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.3000. CNC Concrete Fnd/Floor Pumphouse Structure Well 17 | CNC Concrete Work | 15 Concrete | 1021.07 |  | 930 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.5000. | MET Metals | 20 Fabrication | 0 |  | 7.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.6100. F Misc Framing on Pumphouse Well 17 | F Framing | 12 Finishes | 35 |  | 20 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.6300. DAW Install Doors Well 17 | DAW Doors & Windows | 12 Finishes | 74.02 |  | 60 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.6400. DRY Install Plywood for Wet Wall & Alucoboard Panels Well 1 | DRY Drywall & Metal Studs | 12 Finishes | 94.14 |  | 68 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.7100. IMP Mecahnical Install Pumphouse Well 17 | IMP Interior Mech/Piping | 55 Mechanical | 701.38 |  | 489 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.7300. PLUM Plumbing Piping on Pumphouse Well 17 | PLUM Plumbing | 55 Mechanical | 156.37 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 300.7600. MEQ Install Pipe Pump Station to Surge Tank Well 17 | MEQ Mechanical Equipment | 55 Mechanical | 36.96 |  | 110 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 400.2000. SWC Site Work Complete - Cut/Fill Site Grading Well 17 | SWC Site Work Complete (DO NOT USE) | 11 Earth Work | 360.86 |  | 84.77 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 400.2010. RG Sitework Concrete Prep Well 17 | RG Grading (DO NOT USE) | 11 Earth Work | 224.91 |  | 270.03 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 400.2930. AP Asphalt Prep - 8" Well 17 | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 400.3000. CNC Concrete Exterior Site Concrete Well 17 | CNC Concrete Work | 15 Concrete | 406.49 |  | 530.47 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 800.1700. FS Start Up Well 17 | FS Project Manager | 60 Operations (PM/PE) | 36.75 |  | 400 | 20 | 60 | -40 | 2023-06-30 | 2025-12-30 | 60 |  |  |  | 60
2317. CUWCD CWP Wellhouse 17 | 800.1930. MC Misc. Cleanup Well 17 | MC Misc Cleanup | 12 Finishes | 8.73 |  | 100 | 100 | 90 | 10 | 2023-06-30 | 2025-12-30 | 90 |  |  |  | 90
2317. CUWCD CWP Wellhouse 17 | 800.1940. PL Punch List Work Well 17 | PL Punch List Work | 12 Finishes | 17.5 |  | 200 | 60 | 80 | -20 | 2023-06-30 | 2025-12-30 | 80 |  |  |  | 80
2317. CUWCD CWP Wellhouse 17 | 900.9005. Re-Work Surveying Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 1 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9010. Re-Work Pipe Well 17 | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 45.59 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9012. Re-Work Mechanical Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 35.33 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9015. Re-Work Concrete Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 2 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9020. Re-Work Fab Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 81.55 |  | 0.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9040. Re-Work Drivers Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9055. Re-Work Finishes Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 8.47 |  | 0.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2317. CUWCD CWP Wellhouse 17 | 900.9100. Job Related Equipment Repairs Well 17 | _Unknown Phase Master | 00 _Unknown PR Dept | 4 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-30
2316. CUWCD CWP Wellhouse 16 | 100.1101. TF Temporary Office Trailer Owner/Engineer | TF Temporary Office Trailer VanCon | 00 _Unknown PR Dept | 2 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 100.1500. TR Training Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 40.9 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 100.1510. S Surveying Well 16 | S Surveying | 45 Survey | 622.21 |  | 175 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 100.1700. FS Project Manager | FS Project Manager | 60 Operations (PM/PE) | 1944.29 |  | 704.98 | 20 | 38 | -18 | 2023-06-30 | 2025-12-31 | 38 |  |  |  | 38
2316. CUWCD CWP Wellhouse 16 | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 2220.82 |  | 654.65 | 20 | 23 | -3 | 2023-06-30 | 2025-12-31 | 23 |  |  |  | 23
2316. CUWCD CWP Wellhouse 16 | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 1336.61 |  | 512.76 | 20 | 20 | 0 | 2023-06-30 | 2025-12-31 | 20 |  |  |  | 20
2316. CUWCD CWP Wellhouse 16 | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 2122.06 |  | 1049.46 | 20 | 30 | -10 | 2023-06-30 | 2025-12-31 | 30 |  |  |  | 30
2316. CUWCD CWP Wellhouse 16 | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 1955.48 |  | 104.63 | 10 | 10 | 0 | 2023-06-30 | 2025-12-31 | 10 |  |  |  | 10
2316. CUWCD CWP Wellhouse 16 | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 150.1230. T Transporting Well 16 | T Transporting | 40 Drivers | 173.57 |  | 261.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 150.2750. H Hauling Well 16 | H Hauling | 40 Drivers | 665.03 |  | 940.86 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 150.2760. HO Haul Off Well 16 | HO Haul Off | 40 Drivers | 70.8 |  | 839.49 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 160.5110. Fab Shop Pipe Fabrication | FAB Shop Pipe Fabrication (DO NOT USE) | 20 Fabrication | 1221.42 |  | 308 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 160.5120. Fab Shop Pipe Linings & Coatings | FAB Shop Pipe Linings & Coatings (DO NOT USE) | 20 Fabrication | 2203.25 |  | 440 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 160.5310. Fab Shop Misc Metals Fabrication | FAB Shop Misc Metals Fabrication (DO NOT USE) | 20 Fabrication | 261.39 |  | 300.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 160.5320. Fab Shop Misc Metals Coatings | FAB Shop Misc Metals Coatings (DO NOT USE) | 20 Fabrication | 20.9 |  | 491 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.1650. SB Install Job Site Signage Well 16 | SB Signage | 12 Finishes | 147.58 |  | 15 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.1800. PH Pothole Well 12 | PH Potholing | 10 Pipe | 0 |  | 15 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2000. SWC Mowstrip Prep (4" thick roadbase x 12" wide) | SWC Site Work Complete (DO NOT USE) | 11 Earth Work | 0 |  | 21.52 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2040. LR Landscape Repair Sod/Gravel Small L&E | LR Landscaping/Restoration | 11 Earth Work | 112.55 |  | 80.8 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2070. SWPPP Installation, Maintenence, Inspections Well 16 | RGC Rough Grade Cut | 11 Earth Work | 0 |  | 178 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2080. EXS Excavate Structure Surge Tank & Vault Well 16 | EXS Excavate Structure | 11 Earth Work | 183.38 |  | 298.18 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2200. DPL Drainage System Install Well 16 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 760.93 |  | 264.39 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2300. WPL Welded Steel Pipe Yard Piping Well 16 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 583.11 |  | 783.03 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2500. MH Install Manhole | MH Manholes (DO NOT USE) | 10 Pipe | 13.33 |  | 96 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2600. DW Dewatering Maintenance Easy | DW Dewatering | 10 Pipe | 115.78 |  | 32 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2610. PT Pressure Test/Chlorinating WSP Well 16 | PT Pressure Test/Chlorinating | 10 Pipe | 255.69 |  | 160 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2710. FWF Flowable Fill Surge Tank Well 16 | FWF Flowable Fill | 15 Concrete | 36.44 |  | 8.08 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.2800. BFST Backfill Surge Tank & Vault Well 16 | BFST Backfill (DO NOT USE) | 11 Earth Work | 526.13 |  | 165 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.3000. CNC Concrete Install Surge Tank Well 16 | CNC Concrete Work | 15 Concrete | 1031.7 |  | 573 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.5000. MET Metals Install Surge Tank Well 16 | MET Metals | 20 Fabrication | 187 |  | 52 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.5100. W Welding WSP for Site Piping Well 16 | W Welding | 20 Fabrication | 573.05 |  | 395 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.6200. IN Install Insulation Surge Tank Well 16 | IN Insulation | 12 Finishes | 356.41 |  | 48.28 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 200.7100. IMP Mechanical Install Surge Tank Well 16 | IMP Interior Mech/Piping | 55 Mechanical | 312.92 |  | 109 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 210.2300. WPL 4 Inch HDPE Pipe Installation Well 16 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 96.09 |  | 100 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 220.2300. WPL Cathodic System Install Well 16 | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 67.99 |  | 165 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.1650. SB Sign Install on Building Well 16 | SB Signage | 12 Finishes | 9.52 |  | 10 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.2080. EXS Excavation & Prep Pumphouse Structure Well 16 | EXS Excavate Structure | 11 Earth Work | 24.82 |  | 250 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.2710. FWF Pumphouse Site Flowfill Placements Well 16 | FWF Flowable Fill | 15 Concrete | 0 |  | 17.72 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.2800. BFST Backfill Pumphouse Well 16 | BFST Backfill (DO NOT USE) | 11 Earth Work | 813.93 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.3000. CNC Concrete Install Pumphouse Structure Well 16 | CNC Concrete Work | 15 Concrete | 1177.85 |  | 1569.62 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.5000. MET Metals Install Pumphouse Well 16 | MET Metals | 20 Fabrication | 284.03 |  | 76.92 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.6100. F Misc Framing on Pumphouse Well 16 | F Framing | 12 Finishes | 10.13 |  | 30 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.6300. DAW Install Doors & Window Well 16 | DAW Doors & Windows | 12 Finishes | 424.18 |  | 90 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.6400. DRY Install Plywood for Wet Wall & Alucoboard Panels Well 16 | DRY Drywall & Metal Studs | 12 Finishes | 627.94 |  | 68 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.7100. IMP Mecahnical Install Pumphouse Well 16 | IMP Interior Mech/Piping | 55 Mechanical | 1873.41 |  | 576 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.7300. PLUM Plumbing Piping on Pumphouse Well 16 | PLUM Plumbing | 55 Mechanical | 623.26 |  | 150 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.7600. MEQ Install Pipe Pump Station to Surge Tank Well 16 | MEQ Mechanical Equipment | 55 Mechanical | 127.73 |  | 350 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 300.7900. ELC Electrical Trenching on Site, Set Generator Etc. Well 16 | ELC Electrical | 10 Pipe | 513.17 |  | 90 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 310.3000. CNC Deep Foundation at Generator Well 16 | CNC Concrete Work | 15 Concrete | 333.78 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 310.7900. CUMMINS Repair work | ELC Electrical | 10 Pipe | 15.75 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 400.2000. SWC Site Work - Fill for Pumphouse Well 16 | SWC Site Work Complete (DO NOT USE) | 11 Earth Work | 683.33 |  | 221.16 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 400.2010. RG Exterior Site Concrete Prep Well 16 | RG Grading (DO NOT USE) | 11 Earth Work | 91.32 |  | 308.47 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 400.2930. AP Asphalt Prep for Well 16 | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 0 |  | 75 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 400.3000. CNC Exterior Concrete Install Well 16 | CNC Concrete Work | 15 Concrete | 988.19 |  | 869.56 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 400.5000. M Install Bollards on Well 16 | MET Metals | 20 Fabrication | 0 |  | 67.5 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 500.2000. SWC Well 12 Site Work | SWC Site Work Complete (DO NOT USE) | 11 Earth Work | 129.77 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 500.2010. RG Maintain Access Road for Offisite Piping between Well 16 | RG Grading (DO NOT USE) | 11 Earth Work | 33.59 |  | 160 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 500.2200. DPL 20 Inch Off-Site Pump to Waste Pipe Install Well 16 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 5649.9 |  | 930.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 500.3000. CNC Well 12 Vaults | CNC Concrete Work | 15 Concrete | 1268.29 |  | 287.93 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 500.7100. IMP - Well 11 Wet Wall | IMP Interior Mech/Piping | 55 Mechanical | 34.4 |  | 258.63 | 220 | 249.4 | -29.4 | 2023-06-30 | 2025-12-31 | 249.4 |  |  |  | 249.4
2316. CUWCD CWP Wellhouse 16 | 500.7900. ELC Off Site Trenching Electrical Conduit Well 16 | ELC Electrical | 10 Pipe | 353.5 |  | 661.25 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 510.2040. Well 6 Landscaping | LR Landscaping/Restoration | 11 Earth Work | 308.07 |  | 230 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 510.2200. WPL Fuse 20" pipe & Fittings Well 16 | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 525.21 |  | 225 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 510.2300. Well 1 and 2 Excavation | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 61.47 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 550.2200. DPL DCM 10 HDPE pump to waste line | DPL Drainage Pipe Laying (DO NOT USE) | 10 Pipe | 265.62 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 600.2030. Demo Tunnel - RFI 18 | D Demolition | 11 Earth Work | 233.05 |  | 219 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 600.6000. IF Well #8 Interior Finish Work Contingency | IF Interior Finishes | 20 Fabrication | 46.23 |  | 90 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 800.1700. FS Start Up Well 16 | FS Project Manager | 60 Operations (PM/PE) | 116.84 |  | 400 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 800.1930. MC Misc. Cleanup End of Job Well 16 | MC Misc Cleanup | 12 Finishes | 397.65 |  | 230 | 20 | 20 | 0 | 2023-06-30 | 2025-12-31 | 20 |  |  |  | 20
2316. CUWCD CWP Wellhouse 16 | 800.1940. PL Punch List Work Well 16 | PL Punch List Work | 12 Finishes | 727.89 |  | 222.5 | 20 | 20 | 0 | 2023-06-30 | 2025-12-31 | 20 |  |  |  | 20
2316. CUWCD CWP Wellhouse 16 | 900.9005. Re-Work Surveying Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 4.15 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9010. Re-Work Pipe Well 16 | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 14.5 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9011. Re-Work for Subcontractor | _Unknown Phase Master | 00 _Unknown PR Dept | 50.45 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9012. Re-Work Mechanical Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 55.92 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9015. Re-Work Concrete Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9020. Re-Work Fab Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 14.05 |  | 0.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9040. Re-Work Drivers Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9055. Re-Work Finishes Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 9.88 |  | 0.2 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9100. Job Related Equipment Repairs Well 16 | _Unknown Phase Master | 00 _Unknown PR Dept | 93.78 |  | 1 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2316. CUWCD CWP Wellhouse 16 | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 | 2023-06-30 | 2025-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1000. GR General Requirements | GR General Requirements | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1200. HOOK Hook Truck Dumpster | HOOK Hook Truck Dumpster Transporting | 40 Drivers | 84.5 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1300. PD Per Diem | PDT Per Diem for Budget Only | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1301. Travel for Job | TF Travel for Budget Only | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1302. Hotel for Job | HOT Hotel for Budget Only | 00 _Unknown PR Dept | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1500. TR Training Meetings | VIS Meetings (Vision, Safety, Training) | 60 Operations (PM/PE) | 0 |  | 10 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1510. S Surveying | S Surveying | 45 Survey | 1347.02 |  | 1490 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1600. TC Traffic Control | TC Traffic Control | 30 Traffic Control | 443.53 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1650. SB Install Sign L&E | SB Signage | 12 Finishes | 0 |  | 20 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1700. FS-Field Supervision / Project Manager | FS Project Manager | 60 Operations (PM/PE) | 1908.67 |  | 2524.28 | 19 | 20 | -1 |  | 2024-12-31 | 20 |  |  |  | 20
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 3229.88 |  | 1414.6 | 10 | 20 | -10 |  | 2024-12-31 | 20 |  |  |  | 20
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 1606.4 |  | 1106.32 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 3011.54 |  | 2272.37 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 256.38 |  | 219.63 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1705. FS Estimator/Change Orders/Scheduling | FS Estimator/Changes/Scheduling | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 100.1706. FS Executive | FS Executive | 60 Operations (PM/PE) | 0 |  | 1 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 150.1230. T Transporting | T Transporting | 40 Drivers | 808.75 |  | 620 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 150.2100. SS Potholing Existing Utilties | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 74.98 |  | 560 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 150.2750. H Hauling - From Pit | H Hauling | 40 Drivers | 1471.05 |  | 814.68 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 150.2760. DO NOT USE | HO Haul Off | 40 Drivers | 696.26 |  | 696.26 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 180.2055. LR Topsoil placement | LR Top Soil Placement | 11 Earth Work | 527.07 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 180.2600. DW Bypass Allowance | DW Dewatering | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2010. RG Place 12 Inch Granular Backfill L&E - 1650 CY | RG Grading (DO NOT USE) | 11 Earth Work | 21.9 |  | 664 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2030. D Demo Building L&E | D Demolition | 11 Earth Work | 23.1 |  | 120 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2050. DC Dust Control | RW Retaining Walls | 11 Earth Work | 595.04 |  | 500 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2070. SFC SWPPP | RGC Rough Grade Cut | 11 Earth Work | 345.34 |  | 30 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2100. SPL 48 Inch HDPE Pipe Excavation, Placement, Backfill | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 15755.77 |  | 17035.76 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2300. WPL 8 Inch Relocate Valve & Relocations | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 236.9 |  | 90 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2600. DW Drill Wells, Install Well, Maintain Well Points HDPE Pipe | DW Dewatering | 10 Pipe | 4165.18 |  | 2650 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2610. PT Pressure Test HDPE Pipe | PT Pressure Test/Chlorinating | 10 Pipe | 179.61 |  | 400 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2760. DO NOT USE | HO Haul Off | 40 Drivers | 535.98 |  | 535.98 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2800. BFST Backfill | BFST Backfill (DO NOT USE) | 11 Earth Work | 146.18 |  | 30 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2910. MP Asphalt Milling/Pulverize HDPE Pipe | MP Milling/Pulverize | 11 Earth Work | 53.03 |  | 120 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.2930. AP Prep Asphalt Prep on HDPE Pipe | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 393.94 |  | 270 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.3000. CNC Concrete HDPE Pipe | CNC Concrete Work | 15 Concrete | 0 |  | 60 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.5000. MET Metals Install HDPE Pipe | MET Metals | 20 Fabrication | 0 |  | 60 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.7100. IMP Interior Mech/Piping HDPE Pipe | IMP Interior Mech/Piping | 55 Mechanical | 0 |  | 30 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.7300. PLUM 2"" Gas Line HDPE Pipe | PLUM Plumbing | 55 Mechanical | 0 |  | 225 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 200.7900. ELC Trench Telecommunications Line Relocation HDPE Pipe | ELC Electrical | 10 Pipe | 20.42 |  | 150 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 210.2100. SPL Fusion of Pipe 48 Inch HDPE Pipe | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 3507.17 |  | 2000 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 210.2760. DOT NOT USE - NEVER TURN ON | HO Haul Off | 40 Drivers | 406.97 |  | 646 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 250.2750. H Hauling from Stock Pile HDPE Pipe | H Hauling | 40 Drivers | 23.55 |  | 237 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 250.2760. DO NOT USE | HO Haul Off | 40 Drivers | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2010. RG Grading Influent Pipe Area | RG Grading (DO NOT USE) | 11 Earth Work | 236.88 |  | 4 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2030. D Demo Influent Pipe Area | D Demolition | 11 Earth Work | 35.05 |  | 6 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2100. SPL Influent GFRP Install / Sub Condie | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 13646.28 |  | 7697.5 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2600. DW Drill Wells, Install Well, Maintain Well Points Influent | DW Dewatering | 10 Pipe | 2315.91 |  | 2100 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2750. H Hauling - Stock Pile Influent Pipe | H Hauling | 40 Drivers | 29.22 |  | 52.5 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2760. DO NOT USE | HO Haul Off | 40 Drivers | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2910. MP Milling/Pulverize Influent Pipe | MP Milling/Pulverize | 11 Earth Work | 0 |  | 12 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.2930. AP Asphalt Prep Reclaimation Road Influent Pipe | AP Asphalt Prep (DO NOT USE) | 11 Earth Work | 0 |  | 12 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.3000. CNC Concrete Influent Pipe | CNC Concrete Work | 15 Concrete | 8298.9 |  | 3786 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 300.5000. MET Metals Install Influent Pipe | MET Metals | 20 Fabrication | 126.64 |  | 306 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 320.2100. PCO 54 - 54in Joint 2 Deflection repairs | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 330.2100. PCO 55 -54in Joint 3 & 4 Deflection repair | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 12 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 340.2100. PCO 56 - 84in Joint 6,8,9,10 Deflection repair | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 3690.07 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 350.2760. HO Haul Off (LANDFILL ONLY) | HO Haul Off | 40 Drivers | 0 |  | 1500 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 400.2600. PCO 50 Bypass assist MH 1 & 7 | DW Dewatering | 10 Pipe | 790.5 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 400.2760. HO Haul Off to Marathon Property | HO Haul Off | 40 Drivers | 1449.6 |  | 9651.5 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 450.7600. DO NOT USE - PERMIT ONLY Marathon | MEQ Mechanical Equipment | 55 Mechanical | 17.03 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 500.2100. RFP 6 waterline at midland and riverview | SPL Sewer Pipe Laying (DO NOT USE) | 10 Pipe | 47.68 |  | 231.2 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 600.2300. RFP9 8" inline valve in 1900N | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 630.2300. RFP 10 - 1900 N 12" waterline | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 1395.24 |  | 833.14 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 650.2300. RFP9 12" waterline install | WPL Water Pipe Laying (DO NOT USE) | 10 Pipe | 333.99 |  | 420 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 700.2010. DOT NOT USE | RG Grading (DO NOT USE) | 11 Earth Work | 0 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 800.1930. MC Misc. Cleanup | MC Misc Cleanup | 12 Finishes | 161.53 |  | 300 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 800.1940. PL Punch List Work | PL Punch List Work | 12 Finishes | 1053.65 |  | 200 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 7.43 |  | 1 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9010. Re-Work Pipe | M&E Meal/M&IE PerDiem | 00 _Unknown PR Dept | 637.21 |  | 0.4 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 7.02 |  | 0.4 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9020. Re-Work Fab | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.2 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9040. Re-Work Drivers | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.1 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9055. Re-Work Finishes | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.2 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 33.22 |  | 1 | 0 | 0 | 0 |  | 2024-12-31
2312. SLC SW1 Sewer Forcemains & Influent Pipe | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 6.5 |  | 0 | 0 | 0 | 0 |  | 2024-12-31
2231. UDOT Bangerter Hwy Aqueduct Protection | 100.1600. TC Traffic Control 2023 | TC Traffic Control | 30 Traffic Control | 85.34 |  | 150 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 100.1700. FS-Field Supervision 2023 | FS Project Manager | 60 Operations (PM/PE) | 148.84 |  | 20 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 100.1701. FS Project Engineer/Assitant PM/Scheduler | FS Project Engineer/Assistant PM/Scheduler | 60 Operations (PM/PE) | 0 |  | 0 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 100.1702. FS People Superintendent | FS People Superintendent | 57 Superintendents (Site&People) | 0 |  | 0 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 100.1703. FS Job Site Superintendent | FS Job Site Superintendent | 57 Superintendents (Site&People) | 0 |  | 0 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 100.1704. FS Quality Control/Assurance | FS Quality Control/Assurance | 61 HR/Safety | 0 |  | 0 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 110.1230. FS-Field Supervision 2026 | T Transporting | 40 Drivers | 0 |  | 20 | 20 | 20 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 20 |  |  |  | 20
2231. UDOT Bangerter Hwy Aqueduct Protection | 110.1600. TC Traffic Control 2026 | TC Traffic Control | 30 Traffic Control | 9.75 |  | 225 | 215 | 215 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 215 |  |  |  | 215
2231. UDOT Bangerter Hwy Aqueduct Protection | 150.1230. T Transporting 2023 & 2026 | T Transporting | 40 Drivers | 43.18 |  | 100 | 50 | 50 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 50 |  |  |  | 50
2231. UDOT Bangerter Hwy Aqueduct Protection | 150.2750. H Hauling | H Hauling | 40 Drivers | 21.75 |  | 10 | 10 | 10 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 10 |  |  |  | 10
2231. UDOT Bangerter Hwy Aqueduct Protection | 150.2760. HO Haul Off | HO Haul Off | 40 Drivers | 0 |  | 10 | 10 | 10 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 10 |  |  |  | 10
2231. UDOT Bangerter Hwy Aqueduct Protection | 200.2000. SWC Site Grading for Vault Access | SWC Site Work Complete (DO NOT USE) | 11 Earth Work | 47.38 |  | 30 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 200.2030. D Demolition Needed for Vault Acccess | D Demolition | 11 Earth Work | 4.5 |  | 30 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 200.7100. IMP Weko Seals Install 2023 Support | IMP Interior Mech/Piping | 55 Mechanical | 333.06 |  | 210 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 300.3000. CNC Grout Joints 2026 | CNC Concrete Work | 15 Concrete | 5 |  | 875 | 870 | 870 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 870 |  |  |  | 870
2231. UDOT Bangerter Hwy Aqueduct Protection | 300.5100. W Welding Joint 2026 (Contingency) | W Welding | 20 Fabrication | 0 |  | 247.5 | 247.5 | 247.5 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 247.5 |  |  |  | 247.5
2231. UDOT Bangerter Hwy Aqueduct Protection | 300.6500. P Paint Restoration Blilnd Flanges in Vaults | P Painting | 12 Finishes | 0 |  | 187.5 | 187.5 | 187.5 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 187.5 |  |  |  | 187.5
2231. UDOT Bangerter Hwy Aqueduct Protection | 300.7100. IMP Weko Seal Removal 2026 | IMP Interior Mech/Piping | 55 Mechanical | 34.77 |  | 2482.51 | 2450 | 2450 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 2450 |  |  |  | 2450
2231. UDOT Bangerter Hwy Aqueduct Protection | 800.1930. MC Misc. Cleanup 2023 | MC Misc Cleanup | 12 Finishes | 0 |  | 60 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 800.1940. PL Punch List Work 2023 | PL Punch List Work | 12 Finishes | 0 |  | 40 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 850.1930. MC Misc. Cleanup 2026 | MC Misc Cleanup | 12 Finishes | 0 |  | 60 | 60 | 60 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 60 |  |  |  | 60
2231. UDOT Bangerter Hwy Aqueduct Protection | 850.1940. PL Punch List Work 2026 | PL Punch List Work | 12 Finishes | 0 |  | 40 | 40 | 40 | 0 | 2022-11-01 | 2026-04-30 | [5 empty] | 40 |  |  |  | 40
2231. UDOT Bangerter Hwy Aqueduct Protection | 900.9005. Re-Work Surveying | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 1 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 900.9012. Re-Work Mechanical | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 900.9015. Re-Work Concrete | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.4 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 900.9020. Re-Work Fab | _Unknown Phase Master | 00 _Unknown PR Dept | 0 |  | 0.2 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 900.9100. Job Related Equipment Repairs | _Unknown Phase Master | 00 _Unknown PR Dept | 8.83 |  | 1 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
2231. UDOT Bangerter Hwy Aqueduct Protection | 900.9600. Reallocate EQ/FOO costs to actual | _Unknown Phase Master | 00 _Unknown PR Dept | 2.5 |  | 0 | 0 | 0 | 0 | 2022-11-01 | 2026-04-30
|  |  |  | 438273.13 |  | 482863.86 | 160819.37 | 150514.6 | 10304.77 |  |  | 47043.5 | 39641.4 | 17139.7 | 14116.5 | 117941.1 | 16176.8 | 13999.2 | 2397.5 | 0 | 32573.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0